## Cost Forecast
Code | Name | Projected Forecast | Spent to Date | January | February | March | April | May | June | July | August | September | October | Final Cost | Breakdown Type | Cost Category 1 | Cost Category 2 | Equal? | Unnamed: 19 | Unnamed: 20
00-0001 | SECOND FLOOR APARTMENT REMOVALS | 14032 | 14032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14032 | Phased | Labor | Change Order | 1 | 0 | 0
00-0002 | SITE 8 SLAB SHORING | 15736.31 | 15736.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15736.31 | Phased | Labor | Change Order | 1 | 0 | 0
00-0003 | OG8 Obstruction Removal | 17042.53 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17042.53 | Phased | Labor | Change Order | 1 | 0 | 0
00-0004 | Floor Drain PCO | 0 | 17791.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17791.39 | Phased | Labor | Change Order | 0 | 0 | 0
00-0005 | Equipment Pad PCO | 15000 | 10649.18 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 0 | 0 | 15000 | Phased | Labor | Change Order | 1 | 0 | 0
00-0006 | PCO 15 Additional Windows PCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0007 | IRMA PAGAN APARTMENT MOVE | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | Phased | Labor | Change Order | 1 | 0 | 0
00-0008 | National Grid Gas Line Relocation | 11667.88 | 11667.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11667.88 | Phased | Labor | Change Order | 1 | 0 | 0
00-0009 | Bracing for POE Penetration Through SG4 Wall | 7468.26 | 7468.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7468.26 | Phased | Labor | Change Order | 1 | 0 | 0
00-0010 | SG1 RELOCATE BELONGINGS | 21773.44 | 21773.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21773.44 | Phased | Labor | Change Order | 1 | 0 | 0
00-0011 | PERAMBULATOR ROOM DEMO | 18064.37 | 18064.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18064.37 | Phased | Labor | Change Order | 1 | 0 | 0
00-0012 | OG8 Tank Removal | 20378.14 | 372.43 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 0 | 0 | 20378.14 | Phased | Labor | Change Order | 1 | 0 | 0
00-0013 | Exist Bldgs Bracing due to Penetrations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0014 | SG4 DEMO FOR STEEL BEAMS INSTALL | 12464.98 | 1285.34 | 1397.455 | 1397.455 | 1397.455 | 1397.455 | 1397.455 | 1397.455 | 1397.455 | 1397.455 | 0 | 0 | 12464.98 | Phased | Labor | Change Order | 1 | 0 | 0
00-0015 | SG5 DEMO FOR STEEL BEAMS INSTALL | 1678.93 | 1678.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1678.93 | Phased | Labor | Change Order | 1 | 0 | 0
00-0016 | OG4 BRACING FOR POE PENETRATION | 164120.78 | 30850.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30850.89 | hold | Contingency | Change Order | 0.18798 | 0 | 0
00-0017 | National Grid Additional Allowance | 205770.46 | 5887.46 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 0 | 0 | 205770.46 | Phased | Labor | Change Order | 1 | 0 | 0
00-0018 | SG6 Additional Strobe | 2387.08 | 0 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 0 | 0 | 2387.08 | Phased | Labor | Change Order | 1 | 0 | 0
00-0019 | ODWYER FENCE INSTALL | 62577.96 | 62577.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62577.96 | Phased | Labor | Change Order | 1 | 0 | 0
00-0021 | MOVE PLAYGROUNDS | 1941.36 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941.36 | Phased | Labor | Change Order | 1 | 0 | 0
00-0022 | SITE 8 CLEANING | 5968.61 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968.61 | Phased | Labor | Change Order | 1 | 0 | 0
00-0023 | S8 FIRE STAND PIPE ACCESS | 59605.91 | 7156.91 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 0 | 0 | 59605.91 | Phased | Labor | Change Order | 1 | 0 | 0
00-0024 | Boiler Stack Support | 64820.84 | 796.41 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 0 | 0 | 64820.84 | Phased | Labor | Change Order | 1 | 0 | 0
00-0025 | Bulletin 1 Civil PCO 44 | 76640 | 26990.2 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 0 | 0 | 76640 | Phased | Labor | Change Order | 1 | 0 | 0
00-0026 | DOOR HARDWARE CHANGES | 21947.23 | 0 | 0 | 0 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21947.23 | Phased | Labor | Change Order | 1 | 0 | 0
00-0027 | BOILER ACCESSORY SUPPLY | 185547.35 | 0 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 0 | 0 | 185547.35 | Phased | Labor | Change Order | 1 | 0 | 0
00-0028 | SITE 8 ELECTRICAL REPAIRS | 21203.36 | 0 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 0 | 0 | 21203.36 | Phased | Labor | Change Order | 1 | 0 | 0
00-0029 | PCO46 SANITARY VENTING OG5 & OG6 | 69207.97 | 0 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 0 | 0 | 69207.97 | Phased | Labor | Change Order | 1 | 0 | 0
00-0030 | PCO 54 ACM ABATEMENT MASONRY WATERPROOFING | 120833.26 | 0 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 0 | 0 | 120833.26 | Phased | Labor | Change Order | 1 | 0 | 0
00-0031 | PCO 55 ACM ABATEMENT UTILITY WATERPROOF | 241793.37 | 0 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 0 | 0 | 241793.37 | Phased | Labor | Change Order | 1 | 0 | 0
00-0032 | PCO 64 OG10 ADDITIONAL SWITCH | 2369.68 | 0 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 0 | 0 | 2369.68 | Phased | Labor | Change Order | 1 | 0 | 0
00-0033 | PCO 66 ELECTRICAL DB FOUNDATION CONFLICT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0034 | PCO 76 ADDITIONAL FIRE EXTINGUISHERS | 3809.76 | 0 | 0 | 0 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.76 | Phased | Labor | Change Order | 1 | 0 | 0
00-0035 | PCO 77 ACM ABATEMENT SGS STEAM PIPE | 111590.33 | 0 | 0 | 0 | 33000 | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 99000 | Phased | Labor | Change Order | 0.88717 | 0 | 0
00-0036 | PCO 99 SG5 APARTMENT RENO | 9892.17 | 9892.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9892.17 | Phased | Labor | Change Order | 1 | 0 | 0
00-0037 | JACOBS TRAILER MOVE | 2879.76 | -30038.69 | 0 | 32918.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.76 | Phased | Labor | Change Order | 1 | 0 | 0
00-0038 | PCO 59 SGS REDESIGN | 557295.88 | 4726.71 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 0 | 0 | 557295.88 | Phased | Labor | Change Order | 1 | 0 | 0
00-0039 | AC UNIT DEMO | 7582.95 | 7582.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7582.95 | Phased | Labor | Change Order | 1 | 0 | 0
00-0040 | PCO 8 BULLETIN 1 ELECTRICAL | 38953 | 0 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 0 | 0 | 38953 | Phased | Labor | Change Order | 1 | 0 | 0
00-0041 | PCO 19 WINDOW INFILL | 5922.43 | 0 | 0 | 5922.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5922.43 | Phased | Labor | Change Order | 1 | 0 | 0
00-0042 | PCO 40 SG6 STUD RELOCATION | 10923.98 | 0 | 0 | 10923.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10923.98 | Phased | Labor | Change Order | 1 | 0 | 0
00-0043 | PCO 59 SGS ELECTRICAL CHANGES | 213.43 | 213.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213.43 | Phased | Labor | Change Order | 1 | 0 | 0
00-0044 | PCO 74 OG9 AND S8 GENERATOR SUPPORTS | 60248.81 | 39449.71 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 0 | 0 | 60248.81 | Phased | Labor | Change Order | 1 | 0 | 0
00-0045 | PCO 79 ACM FILING | 4500 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | Phased | Labor | Change Order | 1 | 0 | 0
00-0046 | PCO 85 OG4 & OG5 TANK INSULATION ACM | 75690.92 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 75000 | Phased | Labor | Change Order | 0.99087 | 0 | 0
00-0047 | PCO 90 ODYWER TRAILER POWER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0048 | PCO 45 BULLETIN 1 MECHANICAL | 154900.73 | 0 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 0 | 0 | 154900.73 | Phased | Labor | Change Order | 1 | 0 | 0
00-0049 | PCO 83 SG6 METAL PANEL SUPPORT | 70919.49 | 0 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 0 | 0 | 70919.49 | Phased | Labor | Change Order | 1 | 0 | 0
00-0050 | PCO 63 Conduit Concrete Encasement | 225393.38 | 0 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 0 | 0 | 225393.38 | Phased | Labor | Change Order | 1 | 0 | 0
00-0051 | PCO 49 Electrical Clash with LPS | 9430.53 | 0 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 0 | 0 | 9430.53 | Phased | Labor | Change Order | 1 | 0 | 0
00-0052 | PCO 93 Roof Access and ATS Door | 125820.09 | 7098.56 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 0 | 0 | 125820.09 | Phased | Labor | Change Order | 1 | 0 | 0
00-0053 | PCO 100 Exterior Framing OG8, OG9, OG10 | 204711.04 | 0 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 0 | 0 | 204711.04 | Phased | Labor | Change Order | 1 | 0 | 0
00-0054 | PCO 48 Restore Walkways | 9506.49 | 9506.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9506.49 | Phased | Labor | Change Order | 1 | 0 | 0
00-0055 | Pit Covers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0056 | PCO 27 OG8 Structural Steel | 94993.6 | 0 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 0 | 0 | 94993.6 | Phased | Labor | Change Order | 1 | 0 | 0
00-0057 | PCO 80 LPS Reroute OG6 | 10884.19 | 0 | 0 | 10884.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10884.19 | Phased | Labor | Change Order | 1 | 0 | 0
00-0058 | PCO 98 OG6 Structural Steel | 6536.32 | 1612.44 | 0 | 4923.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6536.32 | Phased | Labor | Change Order | 1 | 0 | 0
00-0059 | PCO 117 OG1 Ramp Restore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0060 | PCO 78 OG10 Clash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0 | 0
00-0061 | PCO 108 STREET CROSSING | 290768 | 0 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 0 | 0 | 290768 | Phased | Labor | Change Order | 1 | 0 | 0
00-0062 | PCO 143 SG2 SHELF SUPPORT | 2073.66 | 2073.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2073.66 | Phased | Labor | Change Order | 1 | 0 | 0
00-0063 | PCO 144 SG3 BASEMENT CLEANING | 10231.24 | 10231.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10231.24 | Phased | Labor | Change Order | 1 | 0 | 0
00-0064 | PCO 148 EB BACKWATER VALVES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0065 | PCO 17 PLUMBING PIT REINF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0066 | PCO 18 SG6 SHAFT BRACING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0067 | PCO 26 SG6 STAIR MOD | 16182.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0068 | PCO 86 OG1 MANHOLE REROUTE | 19514.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0069 | PCO 97 OG2 OG3 STEAM TUNNEL ACM | 14297.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0070 | PCO 102 SGS OUTAGE | 16182.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0071 | PCO 116 ROOF FLASHING AT BULKHEAD | 13624.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0072 | PCO 142 GENERATOR EQUIP | 28230.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-1000 | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
01-6000 | BUILDING CONDITIONS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
01-6100 | CPM SUB | 73150 | 58860 | 2598.1809 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 73149.9991 | monthly | Sub | 0 | 1 | 0 | 0
01-6200 | PHOTO SUB | 87990 | 46410 | 5727.2764 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 87990.0036 | monthly | Sub | 0 | 1 | 0 | 0
01-6300 | OVERHEAD PROTECTION LABOR | 1472.69 | 1472.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472.69 | spent | spent | 0 | 1 | 0 | 0
01-6310 | OVERHEAD PROTECTION MATERIALS | 4491.11 | 4491.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491.11 | spent | spent | 0 | 1 | 0 | 0
01-6320 | OVERHEAD PROTECTION EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
01-6400 | RODENT CONTROL SUB | 28596.9 | 14473.9 | 2000 | 2000 | 2000 | 1223 | 1000 | 1000 | 1000 | 1000 | 2900 | 0 | 28596.9 | Phased | Sub | 0 | 1 | 0 | 0
01-6410 | RODENT CONTROL SUB SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-1000 | EROSION CONTROL FABRIC | 970.55 | 970.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 970.55 | spent | spent | 0 | 1 | 0 | 0
02-1100 | INLET PROTECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-1200 | SILT FENCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-1300 | STABILIZED CONSTRUCTION ENTRANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-1400 | MANTAIN EROSION CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-1500 | REMOVE EROSION CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-1600 | STOCKPILE | 4496.62 | 4496.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4496.62 | spent | spent | 0 | 1 | 0 | 0
02-1700 | REMOVE FENCE | 62785.26 | 24231.19 | 7879.8 | 7879.8 | 7879.8 | 5000 | 9914.67 | 0 | 0 | 0 | 0 | 0 | 62785.26 | Phased | Labor | Site Demo | 1 | 0 | 0
02-1800 | REMOVE/REINSTALL BOLLARDS ODG EAST | 51378.15 | 627.92 | 16916.7417 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 0 | 0 | 0 | 0 | 0 | 51378.1483 | Phased | Labor | Site Demo | 1 | 0 | 0
02-1900 | REMOVE FULL DEPTH ASPHALT PVMT | 85977.83 | 82630 | 777.1117 | 500 | 500 | 500 | 1070.7183 | 0 | 0 | 0 | 0 | 0 | 85977.83 | Phased | Labor | Site Demo | 1 | 0 | 0
02-2000 | REMOVE SITE FURNISHING | 77397.6 | 37619.77 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 12275.5767 | 0 | 0 | 0 | 0 | 0 | 77397.6 | Phased | Labor | Site Demo | 1 | 0 | 0
02-2100 | REMOVE CONCRETE CURB & STEPS | 93000 | 85043.63 | 1833.3933 | 1833.3933 | 1833.3933 | 1833.3933 | 622.7967 | 0 | 0 | 0 | 0 | 0 | 93000 | Phased | Labor | Site Demo | 1 | 0 | 0
02-2200 | REMOVE PVMTS | 97421.11 | 83813.86 | 4443.095 | 4443.095 | 4721.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97421.11 | Phased | Labor | Site Demo | 1 | 0 | 0
02-2300 | BASEMENT MAINTENANCE | 312373.79 | 243894.9 | 10211.18 | 8640 | 8640 | 8640 | 8640 | 8640 | 4320 | 4320 | 4320 | 2107.71 | 312373.79 | Phased | Labor | Site Maintenance | 1 | 0 | 0
02-3000 | CORE DRILLING | 532776.35 | 520023.36 | 15000 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 550023.36 | Phased | Labor | Site Demo | 1.0324 | 0 | 0
02-6000 | OG-7 DEMO LABOR | 21560.01 | 21560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21560.01 | spent | spent | 0 | 1 | 0 | 0
02-6001 | OG-7 DEMO EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-6002 | OG-7 DEMO MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | 373189.17 | 327967.88 | 0 | 0 | 0 | 45221.29 | 0 | 0 | 0 | 0 | 0 | 0 | 373189.17 | hold | labor | Site Demo | 1 | 0 | 0
02-6006 | LEAD CONSULTANT | 19466.75 | 19466.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19466.75 | spent | spent | 0 | 1 | 0 | 0
02-6007 | LEAD DISPOSAL | 5400.21 | 5400.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400.21 | spent | spent | 0 | 1 | 0 | 0
02-6008 | LEAD TRAINING | 8413.33 | 8413.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8413.33 | spent | spent | 0 | 1 | 0 | 0
02-6009 | Paint Removal Elevator Pits | 67200 | 1052.44 | 0 | 0 | 0 | 66147.56 | 0 | 0 | 0 | 0 | 0 | 0 | 67200 | hold | labor | Site Demo | 1 | 0 | 0
02-6010 | REMOVE SUMP PUMPS | 36030 | 25424.05 | 1805.515 | 1805.515 | 1805.515 | 1805.515 | 3383.89 | 0 | 0 | 0 | 0 | 0 | 36030 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | 102770 | 70550.03 | 10739.995 | 5369.995 | 5369.995 | 5369.995 | 5369.995 | 0 | 0 | 0 | 0 | 0 | 102770.005 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | 19766.24 | 2737.32 | 4577.0717 | 3112.9617 | 3112.9617 | 3112.9617 | 3112.9617 | 0 | 0 | 0 | 0 | 0 | 19766.2383 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6025 | REMOVE AREAWAYS LABOR | 82000 | 71381.46 | 2050.3233 | 2050.3233 | 2050.3233 | 2050.3233 | 2417.2467 | 0 | 0 | 0 | 0 | 0 | 82000 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6026 | REMOVE AREAWAYS EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | 227761.46 | 385.53 | 37895.9883 | 37895.9883 | 37895.9883 | 37895.9883 | 37895.9883 | 37895.99 | 0 | 0 | 0 | 0 | 227761.4617 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | 1520.48 | 0 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 253.41 | 0 | 0 | 0 | 0 | 1520.4767 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | 15000 | 3487.09 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.82 | 0 | 0 | 0 | 0 | 15000.0017 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6050 | DEMO STAIRS AND RAMPS LABOR | 17116.64 | 12850.76 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 0 | 0 | 0 | 0 | 17116.64 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | 2259.95 | 2259.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2259.95 | spent | spent | 0 | 1 | 0 | 0
02-6060 | DEMO SECOND FLOOR APARTMENTS | 150000 | 130767.81 | 4808.0475 | 4808.0475 | 4808.0475 | 4808.05 | 0 | 0 | 0 | 0 | 0 | 0 | 150000.0025 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6065 | DEMO FOR MECHANICAL | 200000 | 11078.48 | 0 | 0 | 0 | 47230.38 | 47230.38 | 47230.38 | 47230.38 | 0 | 0 | 0 | 200000 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6066 | FLOOR DRAIN DEMO | 70083.35 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70083.35 | spent | spent | 0 | 1 | 0 | 0
02-6070 | DEMO FOR ELECTRICAL | 156200 | 20057.56 | 47142.44 | 50000 | 19500 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 156200 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6075 | DEMO FOR PLUMBING | 161879.62 | 14739.37 | 50000 | 50000 | 23500 | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 161739.37 | Phased | Labor | Site Demo | 0.99913 | 0 | 0
02-6080 | ENTRANCE RAMP DEMO | 118800 | 35967.54 | 29700 | 27937.11 | 25195.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118800 | Phased | Labor | Site Demo | 1 | 0 | 0
02-6100 | ASBESTOS SUB | 1554903.14 | 1263729.48 | 0 | 27745.7 | 34819.5 | 34316.6667 | 34316.6667 | 75119.0667 | 41802.4 | 38802.4 | 36177.4 | 0 | 1586829.28 | SOV | Sub | 0 | 1.0205 | 0 | 0
02-6110 | ASBESTOS SUB SUPPORT | 79333.7 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 9333.7 | 0 | 0 | 79333.7 | hold | Labor | Sub Support | 1 | 0 | 0
02-6120 | ASEBESTOS CONSULTANT | 23896.55 | 23896.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23896.55 | spent | spent | 0 | 1 | 0 | 0
02-6130 | ASBESTOS SUB ACCESS | 25543.46 | 21820.5 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 0 | 0 | 25543.46 | Phased | Labor | Sub Support | 1 | 0 | 0
02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | 1900.42 | 1900.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900.42 | spent | spent | 0 | 1 | 0 | 0
02-7100 | STONE FOR EROSION CONTROL | 32382.03 | 32382.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32382.03 | spent | spent | 0 | 1 | 0 | 0
02-7200 | SOIL TESTING | 83535 | 83535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83535 | spent | spent | 0 | 1 | 0 | 0
03-1000 | FORMWORK NEW BUILDING | 2150000 | 2109965.74 | 27247.225 | 12787.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150000 | Phased | Labor | New Buildings | 1 | 0 | 0
03-1100 | FORMWORK EXIST BLDGS | 786238.54 | 531231.59 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 15006.95 | 0 | 0 | 0 | 786238.54 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-1105 | Conduit Encasement | 138600 | 53172.85 | 20000 | 20000 | 20000 | 20000 | 5427.15 | 0 | 0 | 0 | 0 | 0 | 138600 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-1200 | OPERATOR FOR CONCRETE WORK | 29756.82 | 29756.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29756.82 | spent | spent | 0 | 1 | 0 | 0
03-1300 | SET ANCHOR BOLTS FOR STEEL COLUMNS | 63065.21 | 63065.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63065.21 | spent | spent | 0 | 1 | 0 | 0
03-1400 | DRILL & GROUT DOWELS | 274808.11 | 254662.76 | 6475.152 | 6475.152 | 6475.152 | 6475.152 | -5755.258 | 0 | 0 | 0 | 0 | 0 | 274808.11 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-1500 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE | 162759.19 | 139750.29 | 6432.236 | 6432.236 | 6432.236 | 5000 | -1287.808 | 0 | 0 | 0 | 0 | 0 | 162759.19 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-1600 | FORMWORK SITE CONCRETE LABOR | 150000 | 107135.72 | 42864.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | Phased | Labor | Site Restoration | 1 | 0 | 0
03-1610 | FORMWORK SITE CONCRETE MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
03-1700 | CONCRETE REINFORCEMENT NEW BUILDING UNLOAD | 56763.12 | 56763.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56763.12 | spent | spent | 0 | 1 | 0 | 0
03-1800 | CONCRETE REINFORCEMENT BARRIER FOUNDATIONS UNLOAD | 45000 | 37721.62 | 1455.676 | 1455.676 | 1455.676 | 1455.676 | 1455.676 | 0 | 0 | 0 | 0 | 0 | 45000 | Phased | Labor | Sub Support | 1 | 0 | 0
03-1900 | POUR CONCRETE NEW BUILDINGS | 530000 | 516247.58 | 13752.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530000 | Phased | Labor | New Buildings | 1 | 0 | 0
03-2000 | FINISH SLABS - NEW BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
03-2100 | POUR CONC EXIST BLDGS | 205190.25 | 189150.65 | 5000 | 5000 | 5000 | 1039.6 | 0 | 0 | 0 | 0 | 0 | 0 | 205190.25 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-2110 | SHOTCRETE SUB | 166500 | 90593.84 | 25302.0533 | 25302.0533 | 25302.0533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166500 | Phased | Sub | 0 | 1 | 0 | 0
03-2120 | SHOTCRETE SUB CLEANUP | 30000 | 27911.35 | 2225.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30136.5233 | Phased | Labor | Sub Support | 1.0046 | 0 | 0
03-2200 | CONCRETE FOOTING FOR SITE FURNISHING | 13759.32 | 0 | 0 | 0 | 3439.83 | 3439.83 | 3439.83 | 3439.83 | 0 | 0 | 0 | 0 | 13759.32 | Phased | Labor | Site Restoration | 1 | 0 | 0
03-2300 | CONCRETE DUCTBANKS | 225000 | 218768.34 | 6231.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | Phased | Labor | Site Utilities | 1 | 0 | 0
03-2400 | CONCRETE SITE RETAINING WALL AND FOOTINGS | 36435.9 | 19492.88 | 16943.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36435.9 | Phased | Labor | Site Restoration | 1 | 0 | 0
03-2500 | CONCRETE SHELF AND BOND BEAM EXTG BL (INCL FORMS) | 108745 | 102502.29 | 2658.22 | 2658.22 | 926.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108745 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-2600 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL | 13834.32 | 726.04 | 0 | 0 | 0 | 0 | 3277.07 | 3277.07 | 3277.07 | 3277.07 | 0 | 0 | 13834.32 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-2700 | EXISTING BLDGS EQUIPMENT PAD WORK | 95.84 | 95.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.84 | spent | spent | 0 | 1 | 0 | 0
03-5000 | FURNISH CONCRETE | 1567803.72 | 1364936.77 | 40000 | 40000 | 40000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 1564936.77 | phased | Material | 0 | 0.99817 | 0 | 0
03-5100 | FURNISH INSULATION | 39414.64 | 39414.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39414.64 | spent | spent | 0 | 1 | 0 | 0
03-5200 | FURNISH REBAR | 14662.42 | 13710.55 | 200 | 200 | 118.9838 | 59.4919 | 373.3944 | 0 | 0 | 0 | 0 | 0 | 14662.42 | phased | Material | 0 | 1 | 0 | 0
03-5250 | FURNISH WIREMESH | 47762.13 | 35283.88 | 3000 | 2500 | 1559.7812 | 1200 | 4218.4688 | 0 | 0 | 0 | 0 | 0 | 47762.13 | phased | Material | 0 | 1 | 0 | 0
03-5400 | FURNISH SAKCRETE | 181500 | 0 | 30000 | 30000 | 30000 | 30000 | 30000 | 31500 | 0 | 0 | 0 | 0 | 181500 | phased | Material | 0 | 1 | 0 | 0
03-5500 | FURNISH CONC PATCH MATERIAL | 9174.5 | 9174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9174.5 | spent | spent | 0 | 1 | 0 | 0
03-6000 | FRP WORK | 420253.96 | 407746.27 | 12507.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420253.96 | Phased | Labor | Existing Buildings | 1 | 0 | 0
03-6010 | FRP Self Perform | 35296.6 | 35296.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35296.6 | spent | spent | 0 | 1 | 0 | 0
03-6100 | REBAR SUB | 1494408.08 | 1231937.68 | 41898.9371 | 41898.9371 | 41898.9371 | 41898.9371 | 94874.6514 | 0 | 0 | 0 | 0 | 0 | 1494408.08 | Phased | Sub | 0 | 1 | 0 | 0
03-6110 | REBAR SUB SUPPORT | 4416.84 | 347.15 | 0 | 4069.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4416.84 | hold | Labor | Sub Support | 1 | 0 | 0
03-6120 | REBAR DELIVERY SUPPORT | 4041.34 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4041.34 | spent | spent | 0 | 1 | 0 | 0
03-7000 | FORMWORK MATERIAL | 709305.66 | 535908.04 | 28000 | 28000 | 28000 | 28000 | 28000 | 33397.62 | 0 | 0 | 0 | 0 | 709305.66 | phased | Material | 0 | 1 | 0 | 0
03-7100 | MATERIAL FOR FLOWABLE FILL BACKFILL | 152745.59 | 152745.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152745.59 | spent | spent | 0 | 1 | 0 | 0
04-1000 | CLEAN CONC SURF FOUND WALL/PATCH VOIDS W/MORTAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
04-6000 | GROUT INJECTION SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
04-6100 | MASONRY SUB | 9090000 | 6613749.56 | 373750.9563 | 403372.1412 | 377150.6342 | 309000.6342 | 309000.6342 | 0 | 0 | 0 | 0 | 0 | 8386024.56 | SOV | Sub | 0 | 0.92255 | 0 | 0
04-6110 | MASONRY SUB SUPPORT | 150000 | 25393.2 | 0 | 30000 | 30000 | 30000 | 30000 | 4606.8 | 0 | 0 | 0 | 0 | 150000 | hold | Labor | Sub Support | 1 | 0 | 0
04-6120 | MASON EUIP SUPPORT | 62569.54 | 62569.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62569.54 | spent | spent | 0 | 1 | 0 | 0
04-6130 | ANGLE FOR FACADE | 103266.58 | 69102.74 | 9088.2475 | 9088.2475 | 15987.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103266.58 | Phased | Labor | Existing Buildings | 1 | 0 | 0
04-6200 | STONE SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
04-7000 | MASONRY CLEANER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
05-6000 | STRUCTURAL STEEL SUB | 5918133.95 | 5907478.54 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5962478.54 | SOV | Sub | 0 | 1.0075 | 0 | 0
05-6010 | STRUCTURAL STEEL SUB SUPPORT | 22760.18 | 15158.89 | 0 | 7601.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22760.18 | hold | Labor | Sub Support | 1 | 0 | 0
05-6020 | GROUT STEEL COLUMNS | 30000 | 27222.11 | 707.605 | 2070.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000.005 | Phased | Labor | Existing Buildings | 1 | 0 | 0
05-6030 | STEEL & CRANE DELIVERIES | 9097.96 | 9097.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9097.96 | spent | spent | 0 | 1 | 0 | 0
05-6040 | Ground Prep For Crane | 8898.32 | 8898.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898.32 | spent | spent | 0 | 1 | 0 | 0
05-6050 | PREP COLUMNS FOR STEEL INSTALL | 2237.81 | 2237.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2237.81 | spent | spent | 0 | 1 | 0 | 0
05-6100 | MISC METALS SUB | 2010175 | 651253.92 | 201980.863 | 142327.963 | 70295.25 | 155988 | 103992 | 12999 | 38997 | 0 | 0 | 0 | 1377833.9959 | SOV | Sub | 0 | 0.68543 | 0 | 0
05-6110 | MISC METALS SUB SUPPORT | 100040.22 | 7104.35 | 0 | 0 | 92935.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100040.22 | hold | Labor | Sub Support | 1 | 0 | 0
05-6120 | BACKCHARGE E&Y | 1174.65 | 1174.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.65 | spent | spent | 0 | 1 | 0 | 0
05-6200 | SIGNAGE SUB | 138024 | 21000 | 0 | 0 | 11316 | 11316 | 0 | 0 | 0 | 0 | 0 | 0 | 43632 | SOV | Sub | 0 | 0.31612 | 0 | 0
05-6210 | SIGNAGE SUB SUPPORT | 10000 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 10000 | hold | Labor | Sub Support | 1 | 0 | 0
06-6000 | CARPENTRY SUB | 1840000 | 1540449.87 | 117331.7297 | 117420.1925 | 67082.066 | 101775.2295 | 105521.171 | 57710.5855 | 0 | 0 | 0 | 0 | 2107290.8442 | SOV | Sub | 0 | 1.1453 | 0 | 267290.8442
06-6010 | CARPENTRY SUB SUPPORT | 50000 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 50000 | hold | Labor | Sub Support | 1 | 0 | 0
07-1000 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
07-1100 | 3 RIGID INSULATION UNDER GRADE NEW BLDGS | 34098.54 | 34098.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34098.54 | spent | spent | 0 | 1 | 0 | 0
07-1200 | PENETRATION FIRESTOPPING EXTG BLDGS | 55337.28 | 0 | 3458.58 | 3458.58 | 6917.16 | 6917.16 | 13834.32 | 13834.32 | 3458.58 | 3458.58 | 0 | 0 | 55337.28 | Phased | Labor | Existing Buildings | 1 | 0 | 0
07-1300 | PENETRATION FIRESTOPPING NEW BLDGS | 27668.64 | 0 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 27668.64 | Phased | Labor | New Buildings | 1 | 0 | 0
07-1400 | JOINT SEALANTS EXTG BLDGS | 55337.28 | 12860.73 | 2654.7844 | 2654.7844 | 5309.5688 | 5309.5688 | 10619.1375 | 10619.1375 | 2654.7844 | 2654.7844 | 0 | 0 | 55337.28 | Phased | Labor | Existing Buildings | 1 | 0 | 0
07-1500 | JOINT SEALANTS NEW BLDGS | 27668.64 | 0 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 27668.64 | Phased | Labor | New Buildings | 1 | 0 | 0
07-2000 | INSTALL WATERSTOP | 3491.54 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3491.54 | spent | spent | 0 | 1 | 0 | 0
07-5000 | FURNISH FIRESTOPPING | 90000 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 90000 | phased | Material | 0 | 1 | 0 | 0
07-5100 | FURNISH JOINT SEALANT | 90000 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 90000 | phased | Material | 0 | 1 | 0 | 0
07-6000 | WATERPROOFING SUB | 1007406.25 | 27305.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27305.01 | SOV | Sub | 0 | 0.027104 | 0 | 0
07-6010 | WATERPROOFING SUB SUPPORT | 103510.13 | 1172.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172.93 | hold | Labor | Sub Support | 0.011332 | 0 | 0
07-6020 | PREP SURFACE FOR WATERPROOFING | 51520.23 | 51520.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51520.23 | Phased | Labor | New Buildings | 1 | 0 | 0
07-6100 | METAL PANELS SUB | 3381506.41 | 1737915.01 | 19900.8667 | 245213.7583 | 346257.0917 | 420549.125 | 235327.9583 | 0 | 0 | 0 | 0 | 0 | 3005163.81 | SOV | Sub | 0 | 0.88871 | 0 | 0
07-6110 | METAL PANELS SUB SUPPORT | 68493.59 | 10719.51 | 0 | 57774.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68493.59 | hold | Labor | Sub Support | 1 | 0 | 0
07-6200 | ROOFING SUB | 1135000 | 705799.78 | 0 | 355028 | 145814.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206642.1509 | SOV | Sub | 0 | 1.0631 | 0 | 0
07-6210 | ROOFING SUB SUPPORT | 60000 | 1171.78 | 0 | 58828.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | hold | Labor | Sub Support | 1 | 0 | 0
07-6220 | PREP ROOF SURFACE FOR WORK | 40000 | 22460.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22460.72 | Phased | Labor | New Buildings | 0.56152 | 0 | 0
07-6300 | SPRAY ON FIREPROOFING SUB | 254755.38 | 247755.38 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254755.38 | Phased | Sub | 0 | 1 | 0 | 0
07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | 21837.92 | 1377.92 | 0 | 20000 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21837.92 | hold | sub | 0 | 1 | 0 | 0
07-6320 | Maintain heat for Fireproofers | 9196.97 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9196.97 | spent | spent | 0 | 1 | 0 | 0
07-6330 | FIREPROOFING CLEANUP | 2771.84 | 2771.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2771.84 | spent | spent | 0 | 1 | 0 | 0
08-1600 | ACCESS HATCH | 114418.44 | 0 | 7151.1525 | 7151.1525 | 14302.305 | 14302.305 | 28604.61 | 28604.61 | 7151.1525 | 7151.1525 | 0 | 0 | 114418.44 | Phased | Labor | Existing Buildings | 1 | 0 | 0
08-1700 | (1''4WX8H) S.S. FLOOD VENTS NEW BL (153) | 19069.74 | 0 | 1191.8588 | 1191.8588 | 2383.7175 | 2383.7175 | 4767.435 | 4767.435 | 1191.8588 | 1191.8588 | 0 | 0 | 19069.74 | Phased | Labor | Existing Buildings | 1 | 0 | 0
08-1800 | 2'9"x8" SS FLOOD VENT W/SS SCRN NEW BLDG(8.06) | 6356.58 | 0 | 397.2862 | 397.2862 | 794.5725 | 794.5725 | 1589.145 | 1589.145 | 397.2862 | 397.2862 | 0 | 0 | 6356.58 | Phased | Labor | Existing Buildings | 1 | 0 | 0
08-5000 | FURNISH HM DOORS | 191266.4 | 83834.36 | 26858.01 | 26858.01 | 26858.01 | 26858.01 | 0 | 0 | 0 | 0 | 0 | 0 | 191266.4 | phased | Material | 0 | 1 | 0 | 0
08-5010 | HM DOOR SUPPORT | 50000 | 0 | 3125 | 3125 | 6250 | 6250 | 12500 | 12500 | 3125 | 3125 | 0 | 0 | 50000 | Phased | Labor | Existing Buildings | 1 | 0 | 0
08-5100 | FURNISH ACCESS HATCHES | 91781 | 91781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91781 | spent | spent | 0 | 1 | 0 | 0
08-6000 | OVERHEAD DOORS SUB | 22632 | 5658 | 0 | 0 | 0 | 0 | 0 | 16974 | 0 | 0 | 0 | 0 | 22632 | Phased | Sub | 0 | 1 | 0 | 0
08-6010 | OVERHEAD DOORS SUB SUPPORT | 5000 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 5000 | hold | sub | 0 | 1 | 0 | 0
08-6100 | GLAZING SUB | 28000 | 0 | 0 | 0 | 0 | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 28000 | Phased | Sub | 0 | 1 | 0 | 0
08-6200 | LOUVERS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
09-6000 | STUCCO SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
09-6100 | TILE SUB | 34200 | 0 | 0 | 11400 | 11400 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | Phased | Sub | 0 | 1 | 0 | 0
09-6110 | TILING SUB SUPPORT | 5000 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 5000 | hold | sub | 0 | 1 | 0 | 0
09-6200 | VCT FLOORING SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
09-6300 | PAINT SUB | 533755 | 0 | 0 | 0 | 51071.4286 | 141428.5714 | 17500 | 75000 | 17500 | 0 | 0 | 0 | 302500 | SOV | Sub | 0 | 0.56674 | 0 | 0
09-6310 | PAINTING SUB SUPPORT | 40000 | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 40000 | hold | sub | 0 | 1 | 0 | 0
10-1000 | FIRE EXTINGUISHERS NEW BLDGS | 2772.14 | 935.19 | 0 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 0 | 0 | 0 | 2772.14 | Phased | Labor | New Buildings | 1 | 0 | 0
10-1100 | TOILET ACCESSORIES NEW BLDGS | 11021.7 | 0 | 0 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 0 | 0 | 0 | 11021.7 | Phased | Labor | New Buildings | 1 | 0 | 0
10-1200 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) | 289147.86 | 14136.86 | 17188.1875 | 17188.1875 | 34376.375 | 34376.375 | 68752.75 | 68752.75 | 17188.1875 | 17188.1875 | 0 | 0 | 289147.86 | Phased | Labor | Existing Buildings | 1 | 0 | 0
10-1300 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) | 22248.03 | 11153.39 | 693.415 | 693.415 | 1386.83 | 1386.83 | 2773.66 | 2773.66 | 693.415 | 693.415 | 0 | 0 | 22248.03 | Phased | Labor | Existing Buildings | 1 | 0 | 0
10-1400 | WINDOW FLOODGATES (8.06 AND 8.14) | 50000.29 | 0 | 3125.0181 | 3125.0181 | 6250.0363 | 6250.0363 | 12500.0725 | 12500.0725 | 3125.0181 | 3125.0181 | 0 | 0 | 50000.29 | Phased | Labor | Existing Buildings | 1 | 0 | 0
10-1500 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE | 19069.74 | 5523.22 | 846.6575 | 846.6575 | 1693.315 | 1693.315 | 3386.63 | 3386.63 | 846.6575 | 846.6575 | 0 | 0 | 19069.74 | Phased | Labor | Existing Buildings | 1 | 0 | 0
10-5000 | FURNISH TOILET ACCESSORIES | 1488.1 | 0 | 1488.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488.1 | phased | Material | 0 | 1 | 0 | 0
10-5100 | FURNISH FIRE EXTINGUISHERS | 2450 | 0 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450 | phased | Material | 0 | 1 | 0 | 0
10-5200 | FURNISH AQUA FLOOD BARRIERS | 1682724.63 | 938308 | 186104.1575 | 186104.1575 | 186104.1575 | 186104.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 1682724.63 | phased | Material | 0 | 1 | 0 | 0
10-5300 | FURNISH 8.08 FLOOD DOORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
11-1000 | EXCAVATE & POUR CONCRETE FOOTINGS | 35505.12 | 0 | 5917.52 | 5917.52 | 5917.52 | 0 | 0 | 5917.52 | 5917.52 | 5917.52 | 0 | 0 | 35505.12 | Phased | Labor | Site Restoration | 1 | 0 | 0
11-6000 | PLAY AREA ITEMS SUB | 426718.49 | 224018 | 50675.1225 | 50675.1225 | 0 | 0 | 0 | 0 | 50675.1225 | 50675.1225 | 0 | 0 | 426718.49 | Phased | Sub | 0 | 1 | 0 | 0
11-6010 | SUPPORT PLAY AREA | 50000 | 13225.17 | 0 | 0 | 0 | 0 | 0 | 6411.3733 | 6411.3733 | 23952.0833 | 0 | 0 | 50000 | Phased | Labor | Sub Support | 1 | 0 | 0
14-6000 | ELEVATOR SUB | 1027903.5 | 31860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1027903.5 | hold | sub | 0 | 1 | 0 | 0
14-6010 | ELEVATOR JUNCTION BOXES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
22-5000 | Purchase Yard Pumps | 99876.64 | 0 | 0 | 39876.64 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 99876.64 | phased | Material | 0 | 1 | 0 | 0
22-6000 | PLUMBING SUB | 13100000 | 8426271.83 | 568177.9197 | 502610.633 | 514449.7498 | 550282.8988 | 415097.0032 | 192758.2754 | 0 | 0 | 0 | 0 | 11169648.31 | SOV | Sub | 0 | 0.85264 | 0 | 0
22-6010 | PLUMBING BOND | 125426 | 125426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125426 | spent | spent | 0 | 1 | 0 | 0
22-6020 | PIPE INSULATION | 450000 | 173905 | 26472.0455 | 61606.7045 | 78393.75 | 34350 | 0 | 0 | 0 | 0 | 0 | 0 | 374727.5 | SOV | Sub | 0 | 0.83273 | 0 | 0
22-6025 | PLUMBING INSULATION REMOVAL | 25000 | 8405.69 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.72 | 0 | 0 | 0 | 0 | 25000.0017 | Phased | Labor | Sub Support | 1 | 0 | 0
22-6030 | YARD PUMP SUPPLY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
22-6040 | YARD PUMP INSTALL | 209344 | 36465.86 | 10804.8838 | 10804.8838 | 21609.7675 | 21609.7675 | 43219.535 | 43219.535 | 10804.8838 | 10804.8838 | 0 | 0 | 209344 | Phased | Labor | Existing Buildings | 1 | 0 | 0
22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | 41078 | 41078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41078 | spent | spent | 0 | 1 | 0 | 0
22-6060 | PLUMBING SUB SUPPORT | 3359.95 | 3359.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3359.95 | spent | spent | 0 | 1 | 0 | 0
22-6070 | PLUMBING SCAFFOLD | 10000 | 8249.4 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 291.77 | 0 | 0 | 0 | 0 | 10000.0033 | Phased | Labor | Sub Support | 1 | 0 | 0
23-6000 | HVAC SUB | 24100000 | 19052215.68 | 966300.1784 | 1053107.6173 | 1288338.8215 | 796401.3526 | 319764.821 | 279375.7121 | 90559.3773 | 24200 | 0 | 0 | 23870263.5602 | SOV | Sub | 0 | 0.99047 | 0 | 0
23-6010 | HVAC SUB SUPPORT | 200000 | 0 | 33333.3333 | 33333.3333 | 33333.3333 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | phased | sub | 0 | 1 | 0 | 0
23-6020 | MECHANICAL LOUVERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
26-6000 | ELECTRICAL SUB | 50099472.19 | 24286356.65 | 1867711.1396 | 2154626.4502 | 1779954.9915 | 2860913.6249 | 2713967.4611 | 2696110.3183 | 2304559.6893 | 1422455.9379 | 1421487.3515 | 0 | 43508143.6145 | SOV | Sub | 0 | 0.86844 | 0 | 0
26-6010 | TEMP ELECTRIC | 2449.46 | 2449.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2449.46 | spent | spent | 0 | 1 | 0 | 0
26-6020 | ELECTRICAL SUB SUPPORT | 50156.66 | 345.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50156.66 | hold | sub | 0 | 1 | 0 | 0
26-6030 | EQUIPMENT INSTALLATION SUPPORT | 30000 | 22091.48 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.56 | 0 | 0 | 29999.995 | Phased | Labor | Sub Support | 1 | 0 | 0
31-1000 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND CONCRETE | 250000 | 184612.63 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 10897.9 | 0 | 0 | 0 | 0 | 250000.005 | Phased | Labor | Existing Buildings | 1 | 0 | 0
31-1100 | BACKFILL FOR FLOOD BARRIER FFTGS & CONCRETE SHELF | 152500 | 115113.87 | 7727.625 | 7727.625 | 7727.625 | 7727.625 | 6475.63 | 0 | 0 | 0 | 0 | 0 | 152500 | Phased | Labor | Existing Buildings | 1 | 0 | 0
31-1200 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - ALL EXIST BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-1300 | EXCAVATION NEW BLDGS | 205909.86 | 205909.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205909.86 | spent | spent | 0 | 1 | 0 | 0
31-1400 | BACKFILL NEW BLDGS | 150000 | 148114.7 | 942.65 | 942.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | Phased | Labor | New Buildings | 1 | 0 | 0
31-1500 | BACKFILL STONE/GRAVEL/CRUSHED STONE - ALL | 25000 | 23506.32 | 746.84 | 746.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | Phased | Labor | New Buildings | 1 | 0 | 0
31-1600 | PUMP OPERATOR FOR FLOOD BARRIERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-1700 | DEWATER NEW BLDGS | 140469.48 | 140469.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140469.48 | spent | spent | 0 | 1 | 0 | 0
31-1800 | INSTALL H PILES | 26802.94 | 26802.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26802.94 | spent | spent | 0 | 1 | 0 | 0
31-1810 | SOE MATERIAL | 445577.25 | 445577.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445577.25 | spent | spent | 0 | 1 | 0 | 0
31-1820 | INSTALL SHEETING | 210938.15 | 208728.89 | 2209.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210938.15 | hold | labor | New Buildings | 1 | 0 | 0
31-1830 | INSTALL LAGGING | 55626.32 | 55626.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55626.32 | spent | spent | 0 | 1 | 0 | 0
31-1840 | MUD SLAB | 55578.77 | 55578.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55578.77 | spent | spent | 0 | 1 | 0 | 0
31-1850 | SOE Sub | 402338.93 | 402338.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402338.93 | spent | spent | 0 | 1 | 0 | 0
31-1860 | SOE Sub Support | 15201.85 | 15201.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15201.85 | spent | spent | 0 | 1 | 0 | 0
31-1900 | TREE PROTECTION | 50000 | 44097.39 | 0 | 0 | 0 | 0 | 0 | 5902.61 | 0 | 0 | 0 | 0 | 50000 | hold | labor | Site Utilities | 1 | 0 | 0
31-2000 | TEST PIT SUPPORT | 83241.53 | 83241.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83241.53 | spent | spent | 0 | 1 | 0 | 0
31-2010 | HAND EXCAVATION SUPPORT | 1978.47 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978.47 | spent | spent | 0 | 1 | 0 | 0
31-2100 | EXCAVATION FOR SITE FURNISHING FOOTINGS | 40000 | 19420.72 | 5905.44 | 3668.46 | 3668.46 | 3668.46 | 3668.46 | 0 | 0 | 0 | 0 | 0 | 40000 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-2200 | BACKFILL UTILITIES | 383288.4 | 311170.6 | 15940.65 | 15940.65 | 15940.65 | 15940.65 | 8355.2 | 0 | 0 | 0 | 0 | 0 | 383288.4 | Phased | Labor | Site Utilities | 1 | 0 | 0
31-2300 | EXCAVATION FOR PAVEMENTS | 10328.22 | 0 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 0 | 0 | 0 | 0 | 10328.22 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-2400 | BACKFILL AND COMPACTION FOR PAVEMENTS | 7141.61 | 0 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.27 | 0 | 0 | 0 | 0 | 7141.6117 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-2500 | DENSE GRADED STONE BASE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-2600 | SITE FURNISHINGS | 38534.4 | 3313.85 | 0 | 0 | 0 | 8891.0525 | 8891.0525 | 8891.0525 | 8547.3925 | 0 | 0 | 0 | 38534.4 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-2700 | BOLLARDS | 4816.8 | 0 | 0 | 0 | 0 | 2408.4 | 2408.4 | 0 | 0 | 0 | 0 | 0 | 4816.8 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-2800 | DRINKING FOUNTAIN | 30000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 30000 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-2900 | LANDSCAPE BOULDERS | 80000 | 67325.84 | 7674.16 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-3000 | BASKETBALL BACKSTOP | 3296.32 | 0 | 0 | 0 | 0 | 0 | 0 | 1648.16 | 1648.16 | 0 | 0 | 0 | 3296.32 | Phased | Labor | Site Restoration | 1 | 0 | 0
31-4000 | VAC TRUCKING SUB | 130000 | 118443.18 | 5000 | 6556.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | Phased | Sub | 0 | 1 | 0 | 0
31-5000 | FURNISH GRAVEL | 12744 | 0 | 0 | 0 | 0 | 12744 | 0 | 0 | 0 | 0 | 0 | 0 | 12744 | phased | Material | 0 | 1 | 0 | 0
31-5100 | FURNISH CLEAN FILL | 60000 | 7761.75 | 13059.5625 | 13059.5625 | 13059.5625 | 13059.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | phased | Material | 0 | 1 | 0 | 0
31-6000 | DISPOSAL & TRUCKING SUB | 1710399 | 1449641.33 | 80000 | 40000 | 40000 | 40000 | 20000 | 20000 | 10000 | 10757.67 | 0 | 0 | 1710399 | Phased | Sub | 0 | 1 | 0 | 0
31-6100 | DEWATERING SUB | 38820 | 38820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38820 | spent | spent | 0 | 1 | 0 | 0
31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6120 | INSTALL SETTLING TANK AND DISCHARGE PIPING BEYOND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6130 | DISCHARGE LOCATIONS NOT INCLUDED WITHIN DEWATERING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6140 | DEEP WELL INSTALL SUPPORT & CLEANUP LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6180 | WATER TREATMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6190 | ELECTRIC SERVICE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6200 | DUMPSTERS FOR DEWATERING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-6210 | DEWATERING DISCHARGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-7000 | LUMBER - TREE PROTECTION | 22925.01 | 22925.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22925.01 | spent | spent | 0 | 1 | 0 | 0
31-7100 | DEWATERING PUMPS | 14.07 | 14.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.07 | spent | spent | 0 | 1 | 0 | 0
31-7200 | SOLDIER PILE & LAGGING BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-7300 | TRENCH BOX - UTILITY TRENCHES | 256261.83 | 190820.52 | 15000 | 15000 | 15000 | 15000 | 5441.31 | 0 | 0 | 0 | 0 | 0 | 256261.83 | Phased | Labor | Site Utilities | 1 | 0 | 0
31-7400 | PLATES - UTILITY TRENCHES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
31-7500 | LUMBER - UTILITY TRENCHES | 16396.43 | 16396.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16396.43 | spent | spent | 0 | 1 | 0 | 0
32-5000 | FURNISH BOLLARDS | 10010 | 10010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10010 | spent | spent | 0 | 1 | 0 | 0
32-5100 | FURNISH SUBBASE | 56700 | 0 | 0 | 0 | 10000 | 10000 | 20000 | 10000 | 6000 | 0 | 0 | 0 | 56000 | phased | Material | 0 | 0.98765 | 0 | 0
32-5200 | FURNISH BENCHES & TABLES | 393000 | 190392.5 | 50651.875 | 50651.875 | 50651.875 | 50651.875 | 0 | 0 | 0 | 0 | 0 | 0 | 393000 | phased | Material | 0 | 1 | 0 | 0
32-5300 | FURNISH PING PONG TABLE | 32700 | 22413 | 2571.75 | 2571.75 | 2571.75 | 2571.75 | 0 | 0 | 0 | 0 | 0 | 0 | 32700 | phased | Material | 0 | 1 | 0 | 0
32-5400 | FURNISH BIKE RACK | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | phased | Material | 0 | 1 | 0 | 0
32-5500 | FURNISH DRINKING FOUNTAIN | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | phased | Material | 0 | 1 | 0 | 0
32-5600 | FURNISH SHOWER EQUIPMENT | 26188.02 | 0 | 0 | 0 | 0 | 26188.02 | 0 | 0 | 0 | 0 | 0 | 0 | 26188.02 | phased | Material | 0 | 1 | 0 | 0
32-5700 | FURNISH LANDSCAPE BOULDERS | 191092.5 | 191092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191092.5 | spent | spent | 0 | 1 | 0 | 0
32-5800 | FURNISH BASKETBALL BOARD AND POST | 5340 | 0 | 0 | 0 | 0 | 5340 | 0 | 0 | 0 | 0 | 0 | 0 | 5340 | phased | Material | 0 | 1 | 0 | 0
32-6000 | SAWCUTTING | 134276.38 | 134276.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134276.38 | spent | spent | 0 | 1 | 0 | 0
32-6100 | ASPHALT SUB | 210269.79 | 0 | 0 | 0 | 0 | 0 | 0 | 70089.93 | 70089.93 | 70089.93 | 0 | 0 | 210269.79 | Phased | Sub | 0 | 1 | 0 | 0
32-6200 | FLATWORK SUB | 3075000 | 243350 | 190246.0105 | 355256.0073 | 436078.6937 | 204528.6937 | 268147.1429 | 165700 | 29095.2381 | 381936.6667 | 273918.0952 | 0 | 2548256.548 | SOV | Sub | 0 | 0.8287 | 0 | 0
32-6210 | FLATWORK SUB SUPPORT | 134287 | 2098.7 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 82098.7 | Hold | Labor | Sub Support | 0.61137 | 0 | 0
32-6220 | JMC EQUIP BACKCHARGE | 9119.41 | 9119.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9119.41 | spent | spent | 0 | 1 | 0 | 0
32-6230 | GRADING FOR RESTORATION | 200000 | 73467.84 | 35366.595 | 30000 | 30000 | 30000 | 1165.565 | 0 | 0 | 0 | 0 | 0 | 200000 | Phased | Labor | Site Restoration | 1 | 0 | 0
32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
32-6400 | COURT SURFACES SUB | 415000 | 0 | 0 | 0 | 0 | 0 | 0 | 141666.6667 | 141666.6667 | 131666.6667 | 0 | 0 | 415000 | Phased | Sub | 0 | 1 | 0 | 0
32-6410 | Prep Basketball Courts | 10000 | 3129.11 | 6870.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | Phased | Labor | Site Restoration | 1 | 0 | 0
32-6500 | FENCING SUB | 1318652.5 | 757678.8 | 0 | 0 | 0 | 67720.9302 | 42461.9638 | 23636.4858 | 373930.6202 | 53223.7 | 0 | 0 | 1318652.5 | SOV | Sub | 0 | 1 | 0 | 0
32-6510 | FENCE MESH INSTALL | 99496.11 | 94176.81 | 1453.4117 | 1453.4117 | 1453.4117 | 1000 | -40.935 | 0 | 0 | 0 | 0 | 0 | 99496.11 | Phased | Labor | Site Maintenance | 1 | 0 | 0
32-6520 | FENCE INSTALL SELF PERFORM | 507000 | 340387.76 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 26612.24 | 0 | 0 | 507000 | Phased | Labor | Site Maintenance | 1 | 0 | 0
32-6600 | LANDSCAPING SUB | 635225.54 | 77215.59 | 0 | 0 | 31696.4952 | 60832.5068 | 0 | 0 | 0 | 214669.3285 | 213247.9221 | 0 | 597661.8426 | SOV | Sub | 0 | 0.94087 | 0 | -37563.6974
32-6610 | CLEAR AND GRUB | 87764.08 | 87764.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87764.08 | spent | spent | 0 | 1 | 0 | 0
32-6620 | SELF PERFORM TREE REMOVAL | 24373.2 | 24373.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24373.2 | Phased | Labor | Site Restoration | 1 | 0 | 0
32-6630 | LANDSCAPING SUB SUPPORT | 50000 | 23531.37 | 0 | 0 | 12500 | 12500 | 1468.63 | 0 | 0 | 0 | 0 | 0 | 50000 | hold | Labor | Sub Support | 1 | 0 | 0
32-6700 | Arbor Consultant | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | spent | spent | 0 | 1 | 0 | 0
33-1000 | MAINT & PROT EXIST PRIVATELY OWNED UTILITIES | 51626.6 | 44180.68 | 1789.6529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 0 | 0 | 0 | 0 | 51626.5971 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-1100 | TERMINATE AND DEMOLISH EXISTING UTILITIES | 56789.26 | 13848.58 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.38 | 0 | 0 | 0 | 56789.2571 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-1200 | WATER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1300 | WELDING OF WATER PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1310 | WATER PIPE FIT UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1400 | INSTALL JOJNT INSULATORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1500 | PRESSURE & AIR TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1600 | FIX 10% FAILURE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1700 | PRESSURE & AIR RE-TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1800 | CONDENSATE & STEAM PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1900 | WELDING OF STEAM AND CONDENSATE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-1910 | STEAM AND CONDENSATE PIPE FIT UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-2000 | INSTALL JOJNT INSULATORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-2100 | PRESSURE & AIR TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-2200 | FIX 10% FAILURE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-2210 | EXCAVATE UTILITIES | 2945.71 | 2945.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2945.71 | spent | spent | 0 | 1 | 0 | 0
33-2300 | PRESSURE & AIR RE-TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-2400 | DEWATER UTILITIES | 53037.69 | 53037.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53037.69 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-2500 | DUCTILE IRON PIPE SEWERS | 276988.13 | 194495.9 | 18158.716 | 18158.716 | 18158.716 | 28016.082 | 0 | 0 | 0 | 0 | 0 | 0 | 276988.13 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-2510 | SEWER LINE WORK | 200000 | 60613.81 | 20000 | 20000 | 28803.258 | 30000 | 20000 | 20582.932 | 0 | 0 | 0 | 0 | 200000 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-2600 | CATCH BASIN CONNECTIONS | 313516.44 | 192176.25 | 20000 | 20000 | 31159 | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | 313335.25 | Phased | Labor | Site Utilities | 0.99942 | 0 | 0
33-2700 | STORM DETENTION TANK (I DON'T THINK THIS EXISTS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-2800 | DRAINAGE MANHOLES | 21873.24 | 552.53 | 4264.142 | 4264.142 | 4264.142 | 4264.142 | 4264.14 | 0 | 0 | 0 | 0 | 0 | 21873.238 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-2900 | REMOVE AREA DRAINS | 32809.86 | 26769.12 | 1357.084 | 1357.084 | 1357.084 | 1969.488 | 0 | 0 | 0 | 0 | 0 | 0 | 32809.86 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-3000 | ELECTRICAL MANHOLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-3100 | UTILITY TRENCHES | 717109.62 | 687874.38 | 8955.502 | 5000 | 5000 | 10279.738 | 0 | 0 | 0 | 0 | 0 | 0 | 717109.62 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-3200 | FENCES & PLATES @ TRENCHES (THIS WILL BE DIFFERENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-3300 | ADD''L CRANE FOR SUBCONTRACTORS SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-4000 | SITE LIGHTING EXCAVATION | 84000 | 7476.97 | 10000 | 10000 | 10000 | 10000 | 15000 | 15000 | 6523.03 | 0 | 0 | 0 | 84000 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | 881653.58 | 723107.04 | 40767.885 | 40767.885 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 884642.81 | phased | Material | 0 | 1.0034 | 0 | 0
33-5100 | FURNISH 2 COPPER WATER PIPE | 115654.5 | 0 | 0 | 0 | 0 | 25000 | 25000 | 35000 | 30654.5 | 0 | 0 | 0 | 115654.5 | phased | Material | 0 | 1 | 0 | 0
33-5200 | FURNISH DIP DRAINAGE PIPE | 276580.36 | 276580.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276580.36 | spent | spent | 0 | 1 | 0 | 0
33-5300 | FURNISH PRECAST AREA DRAINS & MHS | 126016 | 77921.81 | 9211.0475 | 12961.0475 | 12961.0475 | 12961.0475 | 0 | 0 | 0 | 0 | 0 | 0 | 126016 | phased | Material | 0 | 1 | 0 | 0
33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-5500 | FURNISH DETENTION TANK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
33-5600 | CHLORINATION | 100000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 100000 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-6000 | UNDERGROUND UTILITY MATERIAL DELIVERY | 25000 | 20750.65 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 0 | 0 | 0 | 25000 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-6010 | UTILITY PIPE PLACEMENT IN TRENCH | 115000 | 104182.59 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.34 | 0 | 0 | 0 | 114999.9957 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-7000 | WELDING MATERIALS | 32664 | 20429.16 | 1199.567 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 0 | 0 | 0 | 0 | 0 | 32663.9956 | Phased | Labor | Site Utilities | 1 | 0 | 0
33-9000 | GAS LINE DAMAGE | 110287.72 | 83073.27 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 0 | 0 | 110287.72 | Phased | Labor | Site Utilities | 1 | 0 | 0
97-6000 | Bulk ACM removal, hose wire insulation | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | Hold | Labor | Change Order | 1 | 0 | 0
97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 74 | Hold | Labor | Change Order | 1 | 0 | 0
97-6200 | Bulk ACM removal, pipe insulation and assoc jack | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | Hold | Labor | Change Order | 1 | 0 | 0
97-6300 | Bulk ACM removal, pipe insulation and braided wire | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | Hold | Labor | Change Order | 1 | 0 | 0
97-6400 | Bulk ACM removal, ACM Contamined Debris | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | Hold | Labor | Change Order | 1 | 0 | 0
97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | Hold | Labor | Change Order | 1 | 0 | 0
97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | Hold | Labor | Change Order | 1 | 0 | 0
97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | Hold | Labor | Change Order | 1 | 0 | 0
97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 85 | Hold | Labor | Change Order | 1 | 0 | 0
97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | Hold | Labor | Change Order | 1 | 0 | 0
98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | 54722.86 | 2796.2 | 51926.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54722.86 | Phased | Labor | Site Utilities | 1 | 0 | 0
98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | 141408 | 140826.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140826.98 | Phased | Labor | Site Utilities | 0.99589 | 0 | 0
99-1000 | Supervision | 7270000 | 5471488.67 | 220000 | 220000 | 242000 | 220000 | 220000 | 175000 | 175000 | 150000 | 100000 | 67763.55 | 7261252.22 | Phased | overhead | 0 | 0.9988 | 0 | 0
99-1010 | CLAIMS CONSULTANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-1020 | LEGAL COSTS | 50000 | 5030 | 0 | 0 | 0 | 0 | 0 | 4970 | 10000 | 10000 | 10000 | 10000 | 50000 | Phased | overhead | 0 | 1 | 0 | 0
99-1100 | TEAMSTER | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000 | hold | Contingency | 0 | 1 | 0 | 0
99-1200 | OPER ENG MASTER MECH | 270000 | 82331.19 | 0 | 0 | 0 | 27974.1557 | 27974.1557 | 27974.1557 | 0 | 0 | 0 | 0 | 166253.6571 | Hold | Labor | Site Maintenance | 0.61575 | 0 | 0
99-1300 | OPER ENG MECH | 260000 | 74008.48 | 0 | 0 | 0 | 27641.78 | 27641.78 | 27641.78 | 0 | 0 | 0 | 0 | 156933.82 | Hold | Labor | Site Maintenance | 0.60359 | 0 | 0
99-2000 | SURVEY SUB | 687620.75 | 510047 | 50000 | 47573.75 | 20000 | 20000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 687620.75 | Phased | Sub | 0 | 1 | 0 | 0
99-3000 | SECURITY SUB | 648295.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648295.5 | hold | Contingency | 0 | 1 | 0 | 0
99-3100 | CONTAINERS - 30 CY | 1150000 | 710968.41 | 60000 | 60000 | 60000 | 50000 | 50000 | 50000 | 50000 | 30000 | 29031.59 | 0 | 1150000 | Phased | Material | 0 | 1 | 0 | 0
99-4000 | YARD W/ TEMP ELECT | 138034 | 119118.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 8915.59 | 138034 | Phased | Labor | Closeout | 1 | 0 | 0
99-4050 | COMPUTER/SOFTWARE | 90000 | 83929.46 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 90000 | monthly | overhead | 0 | 1 | 0 | 0
99-4100 | STATIONWORK DESK | 8710.4 | 6193.68 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 8710.4 | monthly | overhead | 0 | 1 | 0 | 0
99-4150 | IT SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-4200 | PHONE EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-4250 | PHONE SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-4300 | PRINTERS/PLOTTER | 55000 | 42298.26 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 55000 | monthly | overhead | 0 | 1 | 0 | 0
99-4350 | SUPPLIES | 90000 | 61801.63 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 90000 | monthly | overhead | 0 | 1 | 0 | 0
99-4400 | TELEPHONE | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | hold | Contingency | 0 | 1 | 0 | 0
99-4450 | CELL PHONES | 29506.48 | 19721.09 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 29506.48 | monthly | overhead | 0 | 1 | 0 | 0
99-4500 | ELECTRIC | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | hold | Contingency | 0 | 1 | 0 | 0
99-4550 | SANITATION | 305000 | 154554.47 | 15044.553 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 10000 | 5000 | 400.977 | 305000 | Phased | overhead | 0 | 1 | 0 | 0
99-4560 | SITE MAINTENANCE | 1110000 | 859428.62 | 52771.38 | 34560 | 34560 | 34560 | 17280 | 17280 | 17280 | 17280 | 15000 | 10000 | 1110000 | Phased | Labor | Site Maintenance | 1 | 0 | 0
99-4570 | BASEMENT MAINTENANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-4600 | VEHICLES | 160347.74 | 82359.38 | 20000 | 10000 | 10000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 2988.36 | 160347.74 | Phased | Equipment | 0 | 1 | 0 | 0
99-4650 | FUEL | 158001.22 | 141349.77 | 5000 | 5000 | 5000 | 5000 | 3000 | -6348.55 | 0 | 0 | 0 | 0 | 158001.22 | Phased | Equipment | 0 | 1 | 0 | 0
99-4700 | PETTY CASH | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000 | hold | Contingency | 0 | 1 | 0 | 0
99-5000 | OFFICE RENT | 561000 | 453395.18 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13110.3144 | 0 | 0 | 560999.9956 | Phased | overhead | 0 | 1 | 0 | 0
99-5100 | NYCHA OFFICE FURNITURE | 55000 | 38878.87 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 55000 | monthly | overhead | 0 | 1 | 0 | 0
99-6000 | SMALL TOOLS | 640000 | 548834.52 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 9770.2436 | 0 | 640000 | monthly | Material | 0 | 1 | 0 | 0
99-7000 | LABOR ESCAL | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | hold | Contingency | 0 | 1 | 0 | 0
99-7100 | PREMIUM COST | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | hold | Contingency | 0 | 1 | 0 | 0
99-7200 | HOLIDAY PAY | 265722.37 | 211272.38 | 29609.99 | 9200 | 0 | 0 | 6440 | 0 | 4600 | 0 | 4600 | 0 | 265722.37 | Phased | overhead | 0 | 1 | 0 | 0
99-7210 | PAID TIME OFF | 68000 | 28288.38 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 68000 | monthly | overhead | 0 | 1 | 0 | 0
99-7300 | LOST TIME | 150000 | 49377.75 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 18294.9545 | 150000 | hold | overhead | 0 | 1 | 0 | 0
99-7400 | PERMITS | 30000 | 18673.7 | 2831.5775 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 0 | 0 | 0 | 30000.0025 | Phased | overhead | 0 | 1 | 0 | 0
99-7500 | ENGINEERING SUB | 183350 | 171007.28 | 3085.68 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 0 | 0 | 0 | 183350 | Phased | Sub | 0 | 1 | 0 | 0
99-7510 | CADD SERVICES | 20000 | 12795.69 | 1801.0787 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 0 | 0 | 0 | 20000.0013 | Phased | overhead | 0 | 1 | 0 | 0
99-7600 | SECTION 3 ADMINISTRATOR SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-8000 | EQUIPMENT | 1561716.25 | 1098857 | 80000 | 80000 | 60000 | 50000 | 40000 | 30000 | 20000 | 17725.98 | 85133.27 | 0 | 1561716.25 | Phased | Equipment | 0 | 1 | 0 | 0
99-8050 | AID TO SUBS | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 250000 | Phased | Sub | 0 | 1 | 0 | 0
99-8100 | PROJECT SIGNS | 4000 | 3181.22 | 148.8645 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 0 | 3925.5609 | monthly | Material | 0 | 0.98139 | 0 | 0
99-8200 | PUNCH LIST | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 250000 | Phased | Labor | Closeout | 1 | 0 | 0
99-9000 | BOND | 1170144 | 948765.41 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 1170144 | monthly | overhead | 0 | 1 | 0 | 0
99-9100 | INSURANCE | 3248000 | 1926514.35 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 3248000 | monthly | overhead | 0 | 1 | 0 | 0
99-9999 | Accruals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0 | 0
99-NY0001 | Supervision- Do Not Use | 22408.12 | 22408.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22408.12 | spent | spent | 0 | 1 | 0 | 0