## Cost Forecast
Code | Name | Projected Forecast | Spent to Date | February | March | April | May | June | July | August | September | October | Final Cost | Breakdown Type | Cost Type 1 | Cost Type 2 | Category 1 | Forecast Spent % | January | Cost Category 1 | Cost Category 2 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22
00-0001 | SECOND FLOOR APARTMENT REMOVALS | 14032 | 14032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0002 | SITE 8 SLAB SHORING | 15736.31 | 15736.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0003 | OG8 Obstruction Removal | 17042.53 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0004 | Floor Drain PCO | 0 | 17791.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0005 | Equipment Pad PCO | 15000 | 14912.24 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0006 | PCO 15 Additional Windows PCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0007 | IRMA PAGAN APARTMENT MOVE | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0008 | National Grid Gas Line Relocation | 11667.88 | 11667.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0009 | Bracing for POE Penetration Through SG4 Wall | 7468.26 | 7468.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0010 | SG1 RELOCATE BELONGINGS | 21773.44 | 21773.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0011 | PERAMBULATOR ROOM DEMO | 18064.37 | 18064.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0012 | OG8 Tank Removal | 20378.14 | 372.43 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0013 | Exist Bldgs Bracing due to Penetrations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0014 | SG4 DEMO FOR STEEL BEAMS INSTALL | 1285.34 | 1285.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0015 | SG5 DEMO FOR STEEL BEAMS INSTALL | 1678.93 | 1678.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0016 | OG4 BRACING FOR POE PENETRATION | 164120.78 | 30850.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0017 | National Grid Additional Allowance | 205770.46 | 5887.46 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0018 | SG6 Additional Strobe | 2387.08 | 0 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0019 | ODWYER FENCE INSTALL | 60000 | 62577.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0021 | MOVE PLAYGROUNDS | 1941.36 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0022 | SITE 8 CLEANING | 5968.61 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0023 | S8 FIRE STAND PIPE ACCESS | 59605.91 | 7156.91 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0024 | Boiler Stack Support | 64820.84 | 1417 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0025 | Bulletin 1 Civil PCO 44 | 76640 | 30736.74 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0026 | DOOR HARDWARE CHANGES | 21947.23 | 0 | 0 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0027 | BOILER ACCESSORY SUPPLY | 185547.35 | 0 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0028 | SITE 8 ELECTRICAL REPAIRS | 21203.36 | 0 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0029 | PCO46 SANITARY VENTING OG5 & OG6 | 69207.97 | 0 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0030 | PCO 54 ACM ABATEMENT MASONRY WATERPROOFING | 120833.26 | 0 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0031 | PCO 55 ACM ABATEMENT UTILITY WATERPROOF | 241793.37 | 0 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0032 | PCO 64 OG10 ADDITIONAL SWITCH | 2369.68 | 0 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0033 | PCO 66 ELECTRICAL DB FOUNDATION CONFLICT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0034 | PCO 76 ADDITIONAL FIRE EXTINGUISHERS | 3809.76 | 0 | 0 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0035 | PCO 77 ACM ABATEMENT SGS STEAM PIPE | 111590.33 | 0 | 0 | 33000 | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0036 | PCO 99 SG5 APARTMENT RENO | 9892.17 | 9892.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0037 | JACOBS TRAILER MOVE | 2879.76 | -30038.69 | 32918.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0038 | PCO 59 SGS REDESIGN | 557295.88 | 4726.71 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0039 | AC UNIT DEMO | 7582.95 | 7582.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0040 | PCO 8 BULLETIN 1 ELECTRICAL | 38953 | 0 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0041 | PCO 19 WINDOW INFILL | 5922.43 | 0 | 5922.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0042 | PCO 40 SG6 STUD RELOCATION | 10923.98 | 0 | 10923.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0043 | PCO 59 SGS ELECTRICAL CHANGES | 213.43 | 213.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0044 | PCO 74 OG9 AND S8 GENERATOR SUPPORTS | 60248.81 | 39449.71 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0045 | PCO 79 ACM FILING | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0046 | PCO 85 OG4 & OG5 TANK INSULATION ACM | 75690.92 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0047 | PCO 90 ODYWER TRAILER POWER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0048 | PCO 45 BULLETIN 1 MECHANICAL | 154900.73 | 0 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0049 | PCO 83 SG6 METAL PANEL SUPPORT | 70919.49 | 0 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0050 | PCO 63 Conduit Concrete Encasement | 225393.38 | 0 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0051 | PCO 49 Electrical Clash with LPS | 9430.53 | 0 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0052 | PCO 93 Roof Access and ATS Door | 125820.09 | 9185.52 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0053 | PCO 100 Exterior Framing OG8, OG9, OG10 | 204711.04 | 0 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0054 | PCO 48 Restore Walkways | 5772.17 | 9506.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0055 | Pit Covers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0056 | PCO 27 OG8 Structural Steel | 94993.6 | 0 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0057 | PCO 80 LPS Reroute OG6 | 10884.19 | 0 | 10884.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0058 | PCO 98 OG6 Structural Steel | 6536.32 | 1612.44 | 4923.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0059 | PCO 117 OG1 Ramp Restore | 9555.81 | 9555.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0060 | PCO 78 OG10 Clash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0061 | PCO 108 STREET CROSSING | 290768 | 96922.67 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0062 | PCO 143 SG2 SHELF SUPPORT | 0 | 2073.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0063 | PCO 144 SG3 BASEMENT CLEANING | 0 | 17678.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0064 | PCO 148 EB BACKWATER VALVES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0065 | PCO 17 PLUMBING PIT REINF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0066 | PCO 18 SG6 SHAFT BRACING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0067 | PCO 26 SG6 STAIR MOD | 16182.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0068 | PCO 86 OG1 MANHOLE REROUTE | 19514.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0069 | PCO 97 OG2 OG3 STEAM TUNNEL ACM | 14297.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0070 | PCO 102 SGS OUTAGE | 16182.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0071 | PCO 116 ROOF FLASHING AT BULKHEAD | 13624.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0072 | PCO 142 GENERATOR EQUIP | 28230.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0073 | PCO 124 LOUVER SUPPORT | 0 | 3225.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0074 | PCO 131 SG1 DRAINAGE | 0 | 1430.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0075 | PCO 81 EB Structural Steel Fireproofing | 97275.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0076 | PCO 106 TANK INSUALTION ACM | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0077 | PCO 145 SG6 REVISED BULKHEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-0078 | PCO 152 OG4 STEAM LEAK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
00-1000 | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6000 | BUILDING CONDITIONS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6100 | CPM SUB | 73150 | 61170 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 0 | monthly | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6200 | PHOTO SUB | 87990 | 46410 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 0 | monthly | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6300 | OVERHEAD PROTECTION LABOR | 1472.69 | 1472.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6310 | OVERHEAD PROTECTION MATERIALS | 4491.11 | 4491.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6320 | OVERHEAD PROTECTION EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6400 | RODENT CONTROL SUB | 28596.9 | 14953.9 | 2000 | 2000 | 1223 | 1000 | 1000 | 1000 | 1000 | 2900 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
01-6410 | RODENT CONTROL SUB SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1000 | EROSION CONTROL FABRIC | 970.55 | 970.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1100 | INLET PROTECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1200 | SILT FENCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1300 | STABILIZED CONSTRUCTION ENTRANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1400 | MANTAIN EROSION CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1500 | REMOVE EROSION CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1600 | STOCKPILE | 4496.62 | 4496.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1700 | REMOVE FENCE | 62785.26 | 24231.19 | 7879.8 | 7879.8 | 5000 | 9914.67 | 7879.8 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1800 | REMOVE/REINSTALL BOLLARDS ODG EAST | 51378.15 | 627.92 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-1900 | REMOVE FULL DEPTH ASPHALT PVMT | 85977.83 | 82630 | 500 | 500 | 500 | 1070.7183 | 777.1117 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-2000 | REMOVE SITE FURNISHING | 77397.6 | 37619.77 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 5400.0133 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-2100 | REMOVE CONCRETE CURB & STEPS | 93000 | 85502.3 | 1833.3933 | 1833.3933 | 1833.3933 | 622.7967 | 1374.7233 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-2200 | REMOVE PVMTS | 97421.11 | 87670.24 | 4443.095 | 4721.06 | 586.715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-2300 | BASEMENT MAINTENANCE | 312373.79 | 249803.48 | 8640 | 8640 | 8640 | 8640 | 8640 | 4320 | 4320 | 4320 | 6410.31 | 0 | Phased | Labor | Site Maintenance | Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-3000 | CORE DRILLING | 578853.58 | 528822.04 | 10000 | 10000 | 10000 | 10000 | 10031.54 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6000 | OG-7 DEMO LABOR | 21560.01 | 21560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6001 | OG-7 DEMO EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6002 | OG-7 DEMO MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | 373189.17 | 333301.09 | 0 | 0 | 45221.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6006 | LEAD CONSULTANT | 19466.75 | 19466.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6007 | LEAD DISPOSAL | 5400.21 | 5400.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6008 | LEAD TRAINING | 8413.33 | 8413.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6009 | Paint Removal Elevator Pits | 67036 | 1052.44 | 0 | 0 | 66147.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6010 | REMOVE SUMP PUMPS | 36030 | 27496.03 | 1805.515 | 1805.515 | 1805.515 | 3117.43 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | 102770 | 73904.8 | 5369.995 | 5369.995 | 5369.995 | 5369.995 | 7385.22 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | 19766.24 | 6308.67 | 3112.9617 | 3112.9617 | 3112.9617 | 3112.9617 | 1005.7233 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6025 | REMOVE AREAWAYS LABOR | 82000 | 71381.46 | 2050.3233 | 2050.3233 | 2050.3233 | 2417.2467 | 2050.3233 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6026 | REMOVE AREAWAYS EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | 227761.46 | 385.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | 1520.48 | 0 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 253.41 | 253.4167 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | 15000 | 3487.09 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.82 | 1918.8167 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6050 | DEMO STAIRS AND RAMPS LABOR | 17116.64 | 12850.76 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | 2259.95 | 2259.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6060 | DEMO SECOND FLOOR APARTMENTS | 150000 | 130767.81 | 4808.0475 | 4808.0475 | 4808.05 | 4808.045 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6065 | DEMO FOR MECHANICAL | 200000 | 13880.04 | 2500 | 2500 | 45000 | 45000 | 45000 | 45000 | 1119.96 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6066 | FLOOR DRAIN DEMO | 70083.35 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6070 | DEMO FOR ELECTRICAL | 156200 | 29589.93 | 5000 | 5000 | 5000 | 40000 | 40000 | 31610.07 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6075 | DEMO FOR PLUMBING | 161879.62 | 16967.27 | 5000 | 5000 | 5000 | 40000 | 40000 | 49912.35 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6080 | ENTRANCE RAMP DEMO | 118800 | 46426.87 | 27937.11 | 25195.35 | 19240.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6100 | ASBESTOS SUB | 1554903.14 | 1302498.98 | 27745.7 | 34819.5 | 34316.6667 | 34316.6667 | 75119.0667 | 41802.4 | 38802.4 | 36177.4 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6110 | ASBESTOS SUB SUPPORT | 79333.7 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 9333.7 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6120 | ASEBESTOS CONSULTANT | 23896.55 | 23896.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-6130 | ASBESTOS SUB ACCESS | 25543.46 | 21820.5 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | 1900.42 | 1900.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-7100 | STONE FOR EROSION CONTROL | 32382.03 | 32382.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-7200 | SOIL TESTING | 83535 | 83535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1000 | FORMWORK NEW BUILDING | 2150000 | 2148203.85 | 12787.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1100 | FORMWORK EXIST BLDGS | 786238.54 | 546850.51 | 40000 | 40000 | 40000 | 40000 | 40000 | 15006.95 | 24381.08 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1105 | Conduit Encasement | 138600 | 97818.95 | 20000 | 20000 | 20000 | 5427.15 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1200 | OPERATOR FOR CONCRETE WORK | 29756.82 | 29756.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1300 | SET ANCHOR BOLTS FOR STEEL COLUMNS | 63065.21 | 63065.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1400 | DRILL & GROUT DOWELS | 274808.11 | 263152.93 | 6475.152 | 6475.152 | 6475.152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1500 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE | 162759.19 | 143861.99 | 6432.236 | 6432.236 | 3000 | 3032.728 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1600 | FORMWORK SITE CONCRETE LABOR | 150000 | 126752.74 | 6500 | 6500 | 6500 | 3747.26 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1610 | FORMWORK SITE CONCRETE MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1700 | CONCRETE REINFORCEMENT NEW BUILDING UNLOAD | 56763.12 | 56763.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1800 | CONCRETE REINFORCEMENT BARRIER FOUNDATIONS UNLOAD | 45000 | 38208.34 | 1455.676 | 1455.676 | 1455.676 | 1455.676 | 968.956 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-1900 | POUR CONCRETE NEW BUILDINGS | 530000 | 525785.09 | 4214.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2000 | FINISH SLABS - NEW BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2100 | POUR CONC EXIST BLDGS | 205190.25 | 189150.65 | 5000 | 5000 | 5000 | 1039.6 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2110 | SHOTCRETE SUB | 166500 | 90593.84 | 25302.0533 | 25302.0533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2120 | SHOTCRETE SUB CLEANUP | 30000 | 27911.35 | 2088.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2200 | CONCRETE FOOTING FOR SITE FURNISHING | 13759.32 | 0 | 0 | 3439.83 | 3439.83 | 3439.83 | 3439.83 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2300 | CONCRETE DUCTBANKS | 225000 | 218768.34 | 6231.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2400 | CONCRETE SITE RETAINING WALL AND FOOTINGS | 36435.9 | 25421.31 | 11014.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2500 | CONCRETE SHELF AND BOND BEAM EXTG BL (INCL FORMS) | 108745 | 103915.02 | 2658.22 | 2171.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2600 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL | 13834.32 | 726.04 | 0 | 0 | 0 | 3277.07 | 3277.07 | 3277.07 | 3277.07 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-2700 | EXISTING BLDGS EQUIPMENT PAD WORK | 95.84 | 95.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-5000 | FURNISH CONCRETE | 1749303.72 | 1435171.81 | 40000 | 40000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-5100 | FURNISH INSULATION | 39414.64 | 39414.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-5200 | FURNISH REBAR | 14662.42 | 13710.55 | 200 | 118.9838 | 59.4919 | 373.3944 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-5250 | FURNISH WIREMESH | 47762.13 | 35283.88 | 2500 | 1559.7812 | 1200 | 4218.4688 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-5400 | FURNISH SAKCRETE | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 31500 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-5500 | FURNISH CONC PATCH MATERIAL | 9174.5 | 9174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-6000 | FRP WORK | 420253.96 | 407746.27 | 12507.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-6010 | FRP Self Perform | 35296.6 | 35296.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-6100 | REBAR SUB | 1494408.08 | 1256293.37 | 41898.9371 | 41898.9371 | 41898.9371 | 94874.6514 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-6110 | REBAR SUB SUPPORT | 4416.84 | 3071.9 | 4069.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-6120 | REBAR DELIVERY SUPPORT | 4041.34 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-7000 | FORMWORK MATERIAL | 709305.66 | 551390.3 | 28000 | 28000 | 28000 | 28000 | 33397.62 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
03-7100 | MATERIAL FOR FLOWABLE FILL BACKFILL | 152745.59 | 152745.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-1000 | CLEAN CONC SURF FOUND WALL/PATCH VOIDS W/MORTAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-6000 | GROUT INJECTION SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-6100 | MASONRY SUB | 9090000 | 6613749.56 | 403372.1412 | 377150.6342 | 309000.6342 | 309000.6342 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-6110 | MASONRY SUB SUPPORT | 150000 | 25393.2 | 30000 | 30000 | 30000 | 30000 | 4606.8 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-6120 | MASON EUIP SUPPORT | 62569.54 | 62569.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-6130 | ANGLE FOR FACADE | 103266.58 | 69102.74 | 5000 | 5000 | 5000 | 19163.84 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-6200 | STONE SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
04-7000 | MASONRY CLEANER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6000 | STRUCTURAL STEEL SUB | 5918133.95 | 5907478.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6010 | STRUCTURAL STEEL SUB SUPPORT | 22760.18 | 15158.89 | 7601.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6020 | GROUT STEEL COLUMNS | 30000 | 27222.11 | 2070.29 | 707.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6030 | STEEL & CRANE DELIVERIES | 9097.96 | 9097.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6040 | Ground Prep For Crane | 8898.32 | 8898.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6050 | PREP COLUMNS FOR STEEL INSTALL | 2237.81 | 2237.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6100 | MISC METALS SUB | 2010175 | 871189.78 | 142327.963 | 70295.25 | 155988 | 103992 | 12999 | 38997 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6110 | MISC METALS SUB SUPPORT | 100040.22 | 7104.35 | 0 | 92935.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6120 | BACKCHARGE E&Y | 1174.65 | 1174.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6200 | SIGNAGE SUB | 138024 | 21000 | 0 | 11316 | 11316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
05-6210 | SIGNAGE SUB SUPPORT | 10000 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
06-6000 | CARPENTRY SUB | 1840000 | 1540449.87 | 117420.1925 | 67082.066 | 101775.2295 | 105521.171 | 57710.5855 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
06-6010 | CARPENTRY SUB SUPPORT | 50000 | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
06-6020 | EIFS | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-1000 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-1100 | 3 RIGID INSULATION UNDER GRADE NEW BLDGS | 34098.54 | 34098.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-1200 | PENETRATION FIRESTOPPING EXTG BLDGS | 55337.28 | 0 | 3458.58 | 6917.16 | 6917.16 | 13834.32 | 13834.32 | 3458.58 | 3458.58 | 3458.58 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-1300 | PENETRATION FIRESTOPPING NEW BLDGS | 27668.64 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-1400 | JOINT SEALANTS EXTG BLDGS | 55337.28 | 12860.73 | 2654.7844 | 5309.5688 | 5309.5688 | 10619.1375 | 10619.1375 | 2654.7844 | 2654.7844 | 2654.7844 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-1500 | JOINT SEALANTS NEW BLDGS | 27668.64 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-2000 | INSTALL WATERSTOP | 3491.54 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-5000 | FURNISH FIRESTOPPING | 90000 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-5100 | FURNISH JOINT SEALANT | 90000 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6000 | WATERPROOFING SUB | 1007406.25 | 27305.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6010 | WATERPROOFING SUB SUPPORT | 103510.13 | 1172.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6020 | PREP SURFACE FOR WATERPROOFING | 51520.23 | 53225.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6100 | METAL PANELS SUB | 3381506.41 | 1774255.81 | 245213.7583 | 346257.0917 | 420549.125 | 235327.9583 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6110 | METAL PANELS SUB SUPPORT | 68493.59 | 10719.51 | 57774.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6200 | ROOFING SUB | 1135000 | 705799.78 | 355028 | 145814.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6210 | ROOFING SUB SUPPORT | 60000 | 1171.78 | 58828.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6220 | PREP ROOF SURFACE FOR WORK | 40000 | 26323.7 | 0 | 13676.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6300 | SPRAY ON FIREPROOFING SUB | 254755.38 | 247755.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | 21837.92 | 1377.92 | 20000 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6320 | Maintain heat for Fireproofers | 9196.97 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
07-6330 | FIREPROOFING CLEANUP | 2771.84 | 2771.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-1600 | ACCESS HATCH | 114418.44 | 0 | 7151.1525 | 14302.305 | 14302.305 | 28604.61 | 28604.61 | 7151.1525 | 7151.1525 | 7151.1525 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-1700 | (1''4WX8H) S.S. FLOOD VENTS NEW BL (153) | 19069.74 | 0 | 1191.8588 | 2383.7175 | 2383.7175 | 4767.435 | 4767.435 | 1191.8588 | 1191.8588 | 1191.8587 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-1800 | 2'9"x8" SS FLOOD VENT W/SS SCRN NEW BLDG(8.06) | 6356.58 | 0 | 397.2862 | 794.5725 | 794.5725 | 1589.145 | 1589.145 | 397.2862 | 397.2862 | 397.2862 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-5000 | FURNISH HM DOORS | 191266.4 | 83834.36 | 26858.01 | 26858.01 | 26858.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-5010 | HM DOOR SUPPORT | 50313.29 | 313.29 | 3125 | 6250 | 6250 | 12500 | 12500 | 3125 | 3125 | 3125 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-5100 | FURNISH ACCESS HATCHES | 91781 | 91781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-6000 | OVERHEAD DOORS SUB | 22632 | 5658 | 0 | 0 | 0 | 0 | 16974 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-6010 | OVERHEAD DOORS SUB SUPPORT | 5000 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-6100 | GLAZING SUB | 28000 | 0 | 0 | 0 | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
08-6200 | LOUVERS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6000 | STUCCO SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6100 | TILE SUB | 34200 | 0 | 11400 | 11400 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6110 | TILING SUB SUPPORT | 5000 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6200 | VCT FLOORING SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6300 | PAINT SUB | 533755 | 0 | 0 | 51071.4286 | 141428.5714 | 17500 | 75000 | 17500 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6310 | PAINTING SUB SUPPORT | 40000 | 3160.89 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
09-6320 | EPOXY FLOORING | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-1000 | FIRE EXTINGUISHERS NEW BLDGS | 2772.14 | 935.19 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-1100 | TOILET ACCESSORIES NEW BLDGS | 11260.88 | 1407.61 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-1200 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) | 289147.86 | 14136.86 | 17188.1875 | 34376.375 | 34376.375 | 68752.75 | 68752.75 | 17188.1875 | 17188.1875 | 17188.1875 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-1300 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) | 22248.03 | 13400.37 | 693.415 | 1386.83 | 1386.83 | 2773.66 | 2773.66 | 693.415 | 693.415 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-1400 | WINDOW FLOODGATES (8.06 AND 8.14) | 50000.29 | 0 | 3125.0181 | 6250.0363 | 6250.0363 | 12500.0725 | 12500.0725 | 3125.0181 | 3125.0181 | 3125.0181 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-1500 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE | 19069.74 | 5523.22 | 846.6575 | 1693.315 | 1693.315 | 3386.63 | 3386.63 | 846.6575 | 846.6575 | 846.6575 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-5000 | FURNISH TOILET ACCESSORIES | 1488.1 | 1488.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-5100 | FURNISH FIRE EXTINGUISHERS | 2450 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-5200 | FURNISH AQUA FLOOD BARRIERS | 1682724.63 | 991858 | 186104.1575 | 186104.1575 | 186104.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-5300 | FURNISH 8.08 FLOOD DOORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
11-1000 | EXCAVATE & POUR CONCRETE FOOTINGS | 35505.12 | 0 | 5917.52 | 5917.52 | 0 | 0 | 5917.52 | 5917.52 | 5917.52 | 5917.52 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
11-6000 | PLAY AREA ITEMS SUB | 426718.49 | 251725.08 | 50675.1225 | 0 | 0 | 0 | 0 | 50675.1225 | 50675.1225 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
11-6010 | SUPPORT PLAY AREA | 50000 | 13225.17 | 0 | 0 | 0 | 0 | 6411.3733 | 6411.3733 | 23952.0833 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
14-6000 | ELEVATOR SUB | 1027903.5 | 31860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
14-6010 | ELEVATOR JUNCTION BOXES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-5000 | Purchase Yard Pumps | 99876.64 | 0 | 39876.64 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6000 | PLUMBING SUB | 13100000 | 9558967.31 | 502610.633 | 514449.7498 | 550282.8988 | 415097.0032 | 192758.2754 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6010 | PLUMBING BOND | 125426 | 125426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6020 | PIPE INSULATION | 450000 | 173905 | 61606.7045 | 78393.75 | 34350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6025 | PLUMBING INSULATION REMOVAL | 25000 | 8405.69 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.72 | 2765.7167 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6030 | YARD PUMP SUPPLY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6040 | YARD PUMP INSTALL | 209344 | 39010.84 | 10804.8838 | 21609.7675 | 21609.7675 | 43219.535 | 43219.535 | 10804.8838 | 10804.8838 | 8259.9037 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | 41078 | 41078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6060 | PLUMBING SUB SUPPORT | 3359.95 | 3359.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
22-6070 | PLUMBING SCAFFOLD | 10000 | 9164.95 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 291.77 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
23-6000 | HVAC SUB | 24100000 | 20199921.02 | 1053107.6173 | 1288338.8215 | 796401.3526 | 319764.821 | 279375.7121 | 90559.3773 | 24200 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
23-6010 | HVAC SUB SUPPORT | 200000 | 0 | 33333.3333 | 33333.3333 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
23-6020 | MECHANICAL LOUVERS | 0 | 8876.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
26-6000 | ELECTRICAL SUB | 50099472.19 | 26758199.8 | 2154626.4502 | 1779954.9915 | 2860913.6249 | 2713967.4611 | 2696110.3183 | 2304559.6893 | 1422455.9379 | 1421487.3515 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
26-6010 | TEMP ELECTRIC | 2449.46 | 2449.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
26-6020 | ELECTRICAL SUB SUPPORT | 50000 | 345.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
26-6030 | EQUIPMENT INSTALLATION SUPPORT | 30000 | 22091.48 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.56 | 988.57 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1000 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND CONCRETE | 250000 | 187717.17 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 10897.9 | 7793.35 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1100 | BACKFILL FOR FLOOD BARRIER FFTGS & CONCRETE SHELF | 152500 | 119707.21 | 7727.625 | 7727.625 | 7727.625 | 6475.63 | 3134.285 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1200 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - ALL EXIST BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1300 | EXCAVATION NEW BLDGS | 205909.86 | 205909.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1400 | BACKFILL NEW BLDGS | 150000 | 148114.7 | 942.65 | 0 | 0 | 0 | 942.65 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1500 | BACKFILL STONE/GRAVEL/CRUSHED STONE - ALL | 25000 | 23506.32 | 746.84 | 0 | 0 | 0 | 746.84 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1600 | PUMP OPERATOR FOR FLOOD BARRIERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1700 | DEWATER NEW BLDGS | 140469.48 | 140469.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1800 | INSTALL H PILES | 26802.94 | 26802.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1810 | SOE MATERIAL | 445577.25 | 445577.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1820 | INSTALL SHEETING | 210938.15 | 208728.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | New Buildings | NEW BUILDINGS | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1830 | INSTALL LAGGING | 55626.32 | 55626.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1840 | MUD SLAB | 55578.77 | 55578.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1850 | SOE Sub | 402338.93 | 402338.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1860 | SOE Sub Support | 15201.85 | 15201.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-1900 | TREE PROTECTION | 50000 | 44097.39 | 0 | 0 | 0 | 0 | 5902.61 | 0 | 0 | 0 | 0 | 0 | hold | labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2000 | TEST PIT SUPPORT | 83241.53 | 83241.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2010 | HAND EXCAVATION SUPPORT | 1978.47 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2100 | EXCAVATION FOR SITE FURNISHING FOOTINGS | 40000 | 22024.13 | 3668.46 | 3668.46 | 3668.46 | 3668.46 | 3302.03 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2200 | BACKFILL UTILITIES | 383288.4 | 313276.18 | 15940.65 | 15940.65 | 15940.65 | 8355.2 | 13835.07 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2300 | EXCAVATION FOR PAVEMENTS | 10328.22 | 0 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2400 | BACKFILL AND COMPACTION FOR PAVEMENTS | 7141.61 | 0 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.27 | 1190.2667 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2500 | DENSE GRADED STONE BASE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2600 | SITE FURNISHINGS | 38534.4 | 3313.85 | 0 | 0 | 8891.0525 | 8891.0525 | 8891.0525 | 8547.3925 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2700 | BOLLARDS | 4816.8 | 0 | 0 | 0 | 2408.4 | 2408.4 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2800 | DRINKING FOUNTAIN | 30000 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-2900 | LANDSCAPE BOULDERS | 80000 | 67325.84 | 5000 | 7674.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-3000 | BASKETBALL BACKSTOP | 3296.32 | 0 | 0 | 0 | 0 | 0 | 1648.16 | 1648.16 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-4000 | VAC TRUCKING SUB | 130000 | 118443.18 | 6556.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-5000 | FURNISH GRAVEL | 12744 | 0 | 0 | 0 | 12744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-5100 | FURNISH CLEAN FILL | 60000 | 7761.75 | 13059.5625 | 13059.5625 | 13059.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6000 | DISPOSAL & TRUCKING SUB | 1710399 | 1485850.33 | 40000 | 40000 | 40000 | 20000 | 20000 | 10000 | 10757.67 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6100 | DEWATERING SUB | 38820 | 38820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6120 | INSTALL SETTLING TANK AND DISCHARGE PIPING BEYOND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6130 | DISCHARGE LOCATIONS NOT INCLUDED WITHIN DEWATERING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6140 | DEEP WELL INSTALL SUPPORT & CLEANUP LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6180 | WATER TREATMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6190 | ELECTRIC SERVICE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6200 | DUMPSTERS FOR DEWATERING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-6210 | DEWATERING DISCHARGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-7000 | LUMBER - TREE PROTECTION | 22925.01 | 22925.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-7100 | DEWATERING PUMPS | 14.07 | 14.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-7200 | SOLDIER PILE & LAGGING BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-7300 | TRENCH BOX - UTILITY TRENCHES | 256261.83 | 197207.14 | 15000 | 15000 | 15000 | 5441.31 | 8613.38 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-7400 | PLATES - UTILITY TRENCHES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
31-7500 | LUMBER - UTILITY TRENCHES | 16396.43 | 16396.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5000 | FURNISH BOLLARDS | 10010 | 10010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5100 | FURNISH SUBBASE | 56700 | 0 | 0 | 10000 | 10000 | 20000 | 10000 | 6000 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5200 | FURNISH BENCHES & TABLES | 393000 | 380785 | 50651.875 | 50651.875 | 50651.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5300 | FURNISH PING PONG TABLE | 32700 | 22413 | 2571.75 | 2571.75 | 2571.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5400 | FURNISH BIKE RACK | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5500 | FURNISH DRINKING FOUNTAIN | 9000 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5600 | FURNISH SHOWER EQUIPMENT | 26188.02 | 0 | 0 | 0 | 26188.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5700 | FURNISH LANDSCAPE BOULDERS | 191092.5 | 191092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-5800 | FURNISH BASKETBALL BOARD AND POST | 5340 | 0 | 0 | 0 | 5340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6000 | SAWCUTTING | 134276.38 | 134276.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6100 | ASPHALT SUB | 210269.79 | 0 | 0 | 0 | 0 | 0 | 70089.93 | 70089.93 | 70089.93 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6200 | FLATWORK SUB | 3075000 | 645550.02 | 355256.0073 | 436078.6937 | 204528.6937 | 268147.1429 | 165700 | 29095.2381 | 381936.6667 | 273918.0952 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6210 | FLATWORK SUB SUPPORT | 131865.87 | 3898.15 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | Hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6220 | JMC EQUIP BACKCHARGE | 9119.41 | 14635.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6230 | GRADING FOR RESTORATION | 289044.39 | 99550.67 | 40000 | 40000 | 40000 | 40000 | 29493.72 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6400 | COURT SURFACES SUB | 415000 | 0 | 0 | 0 | 0 | 0 | 141666.6667 | 141666.6667 | 131666.6667 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6410 | Prep Basketball Courts | 10000 | 3129.11 | 0 | 0 | 0 | 0 | 6870.89 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6500 | FENCING SUB | 1318652.5 | 757678.8 | 0 | 0 | 67720.9302 | 42461.9638 | 23636.4858 | 373930.6202 | 53223.7 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6510 | FENCE MESH INSTALL | 99496.11 | 98618.38 | 1453.4117 | 1453.4117 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Maintenance | Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6520 | FENCE INSTALL SELF PERFORM | 507000 | 350859 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 26612.24 | 9528.76 | 0 | 0 | Phased | Labor | Site Maintenance | Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6600 | LANDSCAPING SUB | 635225.54 | 77215.59 | 0 | 31696.4952 | 60832.5068 | 0 | 0 | 0 | 214669.3285 | 213247.9221 | 0 | 0 | SOV | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6610 | CLEAR AND GRUB | 87764.08 | 87764.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6620 | SELF PERFORM TREE REMOVAL | 24373.2 | 27341.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6630 | LANDSCAPING SUB SUPPORT | 50000 | 23531.37 | 0 | 12500 | 12500 | 1468.63 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
32-6700 | Arbor Consultant | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1000 | MAINT & PROT EXIST PRIVATELY OWNED UTILITIES | 51626.6 | 44180.68 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1789.6557 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1100 | TERMINATE AND DEMOLISH EXISTING UTILITIES | 56789.26 | 16146.65 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.38 | 3836.3157 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1200 | WATER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1300 | WELDING OF WATER PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1310 | WATER PIPE FIT UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1400 | INSTALL JOJNT INSULATORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1500 | PRESSURE & AIR TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1600 | FIX 10% FAILURE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1700 | PRESSURE & AIR RE-TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1800 | CONDENSATE & STEAM PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1900 | WELDING OF STEAM AND CONDENSATE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-1910 | STEAM AND CONDENSATE PIPE FIT UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2000 | INSTALL JOJNT INSULATORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2100 | PRESSURE & AIR TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2200 | FIX 10% FAILURE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2210 | EXCAVATE UTILITIES | 2945.71 | 2945.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2300 | PRESSURE & AIR RE-TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2400 | DEWATER UTILITIES | 53037.69 | 53037.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2500 | DUCTILE IRON PIPE SEWERS | 276988.13 | 203154.02 | 18158.716 | 18158.716 | 28016.082 | 9500.596 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2510 | SEWER LINE WORK | 200000 | 60613.81 | 20000 | 28803.258 | 30000 | 20000 | 20582.932 | 20000 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2600 | CATCH BASIN CONNECTIONS | 285541.31 | 212032.93 | 20000 | 31159 | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2700 | STORM DETENTION TANK (I DON'T THINK THIS EXISTS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2800 | DRAINAGE MANHOLES | 1485.51 | 1485.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-2900 | REMOVE AREA DRAINS | 32809.86 | 26769.12 | 1357.084 | 1357.084 | 1969.488 | 1357.084 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-3000 | ELECTRICAL MANHOLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-3100 | UTILITY TRENCHES | 716744.78 | 700923.75 | 5000 | 5000 | 10279.738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-3200 | FENCES & PLATES @ TRENCHES (THIS WILL BE DIFFERENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-3300 | ADD''L CRANE FOR SUBCONTRACTORS SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-4000 | SITE LIGHTING EXCAVATION | 211275.05 | 59306.6 | 10000 | 10000 | 10000 | 15000 | 15000 | 6523.03 | 85445.42 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | 881653.58 | 724386.41 | 40767.885 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5100 | FURNISH 2 COPPER WATER PIPE | 115654.5 | 0 | 0 | 0 | 25000 | 25000 | 35000 | 30654.5 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5200 | FURNISH DIP DRAINAGE PIPE | 276580.36 | 280874.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5300 | FURNISH PRECAST AREA DRAINS & MHS | 126016 | 77921.81 | 12961.0475 | 12961.0475 | 12961.0475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5500 | FURNISH DETENTION TANK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-5600 | CHLORINATION | 100000 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-6000 | UNDERGROUND UTILITY MATERIAL DELIVERY | 25000 | 20750.65 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-6010 | UTILITY PIPE PLACEMENT IN TRENCH | 115000 | 104182.59 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.34 | 1545.3486 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-7000 | WELDING MATERIALS | 32664 | 28362.57 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
33-9000 | GAS LINE DAMAGE | 110287.72 | 87073.27 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6000 | Bulk ACM removal, hose wire insulation | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6200 | Bulk ACM removal, pipe insulation and assoc jack | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6300 | Bulk ACM removal, pipe insulation and braided wire | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6400 | Bulk ACM removal, ACM Contamined Debris | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | Hold | Labor | Change Order | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | 51926.66 | 75219.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | 141408 | 397322.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-1000 | Supervision | 7270000 | 5487436.45 | 220000 | 242000 | 220000 | 220000 | 175000 | 175000 | 150000 | 100000 | 67763.55 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-1010 | CLAIMS CONSULTANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-1020 | LEGAL COSTS | 50000 | 5030 | 0 | 0 | 0 | 0 | 4970 | 10000 | 10000 | 10000 | 10000 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-1100 | TEAMSTER | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-1200 | OPER ENG MASTER MECH | 270000 | 82331.19 | 0 | 0 | 27974.1557 | 27974.1557 | 27974.1557 | 0 | 0 | 0 | 0 | 0 | Hold | Labor | Site Maintenance | Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-1300 | OPER ENG MECH | 260000 | 74008.48 | 0 | 0 | 27641.78 | 27641.78 | 27641.78 | 0 | 0 | 0 | 0 | 0 | Hold | Labor | Site Maintenance | Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-2000 | SURVEY SUB | 687620.75 | 558135 | 47573.75 | 20000 | 20000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-3000 | SECURITY SUB | 648295.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-3100 | CONTAINERS - 30 CY | 1150000 | 783597.85 | 60000 | 60000 | 50000 | 50000 | 50000 | 50000 | 30000 | 29031.59 | 0 | 0 | Phased | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4000 | YARD W/ TEMP ELECT | 138034 | 119118.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 8915.59 | 0 | Phased | Labor | Closeout | Closeout | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4050 | COMPUTER/SOFTWARE | 90000 | 84407.41 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4100 | STATIONWORK DESK | 8710.4 | 6193.68 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4150 | IT SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4200 | PHONE EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4250 | PHONE SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4300 | PRINTERS/PLOTTER | 55000 | 45283.5 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4350 | SUPPLIES | 90000 | 65350.32 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4400 | TELEPHONE | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4450 | CELL PHONES | 29506.48 | 20259 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4500 | ELECTRIC | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4550 | SANITATION | 305000 | 168441.5 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 10000 | 5000 | 400.977 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4560 | SITE MAINTENANCE | 1110000 | 881914.01 | 34560 | 34560 | 34560 | 30000 | 25000 | 25000 | 17280 | 15000 | 12125.99 | 0 | Phased | Labor | Site Maintenance | Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4570 | BASEMENT MAINTENANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4600 | VEHICLES | 160347.74 | 87752.55 | 10000 | 10000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 2988.36 | 0 | Phased | Equipment | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4650 | FUEL | 158001.22 | 154957.01 | 3044.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Equipment | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-4700 | PETTY CASH | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-5000 | OFFICE RENT | 561000 | 466172.95 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13110.3144 | 0 | 0 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-5100 | NYCHA OFFICE FURNITURE | 55000 | 38878.87 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-6000 | SMALL TOOLS | 640000 | 598973.36 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 9770.2436 | 0 | 0 | monthly | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7000 | LABOR ESCAL | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7100 | PREMIUM COST | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7200 | HOLIDAY PAY | 265722.37 | 225352.8 | 9200 | 0 | 0 | 6440 | 0 | 4600 | 0 | 4600 | 0 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7210 | PAID TIME OFF | 68000 | 30333.77 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7300 | LOST TIME | 150000 | 49377.75 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 18294.9545 | 0 | hold | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7400 | PERMITS | 30000 | 18673.7 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 0 | 0 | 0 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7500 | ENGINEERING SUB | 183350 | 171007.28 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7510 | CADD SERVICES | 20000 | 14395.69 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 0 | 0 | 0 | 0 | Phased | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-7600 | SECTION 3 ADMINISTRATOR SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-8000 | EQUIPMENT | 1561716.25 | 1193701.71 | 80000 | 60000 | 50000 | 40000 | 30000 | 20000 | 17725.98 | 85133.27 | 0 | 0 | Phased | Equipment | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-8050 | AID TO SUBS | 250000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | Phased | Sub | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-8100 | PROJECT SIGNS | 4000 | 3181.22 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 0 | 0 | monthly | Material | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-8200 | PUNCH LIST | 250000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | Phased | Labor | Closeout | Closeout | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-9000 | BOND | 1170144 | 948765.41 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-9100 | INSURANCE | 3248000 | 1784034.35 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 0 | monthly | overhead | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-9999 | Accruals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0
99-NY0001 | Supervision- Do Not Use | 22408.12 | 22408.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Billing Forecast
Schedule Act | Item # | Description | Current Commitment | Previous Total | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | Final Total | SOV Level 1 | SOV Level 2 | Percent Complete | Sub | Category 1 | Category 2 | Billing Category | Total>Commitment?
MOBE-01005 | 11 | Mobilization | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
MOBE-01005 | 12 | Bond | 1170144 | 1170144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
MOBE-01005 | 13 | Insurance | 1057256 | 750651.76 | 41133.4242 | 42285.145 | 37330.9183 | 45389.2083 | 37549.2423 | 25657.4558 | 17820.7329 | 14508.8491 | 11855.6435 | 33073.6207 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
OGE-01010 | 14 | Project Management | 7740000 | 5495400 | 301131.139 | 309562.7004 | 273293.6088 | 332287.0449 | 274891.9234 | 187834.0796 | 130462.6999 | 106216.935 | 86793.2464 | 242126.6225 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
01500 | 15 | Noise Reduction Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
02160 | 16 | Lead Safe Work Practice Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
SGN-01010 | 17 | Rodent Control | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
01575 | 18 | Waste Management Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
01500 | 19 | Site Specific Safety Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
01500 | 20 | Site Safety Plan | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
01540 | 21 | Quality Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
01500 | 22 | CPM - Baseline | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
OGE-01010 | 23 | CPM - Monthly Updates | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
MOBE-01005 | 24 | Field Office - Set Up | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
OGE-01010 | 25 | Field Office - Rent, Maintenance and Supplies | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
MOBE-01005 | 26 | Yard - Set Up | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
OGE-01010 | 27 | Yard - Maintenance | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
OGE-01010 | 28 | Photos | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-03315 | 29 | Filing Alt1 permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-03025 | 30 | Filing Alt2 permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-03005 | 31 | Filing NB permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-02005 | 32 | Filing CCD1 for Fence | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-02005 | 33 | Filing Fence Permit | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-04005 | 34 | Filing dewatering permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-01005 | 35 | Filing DOT permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-05005 | 36 | Filing Demo Permit | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-07010 | 37 | Filing Asbestos permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
PERMIT-06005 | 38 | Filing Electrical Permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
02020 | 39 | Shop Drawings / Submittals (exc O&M, As-Built and Warranty) | 218350 | 163762.5 | 10917.5 | 10917.5 | 10917.5 | 0 | 0 | 0 | 0 | 0 | 0 | 21835 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
M905 | 40 | O&M, As-Built and Warranty | 155650 | 0 | 0 | 0 | 0 | 0 | 31130 | 31130 | 31130 | 31130 | 31130 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
MOBE-01005 | 41 | Survey | 24000 | 17040 | 933.74 | 959.8843 | 847.422 | 1030.3474 | 852.3781 | 582.4313 | 404.5355 | 329.3548 | 269.1263 | 750.7802 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
MOBE-01005 | 42 | Engineering | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
S8-01770 | 43 | Demobilization/Project Closeout | 36850 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 | 7370 | 7370 | 7370 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
SGN-01055 | 44 | Soil Testing and Management Plan | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
SG7-03520 | 45 | Punchlist | 51150 | 0 | 0 | 0 | 0 | 0 | 10230 | 10230 | 10230 | 10230 | 10230 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
S8E-03330 | 46 | Training | 61600 | 0 | 0 | 0 | 0 | 0 | 12320 | 12320 | 12320 | 12320 | 12320 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead | 0 | Overhead | 0
SG1-01005 | 47 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01010 | 48 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 49 | Assumed Flooring Material (Slab Penetrations) | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01020 | 50 | Pipe Insulation | 132300 | 132300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01005 | 51 | Duct Seal | 43200 | 43200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 52 | Vinyl Membrane and Mastic | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 53 | Caulk | 110250 | 110250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 54 | Fibrous Slate | 12240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01020 | 55 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01020 | 56 | Underground Utility Materials | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01105 | 57 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01220 | 58 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01105 | 59 | Remove existing vent / window and frame - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01105 | 60 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01115 | 61 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01115 | 62 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01115 | 63 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01210 | 64 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01105 | 65 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01205 | 66 | Remove existing stair - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01205 | 67 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01205 | 68 | Existing Ramp railing to be be removed - 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01410 | 69 | FORM FLOOD BARRIER FOUNDATIONS - SG-1 | 50095 | 30057 | 0 | 20038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01450 | 70 | DRILL & GROUT DOWELS - SG-1 | 6278 | 6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01450 | 71 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-1 | 30151 | 30151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01470 | 72 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-1 | 33906 | 16953 | 9687.4286 | 0 | 0 | 2421.8571 | 2421.8571 | 2421.8571 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01440 | 73 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-1 | 18856 | 18856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01415 | 74 | Footing/Pier | 17434 | 8717 | 4358.5 | 4358.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01435 | 75 | Retaining Walls | 4571 | 2285.5 | 1523.6667 | 761.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01535 | 76 | Entrance Slab | 21380 | 1069 | 10155.5 | 10155.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01810 | 77 | Concrete Shelf | 4895 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01350 | 78 | New Concrete Curb Next to Existing Wall | 297 | 0 | 148.5 | 148.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 79 | GFRP Sikawrap 100 G | 58344 | 0 | 0 | 0 | 19448 | 19448 | 19448 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01440 | 80 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-1 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01015 | 81 | Overhead protection for Masonry | 10175 | 7631.25 | 0 | 2543.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01820 | 82 | 6" vertically reinforced CMU | 230912 | 219366.4 | 0 | 0 | 11545.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 83 | 2" Face brick | 597520 | 179256 | 0 | 100000 | 106088 | 106088 | 106088 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 84 | 2" rigid Insulation | 39424 | 19712 | 0 | 0 | 6570.6667 | 6570.6667 | 6570.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01820 | 85 | Coping Stone C1/A-300 | 13200 | 11880 | 0 | 0 | 440 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05440 | 86 | MATERIAL AND FABRICATION | 5824 | 0 | 5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01315 | 87 | INSTALLATION | 6600 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01860 | 88 | Temporary Aluminum Over Pass Stairs | 57196 | 0 | 28598 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02120 | 89 | PENETRATION FIRESTOPPING EXTG BLDG - SG-1 | 11505 | 0 | 10066.875 | 0 | 0 | 479.375 | 479.375 | 479.375 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01320 | 90 | JOINT SEALANTS EXTG BLDGS - SG-1 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01830 | 91 | Bituthene 4000 waterproofing membrane | 37752 | 9438 | 0 | 0 | 9438 | 9438 | 9438 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 92 | GE Elemax 2600 Silicone air and vapor barrier | 31416 | 0 | 0 | 0 | 10472 | 10472 | 10472 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01370 | 93 | Crystalline Waterproofing at perimeter walls | 37260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01825 | 94 | Waterproofing at foundation walls | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01860 | 95 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 007 - SG1 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01330 | 96 | Doors, Frames & Hardware - Labor | 6672 | 0 | 2224 | 2224 | 2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 007 - SG1 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 97 | Furnish Doors | 2091 | 0 | 522.75 | 522.75 | 522.75 | 261.375 | 261.375 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 98 | Layout | 2829 | 2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 99 | Loading | 3858 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 100 | Framing & Drywall - Materials | 2829 | 0 | 943 | 943 | 943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 101 | Framing- Labor | 4629 | 0 | 1543 | 1543 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01330 | 102 | Drywall - Labor | 4629 | 0 | 1543 | 1543 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01330 | 103 | Tape/ Spackle finishes | 3086 | 0 | 1028.6667 | 1028.6667 | 1028.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01855 | 104 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01860 | 105 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-1 | 70001 | 35000.5 | 21875.3125 | 0 | 0 | 4375.0625 | 4375.0625 | 4375.0625 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01860 | 106 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-1 | 31714 | 0 | 19821.25 | 0 | 0 | 3964.25 | 3964.25 | 3964.25 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01860 | 107 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-1 | 68909 | 0 | 43068.125 | 0 | 0 | 8613.625 | 8613.625 | 8613.625 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01865 | 108 | Temporary Egress Stair Storage Sign | 2640 | 0 | 1760 | 0 | 0 | 293.3333 | 293.3333 | 293.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01865 | 109 | Address Signs | 4950 | 0 | 3300 | 0 | 0 | 550 | 550 | 550 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG6-02150 | 110 | Switches and Receptacles | 10950 | 10402.5 | 0 | 0 | 0 | 182.5 | 182.5 | 182.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02525 | 111 | Switchgear & Panelboard Energization | 19163 | 9581.5 | 0 | 0 | 0 | 3193.8333 | 3193.8333 | 3193.8333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02405 | 112 | Switchgear & Panelboard Installation | 229950 | 218452.5 | 0 | 0 | 11497.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02405 | 113 | Switchgear & Panelboard Terminations | 19163 | 18204.85 | 0 | 0 | 958.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02530 | 114 | Switchgear & Panelboard Testing | 19163 | 14372.25 | 0 | 0 | 0 | 1596.9167 | 1596.9167 | 1596.9167 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02025 | 115 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02110 | 116 | Fire Alarm Conduit | 68438 | 65016.1 | 0 | 0 | 0 | 1140.6333 | 1140.6333 | 1140.6333 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02365 | 117 | Fire Alarm Wiring | 65700 | 62415 | 0 | 0 | 0 | 1095 | 1095 | 1095 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02365 | 118 | Fire Alarm Devices | 93075 | 88421.25 | 0 | 0 | 0 | 1551.25 | 1551.25 | 1551.25 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02365 | 119 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 120 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG6-02505 | 121 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01005 | 122 | EXCAVATION NEW BLDGS - SG-6 | 38439 | 38439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01055 | 123 | BACKFILL NEW BLDGS - SG-6 | 18099 | 18099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01005 | 124 | DEWATERING COVERAGE FOR NEW BUILDINGS - SG-6 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01005 | 125 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-6 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01005 | 126 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-6 | 34172 | 34172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01070 | 127 | FORMWORK NEW BUILDING - SG-7 | 353185 | 353185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01175 | 128 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-7 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01040 | 129 | POUR CONCRETE NEW BUILDINGS - SG-7 | 220248 | 220248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01135 | 130 | FINISH SLABS - SG-7 | 17896 | 17896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 131 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01075 | 132 | Footing/Pier | 174820 | 174820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 133 | Floor Slabs | 31988 | 31988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 134 | Cellar Pit First Floor Slab | 490 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 135 | Cellar Pit Second Floor Slab | 544 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 136 | Meter Room Second Floor Slab | 762 | 762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01130 | 137 | Cellar Pit | 47722 | 47721.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01155 | 138 | Gas Meter Room | 12726 | 12726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01205 | 139 | WWM-Slabs | 6648 | 6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01230 | 140 | 8" CMU (3 hour rated) | 171133 | 162576.35 | 8556.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01275 | 141 | 4" CMU | 39402 | 37431.9 | 985.05 | 985.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 142 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01230 | 143 | 6" CMU (2 hour rated) | 38214 | 36303.3 | 1910.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01275 | 144 | Face Brick 3-5/8" | 235521 | 188416.8 | 47104.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01275 | 145 | 3-1/8" Rigid insulation | 30712 | 15356 | 7678 | 7678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01250 | 146 | Cast Stone with SS letters | 8521 | 3408.39 | 0 | 1704.2033 | 1704.2033 | 1704.2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01230 | 147 | Steel Channel | 16720 | 0 | 0 | 0 | 5573.3333 | 5573.3333 | 5573.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01230 | 148 | Cont. Shelf angle | 9240 | 0 | 0 | 0 | 3080 | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 149 | STEEL (MATERIAL ONLY) | 178532 | 178532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 150 | FABRICATION COSTS | 303034 | 303034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 151 | METAL DECK (BUY-OUT) | 15270 | 15270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 152 | ANCHORS & EMBEDS | 9398 | 9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 153 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01105 | 154 | SURVEYING | 14096 | 14096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 155 | STEEL & DECK ERECTION | 610764 | 610764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 156 | BOLTS AND HARDWARE | 23492 | 23492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 157 | TRUCKING | 11746 | 11746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01270 | 158 | Dunnage Grating Galvanized | 64556 | 0 | 32278 | 32278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01270 | 159 | Dunnage Guard Rail | 30415 | 30415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01270 | 160 | Dunnage Stair and Guard Rail | 13035 | 13035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01290 | 161 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 128548 | 118548 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01295 | 162 | 1st to 2nd Floor Ship Ladder with Cages | 25750 | 15450 | 7725 | 2575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01295 | 163 | Bulkhead Ship Ladder to Roof at 2 Locations | 12383 | 1238.3 | 5572.35 | 5572.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 164 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01305 | 165 | Layout | 8028 | 0 | 0 | 0 | 1146.8571 | 6881.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 166 | Loading | 15326 | 0 | 0 | 0 | 2000 | 3000 | 6884 | 3442 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 167 | Exterior Framing, Insulation & Drywall - Materials | 67511 | 67511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 168 | Exterior Framing- Labor | 58049 | 0 | 0 | 0 | 8292.7143 | 10000 | 26504.1905 | 13252.0952 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01125 | 169 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-7 | 7236 | 7236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-02475 | 170 | PENETRATION FIRESTOPPING NEW BLDG - SG-7 | 11505 | 0 | 0 | 0 | 0 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG3-01320 | 171 | JOINT SEALANTS NEW BLDGS - S7 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01230 | 172 | Air Film | 19195 | 0 | 0 | 0 | 6398.3333 | 6398.3333 | 6398.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 173 | Insulation- Labor | 7798 | 0 | 0 | 0 | 1114 | 6684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01025 | 174 | Crystalline Waterproofing at plumbing shaft | 4474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 175 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01072 | 176 | Waterproofing at foundation | 8522 | 8522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 177 | Layout | 87373 | 0 | 0 | 0 | 29124.3333 | 29124.3333 | 29124.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 178 | Framing | 198097 | 198097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 179 | Insulation | 35480 | 35480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 180 | Cladding Install | 248360 | 0 | 0 | 0 | 82786.6667 | 82786.6667 | 82786.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01225 | 181 | Fireproofing | 41800 | 41800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01265 | 182 | P&I Cold Applied Roof Membrane | 99622 | 0 | 0 | 99622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01265 | 183 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 101829 | 0 | 0 | 101829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01265 | 184 | P&I Aluminum Coping | 7458 | 0 | 0 | 7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01260 | 185 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S7 | 10270 | 0 | 2567.5 | 2567.5 | 2567.5 | 1283.75 | 1283.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 186 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01245 | 187 | Doors, Frames & Hardware - Labor | 18070 | 4517.5 | 13552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01317 | 188 | Louvers Install | 61948 | 0 | 0 | 0 | 20649.3333 | 20649.3333 | 20649.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 189 | Furnish Doors | 18815 | 0 | 4703.75 | 4703.75 | 4703.75 | 2351.875 | 2351.875 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01305 | 190 | Sheathing & Drywall - Labor | 49634 | 0 | 0 | 0 | 7090.5714 | 20000 | 15028.9524 | 7514.4762 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01245 | 191 | Tape/ Spackle finishes | 14144 | 0 | 14144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01315 | 192 | ACT ceilings - Materials | 3858 | 0 | 0 | 0 | 0 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01315 | 193 | ACT ceilings - Labor | 12788 | 0 | 0 | 0 | 0 | 2000 | 7192 | 3596 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01280 | 194 | Direct Applied Stucco | 53251 | 0 | 26625.5 | 26625.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01325 | 195 | Painting SG-7 | 110000 | 0 | 0 | 0 | 0 | 0 | 35000 | 75000 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01310 | 196 | Cermic Tile and Base - SG-7 | 5490 | 0 | 0 | 0 | 0 | 2745 | 2745 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 197 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01260 | 198 | FIRE EXTINGUISHERS NEW BLDGS - SG-7 | 733 | 0 | 183.25 | 183.25 | 183.25 | 91.625 | 91.625 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01260 | 199 | TOILET ACCESSORIES NEW BLDGS - SG-7 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 200 | Stair Identification Sign | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 201 | Stairway Floor number and ID Sign | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 202 | Room Sign | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 203 | Exit Sign | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 204 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 205 | Stairway Flood Access Door | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 206 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 2329.2 | 2846.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 207 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 2640 | 2520 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 208 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-03105 | 209 | ESCUTCHEONS FOR PLUMBING PIPING | 2178 | 0 | 2079 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 210 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 22000 | 0 | 21000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 211 | HANGERS AND SUPPORTS | 21648 | 15153.6 | 6494.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 212 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2728 | 0 | 2604 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 213 | DOMESTIC WATER PIPING | 255409 | 114934.05 | 100000 | 40474.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 214 | DOMESTIC WATER PIPING SPECIALTIES | 30184 | 12073.6 | 18110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 215 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 16500 | 30000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 216 | SANITARY WASTE PIPING | 104439 | 78329.25 | 20000 | 6109.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 217 | SANITARY WASTE PIPING SPECIALTIES | 20504 | 19478.8 | 1025.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 218 | STORM DRAINAGE PIPING SPECIALTIES | 53504 | 45478.4 | 8025.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 219 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-03140 | 220 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 21824 | 0 | 7274.6667 | 14549.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03140 | 221 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 322085 | 128834 | 20000 | 0 | 75000 | 75000 | 15500.6667 | 7750.3333 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 222 | GAS SERVICE AND PIPING | 271645 | 67911.25 | 100000 | 0 | 14664.5 | 29689.75 | 29689.75 | 29689.75 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03140 | 223 | PLUMBING FIXTURES | 18392 | 0 | 6130.6667 | 12261.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 224 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 78682 | 78682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 225 | Plumbing Pipe Insulation | 2374 | 0 | 2266.0909 | 107.9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02145 | 226 | Heat Trace | 5475 | 0 | 0 | 3650 | 0 | 0 | 0 | 0 | 456.25 | 456.25 | 456.25 | 456.25 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGS-M-01005 | 227 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 228 | Exhaust Fans: Furnish | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 229 | Exhaust Fans: Install | 18700 | 14025 | 4007.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 230 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 231 | Electric Unit Heaters: Furnish | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 232 | Steam Unit Heaters: Furnish | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 233 | Steam Unit Heaters: Install | 32175 | 0 | 0 | 0 | 14855.4939 | 17319.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 234 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 235 | Heating and Ventilation Unit: Install | 26675 | 0 | 0 | 0 | 12316.0932 | 14358.9068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 236 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 237 | Condensate Return Unit: Install | 25575 | 0 | 0 | 0 | 11808.2131 | 13766.7869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 238 | Steam Traps: Furnish | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 239 | Steam Traps: Install | 14300 | 0 | 0 | 0 | 6602.4417 | 7697.5583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 240 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 157465 | 15746.5 | 0 | 0 | 73648.2487 | 62739.1269 | 5331.1244 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 241 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 242 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 271700 | 0 | 0 | 0 | 127077.3136 | 108254.0297 | 27063.5074 | 9305.1494 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 243 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 88000 | 0 | 0 | 0 | 41158.6441 | 35062.0339 | 8765.5085 | 3013.8136 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03135 | 244 | Mechanical Pipe: Hydrostatic Testing | 2035 | 0 | 0 | 0 | 951.7936 | 810.8095 | 202.7024 | 69.6944 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 245 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 19250 | 17325 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 246 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 34650 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03145 | 247 | HVAC Ductwork: Testing & Balancing | 2200 | 0 | 0 | 0 | 317.8899 | 0 | 0 | 1882.1101 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 248 | Controls: Furnish and Install: Devices | 110000 | 16500 | 0 | 0 | 0 | 0 | 39947.3684 | 53070.1754 | 482.4561 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 249 | Controls: Furnish and Install: Controls Conduit | 49500 | 5940 | 0 | 0 | 0 | 0 | 17976.3158 | 23881.5789 | 1702.1053 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 250 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 0 | 0 | 3994.7368 | 5307.0175 | 1698.2456 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 251 | Controls: Connect to Final Termination Points | 11000 | 0 | 0 | 0 | 0 | 0 | 3994.7368 | 5307.0175 | 1698.2456 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 252 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-03510 | 253 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 0 | 0 | 2396.8421 | 3184.2105 | 1018.9474 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 254 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14520 | 3630 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 255 | Insulation: Furnish and Install: Piping Insulation | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24200 | 6050 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 256 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14520 | 3630 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 257 | ATS Energization | 24638 | 0 | 0 | 12319 | 0 | 0 | 0 | 0 | 3079.75 | 3079.75 | 3079.75 | 3079.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 258 | ATS Installation | 344925 | 172462.5 | 0 | 86231.25 | 0 | 0 | 0 | 0 | 21557.8125 | 21557.8125 | 21557.8125 | 21557.8125 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 259 | ATS Terminations | 24638 | 0 | 0 | 12319 | 0 | 0 | 0 | 0 | 3079.75 | 3079.75 | 3079.75 | 3079.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 260 | ATS Testing | 24638 | 0 | 0 | 12319 | 0 | 0 | 0 | 0 | 3079.75 | 3079.75 | 3079.75 | 3079.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02125 | 261 | Cabling - Interior Branch (1/0 & Smaller) | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SGS-02125 | 262 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 | 0 | 0 | 0 | 549064.2857 | 0 | 0 | 10558.9286 | 10558.9286 | 10558.9286 | 10558.9286 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 263 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02115 | 264 | Conduit - Branch Circuits (1 1/2" & Smaller) | 123188 | 43115.8 | 0 | 0 | 0 | 0 | 0 | 0 | 20018.05 | 20018.05 | 20018.05 | 20018.05 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02105 | 265 | Conduit - In-Slab | 162608 | 162608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02010 | 266 | Conduit - Risers (2" & Larger) | 591300 | 473040 | 0 | 0 | 0 | 0 | 0 | 0 | 29565 | 29565 | 29565 | 29565 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02475 | 267 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02010 | 268 | Foundation Coring | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG7-01040 | 269 | Generator Delivery | 78750 | 0 | 0 | 0 | 39375 | 0 | 0 | 0 | 9843.75 | 9843.75 | 9843.75 | 9843.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG7-01030 | 270 | Generator Release | 472500 | 472500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02415 | 271 | Generator Terminations | 78750 | 0 | 0 | 0 | 73125 | 0 | 0 | 0 | 1406.25 | 1406.25 | 1406.25 | 1406.25 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02615 | 272 | Generator Test | 78750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19687.5 | 19687.5 | 19687.5 | 19687.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02150 | 273 | Lighting Controls | 11550 | 5775 | 0 | 0 | 0 | 0 | 0 | 0 | 1443.75 | 1443.75 | 1443.75 | 1443.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 274 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02135 | 275 | Lighting Install | 82125 | 41062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10265.625 | 10265.625 | 10265.625 | 10265.625 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02135 | 276 | Lighting Rough | 82125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20531.25 | 20531.25 | 20531.25 | 20531.25 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02135 | 277 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02425 | 278 | Lightning Protection | 21900 | 10950 | 0 | 0 | 0 | 9385.7143 | 0 | 0 | 391.0714 | 391.0714 | 391.0714 | 391.0714 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02140 | 279 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 | 0 | 54437.1429 | 0 | 0 | 0 | 0 | 2268.2143 | 2268.2143 | 2268.2143 | 2268.2143 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGS-E-01030 | 280 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02160 | 281 | Switches and Receptacles | 10950 | 0 | 0 | 5475 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02655 | 282 | Switchgear & Panelboard Energization | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318.75 | 12318.75 | 12318.75 | 12318.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02330 | 283 | Switchgear & Panelboard Installation | 591300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147825 | 147825 | 147825 | 147825 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02330 | 284 | Switchgear & Panelboard Terminations | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318.75 | 12318.75 | 12318.75 | 12318.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 285 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02650 | 286 | Switchgear & Panelboard Testing | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318.75 | 12318.75 | 12318.75 | 12318.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02005 | 287 | Temp Light & Power | 54750 | 35587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4790.625 | 4790.625 | 4790.625 | 4790.625 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02115 | 288 | Fire Alarm Conduit | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02250 | 289 | Fire Alarm Wiring | 32850 | 0 | 16425 | 0 | 0 | 0 | 0 | 0 | 4106.25 | 4106.25 | 4106.25 | 4106.25 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02250 | 290 | Fire Alarm Devices | 53655 | 26827.5 | 13413.75 | 0 | 0 | 0 | 0 | 0 | 3353.4375 | 3353.4375 | 3353.4375 | 3353.4375 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02250 | 291 | Fire Alarm Programming & Pretest | 2738 | 0 | 1369 | 0 | 0 | 0 | 0 | 0 | 342.25 | 342.25 | 342.25 | 342.25 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02625 | 292 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684.5 | 684.5 | 684.5 | 684.5 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01005 | 293 | EXCAVATION NEW BLDGS - SG-7 | 42812 | 42812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01055 | 294 | BACKFILL NEW BLDGS - SG-7 | 18057 | 18057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01005 | 295 | DEWATERING COVERAGE FOR NEW BUILDINGS - SG-7 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 296 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01005 | 297 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-7 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01005 | 298 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-7 | 34172 | 34172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SGN-01035 | 299 | EROSION CONTROL FABRIC - SGN | 71660 | 71660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 300 | INLET PROTECTION - SGN | 31100 | 31100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 301 | SILT FENCE - SGN | 22950 | 22950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 302 | STABILIZED CONSTRUCTION ENTRANCE - SGN | 48300 | 48300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 303 | MANTAIN EROSION CONTROL - SGN | 42735 | 42735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01690 | 304 | REMOVE EROSION CONTROL - SGN | 29979 | 4496.85 | 0 | 0 | 0 | 8494.05 | 8494.05 | 8494.05 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 305 | REMOVE FENCE - SGN | 23500 | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 306 | REMOVE FULL DEPTH ASPHALT PVMT - SGN | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-01380 | 307 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01060 | 308 | REMOVE SITE FURNISHING - SGN | 181360 | 181360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 309 | REMOVE CONCRETE CURB & STEPS - SGN | 40100 | 40100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 310 | REMOVE PVMTS - SGN | 151850 | 151850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01510 | 311 | FORMWORK SITE CONCRETE - SGN | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 312 | CONCRETE FOOTING FOR SITE FURNISHING - SGN | 5947 | 0 | 0 | 2973.5 | 2973.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 313 | CONCRETE DUCTBANKS - SGN | 40284 | 40284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01520 | 314 | CONCRETE SITE RETAINING WALL AND FOOTINGS - SGN | 25224 | 25224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 315 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - SGN | 24647 | 6161.75 | 0 | 0 | 0 | 6161.75 | 6161.75 | 6161.75 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 316 | Crackle Corn | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 317 | Jet Spray | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-01380 | 318 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01635 | 319 | 2-5 year play equipment | 88000 | 44000 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 320 | 5-12 year play equipment | 88000 | 44000 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 321 | Splash Pad | 22000 | 11000 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 322 | Install Water Play Equipment and Piping | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01155 | 323 | Manhole Installation | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02215 | 324 | Site Lighting - Cable | 54750 | 5475 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02210 | 325 | Site Lighting - Conduit | 65700 | 62415 | 1407.8571 | 1407.8571 | 469.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02220 | 326 | Site Lighting - Fixtures | 55407 | 0 | 0 | 0 | 0 | 0 | 18469 | 18469 | 18469 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-SGN-E-01000 | 327 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02125 | 328 | Underground Electric Service - Cable | 821250 | 821250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SG1-01380 | 329 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01155 | 330 | Underground Electric Service - Conduit | 657000 | 657000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-01020 | 331 | TREE PROTECTION - SGN | 14532 | 14532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01020 | 332 | HAND EXCAVATION AS NEEDED - SGN | 19751 | 19751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 333 | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGN | 4025 | 0 | 0 | 2012.5 | 2012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01120 | 334 | BACKFILL - SGN | 153869 | 153869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01650 | 335 | SITE FURNISHINGS - SGN | 37275 | 3727.5 | 0 | 0 | 0 | 11182.5 | 11182.5 | 11182.5 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 336 | DRINKING FOUNTAIN - SGN | 16059 | 1605.9 | 0 | 0 | 0 | 4817.7 | 4817.7 | 4817.7 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 337 | LANDSCAPE BOULDERS - SGN | 22319 | 16739.25 | 0 | 0 | 0 | 1859.9167 | 1859.9167 | 1859.9167 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01090 | 338 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01090 | 339 | Furnish and Install Deep Wells | 146250 | 146250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 340 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 11567.65 | 0 | 0 | 0 | 680.45 | 680.45 | 680.45 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01090 | 341 | Furnish and Install Pumps and Piping | 160800 | 160800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01090 | 342 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01090 | 343 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01090 | 344 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01640 | 345 | 4' Steel Bar Fence with Double Gates | 88000 | 0 | 0 | 0 | 0 | 75428.5714 | 12571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGN-01645 | 346 | 6' Chain Link Fence | 12650 | 0 | 0 | 0 | 0 | 0 | 12650 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGN-01005 | 347 | 8' High Temporary Fence | 242250 | 242250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGN-01610 | 348 | 4" CONCRETE | 100100 | 0 | 0 | 50050 | 42900 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01610 | 349 | 7" CONCRETE RAMP | 3080 | 0 | 0 | 1540 | 1320 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01610 | 350 | 5" POROUS CONCRETE | 462000 | 115500 | 0 | 173250 | 148500 | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SG1-03005 | 351 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01630 | 352 | 5" COLOR CONCRETE | 77000 | 46200 | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01605 | 353 | CONCRETE CURB | 18480 | 18480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01605 | 354 | SFC -STELL FACING CURB | 18480 | 0 | 13200 | 4400 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01709 | 355 | Asphalt Parking | 1161 | 0 | 0 | 0 | 0 | 1078.0714 | 82.9286 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
SGN-01680 | 356 | Deciduous Trees | 14884 | 0 | 0 | 0 | 0 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 357 | Evergreen Trees | 3544 | 0 | 0 | 0 | 0 | 3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 358 | Deciduous Shrubs | 2940 | 0 | 0 | 0 | 0 | 2940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 359 | Evergreen Shrubs | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 360 | Perennials | 8080 | 0 | 0 | 0 | 0 | 8080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 361 | Grasses | 18295 | 0 | 0 | 0 | 9147.5 | 9147.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG1-03005 | 362 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 822 | 0 | 0 | 0 | 0 | 182.6667 | 91.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01025 | 363 | Tree Removal | 41580 | 41580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 364 | Lawn Seeding (not including topsoil) | 14810 | 7405 | 0 | 0 | 3702.5 | 3702.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01025 | 365 | Soil Erosion Mat | 2791 | 2369.6 | 0 | 0 | 210.7 | 210.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 366 | Topsoil Stockpile/Spread | 101317 | 65856.05 | 0 | 0 | 17730.475 | 17730.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 367 | Maintenance | 2678 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01120 | 368 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGN | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01110 | 369 | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGN | 25018 | 25018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01110 | 370 | INSTALL HW, CW PIPE - SGN | 403279 | 403279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SGN-01115 | 371 | TEST HW, CW - SGN | 17587 | 17587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01130 | 372 | INSTALL CONDENSATE AND STEAM PIPE - SGN | 308238 | 308238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SG1-03005 | 373 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3300 | 2475 | 0 | 0 | 0 | 0 | 550 | 275 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01135 | 374 | TEST CONDENSATE, STEAM - SGN | 12947 | 12947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01095 | 375 | DEWATERING COVERAGE FOR UTILITY WORK - SGN | 56118 | 56118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01380 | 376 | SEWER / DRAINAGE PIPE - SGN | 150607 | 150607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01375 | 377 | CATCH BASIN DRAINS AND CONNECTIONS - SGN | 165979 | 165979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01375 | 378 | REMOVE AREA DRAINS - SGN | 23320 | 23320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01255 | 379 | ELECTRICAL MANHOLES - SGN | 6377 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01255 | 380 | ELECTRICAL CONDUIT TRENCHES - SGN | 45340 | 45340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 381 | Equipment SUPPORT FOR SITE - SGN | 167754 | 167754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01035 | 382 | EROSION CONTROL FABRIC - SGS | 71650 | 71650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01035 | 383 | INLET PROTECTION - SGS | 23325 | 23325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 384 | HANGERS AND SUPPORTS | 11526 | 9797.1 | 0 | 0 | 0 | 0 | 1152.6 | 576.3 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01035 | 385 | SILT FENCE - SGS | 29100 | 29100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01035 | 386 | STABILIZED CONSTRUCTION ENTRANCE - SGS | 48390 | 48390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01035 | 387 | MANTAIN EROSION CONTROL - SGS | 42735 | 42735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01770 | 388 | REMOVE EROSION CONTROL - SGS | 29979 | 4496.85 | 0 | 25482.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 389 | REMOVE FENCE - SGS | 24400 | 24400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 390 | REMOVE FULL DEPTH ASPHALT PVMT - SGS | 68825 | 68825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01060 | 391 | REMOVE SITE FURNISHING - SGS | 64615 | 64615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 392 | REMOVE CONCRETE CURB & STEPS - SGS | 60250 | 60250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 393 | REMOVE PVMTS - SGS | 100625 | 100625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01510 | 394 | FORMWORK SITE CONCRETE - SGS | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 104 - SGS - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 395 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 0 | 0 | 0 | 1463.3333 | 731.6667 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01750 | 396 | CONCRETE FOOTING FOR SITE FURNISHING - SGS | 5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947 | 0 | 0 | SGS | 104 - SGS - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 397 | CONCRETE DUCTBANKS - SGS | 59916 | 59915 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 104 - SGS - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-02010 | 398 | Manhole Work | 54750 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 14600 | 14600 | 14600 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02215 | 399 | Site Lighting - Cable | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02210 | 400 | Site Lighting - Conduit | 65700 | 6570 | 0 | 0 | 0 | 0 | 0 | 0 | 19710 | 19710 | 19710 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02220 | 401 | Site Lighting - Fixtures | 62963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20987.6667 | 20987.6667 | 20987.6667 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-SGS-E-01030 | 402 | Survey | 70080 | 70080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02135 | 403 | Underground Electric Service - Cable | 821250 | 0 | 0 | 0 | 205312.5 | 205312.5 | 205312.5 | 205312.5 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-01155 | 404 | Underground Electric Service - Conduit | 657000 | 657000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-01020 | 405 | TREE PROTECTION - SGS | 5882 | 5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 406 | DOMESTIC WATER PIPING | 126720 | 95040 | 0 | 0 | 0 | 0 | 21120 | 10560 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01020 | 407 | HAND EXCAVATION AS NEEDED - SGS | 21068 | 21068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01750 | 408 | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGS | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4025 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01370 | 409 | BACKFILL - SGS | 195501 | 195501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01750 | 410 | SITE FURNISHINGS - SGS | 74550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74550 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01750 | 411 | BOLLARDS - SGS | 15581 | 1558.1 | 0 | 0 | 0 | 4674.3 | 4674.3 | 4674.3 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01750 | 412 | DRINKING FOUNTAIN - SGS | 8030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8030 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01090 | 413 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01090 | 414 | Furnish and Install Deep Wells | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01090 | 415 | Furnish and Install Pumps and Piping | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01090 | 416 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG1-03005 | 417 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 | 0 | 0 | 0 | 0 | 2713.3333 | 1356.6667 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01090 | 418 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01090 | 419 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01005 | 420 | 8' High Temporary Fence | 372400 | 336200 | 36200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGS-01745 | 421 | Ametco Fence | 138050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69025 | 69025 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGS-01710 | 422 | 4" CONCRETE | 71500 | 17875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32175 | 21450 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01710 | 423 | 5"POROUS CONCRETE | 466620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279972 | 186648 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01730 | 424 | 5" COLOR CONCRETE | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000 | 77000 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01705 | 425 | CONCRETE CURB | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23833.3333 | 12833.3333 | 1833.3333 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01705 | 426 | SFC -STELL FACING CURB | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171.4286 | 4400 | 628.5714 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01760 | 427 | Deciduous Trees | 27642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13821 | 13821 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG1-03005 | 428 | SANITARY WASTE PIPING | 118800 | 100980 | 0 | 0 | 0 | 0 | 11880 | 5940 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01760 | 429 | Evergreen Trees | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.5 | 1063.5 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01760 | 430 | Deciduous Shrubs | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735 | 735 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01760 | 431 | Perennials | 4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214.5 | 2214.5 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 432 | Grasses | 7980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3990 | 3990 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01025 | 433 | Tree Removal | 48246 | 44246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 434 | Lawn Seeding (not including topsoil) | 14012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 7006 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 435 | Topsoil Stockpile/Spread | 96170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48085 | 48085 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 436 | Maintenance | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01370 | 437 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGS | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01355 | 438 | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGS | 25860 | 23274 | 0 | 2586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG1-03005 | 439 | SANITARY WASTE PIPING SPECIALTIES | 30070 | 27063 | 0 | 0 | 0 | 0 | 2004.6667 | 1002.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01355 | 440 | INSTALL HW, CW PIPE - SGS | 504915 | 504915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SGS-01360 | 441 | TEST HW, CW - SGS | 21983 | 21983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01330 | 442 | INSTALL CONDENSATE AND STEAM PIPE - SGS | 516372 | 516372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SGS-01335 | 443 | TEST CONDENSATE, STEAM - SGS | 19421 | 19421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01095 | 444 | DEWATERING COVERAGE FOR UTILITY WORK - SGS | 5612 | 5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01595 | 445 | SEWER / DRAINAGE PIPE - SGS | 132508 | 53003.2 | 0 | 0 | 0 | 26501.6 | 26501.6 | 26501.6 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01560 | 446 | CATCH BASIN DRAINS AND CONNECTIONS - SGS | 78622 | 47173.2 | 0 | 31448.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01560 | 447 | REMOVE AREA DRAINS - SGS | 23320 | 5830 | 0 | 0 | 0 | 5830 | 5830 | 5830 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01255 | 448 | ELECTRICAL MANHOLES - SGS | 31811 | 6000 | 0 | 0 | 0 | 8603.6667 | 8603.6667 | 8603.6667 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01255 | 449 | ELECTRICAL CONDUIT TRENCHES - SGS | 61478 | 61478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG1-03005 | 450 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 29700 | 0 | 0 | 0 | 1100 | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01010 | 451 | Equipment SUPPORT FOR SITE - SGS | 167754 | 159366.3 | 0 | 0 | 0 | 2795.9 | 2795.9 | 2795.9 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OG1-01005 | 452 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01010 | 453 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01015 | 454 | Assumed Flooring Material (Slab Penetrations) | 61200 | 61200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 455 | Pipe Insulation | 151200 | 151200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 456 | Tank Insulation | 9750 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01015 | 457 | Fireproofing | 171120 | 171120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01015 | 458 | Fibrous Slate | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 459 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 460 | Underground Utility Materials | 11544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03030 | 461 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 253000 | 240350 | 0 | 0 | 0 | 4216.6667 | 4216.6667 | 4216.6667 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 462 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 463 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 464 | Remove existing door, frame and hardware | 20000 | 10000 | 0 | 0 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01115 | 465 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01115 | 466 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01115 | 467 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 468 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 0 | 3000 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 469 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 470 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 471 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03005 | 472 | GAS SERVICE AND PIPING | 2112 | 0 | 0 | 0 | 0 | 0 | 1408 | 704 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 473 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 474 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 475 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 476 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 477 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 478 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 479 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 480 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 481 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 482 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03005 | 483 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 484 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 485 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01410 | 486 | FORM FLOOD BARRIER FOUNDATIONS - OG-1 | 30105 | 30105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01450 | 487 | DRILL & GROUT DOWELS - OG-1 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01450 | 488 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-1 | 27638 | 27638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01770 | 489 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-1 | 18434 | 13825.5 | 0 | 0 | 2304.25 | 1152.125 | 1152.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01440 | 490 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-1 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01440 | 491 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-1 | 3113 | 3113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01320 | 492 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-1 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01415 | 493 | Footing/Pier | 8892 | 4446 | 0 | 2223 | 2223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-03005 | 494 | Plumbing Pipe Insulation | 34034 | 0 | 17017 | 17017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01435 | 495 | Retaining Walls | 1428 | 714 | 0 | 357 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01615 | 496 | Entrance Slab | 11730 | 8797.5 | 0 | 1466.25 | 1466.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01810 | 497 | Concrete Shelf | 6432 | 6432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01350 | 498 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01830 | 499 | GFRP Sikawrap 100 G | 27456 | 0 | 0 | 0 | 9152 | 9152 | 9152 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01440 | 500 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-1 | 396 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01015 | 501 | Overhead protection for Masonry | 5088 | 3816 | 0 | 0 | 636 | 318 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01830 | 502 | 2" Face brick | 153384 | 138045.6 | 0 | 15338.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01820 | 503 | 6" vertically reinforced CMU | 38368 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01830 | 504 | 2" rigid Insulation | 6715 | 0 | 0 | 0 | 2238.3333 | 2238.3333 | 2238.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02015 | 505 | Heat Trace | 5475 | 0 | 0 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01820 | 506 | Coping stone C1/A-300 | 24909 | 18681.75 | 0 | 0 | 2075.75 | 2075.75 | 2075.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05230 | 507 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01315 | 508 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01860 | 509 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-02145 | 510 | PENETRATION FIRESTOPPING EXTG BLDG - OG-1 | 11505 | 0 | 10066.875 | 0 | 719.0625 | 359.5312 | 359.5312 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01320 | 511 | JOINT SEALANTS EXTG BLDGS - OG-1 | 11505 | 0 | 0 | 0 | 5752.5 | 2876.25 | 2876.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01830 | 512 | Bituthene 4000 waterproofing membrane | 10217 | 8684.45 | 0 | 1532.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01830 | 513 | GE Elemax 2600 Silicone air and vapor barrier | 13728 | 12355.2 | 0 | 1372.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01370 | 514 | Crystalline Waterproofing at perimeter walls | 30878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01825 | 515 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SURV-SGS-M-01005 | 516 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01330 | 517 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 114 - OG1 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 518 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 519 | Layout | 5143 | 5143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 520 | Loading | 7458 | 7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 521 | Framing & Drywall - Materials | 12087 | 12087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 522 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01330 | 523 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01330 | 524 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01855 | 525 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01340 | 526 | Resilient Flooring and base - OG-1 | 12880 | 0 | 0 | 6440 | 6440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 527 | Exhaust Fans: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01860 | 528 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-1 | 57648 | 28824 | 0 | 0 | 9608 | 9608 | 9608 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01860 | 529 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-1 | 63427 | 0 | 0 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01865 | 530 | Temporary Egress Stair Storage Sign | 2640 | 0 | 0 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01865 | 531 | Address Signs | 4675 | 0 | 0 | 0 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01380 | 532 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 533 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 534 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 535 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 536 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 537 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03112 | 538 | Exhaust Fans: Install | 4565 | 4565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 539 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 540 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 541 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 542 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 543 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 544 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 545 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 546 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 547 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 548 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 549 | Steam Unit Heaters: Furnish | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 550 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 551 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 552 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 553 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 554 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 1134.0833 | 1134.0833 | 1134.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 555 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 495 | 18.3333 | 18.3333 | 18.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 556 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 557 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2420 | 1936 | 161.3333 | 161.3333 | 161.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 558 | HANGERS AND SUPPORTS | 11551 | 8663.25 | 962.5833 | 962.5833 | 962.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 559 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03032 | 560 | Steam Unit Heaters: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 561 | DOMESTIC WATER PIPING | 108020 | 81015 | 9001.6667 | 9001.6667 | 9001.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 562 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 14387.25 | 1598.5833 | 1598.5833 | 1598.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 563 | SANITARY WASTE PIPING | 95172 | 85654.8 | 3172.4 | 3172.4 | 3172.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 564 | SANITARY WASTE PIPING SPECIALTIES | 34188 | 32478.6 | 569.8 | 569.8 | 569.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 565 | STORM DRAINAGE PIPING SPECIALTIES | 34188 | 17094 | 5698 | 5698 | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03030 | 566 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 187000 | 140250 | 16362.5 | 0 | 0 | 10129.1667 | 10129.1667 | 10129.1667 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 567 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 568 | Plumbing Pipe Insulation | 41899 | 37709.1 | 2094.95 | 2094.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02040 | 569 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-M-01005 | 570 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 571 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 572 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 573 | Exhaust Fans: Install | 8360 | 0 | 4180 | 4180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 574 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 575 | Steam Unit Heaters: Install | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 576 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 577 | Condensate Return Unit: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 578 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 579 | Heating and Ventilation Unit: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03015 | 580 | Steam Traps: Furnish | 1980 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03015 | 581 | Steam Traps: Install | 14300 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03032 | 582 | Condensate Return Unit: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 583 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 584 | Vacuum Pump Unit: Install | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 585 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 89100 | 89100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 586 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 121000 | 121000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 587 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03025 | 588 | Mechanical Pipe: Hydrostatic Testing | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03107 | 589 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 590 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03135 | 591 | HVAC Ductwork: Testing & Balancing | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 592 | Controls: Furnish and Install: Devices | 77000 | 70840 | 5955.4688 | 204.5312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03112 | 593 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 594 | Controls: Furnish and Install: Controls Conduit | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 595 | Controls: Furnish and Install: Controls Wiring | 11000 | 8250 | 850.7812 | 146.0938 | 0 | 0 | 1753.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 596 | Controls: Connect to Final Termination Points | 7700 | 3850 | 595.5469 | 102.2656 | 0 | 0 | 3152.1875 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03025 | 597 | Controls: Controls Testing | 6600 | 0 | 510.4688 | 87.6562 | 0 | 0 | 6001.875 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 598 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 | 7920 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 599 | Insulation: Furnish and Install: Piping Insulation | 17600 | 2640 | 14080 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 600 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 1486 | 7920 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 601 | ATS Energization | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 602 | ATS Installation | 191625 | 172462.5 | 0 | 0 | 0 | 0 | 6387.5 | 6387.5 | 6387.5 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 603 | ATS Terminations | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03112 | 604 | Heating and Ventilation Unit: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 605 | ATS Testing | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02010 | 606 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02035 | 607 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02395 | 608 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 295650 | 0 | 0 | 147825 | 49275 | 49275 | 49275 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02015 | 609 | Conduit - Branch Circuits (1 1/2" & Smaller) | 246375 | 184781.25 | 0 | 0 | 0 | 0 | 20531.25 | 20531.25 | 20531.25 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02125 | 610 | Conduit - Risers (2" & Larger) | 591300 | 561735 | 0 | 0 | 0 | 0 | 9855 | 9855 | 9855 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02020 | 611 | Demolition/Temp Light & Power | 54750 | 49275 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02145 | 612 | Firestopping | 5250 | 0 | 4593.75 | 0 | 0 | 0 | 218.75 | 218.75 | 218.75 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02025 | 613 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02065 | 614 | Lighting Controls | 25200 | 12600 | 11025 | 0 | 0 | 0 | 525 | 525 | 525 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03015 | 615 | Steam Traps: Furnish | 1760 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02120 | 616 | Lighting Remove & Re-install | 39420 | 0 | 33788.5714 | 0 | 0 | 0 | 1877.1429 | 1877.1429 | 1877.1429 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02160 | 617 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02070 | 618 | Mechanical Terminations(Dampers, Heaters, Motors) | 65700 | 0 | 0 | 0 | 0 | 0 | 21900 | 21900 | 21900 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-01020 | 619 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02250 | 620 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02515 | 621 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02215 | 622 | Switchgear & Panelboard Installation | 361350 | 325215 | 0 | 0 | 0 | 0 | 12045 | 12045 | 12045 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02265 | 623 | Switchgear & Panelboard Terminations | 30113 | 7528.25 | 22584.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02510 | 624 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02015 | 625 | Fire Alarm Conduit | 21900 | 0 | 0 | 0 | 0 | 0 | 7300 | 7300 | 7300 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03015 | 626 | Steam Traps: Install | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02130 | 627 | Fire Alarm Wiring | 19710 | 0 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02115 | 628 | Fire Alarm Devices | 24090 | 12045 | 0 | 0 | 0 | 0 | 4015 | 4015 | 4015 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02535 | 629 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02535 | 630 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01405 | 631 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 122 - OG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01780 | 632 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 3981 | 3582.9 | 0 | 0 | 132.7 | 132.7 | 132.7 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 122 - OG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01780 | 633 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-1 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 122 - OG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01005 | 634 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 15000 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01010 | 635 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01015 | 636 | Assumed Flooring Material (Slab Penetrations) | 57600 | 57600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-03032 | 637 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01020 | 638 | Pipe Insulation | 113400 | 113400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01015 | 639 | Fibrous Slate | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01020 | 640 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01020 | 641 | Underground Utility Materials | 11544 | 11544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 642 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01220 | 643 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 644 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 645 | Remove existing door, frame and hardware | 20000 | 10000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01115 | 646 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01115 | 647 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03032 | 648 | Vacuum Pump Unit: Install | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01115 | 649 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01115 | 650 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 651 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01105 | 652 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 653 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 654 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 655 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 656 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 657 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 658 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03107 | 659 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 88688 | 88688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 660 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 661 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 662 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01105 | 663 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 664 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 665 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 666 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01410 | 667 | FORM FLOOD BARRIER FOUNDATIONS - OG-2 | 30704 | 30704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01450 | 668 | DRILL & GROUT DOWELS - OG-2 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01450 | 669 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-2 | 27638 | 27638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-03007 | 670 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 126500 | 126500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01770 | 671 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-2 | 18763 | 18763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01440 | 672 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-2 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01440 | 673 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-2 | 3113 | 3113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01320 | 674 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-2 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01415 | 675 | Footing/Pier | 9009 | 9009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01435 | 676 | Retaining Walls | 1428 | 1428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01615 | 677 | Entrance Slab | 12342 | 9256.5 | 3085.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01810 | 678 | Concrete Shelf | 6624 | 6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01350 | 679 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01830 | 680 | GFRP Sikawrap 100 G | 26400 | 0 | 0 | 0 | 8800 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-03007 | 681 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 45100 | 45100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01440 | 682 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-2 | 396 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01015 | 683 | Overhead protection for Masonry | 5088 | 3816 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01820 | 684 | 6" vertically reinforced CMU | 38368 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01830 | 685 | 2" Face brick | 153384 | 145714.8 | 0 | 7669.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01830 | 686 | 2" rigid Insulation | 6715 | 0 | 0 | 0 | 2238.3333 | 2238.3333 | 2238.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01820 | 687 | Coping stone C1/A-300 | 25245 | 21458.25 | 0 | 3786.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05080 | 688 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01315 | 689 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01860 | 690 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-02145 | 691 | PENETRATION FIRESTOPPING EXTG BLDG - OG-2 | 11505 | 0 | 10066.875 | 719.0625 | 719.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03025 | 692 | Mechanical Pipe: Hydrostatic Testing | 1513 | 1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01320 | 693 | JOINT SEALANTS EXTG BLDGS - OG-2 | 11505 | 0 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01830 | 694 | Bituthene 4000 waterproofing membrane | 10217 | 9195.3 | 0 | 1021.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01830 | 695 | GE Elemax 2600 Silicone air and vapor barrier | 13728 | 12355.2 | 0 | 1372.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01370 | 696 | Crystalline Waterproofing at perimeter walls | 30878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01825 | 697 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01330 | 698 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 128 - OG2 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 699 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 700 | Layout | 5143 | 5143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 701 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 702 | Framing & Drywall - Materials | 12087 | 12087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03107 | 703 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 704 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01330 | 705 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01330 | 706 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01855 | 707 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01340 | 708 | Resilient Flooring and base - OG-2 | 12880 | 0 | 6440 | 6440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01860 | 709 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-2 | 57648 | 28824 | 9608 | 9608 | 9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01860 | 710 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-2 | 63427 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01865 | 711 | Temporary Egress Stair Storage Sign | 1320 | 0 | 440 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01865 | 712 | Address Signs | 4675 | 0 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01380 | 713 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 714 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 715 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 716 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 717 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 718 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 719 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 720 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 721 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 722 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 723 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 724 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03310 | 725 | HVAC Ductwork: Testing & Balancing | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 726 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 727 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 728 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 729 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 730 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 731 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 732 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 733 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 734 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 735 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 | 0 | 5443.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 736 | Controls: Furnish and Install: Devices | 71500 | 67925 | 0 | 0 | 1191.6667 | 1191.6667 | 1191.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 737 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 495 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 738 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 739 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3739 | 2430.35 | 0 | 1308.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 740 | HANGERS AND SUPPORTS | 11551 | 8663.25 | 0 | 2887.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 741 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 742 | DOMESTIC WATER PIPING | 113740 | 85305 | 0 | 28435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 743 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 14387.25 | 0 | 4795.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 744 | SANITARY WASTE PIPING | 98230 | 78584 | 0 | 19646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 745 | SANITARY WASTE PIPING SPECIALTIES | 30063 | 27056.7 | 0 | 3006.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 746 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 747 | Controls: Furnish and Install: Controls Conduit | 33000 | 31350 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03030 | 748 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 264000 | 224400 | 0 | 0 | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 749 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 750 | Plumbing Pipe Insulation | 28886 | 25997.4 | 1444.3 | 1444.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02035 | 751 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-M-01005 | 752 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 753 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03112 | 754 | Exhaust Fans: Install | 8910 | 0 | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 755 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03032 | 756 | Steam Unit Heaters: Install | 10450 | 10450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 757 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 758 | Controls: Furnish and Install: Controls Wiring | 9900 | 9405 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03032 | 759 | Condensate Return Unit: Install | 17050 | 17050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03112 | 760 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03112 | 761 | Heating and Ventilation Unit: Install | 18150 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03015 | 762 | Steam Traps: Furnish | 1760 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03015 | 763 | Steam Traps: Install | 12100 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 764 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03032 | 765 | Vacuum Pump Unit: Install | 20350 | 20350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03107 | 766 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 86048 | 86048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03007 | 767 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 116050 | 116050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03007 | 768 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 34100 | 34100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 769 | Controls: Connect to Final Termination Points | 6600 | 5940 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03025 | 770 | Mechanical Pipe: Hydrostatic Testing | 3053 | 3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 771 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 38500 | 37730 | 741.7431 | 0 | 0 | 0 | 0 | 28.2569 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 772 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 75460 | 1483.4862 | 0 | 0 | 0 | 0 | 56.5138 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03135 | 773 | HVAC Ductwork: Testing & Balancing | 4400 | 0 | 84.7706 | 0 | 0 | 0 | 0 | 4315.2294 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 774 | Controls: Furnish and Install: Devices | 77000 | 73150 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 775 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 776 | Controls: Furnish and Install: Controls Wiring | 11000 | 8250 | 0 | 1559.7015 | 0 | 1190.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 777 | Controls: Connect to Final Termination Points | 8800 | 4400 | 0 | 1247.7612 | 0 | 3152.2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03025 | 778 | Controls: Controls Testing | 6600 | 0 | 0 | 935.8209 | 0 | 5664.1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 779 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03310 | 780 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 781 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 782 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 783 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 784 | ATS Installation | 153300 | 137970 | 0 | 0 | 0 | 0 | 5110 | 5110 | 5110 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 785 | ATS Terminations | 10950 | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 786 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02010 | 787 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 19162.5 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02025 | 788 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-02115 | 789 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 295650 | 56314.2857 | 42235.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02020 | 790 | Conduit - Branch Circuits (1 1/2" & Smaller) | 232688 | 197784.8 | 0 | 0 | 0 | 0 | 11634.4 | 11634.4 | 11634.4 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 791 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 | 0 | 4950 | 2970 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02130 | 792 | Conduit - Risers (2" & Larger) | 394200 | 374490 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02015 | 793 | Demolition/Temp Light & Power | 54750 | 41062.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02145 | 794 | Firestopping | 5250 | 2625 | 2296.875 | 0 | 0 | 0 | 109.375 | 109.375 | 109.375 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02030 | 795 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02240 | 796 | Lighting Controls | 32550 | 16275 | 0 | 0 | 0 | 0 | 5425 | 5425 | 5425 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02015 | 797 | Lighting Remove & Re-install | 40406 | 0 | 0 | 0 | 0 | 0 | 13468.6667 | 13468.6667 | 13468.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02015 | 798 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02070 | 799 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 | 0 | 0 | 0 | 0 | 21170 | 21170 | 21170 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-E-01015 | 800 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02245 | 801 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 802 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 | 0 | 8800 | 5280 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02515 | 803 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02260 | 804 | Switchgear & Panelboard Installation | 361350 | 343282.5 | 15486.4286 | 2581.0714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02260 | 805 | Switchgear & Panelboard Terminations | 30113 | 7528.25 | 25811.1429 | 0 | 0 | 0 | -1075.4643 | -1075.4643 | -1075.4643 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02510 | 806 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02020 | 807 | Fire Alarm Conduit | 21900 | 16425 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02115 | 808 | Fire Alarm Wiring | 16425 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02115 | 809 | Fire Alarm Devices | 22995 | 11497.5 | 0 | 0 | 0 | 0 | 3832.5 | 3832.5 | 3832.5 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02115 | 810 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02535 | 811 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01405 | 812 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 136 - OG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03040 | 813 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 | 0 | 4950 | 2970 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01780 | 814 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 3981 | 3981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 136 - OG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01780 | 815 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-2 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 136 - OG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01005 | 816 | Gaskets | 78750 | 0 | 0 | 0 | 0 | 26250 | 26250 | 26250 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01010 | 817 | Wire Insulation | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01015 | 818 | Assumed Flooring Material (Slab Penetrations) | 46800 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01005 | 819 | Duct Seal | 3600 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01015 | 820 | Fibrous Slate | 9180 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01020 | 821 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01020 | 822 | Underground Utility Materials | 11388 | 11388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 823 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-02010 | 824 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 20531.25 | 3421.875 | 3421.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01220 | 825 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 826 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 827 | Remove existing door, frame and hardware | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01115 | 828 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01115 | 829 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01115 | 830 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 831 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 832 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 833 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01210 | 834 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-02065 | 835 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01210 | 836 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 837 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 838 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 839 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 840 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01210 | 841 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01105 | 842 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 843 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 844 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 845 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-02130 | 846 | Cabling - Risers & Feeders (2/0 & Larger) | 295650 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 66412.5 | 66412.5 | 66412.5 | 66412.5 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01410 | 847 | FORM FLOOD BARRIER FOUNDATIONS - OG-3 | 30704 | 23028 | 0 | 4605.6 | 3070.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01450 | 848 | DRILL & GROUT DOWELS - OG-3 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01450 | 849 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-3 | 27638 | 27638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01770 | 850 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-3 | 18763 | 14072.25 | 0 | 4690.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01440 | 851 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-3 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01440 | 852 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-3 | 3113 | 0 | 1037.6667 | 1037.6667 | 1037.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01320 | 853 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-3 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01415 | 854 | Footing/Pier | 9009 | 6756.75 | 2252.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01435 | 855 | Retaining Walls | 1428 | 714 | 357 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01615 | 856 | Entrance Slab | 11730 | 0 | 11730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02035 | 857 | Conduit - Branch Circuits (1 1/2" & Smaller) | 246375 | 24637.5 | 40000 | 20157.9545 | 0 | 0 | 0 | 0 | 40394.8864 | 40394.8864 | 40394.8864 | 40394.8864 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01810 | 858 | Concrete Shelf | 6768 | 6768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01350 | 859 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01830 | 860 | GFRP Sikawrap 100 G | 27456 | 0 | 0 | 0 | 9152 | 9152 | 9152 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01440 | 861 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-3 | 396 | 0 | 132 | 132 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01015 | 862 | Overhead protection for Masonry | 5088 | 3816 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01820 | 863 | 6" vertically reinforced CMU | 38368 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01830 | 864 | 2" Face brick | 153384 | 138045.6 | 0 | 15338.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01830 | 865 | 2" rigid Insulation | 6715 | 1343 | 0 | 0 | 1790.6667 | 1790.6667 | 1790.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01820 | 866 | Coping stone C1/A-300 | 25245 | 18933.75 | 0 | 0 | 2103.75 | 2103.75 | 2103.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05110 | 867 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02030 | 868 | Conduit - Risers (2" & Larger) | 295650 | 29565 | 0 | 0 | 0 | 0 | 0 | 0 | 66521.25 | 66521.25 | 66521.25 | 66521.25 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01315 | 869 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01860 | 870 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-02150 | 871 | PENETRATION FIRESTOPPING EXTG BLDG - OG-3 | 11505 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01320 | 872 | JOINT SEALANTS EXTG BLDGS - OG-3 | 11505 | 0 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01830 | 873 | Bituthene 4000 waterproofing membrane | 10217 | 0 | 0 | 0 | 3405.6667 | 3405.6667 | 3405.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01830 | 874 | GE Elemax 2600 Silicone air and vapor barrier | 14784 | 0 | 0 | 0 | 4928 | 4928 | 4928 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01370 | 875 | Crystalline Waterproofing at perimeter walls | 29843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01825 | 876 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01330 | 877 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 142 - OG3 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 878 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 879 | Demolition/Temp Light & Power | 54750 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 5475 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 880 | Layout | 5401 | 5401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 881 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 882 | Framing & Drywall - Materials | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 883 | Framing- Labor | 13629 | 13629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01330 | 884 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01330 | 885 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01855 | 886 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01340 | 887 | Resilient Flooring and base - OG-3 | 15640 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01860 | 888 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-3 | 57648 | 28824 | 9608 | 9608 | 9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01860 | 889 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-3 | 63427 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02120 | 890 | Firestopping | 5250 | 0 | 4593.75 | 0 | 0 | 0 | 0 | 0 | 164.0625 | 164.0625 | 164.0625 | 164.0625 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01865 | 891 | Temporary Egress Stair Storage Sign | 2640 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01865 | 892 | Address Signs | 4675 | 0 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01380 | 893 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 894 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 895 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 896 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 897 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 898 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 899 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 900 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02030 | 901 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 902 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 903 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 904 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 905 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 906 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 907 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 908 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 909 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 910 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 911 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02115 | 912 | Lighting Controls | 26250 | 13125 | 3750 | 0 | 0 | 0 | 0 | 0 | 2343.75 | 2343.75 | 2343.75 | 2343.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 913 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 914 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 915 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 | 0 | 5443.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 916 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 786 | 550.2 | 0 | 235.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 917 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 330 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 918 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2637 | 1582.2 | 0 | 1054.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 919 | HANGERS AND SUPPORTS | 11526 | 9797.1 | 0 | 1728.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 920 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 921 | DOMESTIC WATER PIPING | 128777 | 109460.45 | 0 | 19316.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 922 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 18223.85 | 0 | 959.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 923 | Lighting Remove & Re-install | 27972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6993 | 6993 | 6993 | 6993 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 924 | SANITARY WASTE PIPING | 147017 | 117613.6 | 0 | 0 | 14701.7 | 14701.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 925 | SANITARY WASTE PIPING SPECIALTIES | 33792 | 30412.8 | 0 | 3379.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 926 | STORM DRAINAGE PIPING SPECIALTIES | 33792 | 16896 | 0 | 16896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03030 | 927 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 264000 | 224400 | 0 | 0 | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 928 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9317 | 9317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 929 | Plumbing Pipe Insulation | 35464 | 8866 | 0 | 13299 | 13299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02030 | 930 | Heat Trace | 5475 | 0 | 4380 | 0 | 0 | 0 | 365 | 365 | 365 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-M-01005 | 931 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 932 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03112 | 933 | Exhaust Fans: Install | 14960 | 7480 | 326.781 | 7153.219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 934 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 935 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03032 | 936 | Steam Unit Heaters: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 937 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03032 | 938 | Condensate Return Unit: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03112 | 939 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03112 | 940 | Heating and Ventilation Unit: Install | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03015 | 941 | Steam Traps: Furnish | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03015 | 942 | Steam Traps: Install | 25025 | 25025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 943 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03032 | 944 | Vacuum Pump Unit: Install | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02040 | 945 | Mechanical Terminations(Dampers, Heaters, Motors) | 39420 | 0 | 0 | 33788.5714 | 0 | 0 | 0 | 0 | 1407.8571 | 1407.8571 | 1407.8571 | 1407.8571 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03007 | 946 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 331045 | 331045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03007 | 947 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 421300 | 421300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 948 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 143000 | 143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03025 | 949 | Mechanical Pipe: Hydrostatic Testing | 4455 | 4455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03107 | 950 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 951 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 66000 | 62700 | 0 | 2129.0323 | 0 | 0 | 0 | 1170.9677 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03135 | 952 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 106.4516 | 0 | 0 | 0 | 3193.5484 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 953 | Controls: Furnish and Install: Devices | 77000 | 65450 | 0 | 10745.5224 | 0 | 804.4776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 954 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 955 | Controls: Furnish and Install: Controls Wiring | 11000 | 8580 | 0 | 1535.0746 | 0 | 884.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-E-01030 | 956 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 957 | Controls: Connect to Final Termination Points | 8800 | 4400 | 0 | 1228.0597 | 0 | 3171.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03025 | 958 | Controls: Controls Testing | 6600 | 0 | 0 | 921.0448 | 0 | 5678.9552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 959 | Insulation: Furnish and Install: Ductwork Insulation | 19800 | 0 | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 960 | Insulation: Furnish and Install: Piping Insulation | 39600 | 27720 | 11880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 961 | Insulation: Furnish and Install: Equipment Insulation | 19800 | 13860 | 5940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 962 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 963 | ATS Installation | 153300 | 137970 | 0 | 0 | 0 | 0 | 5110 | 5110 | 5110 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 964 | ATS Terminations | 10950 | 2737.5 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 965 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02010 | 966 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02105 | 967 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 2737.5 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02025 | 968 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 0 | 42857.1429 | 0 | 0 | 0 | 35714.2857 | 35714.2857 | 35714.2857 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02260 | 969 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 295650 | 56314.2857 | 42235.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02020 | 970 | Conduit - Branch Circuits (1 1/2" & Smaller) | 219000 | 175200 | 0 | 0 | 0 | 0 | 14600 | 14600 | 14600 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02130 | 971 | Conduit - Risers (2" & Larger) | 394200 | 374490 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02015 | 972 | Demolition/Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02150 | 973 | Firestopping | 5250 | 2625 | 0 | 0 | 0 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02035 | 974 | Foundation Coring | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02240 | 975 | Lighting Controls | 33600 | 16800 | 0 | 0 | 0 | 0 | 5600 | 5600 | 5600 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02015 | 976 | Lighting Remove & Re-install | 39420 | 0 | 0 | 0 | 0 | 0 | 13140 | 13140 | 13140 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02015 | 977 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02655 | 978 | Switchgear & Panelboard Energization | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02070 | 979 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 15877.5 | 41678.4375 | 0 | 0 | 0 | 1984.6875 | 1984.6875 | 1984.6875 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-E-01015 | 980 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02245 | 981 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02515 | 982 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02265 | 983 | Switchgear & Panelboard Installation | 361350 | 343282.5 | 18067.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02265 | 984 | Switchgear & Panelboard Terminations | 30525 | 7631.25 | 26709.375 | 0 | 0 | 0 | -1271.875 | -1271.875 | -1271.875 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02510 | 985 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02020 | 986 | Fire Alarm Conduit | 21900 | 5475 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02115 | 987 | Fire Alarm Wiring | 16425 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02115 | 988 | Fire Alarm Devices | 20805 | 10402.5 | 0 | 0 | 0 | 0 | 3467.5 | 3467.5 | 3467.5 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02330 | 989 | Switchgear & Panelboard Installation | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 16425 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02115 | 990 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02535 | 991 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01405 | 992 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 150 - OG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01780 | 993 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 3981 | 3582.9 | 0 | 398.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 150 - OG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01780 | 994 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-3 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 150 - OG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01005 | 995 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 7500 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01010 | 996 | Wire Insulation | 37500 | 35625 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01015 | 997 | Assumed Flooring Material (Slab Penetrations) | 75600 | 75600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 998 | Pipe Insulation | 126000 | 120000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 999 | Tank Insulation | 9750 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG7-02330 | 1000 | Switchgear & Panelboard Terminations | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01015 | 1001 | Fireproofing | 32550 | 32550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01015 | 1002 | Fibrous Slate | 9180 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 1003 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 1004 | Underground Utility Materials | 11388 | 11388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1005 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01220 | 1006 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1007 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1008 | Remove existing door, frame and hardware | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01115 | 1009 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01115 | 1010 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG7-02650 | 1011 | Switchgear & Panelboard Testing | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01115 | 1012 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1013 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01210 | 1014 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01105 | 1015 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1016 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1017 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01210 | 1018 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1019 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1020 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1021 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01405 | 1022 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 20834 | 20834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 014 - SG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01210 | 1023 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1024 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01210 | 1025 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01105 | 1026 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1027 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1028 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1029 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01410 | 1030 | FORM FLOOD BARRIER FOUNDATIONS - OG-4 | 30704 | 30704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01450 | 1031 | DRILL & GROUT DOWELS - OG-4 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01450 | 1032 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-4 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01480 | 1033 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 7542 | 1131.3 | 6464.5714 | 0 | 0 | 0 | -17.9571 | -17.9571 | -17.9571 | 0 | 0 | 0 | 0 | SG1 | 014 - SG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01570 | 1034 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-4 | 18763 | 18763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01440 | 1035 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-4 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01440 | 1036 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-4 | 3232 | 0 | 0 | 1616 | 1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01320 | 1037 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-4 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01415 | 1038 | Footing/Pier | 9009 | 6756.75 | 2252.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01435 | 1039 | Retaining Walls | 1428 | 714 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01615 | 1040 | Entrance Slab | 12342 | 0 | 12342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01810 | 1041 | Concrete Shelf | 6528 | 6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01350 | 1042 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01830 | 1043 | GFRP Sikawrap 100 G | 41184 | 0 | 0 | 0 | 13728 | 13728 | 13728 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01480 | 1044 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-1 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 014 - SG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01440 | 1045 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-4 | 396 | 0 | 0 | 198 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01015 | 1046 | Overhead protection for Masonry | 5088 | 3816 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01820 | 1047 | 6" vertically reinforced CMU | 44875 | 42631.25 | 0 | 2243.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01830 | 1048 | 2" Face brick | 198275 | 198275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01830 | 1049 | 2" rigid Insulation | 7662 | 5363.4 | 0 | 2298.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01820 | 1050 | Coping stone C1/A-300 | 28328 | 28328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05140 | 1051 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01315 | 1052 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01860 | 1053 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-02145 | 1054 | PENETRATION FIRESTOPPING EXTG BLDG - OG 4 | 11505 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01005 | 1055 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01320 | 1056 | JOINT SEALANTS EXTG BLDGS - OG-4 | 11505 | 0 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01830 | 1057 | Bituthene 4000 waterproofing membrane | 7491 | 7116.45 | 0 | 374.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01830 | 1058 | GE Elemax 2600 Silicone air and vapor barrier | 22176 | 21067.2 | 0 | 1108.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01370 | 1059 | Crystalline Waterproofing at perimeter walls | 30360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01825 | 1060 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01330 | 1061 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 156 - OG4 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 1062 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01325 | 1063 | Layout | 5401 | 5401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01325 | 1064 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01325 | 1065 | Framing & Drywall - Materials | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01010 | 1066 | Wire Insulation | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01325 | 1067 | Framing- Labor | 13372 | 13372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01330 | 1068 | Drywall - Labor | 15687 | 15687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01330 | 1069 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01855 | 1070 | Stucco | 10183 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01340 | 1071 | Resilient Flooring and base - OG-4 | 15640 | 0 | 0 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01860 | 1072 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-4 | 57648 | 57648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01860 | 1073 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-4 | 63427 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01865 | 1074 | Temporary Egress Stair Storage Sign | 2640 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01865 | 1075 | Address Signs | 4950 | 0 | 1650 | 1650 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01380 | 1076 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1077 | Assumed Flooring Material (Slab Penetrations) | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01380 | 1078 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1079 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1080 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1081 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1082 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1083 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1084 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1085 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1086 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1087 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1088 | Pipe Insulation | 113400 | 97776 | 0 | 0 | 15624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01380 | 1089 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1090 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1091 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1092 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1093 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1094 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1095 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1096 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1097 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1098 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 6804.5 | 1701.125 | 1701.125 | 1701.125 | 1701.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1099 | Tank Insulation | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03005 | 1100 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 786 | 471.6 | 78.6 | 78.6 | 78.6 | 78.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1101 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 440 | 165 | 165 | 165 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1102 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3282 | 656.4 | 656.4 | 656.4 | 656.4 | 656.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1103 | HANGERS AND SUPPORTS | 11539 | 8077.3 | 865.425 | 865.425 | 865.425 | 865.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1104 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 548.75 | 548.75 | 548.75 | 548.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1105 | DOMESTIC WATER PIPING | 125548 | 87883.6 | 9416.1 | 9416.1 | 9416.1 | 9416.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1106 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 15346.4 | 959.15 | 959.15 | 959.15 | 959.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1107 | SANITARY WASTE PIPING | 106914 | 96222.6 | 2672.85 | 2672.85 | 2672.85 | 2672.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1108 | SANITARY WASTE PIPING SPECIALTIES | 30067 | 27060.3 | 751.675 | 751.675 | 751.675 | 751.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1109 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 | 4125 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01005 | 1110 | Duct Seal | 18000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03030 | 1111 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 187000 | 149600 | 18700 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1112 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9306 | 9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1113 | Plumbing Pipe Insulation | 35464 | 21278.4 | 7092.8 | 7092.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02045 | 1114 | Heat Trace | 5475 | 0 | 0 | 4692.8571 | 0 | 0 | 260.7143 | 260.7143 | 260.7143 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-M-01005 | 1115 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 1116 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03112 | 1117 | Exhaust Fans: Install | 13860 | 0 | 1663.7592 | 12196.2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1118 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03032 | 1119 | Steam Unit Heaters: Install | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1120 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1121 | Vinyl Membrane and Mastic | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03032 | 1122 | Condensate Return Unit: Install | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03112 | 1123 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03112 | 1124 | Heating and Ventilation Unit: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03015 | 1125 | Steam Traps: Furnish | 1980 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03015 | 1126 | Steam Traps: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1127 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03032 | 1128 | Vacuum Pump Unit: Install | 25300 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1129 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 270930 | 270930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1130 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 352000 | 352000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1131 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 132000 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1132 | Caulk | 112500 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03025 | 1133 | Mechanical Pipe: Hydrostatic Testing | 4070 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 1134 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 27500 | 26125 | 0 | 793.2692 | 0 | 193.9103 | 193.9103 | 193.9103 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 1135 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 55000 | 54450 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03032 | 1136 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 95.1923 | 0 | 0 | 0 | 3204.8077 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1137 | Controls: Furnish and Install: Devices | 77000 | 69300 | 0 | 5688.806 | 0 | 2011.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1138 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1139 | Controls: Furnish and Install: Controls Wiring | 11000 | 10450 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1140 | Controls: Connect to Final Termination Points | 8800 | 8360 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03025 | 1141 | Controls: Controls Testing | 6600 | 0 | 0 | 487.6119 | 0 | 6112.3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1142 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 9075 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1143 | Fibrous Slate | 14025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-03040 | 1144 | Insulation: Furnish and Install: Piping Insulation | 37950 | 22770 | 12228.3333 | 2951.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1145 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 10890 | 5848.3333 | 1411.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1146 | ATS Energization | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1147 | ATS Installation | 191625 | 172462.5 | 0 | 0 | 0 | 0 | 6387.5 | 6387.5 | 6387.5 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1148 | ATS Terminations | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1149 | ATS Testing | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02015 | 1150 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 6843.75 | 0 | 0 | 0 | 0 | 6843.75 | 6843.75 | 6843.75 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02040 | 1151 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGP1-02010 | 1152 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 295650 | 147825 | 147825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02020 | 1153 | Conduit - Branch Circuits (1 1/2" & Smaller) | 260063 | 208050.4 | 0 | 0 | 0 | 0 | 17337.5333 | 17337.5333 | 17337.5333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1154 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-02130 | 1155 | Conduit - Risers (2" & Larger) | 492750 | 468112.5 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02025 | 1156 | Demolition/Temp Light & Power | 54750 | 52012.5 | 1368.75 | 1368.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02145 | 1157 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 0 | 1750 | 1750 | 1750 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02030 | 1158 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02240 | 1159 | Lighting Controls | 26250 | 13125 | 0 | 11250 | 0 | 0 | 625 | 625 | 625 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02025 | 1160 | Lighting Remove & Re-install | 39420 | 0 | 0 | 0 | 0 | 0 | 13140 | 13140 | 13140 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02025 | 1161 | Lighting System Program & Energize | 5550 | 0 | 0 | 0 | 0 | 0 | 1850 | 1850 | 1850 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02050 | 1162 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 15877.5 | 0 | 0 | 0 | 0 | 15877.5 | 15877.5 | 15877.5 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-E-01010 | 1163 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02245 | 1164 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1165 | Underground Utility Materials | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-02515 | 1166 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02260 | 1167 | Switchgear & Panelboard Installation | 361350 | 325215 | 18067.5 | 18067.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02260 | 1168 | Switchgear & Panelboard Terminations | 30525 | 7631.25 | 0 | 0 | 0 | 0 | 7631.25 | 7631.25 | 7631.25 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02510 | 1169 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02020 | 1170 | Fire Alarm Conduit | 27375 | 19162.5 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02115 | 1171 | Fire Alarm Wiring | 19710 | 0 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02115 | 1172 | Fire Alarm Devices | 21900 | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02115 | 1173 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02535 | 1174 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01405 | 1175 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 164 - OG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01105 | 1176 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01580 | 1177 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 3981 | 3582.9 | 398.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 164 - OG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01580 | 1178 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-4 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 164 - OG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01005 | 1179 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01010 | 1180 | Wire Insulation | 37500 | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01015 | 1181 | Assumed Flooring Material (Slab Penetrations) | 57600 | 57600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1182 | Pipe Insulation | 113400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1183 | Tank Insulation | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01015 | 1184 | Fireproofing | 127875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01015 | 1185 | Fibrous Slate | 9180 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1186 | Waterproofing | 4971 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01220 | 1187 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1188 | Underground Utility Materials | 11388 | 9110.4 | 0 | 2277.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1189 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01220 | 1190 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1191 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1192 | Remove existing door, frame and hardware | 20000 | 0 | 0 | 0 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01115 | 1193 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01115 | 1194 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01115 | 1195 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1196 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 0 | 3000 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01210 | 1197 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01105 | 1198 | Remove existing vent / window and frame - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1199 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1200 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1201 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01210 | 1202 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1203 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1204 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1205 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1206 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1207 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01210 | 1208 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01105 | 1209 | Remove existing door, frame and hardware - cellar | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1210 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1211 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1212 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1213 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01410 | 1214 | FORM FLOOD BARRIER FOUNDATIONS - OG-5 | 30704 | 30704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01450 | 1215 | DRILL & GROUT DOWELS - OG-5 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01450 | 1216 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-5 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01570 | 1217 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-5 | 18763 | 18763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01440 | 1218 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-5 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01440 | 1219 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-5 | 3113 | 0 | 0 | 0 | 1556.5 | 778.25 | 778.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01115 | 1220 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01320 | 1221 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-5 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01415 | 1222 | Footing/Pier | 14820 | 14820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01435 | 1223 | Retaining Walls | 1428 | 714 | 0 | 357 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01565 | 1224 | Entrance Slab | 12342 | 0 | 0 | 6171 | 6171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01810 | 1225 | Concrete Shelf | 6576 | 5918.4 | 0 | 328.8 | 328.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01350 | 1226 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01830 | 1227 | GFRP Sikawrap 100 G | 41184 | 41184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01440 | 1228 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-5 | 396 | 0 | 0 | 0 | 198 | 99 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01015 | 1229 | Overhead protection for Masonry | 5088 | 3816 | 0 | 0 | 636 | 318 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01820 | 1230 | 6" vertically reinforced CMU | 44875 | 44875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01115 | 1231 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01830 | 1232 | 2" Face brick | 198275 | 198275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01830 | 1233 | 2" rigid Insulation | 7662 | 7662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01820 | 1234 | Coping stone C1/A-300 | 28002 | 28002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05260 | 1235 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01315 | 1236 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01860 | 1237 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02145 | 1238 | PENETRATION FIRESTOPPING EXTG BLDG - OG 5 | 11505 | 0 | 0 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01320 | 1239 | JOINT SEALANTS EXTG BLDGS - OG-5 | 11505 | 0 | 0 | 0 | 5752.5 | 2876.25 | 2876.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01830 | 1240 | Bituthene 4000 waterproofing membrane | 7491 | 7491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01830 | 1241 | GE Elemax 2600 Silicone air and vapor barrier | 22176 | 22176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01115 | 1242 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01370 | 1243 | Crystalline Waterproofing at perimeter walls | 29440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01825 | 1244 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01330 | 1245 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 170 - OG5 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 1246 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1247 | Layout | 3858 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1248 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1249 | Framing & Drywall - Materials | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1250 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01330 | 1251 | Drywall - Labor | 16715 | 16715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01330 | 1252 | Tape/ Spackle finishes | 12087 | 12087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01210 | 1253 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01855 | 1254 | Stucco | 10183 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01340 | 1255 | Resilient Flooring and base - OG-5 | 15640 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01860 | 1256 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-5 | 57648 | 57648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01860 | 1257 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-5 | 63427 | 0 | 0 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01865 | 1258 | Temporary Egress Stair Storage Sign | 2640 | 0 | 0 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01865 | 1259 | Address Signs | 4950 | 0 | 0 | 0 | 1650 | 1650 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01380 | 1260 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1261 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1262 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1263 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01105 | 1264 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01380 | 1265 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1266 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1267 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1268 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1269 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1270 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1271 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1272 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1273 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1274 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01205 | 1275 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01380 | 1276 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1277 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1278 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1279 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1280 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1281 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1282 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 0 | 3402.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1283 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 440 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1284 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 825 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1285 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2860 | 1430 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01205 | 1286 | Existing Ramp railing to be be removed - 1st fllor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-03005 | 1287 | HANGERS AND SUPPORTS | 11541 | 11541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1288 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1289 | DOMESTIC WATER PIPING | 120919 | 120919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1290 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 | 0 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1291 | SANITARY WASTE PIPING | 111989 | 100790.1 | 0 | 11198.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1292 | SANITARY WASTE PIPING SPECIALTIES | 30069 | 27062.1 | 0 | 3006.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1293 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03030 | 1294 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 186998 | 149598.4 | 0 | 0 | 18699.8 | 18699.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1295 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1296 | Plumbing Pipe Insulation | 35464 | 31917.6 | 0 | 1773.2 | 1773.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01410 | 1297 | FORM FLOOD BARRIER FOUNDATIONS - SG-2 | 33187 | 16593.5 | 0 | 16593.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02045 | 1298 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-M-01005 | 1299 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 1300 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03112 | 1301 | Exhaust Fans: Install | 17160 | 0 | 5720 | 5720 | 5720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1302 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03032 | 1303 | Steam Unit Heaters: Install | 18700 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1304 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03032 | 1305 | Condensate Return Unit: Install | 25300 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03112 | 1306 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03112 | 1307 | Heating and Ventilation Unit: Install | 26400 | 0 | 8800 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01450 | 1308 | DRILL & GROUT DOWELS - SG-2 | 3359 | 3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-03015 | 1309 | Steam Traps: Furnish | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03015 | 1310 | Steam Traps: Install | 25300 | 12650 | 1753.7673 | 1555.5154 | 9340.7173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1311 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03032 | 1312 | Vacuum Pump Unit: Install | 28600 | 28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03107 | 1313 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 350570 | 262927.5 | 52287.1026 | 35355.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03007 | 1314 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 451000 | 225500 | 112750 | 112750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1315 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 220000 | 110000 | 32812.7409 | 77187.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03025 | 1316 | Mechanical Pipe: Hydrostatic Testing | 5830 | 0 | 2915 | 2915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1317 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 38500 | 37730 | 0 | 0 | 741.7431 | 0 | 0 | 28.2569 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1318 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 75460 | 0 | 0 | 1483.4862 | 0 | 0 | 56.5138 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01450 | 1319 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-2 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-03310 | 1320 | HVAC Ductwork: Testing & Balancing | 4400 | 0 | 0 | 0 | 84.7706 | 0 | 0 | 4315.2294 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1321 | Controls: Furnish and Install: Devices | 77000 | 55440 | 0 | 20456.7164 | 0 | 1103.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1322 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1323 | Controls: Furnish and Install: Controls Wiring | 11000 | 4400 | 0 | 2922.3881 | 0 | 3677.6119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1324 | Controls: Connect to Final Termination Points | 8800 | 0 | 0 | 2337.9104 | 0 | 6462.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03025 | 1325 | Controls: Controls Testing | 6600 | 0 | 0 | 1753.4328 | 0 | 4846.5672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1326 | Insulation: Furnish and Install: Ductwork Insulation | 22000 | 0 | 0 | 0 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1327 | Insulation: Furnish and Install: Piping Insulation | 44000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1328 | Insulation: Furnish and Install: Equipment Insulation | 22000 | 0 | 0 | 0 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02210 | 1329 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01470 | 1330 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-2 | 25018 | 12509 | 10424.1667 | 0 | 0 | 1042.4167 | 1042.4167 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02210 | 1331 | ATS Installation | 153300 | 137970 | 0 | 0 | 0 | 0 | 5110 | 5110 | 5110 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02210 | 1332 | ATS Terminations | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02210 | 1333 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02010 | 1334 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02040 | 1335 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGP1-02025 | 1336 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 246375 | 82125 | 82125 | 82125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02015 | 1337 | Conduit - Branch Circuits (1 1/2" & Smaller) | 232688 | 197784.8 | 0 | 0 | 0 | 0 | 11634.4 | 11634.4 | 11634.4 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02125 | 1338 | Conduit - Risers (2" & Larger) | 492750 | 468112.5 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02025 | 1339 | Demolition/Temp Light & Power | 54750 | 43800 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02145 | 1340 | Firestopping | 5250 | 2625 | 0 | 0 | 0 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01440 | 1341 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-2 | 24855 | 24855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02030 | 1342 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02240 | 1343 | Lighting Controls | 32550 | 16275 | 0 | 13950 | 0 | 0 | 775 | 775 | 775 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02025 | 1344 | Lighting Remove & Re-install | 39420 | 0 | 0 | 0 | 0 | 0 | 13140 | 13140 | 13140 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02025 | 1345 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02050 | 1346 | Mechanical Terminations(Dampers, Heaters, Motors) | 65700 | 16425 | 43115.625 | 0 | 0 | 0 | 2053.125 | 2053.125 | 2053.125 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-E-01010 | 1347 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02250 | 1348 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02515 | 1349 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 25811.1429 | 0 | 1433.9524 | 1433.9524 | 1433.9524 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02265 | 1350 | Switchgear & Panelboard Installation | 366300 | 329670 | 18315 | 18315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02265 | 1351 | Switchgear & Panelboard Terminations | 30113 | 7528.25 | 0 | 0 | 0 | 0 | 7528.25 | 7528.25 | 7528.25 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01415 | 1352 | Footing/Pier | 11409 | 5704.5 | 3803 | 1901.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02510 | 1353 | Switchgear & Panelboard Testing | 30113 | 0 | 4301.8571 | 4301.8571 | 4301.8571 | 5735.8095 | 5735.8095 | 5735.8095 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02015 | 1354 | Fire Alarm Conduit | 21900 | 16425 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02115 | 1355 | Fire Alarm Wiring | 19710 | 0 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02115 | 1356 | Fire Alarm Devices | 20805 | 10402.5 | 0 | 0 | 0 | 0 | 3467.5 | 3467.5 | 3467.5 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02115 | 1357 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02535 | 1358 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01405 | 1359 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 178 - OG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01580 | 1360 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 3981 | 3981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 178 - OG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01580 | 1361 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-5 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 178 - OG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01005 | 1362 | Gaskets | 58500 | 43875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14625 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01435 | 1363 | Retaining Walls | 3047 | 3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01010 | 1364 | Wire Insulation | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01015 | 1365 | Assumed Flooring Material (Slab Penetrations) | 64800 | 64800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01020 | 1366 | Pipe Insulation | 90720 | 90720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01005 | 1367 | Duct Seal | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01015 | 1368 | Asbestos Panels | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01015 | 1369 | Fibrous Slate | 14280 | 14280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01020 | 1370 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01020 | 1371 | Underground Utility Materials | 11388 | 11388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1372 | Remove existing paint and plaster - cellar and basement | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01220 | 1373 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01535 | 1374 | Entrance Slab | 17178 | 4294.5 | 4294.5 | 4294.5 | 4294.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01105 | 1375 | Remove existing vent / window and frame- cellar and basement | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1376 | Remove existing door, frame and hardware - basement | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01115 | 1377 | Remove Areaway slab and drain - basement | 60000 | 51000 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 1800 | 1800 | 1800 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01115 | 1378 | Remove Areaway grate - cellar and basement | 20000 | 15000 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01115 | 1379 | Sawcut and remove portion of areaway wall - basement | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1380 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01105 | 1381 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1382 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1383 | Sawcut slab opening for mechanical - 1st floor | 40000 | 20000 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01210 | 1384 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01810 | 1385 | Concrete Shelf | 5241 | 5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01210 | 1386 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1387 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1388 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1389 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1390 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01210 | 1391 | Cut openings in slab - 2nd floor | 40000 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01105 | 1392 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1393 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1394 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1395 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01350 | 1396 | New Concrete Curb Next to Existing Wall | 297 | 0 | 148.5 | 148.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01410 | 1397 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - OG-6 | 196219 | 117731.4 | 39243.8 | 39243.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01450 | 1398 | DRILL & GROUT DOWELS - OG-6 | 42646 | 42646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01450 | 1399 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-6 | 57788 | 15894 | 0 | 35909.1429 | 2992.4286 | 1496.2143 | 1496.2143 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01770 | 1400 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-6 | 56948 | 28474 | 0 | 0 | 9491.3333 | 9491.3333 | 9491.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01440 | 1401 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-6 | 11142 | 8356.5 | 0 | 2785.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01440 | 1402 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-6 | 3927 | 0 | 0 | 3272.5 | 327.25 | 163.625 | 163.625 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01320 | 1403 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-6 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01415 | 1404 | Footing/Pier | 13845 | 0 | 0 | 0 | 6922.5 | 6922.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01435 | 1405 | Retaining Walls | 1275 | 637.5 | 637.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01765 | 1406 | Entrance Slab | 23358 | 0 | 0 | 0 | 11679 | 11679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01830 | 1407 | GFRP Sikawrap 100 G | 44616 | 0 | 0 | 0 | 14872 | 14872 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01810 | 1408 | Concrete Shelf | 5472 | 0 | 0 | 0 | 2736 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01350 | 1409 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01765 | 1410 | Boiler Room Walls | 18288 | 18288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1411 | GFRP Sikawrap 100 G | 32604 | 0 | 10868 | 10868 | 10868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OGE-01015 | 1412 | Overhead protection for Masonry | 15262 | 0 | 0 | 0 | 7631 | 3815.5 | 3815.5 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01820 | 1413 | 6" vertically reinforced CMU | 34760 | 26070 | 0 | 0 | 8690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1414 | 2" Face brick | 161546 | 0 | 80773 | 80773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1415 | 2" rigid Insulation | 6083 | 0 | 2027.6667 | 2027.6667 | 2027.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01820 | 1416 | Coping stone C1/A-300 | 12375 | 0 | 0 | 0 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05290 | 1417 | MATERIAL AND FABRICATION | 16765 | 0 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01440 | 1418 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-2 | 324 | 0 | 162 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01315 | 1419 | INSTALLATION | 19800 | 0 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01860 | 1420 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-02145 | 1421 | PENETRATION FIRESTOPPING EXTG BLDG - OG-6 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11505 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01320 | 1422 | JOINT SEALANTS EXTG BLDGS - OG 6 | 33516 | 0 | 0 | 0 | 11172 | 11172 | 11172 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01830 | 1423 | Bituthene 4000 waterproofing membrane | 9485 | 0 | 3161.6667 | 3161.6667 | 3161.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1424 | GE Elemax 2600 Silicone air and vapor barrier | 18810 | 0 | 6270 | 6270 | 6270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01370 | 1425 | Crystalline Waterproofing at perimeter walls | 54338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01825 | 1426 | Waterproofing at foundation walls | 22080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
08140 | 1427 | ALUMINUM WINDOWS | 19222 | 0 | 0 | 0 | 9611 | 4805.5 | 4805.5 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 184 - OG6 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01330 | 1428 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 184 - OG6 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01015 | 1429 | Overhead protection for Masonry | 5088 | 2544 | 0 | 0 | 0 | 1272 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
08020 | 1430 | Furnish Doors | 14634 | 4829.22 | 0 | 0 | 4902.39 | 2451.195 | 2451.195 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1431 | Layout | 3858 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1432 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1433 | Framing & Drywall - Materials | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1434 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01330 | 1435 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01330 | 1436 | Tape/ Spackle finishes | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01855 | 1437 | Stucco | 10183 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01340 | 1438 | Resilient Flooring and base - OG-6 | 15640 | 0 | 0 | 0 | 0 | 0 | 11730 | 3910 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01860 | 1439 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-6 | 111178 | 55589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55589 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01820 | 1440 | 6" vertically reinforced CMU | 125840 | 119548 | 0 | 0 | 6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01860 | 1441 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-6 | 63427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63427 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01865 | 1442 | Temporary Egress Stair Storage Sign | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2640 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01865 | 1443 | Address Signs | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01380 | 1444 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1445 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1446 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1447 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1448 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1449 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1450 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01830 | 1451 | 2" Face brick | 357280 | 285824 | 0 | 0 | 71456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01380 | 1452 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1453 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1454 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1455 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1456 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1457 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1458 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1459 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1460 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1461 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01830 | 1462 | 2" rigid Insulation | 18876 | 9438 | 0 | 0 | 3146 | 3146 | 3146 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01380 | 1463 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1464 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1465 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1466 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 | 1814.5333 | 1814.5333 | 1814.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1467 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 2634 | 2107.2 | 175.6 | 175.6 | 175.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1468 | ESCUTCHEONS FOR PLUMBING PIPING | 1650 | 1320 | 110 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1469 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4171 | 2502.6 | 556.1333 | 556.1333 | 556.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1470 | HANGERS AND SUPPORTS | 11526 | 8644.5 | 960.5 | 960.5 | 960.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1471 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1472 | DOMESTIC WATER PIPING | 195822 | 176239.8 | 6527.4 | 6527.4 | 6527.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01820 | 1473 | Coping Stone C1/A-300 | 30958 | 30958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-03005 | 1474 | DOMESTIC WATER PIPING SPECIALTIES | 16279 | 13837.15 | 813.95 | 813.95 | 813.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1475 | SANITARY WASTE PIPING | 37529 | 35652.55 | 625.4833 | 625.4833 | 625.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1476 | SANITARY WASTE PIPING SPECIALTIES | 162217 | 145995.3 | 5407.2333 | 5407.2333 | 5407.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1477 | STORM DRAINAGE PIPING SPECIALTIES | 53592 | 34834.8 | 6252.4 | 6252.4 | 6252.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03030 | 1478 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 231000 | 127050 | 34650 | 34650 | 34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1479 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13277 | 13277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1480 | Plumbing Pipe Insulation | 35464 | 26598 | 0 | 4433 | 4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02045 | 1481 | Heat Trace | 5475 | 0 | 0 | 4692.8571 | 0 | 0 | 260.7143 | 260.7143 | 260.7143 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-M-01005 | 1482 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 1483 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
05470 | 1484 | MATERIAL AND FABRICATION | 5824 | 0 | 5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03112 | 1485 | Exhaust Fans: Install | 12595 | 6297.5 | 0 | 2226.936 | 4070.564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1486 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03032 | 1487 | Steam Unit Heaters: Install | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1488 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03032 | 1489 | Condensate Return Unit: Install | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03112 | 1490 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03112 | 1491 | Heating and Ventilation Unit: Install | 23100 | 0 | 0 | 4084.3368 | 19015.6632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03015 | 1492 | Steam Traps: Furnish | 2860 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03015 | 1493 | Steam Traps: Install | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1494 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01315 | 1495 | INSTALLATION | 6600 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03032 | 1496 | Vacuum Pump Unit: Install | 25300 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03107 | 1497 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 263780 | 255866.6 | 3956.7 | 3956.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03007 | 1498 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 341000 | 330770 | 5115 | 5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1499 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 165000 | 160050 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03025 | 1500 | Mechanical Pipe: Hydrostatic Testing | 5720 | 0 | 2860 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1501 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 27500 | 26950 | 0 | 0 | 528.8462 | 0 | 0 | 0 | 21.1538 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 1502 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 55000 | 53900 | 0 | 0 | 1057.6923 | 0 | 0 | 0 | 42.3077 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03135 | 1503 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 0 | 63.4615 | 0 | 0 | 0 | 3236.5385 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1504 | Controls: Furnish and Install: Devices | 71500 | 57200 | 0 | 0 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1505 | Controls: Furnish and Install: Controls Conduit | 38500 | 36575 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01860 | 1506 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 1507 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 3420.7317 | 7579.2683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1508 | Controls: Connect to Final Termination Points | 7700 | 0 | 0 | 0 | 2394.5122 | 5305.4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03025 | 1509 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 2052.439 | 4547.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1510 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 0 | 0 | 9075 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1511 | Insulation: Furnish and Install: Piping Insulation | 33000 | 0 | 0 | 0 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1512 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 | 0 | 0 | 9075 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1513 | ATS Energization | 13688 | 0 | 5475.2 | 5475.2 | 0 | 0 | 912.5333 | 912.5333 | 912.5333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1514 | ATS Installation | 191625 | 153300 | 38325 | 38325 | 0 | 0 | -12775 | -12775 | -12775 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1515 | ATS Terminations | 13688 | 0 | 5475.2 | 5475.2 | 0 | 0 | 912.5333 | 912.5333 | 912.5333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1516 | ATS Testing | 13688 | 0 | 5475.2 | 5475.2 | 0 | 0 | 912.5333 | 912.5333 | 912.5333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02125 | 1517 | PENETRATION FIRESTOPPING EXTG BLDG - SG-2 | 11505 | 0 | 10226.6667 | 0 | 0 | 639.1667 | 639.1667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02015 | 1518 | Bypass Connections (Misc Panels, Re-routes, etc) | 27750 | 15262.5 | 0 | 0 | 0 | 0 | 4162.5 | 4162.5 | 4162.5 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02040 | 1519 | Cabling - Interior Branch (1/0 & Smaller) | 136875 | 0 | 109500 | 13687.5 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-02115 | 1520 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 | 0 | 0 | 147825 | 147825 | 147825 | 147825 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02020 | 1521 | Conduit - Branch Circuits (1 1/2" & Smaller) | 273750 | 0 | 39107.1429 | 39107.1429 | 39107.1429 | 52142.8571 | 52142.8571 | 52142.8571 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02115 | 1522 | Conduit - Risers (2" & Larger) | 689850 | 137970 | 75366.8722 | 0 | 0 | 0 | 158837.7093 | 158837.7093 | 158837.7093 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02025 | 1523 | Demolition/Temp Light & Power | 55500 | 36075 | 3171.4286 | 3171.4286 | 3171.4286 | 3303.5714 | 3303.5714 | 3303.5714 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02145 | 1524 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 4500 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02030 | 1525 | Foundation Coring | 21000 | 13650 | 567.9545 | 0 | 0 | 0 | 2260.6818 | 2260.6818 | 2260.6818 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02240 | 1526 | Lighting Controls | 49350 | 24675 | 0 | 0 | 0 | 10575 | 4700 | 4700 | 4700 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02025 | 1527 | Lighting Remove & Re-install | 40406 | 0 | 11544.5714 | 0 | 0 | 0 | 9620.4762 | 9620.4762 | 9620.4762 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01320 | 1528 | JOINT SEALANTS EXTG BLDGS - SG-2 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02025 | 1529 | Lighting System Program & Energize | 5550 | 0 | 1585.7143 | 0 | 0 | 0 | 1321.4286 | 1321.4286 | 1321.4286 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02050 | 1530 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 | 0 | 54437.1429 | 0 | 0 | 3024.2857 | 3024.2857 | 3024.2857 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-01020 | 1531 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02245 | 1532 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 9385.7143 | 521.4286 | 521.4286 | 521.4286 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02515 | 1533 | Switchgear & Panelboard Energization | 32850 | 0 | 0 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02260 | 1534 | Switchgear & Panelboard Installation | 492750 | 394200 | 0 | 0 | 0 | 211178.5714 | -37542.8571 | -37542.8571 | -37542.8571 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02260 | 1535 | Switchgear & Panelboard Terminations | 32850 | 0 | 0 | 0 | 0 | 28157.1429 | 1564.2857 | 1564.2857 | 1564.2857 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02510 | 1536 | Switchgear & Panelboard Testing | 32850 | 0 | 0 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02020 | 1537 | Fire Alarm Conduit | 27375 | 0 | 3910.7143 | 3910.7143 | 3910.7143 | 5214.2857 | 5214.2857 | 5214.2857 | 0 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02120 | 1538 | Fire Alarm Wiring | 24638 | 0 | 0 | 0 | 12319 | 0 | 4106.3333 | 4106.3333 | 4106.3333 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01830 | 1539 | Bituthene 4000 waterproofing membrane | 16940 | 8470 | 0 | 0 | 2823.3333 | 2823.3333 | 2823.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-02120 | 1540 | Fire Alarm Devices | 24090 | 12045 | 0 | 0 | 6022.5 | 0 | 2007.5 | 2007.5 | 2007.5 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02120 | 1541 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 1369 | 0 | 456.3333 | 456.3333 | 456.3333 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02535 | 1542 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01405 | 1543 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 19775 | 14831.25 | 0 | 0 | 1647.9167 | 1647.9167 | 1647.9167 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 192 - OG6 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01780 | 1544 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 6285 | 4085.25 | 0 | 0 | 1099.875 | 1099.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 192 - OG6 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01780 | 1545 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-6 | 1181 | 590.5 | 0 | 0 | 295.25 | 295.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 192 - OG6 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG10-01013 | 1546 | Caulk | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG10-01013 | 1547 | Fibrous Slate | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG10-01015 | 1548 | Demo Existing Building/Temp Light & Power | 35150 | 35150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 194 - OG7 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01070 | 1549 | FORMWORK NEW BUILDING - OG-8 | 751900 | 751900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01830 | 1550 | GE Elemax 2600 Silicone air and vapor barrier | 18876 | 0 | 0 | 0 | 6292 | 6292 | 6292 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01175 | 1551 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-8 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01040 | 1552 | POUR CONCRETE NEW BUILDINGS - OG-8 | 402192 | 402192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01135 | 1553 | FINISH SLABS - OG-8 | 34800 | 34800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01075 | 1554 | Footing/Pier | 80925 | 80925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01075 | 1555 | Grade Beams | 15788 | 15788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01170 | 1556 | Floor Slabs | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01130 | 1557 | Equipment Pads | 3855 | 3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01155 | 1558 | Foundation Walls | 8538 | 8538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01170 | 1559 | Concrete Stairs | 1122 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01205 | 1560 | WWM-Slabs | 13163 | 13163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01370 | 1561 | Crystalline Waterproofing at perimeter walls | 32200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01230 | 1562 | 8" CMU (3 hour rated) | 434720 | 434720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01275 | 1563 | 4" CMU | 151404 | 151404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01230 | 1564 | 6" CMU (2 hour rated) | 8910 | 8910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01275 | 1565 | Face Brick 3-5/8" | 373450 | 373450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01275 | 1566 | 3-1/8" Rigid insulation | 32010 | 32010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01250 | 1567 | Cast Stone with SS letters | 8650 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01230 | 1568 | Steel Channel | 23642 | 23642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01230 | 1569 | Cont. Shelf angle | 12690 | 12690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1570 | STEEL (MATERIAL ONLY) | 245175 | 245175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1571 | FABRICATION COSTS | 338575 | 338575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01825 | 1572 | Waterproofing at foundation walls | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01105 | 1573 | METAL DECK (BUY-OUT) | 24518 | 24518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1574 | ANCHORS & EMBEDS | 11676 | 11676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1575 | SURVEYING | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1576 | STEEL & DECK ERECTION | 817248 | 817248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1577 | BOLTS AND HARDWARE | 23351 | 23351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1578 | TRUCKING | 11676 | 11676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01270 | 1579 | Dunnage Grating Galvanized | 72626 | 18156.5 | 54469.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01270 | 1580 | Dunnage Guard Rail | 32588 | 32588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01270 | 1581 | Dunnage Stair and Railing (1) | 13242 | 11917.8 | 0 | 1324.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01290 | 1582 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 172065 | 172065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01860 | 1583 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-2 | 1200 | 0 | 300 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 020 - SG2 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01290 | 1584 | Stair B: Stair, Landing and Hand & Guard Rail | 81523 | 81523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01295 | 1585 | 1st to 2nd Floor Ship Ladder with Cage and Platform Landing | 27106 | 23040.1 | 0 | 4065.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01290 | 1586 | Egress Stair: Stair & Landing with Hand & Guard Rail | 47590 | 11897.5 | 0 | 0 | 35692.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1587 | Layout | 9195 | 9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1588 | Loading | 26857 | 26857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1589 | Exterior Framing, Insulation & Drywall - Materials | 116188 | 116188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1590 | Exterior Framing- Labor | 64809 | 64809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01125 | 1591 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-8 | 24599 | 24599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-02495 | 1592 | PENETRATION FIRESTOPPING NEW BLDG - OG-8 | 11505 | 0 | 0 | 0 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG3-01320 | 1593 | JOINT SEALANTS NEW BLDGS - OG-8 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01330 | 1594 | Doors, Frames & Hardware - Labor | 7784 | 7784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 020 - SG2 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01230 | 1595 | Air Film | 32010 | 32010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1596 | Insulation- Labor | 10399 | 7799.25 | 2599.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01025 | 1597 | Crystalline Waterproofing at plumbing shaft | 10350 | 10350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01072 | 1598 | Waterproofing at foundation | 123540 | 123540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1599 | Layout | 138040 | 0 | 0 | 46013.3333 | 46013.3333 | 46013.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1600 | Framing | 328661 | 328661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1601 | Insulation | 58865 | 58865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1602 | Cladding Install | 412052 | 20602.6 | 0 | 130483.1333 | 130483.1333 | 130483.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01225 | 1603 | Fireproofing | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01265 | 1604 | P&I Cold Applied Roof Membrane | 151996 | 106397.2 | 0 | 0 | 45598.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1605 | Furnish Doors | 2091 | 0 | 522.75 | 522.75 | 522.75 | 261.375 | 261.375 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01265 | 1606 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 160693 | 70346.5 | 0 | 0 | 90346.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01265 | 1607 | P&I Aluminum Coping | 9240 | 0 | 0 | 0 | 9240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01260 | 1608 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-8 | 14378 | 1437.8 | 0 | 0 | 0 | 6470.1 | 6470.1 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01245 | 1609 | Doors, Frames & Hardware - Labor | 35030 | 12000 | 5353.33 | 10000 | 7676.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01317 | 1610 | Louvers Install | 102778 | 0 | 0 | 34259.3333 | 34259.3333 | 34259.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08080 | 1611 | Overhead Door | 16000 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | Loading Dock | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1612 | Furnish Doors | 37629 | 0 | 9407.25 | 9407.25 | 9407.25 | 4703.625 | 4703.625 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01305 | 1613 | Sheathing & Drywall - Labor | 87184 | 0 | 0 | 30000 | 30000 | 27184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01245 | 1614 | Tape/ Spackle finishes | 41405 | 0 | 15000 | 15000 | 11405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01315 | 1615 | ACT ceilings - Materials | 1286 | 0 | 0 | 964.5 | 321.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01325 | 1616 | Layout | 2315 | 0 | 771.6667 | 771.6667 | 771.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01315 | 1617 | ACT ceilings - Labor | 3086 | 0 | 0 | 3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01280 | 1618 | Direct Applied Stucco | 26335 | 0 | 13167.5 | 13167.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01325 | 1619 | Painting OG-8 | 110000 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01310 | 1620 | Cermic Tile and Base - OG-8 | 5124 | 0 | 0 | 2562 | 2562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01260 | 1621 | FIRE EXTINGUISHERS NEW BLDGS - S8 | 1466 | 0 | 366.5 | 366.5 | 366.5 | 183.25 | 183.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01260 | 1622 | TOILET ACCESSORIES NEW BLDGS - OG-8 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1623 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1624 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1625 | Room Sign | 4400 | 0 | 0 | 0 | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1626 | Exit Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01325 | 1627 | Loading | 3601 | 0 | 1200.3333 | 1200.3333 | 1200.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01330 | 1628 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1629 | Stairway Flood Access Door | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1630 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 4140.8 | 323.5 | 323.5 | 0 | 129.4 | 129.4 | 129.4 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1631 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5016 | 132 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1632 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 2090 | 0 | 0 | 0 | 36.6667 | 36.6667 | 36.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1633 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 15180 | 14421 | 379.5 | 379.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1634 | HANGERS AND SUPPORTS | 21784 | 20694.8 | 544.6 | 544.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1635 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 | 913 | 913 | 913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1636 | DOMESTIC WATER PIPING | 207347 | 196979.65 | 6738.7775 | 0 | 0 | 1209.5242 | 1209.5242 | 1209.5242 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1637 | DOMESTIC WATER PIPING SPECIALTIES | 14344 | 13913.68 | 215.16 | 215.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01325 | 1638 | Framing & Drywall - Materials | 3858 | 0 | 1286 | 1286 | 1286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03105 | 1639 | SANITARY WASTE PIPING | 146824 | 142419.28 | 2202.36 | 2202.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1640 | SANITARY WASTE PIPING SPECIALTIES | 29738 | 28251.1 | 495.6333 | 495.6333 | 495.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1641 | STORM DRAINAGE PIPING SPECIALTIES | 73736 | 73736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1642 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 4910.4 | 3819.2 | 3819.2 | 3819.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1643 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 4012.8 | 4012.8 | 4012.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1644 | GAS SERVICE AND PIPING | 398429 | 358586.1 | 14941.0875 | 0 | 0 | 8300.6042 | 8300.6042 | 8300.6042 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1645 | PLUMBING FIXTURES | 18392 | 0 | 6130.6667 | 6130.6667 | 6130.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1646 | EMERGENCY PLUMBING FIXTURES | 5104 | 0 | 1701.3333 | 1701.3333 | 1701.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1647 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 15101 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1648 | Plumbing Pipe Insulation | 8895 | 0 | 0 | 0 | 4447.5 | 4447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01325 | 1649 | Framing- Labor | 5658 | 0 | 1886 | 1886 | 1886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-02150 | 1650 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGP1-M-01005 | 1651 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 1652 | Exhaust Fans: Furnish | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1653 | Exhaust Fans: Install | 40040 | 40040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1654 | Steam Unit Heaters: Furnish | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1655 | Steam Unit Heaters: Install | 85250 | 42625 | 42625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1656 | Electric Heaters: Furnish | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1657 | Condensate Return Unit: Furnish | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1658 | Condensate Return Unit: Install | 58850 | 58850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1659 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01330 | 1660 | Drywall - Labor | 5401 | 0 | 1800.3333 | 1800.3333 | 1800.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03142 | 1661 | Heating and Ventilation Unit: Install | 46750 | 0 | 23375 | 23375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1662 | Steam Traps: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1663 | Steam Traps: Install | 50600 | 50600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1664 | Steam Separator: Furnish | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1665 | Steam Separator: Install | 384450 | 384450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03210 | 1666 | Low Pressure Steam Boilers: Install | 208450 | 208450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1667 | Boiler Feed Unit: Furnish | 82500 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 1668 | Boiler Feed Unit: Install | 54450 | 54450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1669 | Fuel Oil Pump: Furnish | 77000 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1670 | Fuel Oil Pump: Install | 54450 | 54450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01330 | 1671 | Tape/ Spackle finishes | 4629 | 0 | 1543 | 1543 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03142 | 1672 | Fuel Oil Storage Tank: Furnish | 71500 | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03110 | 1673 | Fuel Oil Storage Tank: Install | 65450 | 65450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03110 | 1674 | Rigging | 285450 | 285450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03107 | 1675 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 719400 | 719400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1676 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 949300 | 949300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1677 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 379500 | 371910 | 7590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 1678 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 385000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03135 | 1679 | Mechanical Pipe: Hydrostatic Testing | 12100 | 10285 | 1815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1680 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 99000 | 89100 | 2475 | 2475 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 1681 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 192500 | 173250 | 4812.5 | 4812.5 | 4812.5 | 4812.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01855 | 1682 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03245 | 1683 | HVAC Ductwork: Testing & Balancing | 11000 | 0 | 530 | 0 | 0 | 3490 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1684 | Controls: Furnish and Install: Devices | 275000 | 137500 | 45833.3333 | 45833.3333 | 45833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1685 | Controls: Furnish and Install: Controls Conduit | 121000 | 90750 | 15125 | 15125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1686 | Controls: Furnish and Install: Controls Wiring | 33000 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1687 | Controls: Connect to Final Termination Points | 22000 | 0 | 7333.3333 | 7333.3333 | 7333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03135 | 1688 | Controls: Controls Testing | 19030 | 0 | 6343.3333 | 6343.3333 | 6343.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1689 | Insulation: Furnish and Install: Ductwork Insulation | 60500 | 0 | 30250 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1690 | Insulation: Furnish and Install: Piping Insulation | 126500 | 25300 | 37668.8889 | 63531.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1691 | Insulation: Furnish and Install: Equipment Insulation | 60500 | 0 | 30250 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 1692 | Furnish and Install: Chemical Feed Equipment | 10230 | 5115 | 1705 | 1705 | 1705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01860 | 1693 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-2 | 43236 | 21618 | 5404.5 | 0 | 5404.5 | 5404.5 | 5404.5 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-03242 | 1694 | Chemical Cleaning | 8250 | 0 | 2750 | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1695 | ATS Energization | 16425 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1696 | ATS Installation | 229950 | 206955 | 0 | 0 | 0 | 7665 | 7665 | 7665 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1697 | ATS Terminations | 16425 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1698 | ATS Testing | 16425 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02130 | 1699 | Cabling - Interior Branch (1/0 & Smaller) | 219000 | 109500 | 0 | 0 | 0 | 36500 | 36500 | 36500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02490 | 1700 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 0 | 0 | 470352.2727 | 22397.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02115 | 1701 | Conduit - Branch Circuits (1 1/2" & Smaller) | 164250 | 139612.5 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02205 | 1702 | Conduit - In-Slab | 216810 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02010 | 1703 | Conduit - Risers (2" & Larger) | 443475 | 421301.25 | 0 | 0 | 0 | 7391.25 | 7391.25 | 7391.25 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01860 | 1704 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-2 | 31714 | 0 | 7928.5 | 0 | 7928.5 | 7928.5 | 7928.5 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-02495 | 1705 | Firestopping | 5250 | 3150 | 0 | 1050 | 525 | 175 | 175 | 175 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG8-01170 | 1706 | Generator Delivery | 78750 | 0 | 39375 | 0 | 0 | 13125 | 13125 | 13125 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG8-01010 | 1707 | Generator Release | 472500 | 472500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02420 | 1708 | Generator Terminations | 78750 | 0 | 0 | 0 | 73125 | 1875 | 1875 | 1875 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02730 | 1709 | Generator Test | 78750 | 39375 | 0 | 0 | 0 | 13125 | 13125 | 13125 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02120 | 1710 | Lighting Controls | 14700 | 7350 | 0 | 0 | 0 | 2450 | 2450 | 2450 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02140 | 1711 | Lighting Install | 144900 | 130410 | 7308.5526 | 0 | 0 | 2393.8158 | 2393.8158 | 2393.8158 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02140 | 1712 | Lighting Rough | 151110 | 143554.5 | 3048.7105 | 0 | 0 | 1502.2632 | 1502.2632 | 1502.2632 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02140 | 1713 | Lighting System Program & Energize | 5475 | 0 | 1104.6053 | 0 | 0 | 1456.7982 | 1456.7982 | 1456.7982 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02425 | 1714 | Lightning Protection | 21900 | 10950 | 0 | 0 | 9385.7143 | 521.4286 | 521.4286 | 521.4286 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01860 | 1715 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-2 | 80599 | 0 | 20149.75 | 0 | 20149.75 | 20149.75 | 20149.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-02145 | 1716 | Mechanical Terminations(Dampers, Heaters, Motors) | 164250 | 0 | 0 | 0 | 0 | 54750 | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGP1-E-01010 | 1717 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02160 | 1718 | Switches and Receptacles | 21900 | 5475 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02725 | 1719 | Switchgear & Panelboard Energization | 24638 | 0 | 0 | 0 | 0 | 8212.6667 | 8212.6667 | 8212.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02275 | 1720 | Switchgear & Panelboard Installation | 295650 | 221737.5 | 10558.9286 | 10558.9286 | 10558.9286 | 14078.5714 | 14078.5714 | 14078.5714 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02275 | 1721 | Switchgear & Panelboard Terminations | 24638 | 0 | 12319 | 0 | 0 | 4106.3333 | 4106.3333 | 4106.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02720 | 1722 | Switchgear & Panelboard Testing | 24638 | 0 | 0 | 0 | 0 | 8212.6667 | 8212.6667 | 8212.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02005 | 1723 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02115 | 1724 | Fire Alarm Conduit | 68438 | 58172.3 | 0 | 0 | 0 | 3421.9 | 3421.9 | 3421.9 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02480 | 1725 | Fire Alarm Wiring | 65700 | 32850 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01865 | 1726 | Temporary Egress Stair Storage Sign | 1320 | 0 | 880 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-02480 | 1727 | Fire Alarm Devices | 140160 | 119136 | 0 | 0 | 0 | 7008 | 7008 | 7008 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02480 | 1728 | Fire Alarm Programming & Pretest | 2750 | 0 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02740 | 1729 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01005 | 1730 | EXCAVATION NEW BLDGS - OG-8 | 86240 | 86240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01055 | 1731 | BACKFILL NEW BLDGS - OG-8 | 36868 | 36868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1732 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-8 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1733 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-8 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1734 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-8 | 68282 | 68282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1735 | STONE FOR FOUNDATION - OG-8 | 7221 | 7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01070 | 1736 | FORMWORK NEW BUILDING - OG-9 | 215221 | 215221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01865 | 1737 | Address Signs | 4950 | 0 | 3300 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG9-01175 | 1738 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-9 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01040 | 1739 | POUR CONCRETE NEW BUILDINGS - OG-9 | 102272 | 102272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01135 | 1740 | FINISH SLABS - OG-9 | 10493 | 10493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01075 | 1741 | Footing/Pier | 38922 | 38922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01075 | 1742 | Grade Beams | 11369 | 11369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01170 | 1743 | Floor Slabs | 15984 | 15984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01130 | 1744 | Equipment Pads | 106 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01035 | 1745 | Second Floor Plumbing Shaft Slab | 528 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01035 | 1746 | Plumbing Shafts | 23767 | 23767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01205 | 1747 | WWM-Slabs | 5262 | 5262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1748 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01230 | 1749 | 8" CMU (3 hour rated) | 101420 | 101420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01275 | 1750 | 4" CMU | 13860 | 13860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01230 | 1751 | 6" CMU (2 hour rated) | 51414 | 51414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01275 | 1752 | Face Brick 3-5/8" | 99578 | 99578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01275 | 1753 | 3-1/8" Rigid insulation | 8415 | 8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01250 | 1754 | Cast Stone with SS letters | 142454 | 110000 | 27817.7143 | 4636.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01230 | 1755 | Steel Channel | 24020 | 24020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01230 | 1756 | Cont. Shelf angle | 11330 | 11330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1757 | STEEL (MATERIAL ONLY) | 101945 | 101945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1758 | FABRICATION COSTS | 173771 | 173771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1759 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01105 | 1760 | METAL DECK (BUY-OUT) | 7531 | 7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1761 | ANCHORS & EMBEDS | 6951 | 6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1762 | SURVEYING | 9848 | 9848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1763 | STEEL & DECK ERECTION | 347540 | 347540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1764 | BOLTS AND HARDWARE | 6951 | 6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1765 | TRUCKING | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01270 | 1766 | Dunnage Grating | 23588 | 23588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01290 | 1767 | Railing | 11768 | 11768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01270 | 1768 | Dunnage Stair and Railing | 17380 | 17380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01290 | 1769 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 141827 | 141827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1770 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01295 | 1771 | 1st to 2nd Floor Ship Ladder with Safety Cage and Landing Platform with Rail | 25036 | 25036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01295 | 1772 | Ship Ladder Bulkhead Roof | 7035 | 7035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1773 | Layout | 3065 | 3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1774 | Loading | 10218 | 10218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1775 | Exterior Framing, Insulation & Drywall - Materials | 37221 | 37221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1776 | Exterior Framing- Labor | 56196 | 56196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01125 | 1777 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-9 | 10055 | 10055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-02400 | 1778 | PENETRATION FIRESTOPPING NEW BLDG - OG-9 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG4-01320 | 1779 | JOINT SEALANTS NEW BLDGS - OG-9 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01230 | 1780 | Air Film | 8415 | 8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1781 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01305 | 1782 | Insulation- Labor | 2906 | 2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01025 | 1783 | Crystalline Waterproofing at plumbing shaft | 3738 | 3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01072 | 1784 | Waterproofing at foundation | 43413 | 43413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1785 | Layout | 55016 | 55016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1786 | Framing | 114716 | 114716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1787 | Insulation | 20546 | 20546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1788 | Cladding Install | 143823 | 107867.25 | 0 | 8988.9375 | 8988.9375 | 8988.9375 | 8988.9375 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01225 | 1789 | Fireproofing | 29700 | 29700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01265 | 1790 | P&I Cold Applied Roof Membrane | 54257 | 54257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01265 | 1791 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 69054 | 69054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1792 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01265 | 1793 | P&I Aluminum Coping | 6592 | 0 | 0 | 6592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01260 | 1794 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-9 | 12324 | 12324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01245 | 1795 | Doors, Frames & Hardware - Labor | 17514 | 15514 | 1333.3333 | 666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01317 | 1796 | Louvers Install | 35874 | 0 | 0 | 8968.5 | 8968.5 | 8968.5 | 8968.5 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1797 | Furnish Doors | 22996 | 11000 | 0 | 0 | 0 | 5998 | 5998 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01305 | 1798 | Sheathing & Drywall - Labor | 18774 | 15774 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01245 | 1799 | Tape/ Spackle finishes | 9258 | 8332.2 | 925.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01315 | 1800 | ACT ceilings - Materials | 2058 | 0 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01315 | 1801 | ACT ceilings - Labor | 4372 | 0 | 0 | 4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01280 | 1802 | Direct Applied Stucco | 13167 | 0 | 0 | 13167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1803 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01325 | 1804 | Painting OG-9 | 110000 | 0 | 0 | 0 | 47142.8571 | 62857.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01310 | 1805 | Cermic Tile and Base - OG-9 | 7198 | 0 | 0 | 3599 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01260 | 1806 | TOILET ACCESSORIES NEW BLDGS - OG-9 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1807 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1808 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1809 | Room Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1810 | Exit Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1811 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1812 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 4917.2 | 129.4 | 129.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1813 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5121.6 | 52.8 | 52.8 | 52.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1814 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-03105 | 1815 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1816 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 14740 | 14297.8 | 147.4 | 147.4 | 147.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1817 | HANGERS AND SUPPORTS | 21930 | 21272.1 | 219.3 | 219.3 | 219.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1818 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 | 913 | 913 | 913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1819 | DOMESTIC WATER PIPING | 169254 | 160791.3 | 2820.9 | 2820.9 | 2820.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1820 | DOMESTIC WATER PIPING SPECIALTIES | 3432 | 3329.04 | 34.32 | 34.32 | 34.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1821 | SANITARY WASTE PIPING | 128128 | 124284.16 | 1601.6 | 1601.6 | 640.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1822 | SANITARY WASTE PIPING SPECIALTIES | 19050 | 19050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1823 | STORM DRAINAGE PIPING SPECIALTIES | 41052 | 41052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03140 | 1824 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 10120 | 5060 | 2530 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1825 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-03140 | 1826 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 4012.8 | 4012.8 | 4012.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1827 | GAS SERVICE AND PIPING | 224774 | 213535.3 | 3746.2333 | 3746.2333 | 3746.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03140 | 1828 | PLUMBING FIXTURES | 14167 | 1416.7 | 4250.1 | 4250.1 | 4250.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1829 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1830 | Plumbing Pipe Insulation | 3175 | 0 | 0 | 0 | 1587.5 | 1587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02130 | 1831 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGW-M-01005 | 1832 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 1833 | Exhaust Fans: Furnish | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1834 | Exhaust Fans: Install | 21725 | 21725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1835 | Electric Unit Heaters: Furnish | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1836 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1837 | Steam Unit Heater: Furnish | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1838 | Steam Unit Heater: Install | 48400 | 48400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1839 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1840 | Condensate Return Unit: Install | 28600 | 28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1841 | Steam Traps: Furnish | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1842 | Steam Traps: Install | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03107 | 1843 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 181775 | 181775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03107 | 1844 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 212850 | 212850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1845 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 100650 | 100650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03135 | 1846 | Mechanical Pipe: Hydrostatic Testing | 3025 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1847 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-03107 | 1848 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 18975 | 18975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 1849 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03145 | 1850 | HVAC Ductwork: Testing & Balancing | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1851 | Controls: Furnish and Install: Devices | 99000 | 31680 | 0 | 0 | 49767.5676 | 14247.973 | 3304.4595 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1852 | Controls: Furnish and Install: Controls Conduit | 38500 | 19250 | 0 | 0 | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1853 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 5529.7297 | 1583.1081 | 3887.1622 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1854 | Controls: Connect to Final Termination Points | 7700 | 0 | 0 | 0 | 3870.8108 | 1108.1757 | 2721.0135 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03135 | 1855 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 3317.8378 | 949.8649 | 2332.2973 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1856 | Insulation: Furnish and Install: Ductwork Insulation | 12100 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1857 | Insulation: Furnish and Install: Piping Insulation | 25300 | 0 | 0 | 0 | 12650 | 12650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1858 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1859 | Insulation: Furnish and Install: Equipment Insulation | 12100 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1860 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1861 | ATS Installation | 153300 | 145635 | 0 | 0 | 0 | 7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1862 | ATS Terminations | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1863 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02125 | 1864 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 30000 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02255 | 1865 | Cabling - Risers & Feeders (2/0 & Larger) | 354780 | 0 | 50682.8571 | 50682.8571 | 50682.8571 | 67577.1429 | 67577.1429 | 67577.1429 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02115 | 1866 | Conduit - Branch Circuits (1 1/2" & Smaller) | 83250 | 70762.5 | 0 | 0 | 0 | 4162.5 | 4162.5 | 4162.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02105 | 1867 | Conduit - In-Slab | 126473 | 126473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02010 | 1868 | Conduit - Risers (2" & Larger) | 299700 | 284715 | 0 | 0 | 0 | 4995 | 4995 | 4995 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1869 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-02400 | 1870 | Firestopping | 5250 | 2625 | 0 | 0 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG9-01046 | 1871 | Generator Delivery | 52500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG9-01010 | 1872 | Generator Release | 315000 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02335 | 1873 | Generator Terminations | 52500 | 0 | 0 | 0 | 0 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02530 | 1874 | Generator Test | 52500 | 26250 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02160 | 1875 | Lighting Controls | 8400 | 5040 | 0 | 0 | 0 | 1120 | 1120 | 1120 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02140 | 1876 | Lighting Install | 71820 | 57456 | 0 | 0 | 0 | 4788 | 4788 | 4788 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02140 | 1877 | Lighting Rough | 74898 | 71153.1 | 1872.45 | 1872.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02140 | 1878 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02310 | 1879 | Lightning Protection | 21900 | 10950 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1880 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-02145 | 1881 | Mechanical Terminations(Dampers, Heaters, Motors) | 66600 | 19980 | 0 | 0 | 0 | 15540 | 15540 | 15540 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGW-E-01015 | 1882 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02155 | 1883 | Switches and Receptacles | 10950 | 1642.5 | 0 | 0 | 0 | 3102.5 | 3102.5 | 3102.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02515 | 1884 | Switchgear & Panelboard Energization | 19163 | 0 | 0 | 0 | 0 | 6387.6667 | 6387.6667 | 6387.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02260 | 1885 | Switchgear & Panelboard Installation | 229950 | 218452.5 | 9855 | 1642.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02260 | 1886 | Switchgear & Panelboard Terminations | 19163 | 0 | 16425.4286 | 0 | 0 | 912.5238 | 912.5238 | 912.5238 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02510 | 1887 | Switchgear & Panelboard Testing | 19425 | 0 | 0 | 0 | 0 | 6475 | 6475 | 6475 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02005 | 1888 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02115 | 1889 | Fire Alarm Conduit | 27375 | 24637.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02365 | 1890 | Fire Alarm Wiring | 24638 | 2463.8 | 0 | 0 | 0 | 7391.4 | 7391.4 | 7391.4 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1891 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-02365 | 1892 | Fire Alarm Devices | 36135 | 18067.5 | 0 | 0 | 0 | 6022.5 | 6022.5 | 6022.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02365 | 1893 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02535 | 1894 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01005 | 1895 | EXCAVATION NEW BLDGS - OG-9 | 70840 | 70840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01055 | 1896 | BACKFILL NEW BLDGS - OG-9 | 37706 | 37706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01005 | 1897 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-9 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01005 | 1898 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-9 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01005 | 1899 | STONE FOR FOUNDATION - OG-9 | 7221 | 7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01070 | 1900 | FORMWORK NEW BUILDING - OG-10 | 202716 | 202716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01175 | 1901 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-10 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1902 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01040 | 1903 | POUR CONCRETE NEW BUILDINGS - OG-10 | 123339 | 123339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01135 | 1904 | FINISH SLABS - OG-10 | 13020 | 13020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01075 | 1905 | Footing/Pier | 49491 | 49491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01075 | 1906 | Grade Beams | 10811 | 10811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01170 | 1907 | Floor Slabs | 22032 | 22032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01130 | 1908 | First Floor Plumbing Shaft Slab | 1848 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01130 | 1909 | Second Floor Plumbing Shaft Slab | 792 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01035 | 1910 | Plumbing Shafts | 25269 | 25269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01205 | 1911 | WWM-Slabs | 4869 | 4869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1912 | 8" CMU (3 hour rated) | 112024 | 112024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1913 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01230 | 1914 | 6" CMU (2 hour rated) | 140624 | 140624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01275 | 1915 | 4" CMU | 39688 | 39688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01275 | 1916 | Face Brick 3-5/8" | 93486 | 93486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1917 | 3-1/8" Rigid insulation | 7901 | 7901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01250 | 1918 | Cast Stone with SS letters | 6487 | 3243.5 | 0 | 1081.1667 | 1081.1667 | 1081.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1919 | Steel Channel | 24097 | 24097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1920 | Cont. Shelf angle | 12731 | 12731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1921 | STEEL (MATERIAL ONLY) | 102320 | 102320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1922 | FABRICATION COSTS | 226149 | 226149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1923 | METAL DECK (BUY-OUT) | 11629 | 11629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1924 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01105 | 1925 | ANCHORS & EMBEDS | 6978 | 6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1926 | SURVEYING | 9884 | 9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1927 | STEEL & DECK ERECTION | 348817 | 348817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1928 | BOLTS AND HARDWARE | 6978 | 6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1929 | TRUCKING | 6978 | 6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01270 | 1930 | Dunnage Grating Galvanized | 19967 | 19967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01270 | 1931 | Dunnage Stair with Guard Railing | 21932 | 21932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01290 | 1932 | Stair B: First Floor to Roof Stair and Landing with Hand & Guard Rail | 123974 | 123974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01295 | 1933 | Ship Ladder First Floor to Second Floor with Cage and Upper Platform | 16760 | 16760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01295 | 1934 | Ship Ladder Bulkhead | 7035 | 7035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1935 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01305 | 1936 | Layout | 6292 | 6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1937 | Loading | 17370 | 17370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1938 | Exterior Framing, Insulation & Drywall - Materials | 57656 | 57656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1939 | Exterior Framing- Labor | 84514 | 84514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01125 | 1940 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-10 | 12749 | 12749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-02400 | 1941 | PENETRATION FIRESTOPPING NEW BLDG - OG-10 | 11505 | 0 | 0 | 0 | 8628.75 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG6-01320 | 1942 | JOINT SEALANTS NEW BLDGS - OG-10 | 11505 | 0 | 0 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01230 | 1943 | Air Film | 6584 | 6584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1944 | Insulation- Labor | 4740 | 4740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01027 | 1945 | Crystalline Waterproofing at plumbing shaft | 4888 | 4888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1946 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01072 | 1947 | Waterproofing at foundation walls | 49565 | 49565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1948 | Layout | 89238 | 89238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1949 | Framing | 202902 | 202902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1950 | Insulation | 36341 | 36341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1951 | Cladding Install | 254386 | 241666.7 | 4239.7667 | 4239.7667 | 4239.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01225 | 1952 | Fireproofing | 37400 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01265 | 1953 | P&I Cold Applied Roof Membrane | 48805 | 48805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01265 | 1954 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 59708 | 59708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01265 | 1955 | P&I Aluminum Coping | 6138 | 0 | 0 | 6138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01260 | 1956 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-10 | 8216 | 2875.6 | 0 | 0 | 0 | 2670.2 | 2670.2 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1957 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01245 | 1958 | Doors, Frames & Hardware - Labor | 18906 | 16906 | 1333.3333 | 0 | 666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01317 | 1959 | Louvers Install | 63452 | 0 | 31726 | 31726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1960 | Furnish Doors | 25086 | 2508.6 | 0 | 0 | 0 | 11288.7 | 11288.7 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01305 | 1961 | Sheathing & Drywall - Labor | 36519 | 36519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01245 | 1962 | Tape/ Spackle finishes | 14144 | 14144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01315 | 1963 | ACT ceilings - Materials | 3086 | 0 | 0 | 0 | 3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01315 | 1964 | ACT ceilings - Labor | 14915 | 0 | 0 | 14915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01280 | 1965 | Direct Applied Stucco | 41559 | 0 | 21559 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01325 | 1966 | Painting OG-10 | 110000 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01310 | 1967 | Cermic Tile and Base - OG-10 | 4636 | 0 | 0 | 4636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 1968 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 0 | 0 | 1134.0833 | 1134.0833 | 1134.0833 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01260 | 1969 | TOILET ACCESSORIES NEW BLDGS - OG-10 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1970 | Stair Identification Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1971 | Stairway Floor number and ID Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1972 | Room Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1973 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1974 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 4658.4 | 258.8 | 258.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1975 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5016 | 88 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1976 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 2134 | 27.5 | 27.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1977 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 18920 | 17974 | 236.5 | 236.5 | 236.5 | 236.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1978 | HANGERS AND SUPPORTS | 21930 | 21272.1 | 657.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 1979 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1100 | 770 | 0 | 0 | 110 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-03105 | 1980 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 2465.1 | 0 | 0 | 0 | 0 | 182.6 | 91.3 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1981 | DOMESTIC WATER PIPING | 219912 | 208916.4 | 10995.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1982 | DOMESTIC WATER PIPING SPECIALTIES | 30184 | 28674.8 | 1509.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1983 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 78375 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1984 | SANITARY WASTE PIPING | 131989 | 129349.22 | 879.9267 | 879.9267 | 879.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1985 | SANITARY WASTE PIPING SPECIALTIES | 20064 | 20064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1986 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03140 | 1987 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 5401.44 | 4092 | 4092 | 2782.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03140 | 1988 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 4012.8 | 4012.8 | 4012.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1989 | GAS SERVICE AND PIPING | 244728 | 232491.6 | 6118.2 | 6118.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 1990 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 548 | 0 | 0 | 182.6667 | 182.6667 | 182.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-03140 | 1991 | PLUMBING FIXTURES | 18392 | 1839.2 | 5517.6 | 5517.6 | 5517.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1992 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 31900 | 31900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1993 | Plumbing Pipe Insulation | 2317 | 0 | 0 | 0 | 1158.5 | 1158.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02145 | 1994 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGE-M-01005 | 1995 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 1996 | Exhaust Fans: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03410 | 1997 | Exhaust Fans: Install | 17325 | 17325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1998 | Electric Unit Heaters: Furnish | 3850 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1999 | Steam Unit Heater: Furnish | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2000 | Steam Unit Heater: Install | 37400 | 28050 | 9350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2001 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2860 | 1430 | 0 | 0 | 476.6667 | 476.6667 | 476.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2002 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2003 | Condensate Return Unit: Install | 24200 | 12100 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2004 | Steam Traps: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2005 | Steam Traps: Install | 11550 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03107 | 2006 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 135795 | 135795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03107 | 2007 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 154000 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 2008 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 82500 | 74250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03135 | 2009 | Mechanical Pipe: Hydrostatic Testing | 1705 | 0 | 852.5 | 852.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03107 | 2010 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 2011 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2012 | HANGERS AND SUPPORTS | 11509 | 9782.65 | 0 | 0 | 575.45 | 575.45 | 575.45 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-03145 | 2013 | HVAC Ductwork: Testing & Balancing | 1650 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2014 | Controls: Furnish and Install: Devices | 99000 | 49500 | 0 | 0 | 16500 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2015 | Controls: Furnish and Install: Controls Conduit | 38500 | 23100 | 0 | 0 | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2016 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 3218.2432 | 3693.9189 | 4087.8378 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2017 | Controls: Connect to Final Termination Points | 7700 | 0 | 0 | 0 | 2252.7703 | 2585.7432 | 2861.4865 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03135 | 2018 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 1930.9459 | 2216.3514 | 2452.7027 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 2019 | Insulation: Furnish and Install: Ductwork Insulation | 12100 | 0 | 0 | 0 | 2420 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 2020 | Insulation: Furnish and Install: Piping Insulation | 24200 | 0 | 0 | 0 | 4840 | 19360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 2021 | Insulation: Furnish and Install: Equipment Insulation | 12100 | 0 | 0 | 0 | 2420 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02335 | 2022 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2023 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02335 | 2024 | ATS Installation | 153300 | 145635 | 0 | 0 | 0 | 7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02335 | 2025 | ATS Terminations | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02335 | 2026 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02125 | 2027 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 37500 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02395 | 2028 | Cabling - Risers & Feeders (2/0 & Larger) | 295650 | 0 | 0 | 0 | 73912.5 | 73912.5 | 73912.5 | 73912.5 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02115 | 2029 | Conduit - Branch Circuits (1 1/2" & Smaller) | 82125 | 73912.5 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02105 | 2030 | Conduit - In-Slab | 126473 | 126473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02110 | 2031 | Conduit - Risers (2" & Larger) | 315360 | 299592 | 0 | 0 | 0 | 5256 | 5256 | 5256 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02400 | 2032 | Firestopping | 5250 | 3937.5 | 0 | 0 | 984.375 | 109.375 | 109.375 | 109.375 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG10-01145 | 2033 | Generator Delivery | 52500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2034 | DOMESTIC WATER PIPING | 115682 | 98329.7 | 0 | 0 | 5784.1 | 5784.1 | 5784.1 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
P-OG10-01010 | 2035 | Generator Release | 315000 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02315 | 2036 | Generator Terminations | 52500 | 0 | 0 | 0 | 0 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02535 | 2037 | Generator Test | 52500 | 26250 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02160 | 2038 | Lighting Controls | 21000 | 10500 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02135 | 2039 | Lighting Install | 56700 | 42525 | 0 | 0 | 0 | 4725 | 4725 | 4725 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02240 | 2040 | Lighting Rough | 59940 | 53946 | 2997 | 2997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02160 | 2041 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02325 | 2042 | Lightning Protection | 21900 | 10950 | 4106.25 | 0 | 0 | 2281.25 | 2281.25 | 2281.25 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02140 | 2043 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 19053 | 0 | 0 | 0 | 14819 | 14819 | 14819 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGE-01020 | 2044 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2045 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 13838 | 0 | 0 | 814 | 814 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02155 | 2046 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02525 | 2047 | Switchgear & Panelboard Energization | 19163 | 0 | 0 | 0 | 0 | 6387.6667 | 6387.6667 | 6387.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02405 | 2048 | Switchgear & Panelboard Installation | 229950 | 218451.5 | 0 | 0 | 6570.5714 | 4927.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02405 | 2049 | Switchgear & Panelboard Terminations | 19163 | 0 | 0 | 0 | 10950.2857 | 2737.5714 | 2737.5714 | 2737.5714 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02520 | 2050 | Switchgear & Panelboard Testing | 19163 | 0 | 0 | 0 | 0 | 6387.6667 | 6387.6667 | 6387.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02005 | 2051 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02115 | 2052 | Fire Alarm Conduit | 32850 | 26280 | 0 | 0 | 0 | 2190 | 2190 | 2190 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02385 | 2053 | Fire Alarm Wiring | 32850 | 0 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02385 | 2054 | Fire Alarm Devices | 50370 | 25185 | 0 | 0 | 0 | 8395 | 8395 | 8395 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02385 | 2055 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2056 | SANITARY WASTE PIPING | 135432 | 121888.8 | 0 | 0 | 4514.4 | 4514.4 | 4514.4 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02540 | 2057 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01020 | 2058 | EXCAVATION NEW BLDGS - OG-10 | 80696 | 80696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01055 | 2059 | BACKFILL NEW BLDGS - OG-10 | 39801 | 39801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2060 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-10 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2061 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-10 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2062 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-10 | 34172 | 34172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2063 | STONE FOR FOUNDATION - OG-10 | 7221 | 7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OGE-01035 | 2064 | EROSION CONTROL FABRIC - OGE | 184400 | 184400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01035 | 2065 | INLET PROTECTION - OGE | 38875 | 38875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01035 | 2066 | SILT FENCE - OGE | 19290 | 19290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2067 | SANITARY WASTE PIPING SPECIALTIES | 19388 | 18418.6 | 0 | 0 | 323.1333 | 323.1333 | 323.1333 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01035 | 2068 | STABILIZED CONSTRUCTION ENTRANCE - OGE | 47400 | 47400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01035 | 2069 | MANTAIN EROSION CONTROL - OGE | 42735 | 42735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01770 | 2070 | REMOVE EROSION CONTROL - OGE | 29979 | 4496.85 | 0 | 0 | 0 | 8494.05 | 8494.05 | 8494.05 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2071 | REMOVE FENCE - OGE | 23930 | 23930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2072 | REMOVE FULL DEPTH ASPHALT PVMT - OGE | 141750 | 141750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01060 | 2073 | REMOVE SITE FURNISHING - OGE | 98825 | 98825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2074 | REMOVE CONCRETE CURB & STEPS - OGE | 69775 | 69775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2075 | REMOVE PVMTS - OGE | 202600 | 202600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01610 | 2076 | FORMWORK SITE CONCRETE - OGE | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2077 | CONCRETE FOOTING FOR SITE FURNISHING - OGE | 3304 | 0 | 0 | 0 | 1101.3333 | 1101.3333 | 1101.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2078 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 13200 | 0 | 0 | 6600 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
260543-01025 | 2079 | CONCRETE DUCTBANKS - OGE | 56347 | 56347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01520 | 2080 | CONCRETE SITE RETAINING WALL AND FOOTINGS - OGE | 33106 | 33106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-02010 | 2081 | Manhole Work | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02215 | 2082 | Site Lighting - Cable | 68438 | 0 | 0 | 0 | 0 | 0 | 22812.6667 | 22812.6667 | 22812.6667 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02210 | 2083 | Site Lighting - Conduit | 87600 | 65700 | 3128.5714 | 3128.5714 | 3128.5714 | 4171.4286 | 4171.4286 | 4171.4286 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02220 | 2084 | Site Lighting - Fixtures | 108296 | 0 | 0 | 0 | 0 | 0 | 36098.6667 | 36098.6667 | 36098.6667 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-OGE-01020 | 2085 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02115 | 2086 | Underground Electric Service - Cable | 1040250 | 676162.5 | 0 | 0 | 121362.5 | 121362.5 | 121362.5 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-01155 | 2087 | Underground Electric Service - Conduit | 821250 | 821250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGP1-01020 | 2088 | TREE PROTECTION - OGE | 14532 | 14532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03030 | 2089 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 186998 | 158948.3 | 0 | 0 | 9349.9 | 9349.9 | 9349.9 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGP1-01020 | 2090 | HAND EXCAVATION AS NEEDED - OGE | 36868 | 36868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2091 | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGE | 4025 | 0 | 0 | 0 | 1341.6667 | 1341.6667 | 1341.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01395 | 2092 | BACKFILL - OGE | 222505 | 222505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01709 | 2093 | EXCAVATE FOR ASPHALT PAVEMENTS - OGE | 21187 | 0 | 0 | 0 | 7062.3333 | 7062.3333 | 7062.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2094 | BACKFILL FOR ASPHALT PAVEMENTS - OGE | 9846 | 0 | 0 | 0 | 3282 | 3282 | 3282 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2095 | SITE FURNISHINGS - OGE | 46594 | 0 | 0 | 0 | 15531.3333 | 15531.3333 | 15531.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2096 | DRINKING FOUNTAIN - OGE | 8030 | 0 | 0 | 0 | 2676.6667 | 2676.6667 | 2676.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01090 | 2097 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01090 | 2098 | Furnish and Install Deep Wells | 157500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01090 | 2099 | Furnish and Install Pumps and Piping | 128400 | 128400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2100 | GAS SERVICE AND PIPING | 2112 | 0 | 0 | 0 | 704 | 704 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01090 | 2101 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01090 | 2102 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01090 | 2103 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01740 | 2104 | 4' Chain Link Fence | 23650 | 0 | 0 | 0 | 0 | 0 | 22073.3333 | 1576.6667 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01745 | 2105 | 10' Chain Link Fence | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 24750 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01005 | 2106 | 8' High Temporary Fence | 242250 | 242250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01745 | 2107 | Ametco Fence | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68475 | 68475 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01710 | 2108 | 4" CONCRETE | 49500 | 24750 | 0 | 0 | 0 | 22982.1429 | 1767.8571 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01710 | 2109 | 5"POROUS CONCRETE | 551320 | 220528 | 0 | 0 | 110264 | 110264 | 110264 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01730 | 2110 | 5" COLOR CONCRETE | 38500 | 36575 | 0 | 641.6667 | 641.6667 | 641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2111 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01705 | 2112 | CONCRETE CURB | 38500 | 23100 | 0 | 0 | 14666.6667 | 733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01705 | 2113 | SFC -STELL FACING CURB | 4400 | 0 | 0 | 0 | 4190.4762 | 209.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01710 | 2114 | CONCRETE STEPS | 36960 | 27720 | 0 | 0 | 0 | 8580 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2115 | Asphalt Parking | 291050 | 0 | 0 | 0 | 0 | 270260.7143 | 20789.2857 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2116 | Pavement Marking for Parking | 4641 | 0 | 0 | 0 | 0 | 4309.5 | 331.5 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2117 | Pavement Marking for Basketball Court | 6195 | 0 | 0 | 0 | 0 | 5752.5 | 442.5 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01760 | 2118 | Deciduous Trees | 14175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7087.5 | 7087.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01760 | 2119 | Evergreen Trees | 2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417.5 | 1417.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01760 | 2120 | Deciduous Shrubs | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.5 | 220.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01025 | 2121 | Tree Removal | 34914 | 34914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2122 | Plumbing Pipe Insulation | 35464 | 31917.6 | 0 | 1773.2 | 1773.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01755 | 2123 | Lawn Seeding (not including topsoil) | 9671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4835.5 | 4835.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01025 | 2124 | Soil Erosion Mat | 6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353.5 | 3353.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01755 | 2125 | Topsoil Stockpile/Spread | 67996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33998 | 33998 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01755 | 2126 | Maintenance | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01395 | 2127 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGE | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01380 | 2128 | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGE | 8796 | 8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01380 | 2129 | INSTALL HW, CW PIPE - OGE | 231845 | 231845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
OGP1-01115 | 2130 | TEST HW, CW - OGE | 8794 | 8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01280 | 2131 | INSTALL CONDENSATE AND STEAM PIPE - OGE | 427171 | 427171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
OGE-01285 | 2132 | TEST CONDENSATE, STEAM - OGE | 19421 | 19421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG2-02040 | 2133 | Heat Trace | 5475 | 0 | 0 | 0 | 4380 | 0 | 0 | 0 | 273.75 | 273.75 | 273.75 | 273.75 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01095 | 2134 | DEWATERING COVERAGE FOR UTILITY WORK - OGE | 56118 | 56118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01565 | 2135 | SEWER / DRAINAGE PIPE - OGE | 221493 | 159475.26 | 0 | 0 | 0 | 20672.58 | 20672.58 | 20672.58 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2136 | CATCH BASIN DRAINS AND CONNECTIONS - OGE | 157243 | 113214.96 | 0 | 0 | 0 | 14676.0133 | 14676.0133 | 14676.0133 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2137 | DRAINAGE MANHOLES - OGE | 33988 | 21072.56 | 0 | 0 | 0 | 4305.1467 | 4305.1467 | 4305.1467 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2138 | REMOVE AREA DRAINS - OGE | 58300 | 36146 | 0 | 0 | 0 | 7384.6667 | 7384.6667 | 7384.6667 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2139 | ELECTRICAL MANHOLES - OGE | 12725 | 12725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01205 | 2140 | ELECTRICAL CONDUIT TRENCHES - OGE | 91065 | 91065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 2141 | Equipment SUPPORT FOR SITE - OGE | 167754 | 167754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01035 | 2142 | EROSION CONTROL FABRIC - OGW | 12350 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01035 | 2143 | INLET PROTECTION - OGW | 34210 | 34210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SURV-SGS-M-01005 | 2144 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01035 | 2145 | SILT FENCE - OGW | 26085 | 26085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01035 | 2146 | STABILIZED CONSTRUCTION ENTRANCE - OGW | 48150 | 48150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01035 | 2147 | MANTAIN EROSION CONTROL - OGW | 42735 | 25641 | 0 | 0 | 0 | 0 | 5698 | 5698 | 5698 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01770 | 2148 | REMOVE EROSION CONTROL - OGW | 29979 | 4496.85 | 0 | 0 | 0 | 0 | 8494.05 | 8494.05 | 8494.05 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2149 | REMOVE FENCE - OGW | 6800 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2150 | REMOVE FULL DEPTH ASPHALT PVMT - OGW | 157695 | 157695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01060 | 2151 | REMOVE SITE FURNISHING - OGW | 116200 | 116200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2152 | REMOVE CONCRETE CURB & STEPS - OGW | 98525 | 98525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2153 | REMOVE PVMTS - OGW | 209575 | 209575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01610 | 2154 | FORMWORK SITE CONCRETE - OGW | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OG1-03112 | 2155 | Exhaust Fans: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01750 | 2156 | CONCRETE FOOTING FOR SITE FURNISHING - OGW | 5286 | 0 | 0 | 0 | 0 | 0 | 0 | 2643 | 2643 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 2157 | CONCRETE DUCTBANKS - OGW | 61956 | 61956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01610 | 2158 | CONCRETE SITE RETAINING WALL AND FOOTINGS OGW | 31529 | 31529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2159 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - OGW | 24647 | 0 | 0 | 0 | 0 | 0 | 0 | 12323.5 | 12323.5 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2160 | Jet Spray | 88000 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2161 | Crackle Corn | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2162 | 2-5 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2163 | 5-12 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2164 | Aquavator | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2165 | Install Water Play Equipment and Piping | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 27500 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03112 | 2166 | Exhaust Fans: Install | 4565 | 0 | 0 | 4565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-02010 | 2167 | Manhole Installation | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-02215 | 2168 | Site Lighting - Cable | 82125 | 0 | 0 | 0 | 0 | 0 | 27375 | 27375 | 27375 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-02210 | 2169 | Site Lighting - Conduit | 76650 | 68985 | 1642.5 | 1642.5 | 1642.5 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OG5-02250 | 2170 | Site Lighting - Fixtures | 85629 | 0 | 0 | 0 | 0 | 0 | 28543 | 28543 | 28543 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-OGW-E-01015 | 2171 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-02115 | 2172 | Underground Electric Service - Cable | 1095000 | 821250 | 156428.5714 | 117321.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-01155 | 2173 | Underground Electric Service - Conduit | 903375 | 903375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-01020 | 2174 | TREE PROTECTION - OGW | 24912 | 24912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01020 | 2175 | HAND EXCAVATION AS NEEDED - OGW | 86903 | 81903 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2176 | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGW | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 2012.5 | 2012.5 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OG1-03032 | 2177 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01315 | 2178 | BACKFILL - OGW | 196176 | 176558.4 | 0 | 0 | 0 | 6539.2 | 6539.2 | 6539.2 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01709 | 2179 | EXCAVATE FOR ASPHALT PAVEMENTS - OGW | 21187 | 0 | 0 | 0 | 7062.3333 | 7062.3333 | 7062.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01709 | 2180 | BACKFILL FOR ASPHALT PAVEMENTS - OGW | 4190 | 0 | 0 | 0 | 1396.6667 | 1396.6667 | 1396.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2181 | SITE FURNISHINGS - OGW | 31684 | 3168.4 | 0 | 0 | 0 | 9505.2 | 9505.2 | 9505.2 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2182 | DRINKING FOUNTAIN - OGW | 8030 | 0 | 0 | 0 | 0 | 0 | 0 | 4015 | 4015 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2183 | LANDSCAPE BOULDERS - OGW | 277962 | 222369.6 | 0 | 0 | 0 | 18530.8 | 18530.8 | 18530.8 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01090 | 2184 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01090 | 2185 | Furnish and Install Deep Wells | 123750 | 123750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01090 | 2186 | Furnish and Install Pumps and Piping | 24600 | 24600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01090 | 2187 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG2-03032 | 2188 | Steam Unit Heaters: Install | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01090 | 2189 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01090 | 2190 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01740 | 2191 | 4' Chain Link Fence | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01745 | 2192 | 10' Chain Link Fence | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19250 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01005 | 2193 | 8' High Temporary Fence | 316350 | 316350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01745 | 2194 | Ametco Fence | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68475 | 68475 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2195 | 4" CONCRETE | 143000 | 21450 | 0 | 40516.6667 | 40516.6667 | 40516.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2196 | 7" CONCRETE RAMP | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2197 | 5" POROUS CONCRETE | 459030 | 0 | 153010 | 153010 | 153010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01730 | 2198 | 5" COLOR CONCRETE | 39600 | 17820 | 0 | 7260 | 7260 | 7260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OG2-03032 | 2199 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01705 | 2200 | CONCRETE CURB | 39600 | 15840 | 0 | 7920 | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01705 | 2201 | SFC -STELL FACING CURB | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13750 | 13750 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2202 | CONCRETE STEPS | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01709 | 2203 | Asphalt Parking | 129675 | 0 | 0 | 0 | 0 | 0 | 129675 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2204 | Pavement Marking for Parking | 2730 | 0 | 0 | 0 | 0 | 2535 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2205 | Deciduous Trees | 9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4607 | 4607 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2206 | Deciduous Shrubs | 2793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396.5 | 1396.5 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2207 | Evergreen Shrubs | 3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843 | 1843 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2208 | Perennials | 8180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4090 | 4090 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2209 | Grasses | 16160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080 | 8080 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG2-03032 | 2210 | Condensate Return Unit: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01025 | 2211 | Tree Removal | 39351 | 39351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2212 | Lawn Seeding (not including topsoil) | 9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4796.5 | 4796.5 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01025 | 2213 | Soil Erosion Mat | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504 | 504 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2214 | Topsoil Stockpile/Spread | 67725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33862.5 | 33862.5 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2215 | Maintenance | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01315 | 2216 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGW | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01355 | 2217 | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGW | 20278 | 17236.3 | 0 | 0 | 0 | 0 | 1013.9 | 1013.9 | 1013.9 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01355 | 2218 | INSTALL HW, CW PIPE - OGW | 452669 | 452669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
OGW-01115 | 2219 | TEST HW, CW - OGW | 21983 | 21983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01280 | 2220 | INSTALL CONDENSATE AND STEAM PIPE - OGW | 622421 | 609972.58 | 0 | 0 | 12448.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SG2-03112 | 2221 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01305 | 2222 | TEST CONDENSATE, STEAM - OGW | 32367 | 32367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01095 | 2223 | DEWATERING COVERAGE FOR UTILITY WORK - OGW | 56118 | 56118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01565 | 2224 | SEWER / DRAINAGE PIPE - OGW | 187235 | 140426.25 | 46808.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01560 | 2225 | CATCH BASIN DRAINS AND CONNECTIONS - OGW | 131036 | 98277 | 0 | 0 | 0 | 10919.6667 | 10919.6667 | 10919.6667 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01560 | 2226 | REMOVE AREA DRAINS - OGW | 46640 | 46640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01205 | 2227 | ELECTRICAL CONDUIT TRENCHES - OGW | 77232 | 77232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 2228 | Equipment SUPPORT FOR SITE - OGW | 167754 | 167754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01035 | 2229 | INLET PROTECTION - S8 | 21770 | 21770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01035 | 2230 | SILT FENCE - S8 | 14520 | 14520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01035 | 2231 | STABILIZED CONSTRUCTION ENTRANCE - S8 | 45660 | 45660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03112 | 2232 | Heating and Ventilation Unit: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01035 | 2233 | EROSION CONTROL FABRIC - S8 | 31260 | 31260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01035 | 2234 | MANTAIN EROSION CONTROL - S8 | 42735 | 29914.5 | 0 | 0 | 4273.5 | 4273.5 | 4273.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01770 | 2235 | REMOVE EROSION CONTROL - S8 | 29979 | 2997.9 | 0 | 0 | 8993.7 | 8993.7 | 8993.7 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2236 | REMOVE FENCE - S8 | 10510 | 10510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2237 | REMOVE FULL DEPTH ASPHALT PVMT - S8 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01060 | 2238 | REMOVE SITE FURNISHING -S8 | 120545 | 120545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2239 | REMOVE CONCRETE CURB & STEPS - S8 | 15600 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2240 | REMOVE PVMTS - S8 | 115615 | 115615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01005 | 2241 | Gaskets | 101250 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 20250 | 20250 | 20250 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01010 | 2242 | Wire Insulation | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-03015 | 2243 | Steam Traps: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01015 | 2244 | Assumed Flooring Material (Slab Penetrations) | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 | 2160 | 2160 | 2160 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01015 | 2245 | Vinyl Membrane and Mastic | 72114 | 0 | 0 | 0 | 0 | 0 | 0 | 14422.8 | 14422.8 | 14422.8 | 14422.8 | 14422.8 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01015 | 2246 | Caulk | 184500 | 51750 | 0 | 0 | 0 | 0 | 0 | 26550 | 26550 | 26550 | 26550 | 26550 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01015 | 2247 | Fibrous Slate | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 5100 | 5100 | 5100 | 5100 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01020 | 2248 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 1988.4 | 1988.4 | 1988.4 | 1988.4 | 1988.4 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01020 | 2249 | Underground Utility Materials | 4680 | 0 | 0 | 0 | 0 | 0 | 0 | 936 | 936 | 936 | 936 | 936 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01105 | 2250 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01220 | 2251 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2252 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 0 | 5000 | 5000 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2253 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 | 5000 | 5000 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03015 | 2254 | Steam Traps: Install | 12100 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01115 | 2255 | Remove Areaway slab and drain - cellar | 60000 | 21000 | 0 | 0 | 13000 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01115 | 2256 | Remove Areaway grate - cellar | 20000 | 10000 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01115 | 2257 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2258 | Remove existing portion wall - 1st floor | 60000 | 0 | 15000 | 15000 | 15000 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01210 | 2259 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 | 10000 | 10000 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2260 | Remove window sill - 1st floor | 10000 | 0 | 2500 | 2500 | 2500 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01610 | 2261 | FORMWORK SITE CONCRETE - S8 | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 248 - S8 - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2262 | CONCRETE FOOTING FOR SITE FURNISHING - S8 | 5947 | 0 | 1486.75 | 1486.75 | 1486.75 | 743.375 | 743.375 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 248 - S8 - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 2263 | CONCRETE DUCTBANKS - S8 | 38245 | 38245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 248 - S8 - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8A-01250 | 2264 | Cast Stone with SS letters | 6870 | 0 | 6870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 249 - S8 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG1-03032 | 2265 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01270 | 2266 | Dunnage Grating Galvanized | 20173 | 20173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01270 | 2267 | Dunnage Stair and Guard Rail at 1 Location | 13035 | 0 | 0 | 0 | 13035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01290 | 2268 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 124892 | 112402.8 | 12489.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01295 | 2269 | Ship Ladder with Cage and Platform | 25450 | 0 | 12725 | 12725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01295 | 2270 | Bulkhead Roof Access Ship Ladder at 2 Locations | 15311 | 0 | 7655.5 | 7655.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8E-01860 | 2271 | Temporary Aluminum Over Pass Stair | 114392 | 0 | 0 | 0 | 0 | 0 | 114392 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 250 - S8 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
08080 | 2272 | Overhead Door | 16000 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 251 - S8 - Division 8 | 0% | Loading Dock | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01325 | 2273 | Painting S8-2 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 35000 | 0 | 0 | 0 | 0 | S82 | 252 - S8 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
S8E-01865 | 2274 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2275 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03032 | 2276 | Vacuum Pump Unit: Install | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01865 | 2277 | Room Sign | 2200 | 0 | 0 | 0 | 0 | 0 | 733.3333 | 733.3333 | 733.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2278 | Exit Sign | 550 | 0 | 0 | 0 | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2279 | Stairway Flood Access Door | 550 | 0 | 0 | 0 | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2280 | Temporary Egress Stair Storage Sign | 1320 | 0 | 0 | 0 | 0 | 0 | 440 | 440 | 440 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2281 | Address Signs | 3850 | 0 | 0 | 0 | 0 | 0 | 1283.3333 | 1283.3333 | 1283.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2282 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - S8 | 36970 | 0 | 9242.5 | 9242.5 | 9242.5 | 4621.25 | 4621.25 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2283 | Arch Jet | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2284 | Mist Spray | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2285 | 2-5 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2286 | 5-12 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03107 | 2287 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 91850 | 91850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01735 | 2288 | Aquavator | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2289 | Splash Pad | 22000 | 11000 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2290 | Install Water Play Equipment and Piping | 55000 | 27500 | 0 | 0 | 0 | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01380 | 2291 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2292 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2293 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2294 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2295 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2296 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2297 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-03007 | 2298 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 122100 | 122100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2299 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2300 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2301 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2302 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2303 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2304 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2305 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2306 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2307 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2308 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-03007 | 2309 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 45100 | 45100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2310 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2311 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2312 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2313 | Plumbing Pipe Insulation | 53797 | 0 | 0 | 0 | 26898.5 | 26898.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 256 - S8 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01020 | 2314 | TREE PROTECTION - S8 | 4844 | 4117.4 | 0 | 0 | 0 | 363.3 | 363.3 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01020 | 2315 | HAND EXCAVATION AS NEEDED - S8 | 52668 | 44767.8 | 0 | 0 | 0 | 3950.1 | 3950.1 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2316 | EXCAVATION FOR SITE FURNISHING FOOTINGS - S8 | 4025 | 0 | 1006.25 | 1006.25 | 1006.25 | 503.125 | 503.125 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01675 | 2317 | BACKFILL - S8 | 141886 | 70943 | 0 | 70943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01709 | 2318 | EXCAVATE FOR ASPHALT PAVEMENTS - S8 | 7063 | 0 | 0 | 0 | 0 | 3531.5 | 3531.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01709 | 2319 | BACKFILL FOR ASPHALT PAVEMENTS - S8 | 4190 | 0 | 0 | 0 | 0 | 2095 | 2095 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03025 | 2320 | Mechanical Pipe: Hydrostatic Testing | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01750 | 2321 | SITE FURNISHINGS - S8 | 27956 | 0 | 6989 | 6989 | 6989 | 3494.5 | 3494.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2322 | DRINKING FOUNTAIN - S8 | 8030 | 0 | 2007.5 | 2007.5 | 2007.5 | 1003.75 | 1003.75 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01090 | 2323 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01090 | 2324 | Furnish and Install Deep Wells | 67500 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01090 | 2325 | Furnish and Install Pumps and Piping | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01090 | 2326 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01090 | 2327 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01090 | 2328 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01740 | 2329 | 4' High Steel Bar Fence | 87450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87450 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
S8-01005 | 2330 | 8' High Temporary Fence | 138225 | 138225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OG1-03007 | 2331 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9702 | 0 | 0 | 190.3846 | 0 | 0 | 7.6154 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01710 | 2332 | 4" CONCRETE | 38500 | 0 | 0 | 0 | 0 | 0 | 19250 | 19250 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01710 | 2333 | 5"POROUS CONCRETE | 148940 | 0 | 0 | 0 | 0 | 0 | 74470 | 74470 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01730 | 2334 | 5" COLOR CONCRETE | 121000 | 0 | 0 | 0 | 0 | 0 | 60500 | 60500 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01705 | 2335 | CONCRETE CURB | 38500 | 0 | 0 | 0 | 0 | 0 | 19250 | 19250 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01705 | 2336 | SFC -STELL FACING CURB | 8800 | 0 | 0 | 0 | 0 | 0 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01710 | 2337 | CONCRETE STEPS | 9240 | 0 | 0 | 0 | 0 | 0 | 4620 | 4620 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01709 | 2338 | Asphalt Parking | 43544 | 0 | 0 | 0 | 0 | 0 | 43544 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
S8-01760 | 2339 | Deciduous Trees | 11340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5670 | 5670 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01760 | 2340 | Evergreen Trees | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.5 | 1063.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01760 | 2341 | Deciduous Shrubs | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441 | 441 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OG1-03110 | 2342 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 17248 | 0 | 0 | 338.4615 | 0 | 0 | 13.5385 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01760 | 2343 | Evergreen Shrubs | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709 | 709 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01760 | 2344 | Perennials | 3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 1676 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2345 | Grasses | 6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112.5 | 3112.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01025 | 2346 | Tree Removal | 32700 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16350 | 11350 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2347 | Lawn Seeding (not including topsoil) | 2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310.5 | 1310.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2348 | Topsoil Stockpile/Spread | 18963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9481.5 | 9481.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2349 | Maintenance | 2659.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329.67 | 1329.67 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01675 | 2350 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - S8 | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01135 | 2351 | TERMINATE AND DEMOLISH EXISTING UTILITIES - S8 | 6926 | 5887.1 | 0 | 0 | 346.3 | 346.3 | 346.3 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01135 | 2352 | INSTALL CONDENSATE AND STEAM PIPE - S8 | 55999 | 0 | 0 | 0 | 25845.6943 | 30153.3057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SG2-03135 | 2353 | HVAC Ductwork: Testing & Balancing | 1100 | 0 | 0 | 0 | 21.1538 | 0 | 0 | 1078.8462 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01305 | 2354 | TEST CONDENSATE, STEAM - S8 | 6474 | 0 | 1618.5 | 1618.5 | 1618.5 | 809.25 | 809.25 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01095 | 2355 | DEWATERING COVERAGE FOR UTILITY WORK - S8 | 56118 | 53312.1 | 0 | 0 | 935.3 | 935.3 | 935.3 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01655 | 2356 | SEWER / DRAINAGE PIPE - S8 | 126691 | 44341.85 | 41174.575 | 41174.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01560 | 2357 | CATCH BASIN DRAINS AND CONNECTIONS - S8 | 69886 | 34943 | 33354.6818 | 0 | 0 | 794.1591 | 794.1591 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01560 | 2358 | REMOVE AREA DRAINS - S8 | 58300 | 29150 | 27825 | 0 | 0 | 662.5 | 662.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01255 | 2359 | ELECTRICAL MANHOLES - S8 | 6363 | 6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01255 | 2360 | ELECTRICAL CONDUIT TRENCHES - S8 | 39193 | 39193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 2361 | Equipment SUPPORT FOR SITE - S8 | 167754 | 75489.3 | 0 | 0 | 30754.9 | 30754.9 | 30754.9 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8E-01420 | 2362 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - S8 | 143660 | 50281 | 93379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01450 | 2363 | DRILL & GROUT DOWELS - S8 | 20861 | 0 | 0 | 0 | 18253.375 | 1303.8125 | 1303.8125 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 2364 | Controls: Furnish and Install: Devices | 71500 | 67925 | 0 | 0 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01450 | 2365 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - S8 | 60871 | 0 | 0 | 0 | 53262.125 | 3804.4375 | 3804.4375 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01570 | 2366 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - S8 | 117673 | 88254.75 | 0 | 0 | 9806.0833 | 9806.0833 | 9806.0833 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01540 | 2367 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - S8 | 10239 | 2559.75 | 0 | 7679.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01415 | 2368 | Footing/Pier | 38805 | 0 | 12935 | 12935 | 12935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01435 | 2369 | Retaining Walls | 8668 | 0 | 0 | 8001.2308 | 666.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01565 | 2370 | Entrance Slab | 90825 | 0 | 0 | 0 | 0 | 50000 | 40825 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01810 | 2371 | Concrete Shelf | 5785 | 0 | 0 | 4958.5714 | 0 | 826.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01810 | 2372 | Brick Shelf | 29445 | 0 | 0 | 25238.5714 | 0 | 4206.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01350 | 2373 | Boiler Room Concrete Curb | 6508 | 0 | 0 | 0 | 0 | 6508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2374 | GFRP Sikawrap 100 G | 23232 | 0 | 0 | 0 | 7744 | 7744 | 7744 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 2375 | Controls: Furnish and Install: Controls Conduit | 33000 | 31350 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01015 | 2376 | Overhead protection for Masonry | 94478 | 0 | 23619.5 | 23619.5 | 23619.5 | 11809.75 | 11809.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2377 | Face Brick 3-5/8" | 166796 | 0 | 83398 | 83398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2378 | 2" Face Brick | 346786 | 0 | 173393 | 173393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2379 | 8" CMU | 146034 | 29206.8 | 0 | 20000 | 32275.7333 | 32275.7333 | 32275.7333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2380 | 6" CMU (2 hour rated) | 249945 | 0 | 0 | 50000 | 66648.3333 | 66648.3333 | 66648.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2381 | 4" CMU | 109956 | 0 | 54978 | 54978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2382 | 3-1/8" Rigid insulation | 14969 | 0 | 0 | 0 | 4989.6667 | 4989.6667 | 4989.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2383 | 2" Rigid Insulation | 17391 | 0 | 0 | 0 | 5797 | 5797 | 5797 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2384 | Coping stone C1/A-260 | 32747 | 0 | 0 | 0 | 10915.6667 | 10915.6667 | 10915.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2385 | Steel Channel on top | 9460 | 0 | 0 | 0 | 3153.3333 | 3153.3333 | 3153.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 2386 | Controls: Furnish and Install: Controls Wiring | 9900 | 9405 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01230 | 2387 | Cont. Shelf angle | 9680 | 0 | 0 | 0 | 3226.6667 | 3226.6667 | 3226.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2388 | Steel Channel on top | 9680 | 0 | 0 | 0 | 3226.6667 | 3226.6667 | 3226.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01105 | 2389 | STEEL (MATERIAL ONLY) | 117614 | 117614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2390 | FABRICATION COSTS | 226674 | 226674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2391 | METAL DECK (BUY-OUT) | 10693 | 10693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2392 | ANCHORS & EMBEDS | 8554 | 8554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2393 | SURVEYING | 6416 | 6416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2394 | STEEL & DECK ERECTION | 433032 | 433032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2395 | BOLTS AND HARDWARE | 9623 | 9623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2396 | TRUCKING | 10693 | 10693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2397 | Controls: Connect to Final Termination Points | 6600 | 6270 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02130 | 2398 | PENETRATION FIRESTOPPING EXTG BLDG - S8 | 9611 | 0 | 0 | 0 | 7688.8 | 961.1 | 961.1 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01320 | 2399 | JOINT SEALANTS EXTG BLDGS - S8 | 9611 | 0 | 2402.75 | 2402.75 | 2402.75 | 1201.375 | 1201.375 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01230 | 2400 | Air Film | 17108 | 0 | 0 | 0 | 5702.6667 | 5702.6667 | 5702.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2401 | Bituthene 4000 waterproofing membrane | 27967 | 0 | 0 | 0 | 9322.3333 | 9322.3333 | 9322.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2402 | GE Elemax 2600 Silicone air and vapor barrier | 16896 | 0 | 0 | 0 | 5632 | 5632 | 5632 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01370 | 2403 | Crystalline Waterproofing at perimeter walls | 48933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01825 | 2404 | Waterproofing at foundation walls | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01255 | 2405 | Layout | 55794 | 0 | 0 | 0 | 0 | 27897 | 27897 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01255 | 2406 | Framing | 116720 | 116720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01255 | 2407 | Insulation | 20905 | 20905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG2-03135 | 2408 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01255 | 2409 | Cladding Install | 146335 | 0 | 0 | 0 | 0 | 73167.5 | 73167.5 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01317 | 2410 | Louvers Install | 36500 | 0 | 0 | 0 | 0 | 18250 | 18250 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 264 - S81 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 2411 | Furnish Doors | 6272 | 0 | 1568 | 1568 | 1568 | 784 | 784 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 265 - S81 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01860 | 2412 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - S8 | 306768 | 153379 | 0 | 0 | 0 | 76694.5 | 76694.5 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 266 - S81 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01860 | 2413 | WINDOW FLOODGATES (8.06 AND 8.14) - S8 | 49836 | 0 | 0 | 0 | 0 | 24918 | 24918 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 266 - S81 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-03005 | 2414 | COMMON WORK RESULTS FOR PLUMBING | 15371 | 8454.05 | 0 | 0 | 2305.65 | 2305.65 | 2305.65 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2415 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 6000 | 4500 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2416 | ESCUTCHEONS FOR PLUMBING PIPING | 2500 | 750 | 0 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2417 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 12200 | 1220 | 0 | 0 | 3660 | 3660 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2418 | HANGERS AND SUPPORTS | 21800 | 10900 | 0 | 0 | 3633.3333 | 3633.3333 | 3633.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2419 | Insulation: Furnish and Install: Ductwork Insulation | 7700 | 0 | 0 | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2420 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2975 | 0 | 0 | 0 | 991.6667 | 991.6667 | 991.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2421 | DOMESTIC WATER PIPING | 284883 | 99709.05 | 0 | 0 | 0 | 61724.65 | 61724.65 | 61724.65 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2422 | DOMESTIC WATER PIPING SPECIALTIES | 38000 | 0 | 0 | 0 | 12666.6667 | 12666.6667 | 12666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2423 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 18750 | 0 | 0 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2424 | SANITARY WASTE PIPING | 170771 | 145155.35 | 0 | 0 | 8538.55 | 8538.55 | 8538.55 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2425 | SANITARY WASTE PIPING SPECIALTIES | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2426 | STORM DRAINAGE PIPING SPECIALTIES | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03030 | 2427 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 359996 | 269997 | 0 | 0 | 29999.6667 | 29999.6667 | 29999.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03030 | 2428 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 145920 | 58368 | 0 | 0 | 29184 | 29184 | 29184 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2429 | GAS SERVICE AND PIPING | 262955 | 65738.75 | 0 | 0 | 0 | 65738.75 | 65738.75 | 65738.75 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2430 | Insulation: Furnish and Install: Piping Insulation | 18150 | 0 | 0 | 9075 | 0 | 0 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03030 | 2431 | PLUMBING FIXTURES | 5200 | 0 | 0 | 0 | 1733.3333 | 1733.3333 | 1733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2432 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 63171 | 31585.5 | 0 | 0 | 10528.5 | 10528.5 | 10528.5 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02055 | 2433 | Heat Trace | 5000 | 0 | 0 | 4285.7143 | 0 | 0 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-S8-M-01005 | 2434 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 2435 | Exhaust Fans: Furnish | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2436 | Exhaust Fans: Install | 19050 | 0 | 2625.354 | 1539.2486 | 13596.0968 | 1289.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2437 | Electric Unit Heaters: Furnish | 3500 | 0 | 482.3485 | 282.8016 | 2497.9705 | 236.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2438 | Steam Unit Heater: Install | 20000 | 0 | 2756.2771 | 1616.0091 | 14274.1174 | 1353.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2439 | Steam Unit Heater: Furnish | 54000 | 0 | 7441.9483 | 4363.2245 | 38540.117 | 3654.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2440 | Condensate Return Unit: Furnish | 14000 | 0 | 1929.394 | 1131.2063 | 9991.8822 | 947.5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2441 | Insulation: Furnish and Install: Equipment Insulation | 7700 | 0 | 0 | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2442 | Condensate Return Unit: Install | 35000 | 0 | 4823.485 | 2828.0159 | 24979.7055 | 2368.7937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2443 | Steam Traps: Furnish | 4400 | 0 | 606.381 | 355.522 | 3140.3058 | 297.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2444 | Steam Traps: Install | 34000 | 0 | 4685.6711 | 2747.2154 | 24265.9996 | 2301.1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2445 | Heating and Ventilation Unit: Furnish | 6500 | 0 | 895.7901 | 525.2029 | 4639.0882 | 439.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2446 | Heating and Ventilation Unit: Install | 24000 | 0 | 3307.5326 | 1939.2109 | 17128.9409 | 1624.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2447 | Vacuum Pump Unit: Furnish | 16000 | 0 | 2205.0217 | 1292.8072 | 11419.2939 | 1082.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2448 | Vacuum Pump Unit : Install | 26000 | 0 | 3583.1603 | 2100.8118 | 18556.3527 | 1759.6753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2449 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 250500 | 25050 | 41140.3551 | 62304.7585 | 61230.1705 | 49843.8068 | 10930.9091 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2450 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 511500 | 10230 | 84005.1562 | 127221.0938 | 125026.875 | 101776.875 | 63240 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2451 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 0 | 26277.2727 | 39795.4545 | 39109.0909 | 31836.3636 | 22981.8182 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02010 | 2452 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 5475 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03135 | 2453 | Mechanical Pipe: Hydrostatic Testing | 4950 | 0 | 812.9531 | 1231.1719 | 1209.9375 | 984.9375 | 711 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2454 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 17500 | 0 | 8467.7419 | 8467.7419 | 8467.7419 | -2634.4086 | -2634.4086 | -2634.4086 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 2455 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 38500 | 0 | 18629.0323 | 18629.0323 | 18629.0323 | -5795.6989 | -5795.6989 | -5795.6989 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03145 | 2456 | HVAC Ductwork: Testing & Balancing | 3500 | 0 | 0 | 846.7742 | 846.7742 | 846.7742 | 846.7742 | 0 | 112.9032 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2457 | Controls: Furnish and Install: Devices | 115000 | 42550 | 0 | 0 | 0 | 0 | 22406.3625 | 50043.6375 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2458 | Controls: Furnish and Install: Controls Conduit | 60000 | 18000 | 0 | 0 | 0 | 0 | 11690.2761 | 29135.6543 | 1174.0696 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2459 | Controls: Furnish and Install: Controls Wiring | 17250 | 0 | 0 | 0 | 0 | 0 | 3360.9544 | 8376.5006 | 5512.545 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2460 | Controls: Connect to Final Termination Points | 10000 | 0 | 0 | 0 | 0 | 0 | 1948.3794 | 4855.9424 | 3195.6783 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03135 | 2461 | Controls: Controls Testing | 6000 | 0 | 0 | 0 | 0 | 0 | 1169.0276 | 2913.5654 | 1917.407 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2462 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 9075 | 5445 | 3630 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02035 | 2463 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 8750 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2464 | Insulation: Furnish and Install: Piping Insulation | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 15125 | 9075 | 6050 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2465 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 4950 | 3300 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2466 | ATS Energization | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2467 | ATS Installation | 210000 | 168000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2468 | ATS Terminations | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2469 | ATS Testing | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02010 | 2470 | Bypass Connections (Misc Panels, Re-routes, etc) | 5000 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02040 | 2471 | Cabling - Interior Branch (1/0 & Smaller) | 225000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02115 | 2472 | Cabling - Risers & Feeders (2/0 & Larger) | 886950 | 0 | 0 | 0 | 221737.5 | 221737.5 | 221737.5 | 221737.5 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02030 | 2473 | Conduit - Branch Circuits (1 1/2" & Smaller) | 136875 | 13687.5 | 17598.2143 | 17598.2143 | 17598.2143 | 23464.2857 | 23464.2857 | 23464.2857 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02135 | 2474 | Cabling - Risers & Feeders (2/0 & Larger) | 689850 | 0 | 30000 | 98550 | 98550 | 20000 | 20000 | 20000 | 100687.5 | 100687.5 | 100687.5 | 100687.5 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02155 | 2475 | Conduit - In-Slab | 216810 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02105 | 2476 | Conduit - Risers (2" & Larger) | 985500 | 689850 | 0 | 295650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02010 | 2477 | Demolition | 20000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 5666.6667 | 5666.6667 | 5666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02130 | 2478 | Firestopping | 5000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02025 | 2479 | Foundation Coring | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
P-S8A-01100 | 2480 | Generator Delivery | 50000 | 0 | 0 | 0 | 0 | 28571.4286 | 14285.7143 | 0 | 2380.9524 | 2380.9524 | 2380.9524 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
P-S8A-01030 | 2481 | Generator Release | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02310 | 2482 | Generator Terminations | 50000 | 0 | 0 | 0 | 0 | 0 | 46428.5714 | 0 | 1190.4762 | 1190.4762 | 1190.4762 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02510 | 2483 | Generator Test | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02160 | 2484 | Lighting Controls | 50000 | 25000 | 0 | 0 | 12500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02020 | 2485 | Conduit - Branch Circuits (1 1/2" & Smaller) | 191625 | 19162.5 | 0 | 0 | 7839.2045 | 0 | 0 | 0 | 41155.8239 | 41155.8239 | 41155.8239 | 41155.8239 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02110 | 2486 | Lighting Install | 67800 | 33900 | 0 | 0 | 27120 | 0 | 0 | 0 | 2260 | 2260 | 2260 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02365 | 2487 | Lighting Rough | 67800 | 0 | 0 | 0 | 0 | 54240 | 0 | 0 | 4520 | 4520 | 4520 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 2488 | Lighting System Program & Energize | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02370 | 2489 | Lightning Protection | 20000 | 10000 | 0 | 0 | 0 | 0 | 8333.3333 | 0 | 555.5556 | 555.5556 | 555.5556 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-02010 | 2490 | Manhole Work | 25000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8E-02045 | 2491 | Mechanical Terminations(Dampers, Heaters, Motors) | 100000 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-02215 | 2492 | Site Lighting - Cable | 24638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.6667 | 8212.6667 | 8212.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8-02210 | 2493 | Site Lighting - Conduit | 32850 | 3285 | 0 | 0 | 0 | 0 | 0 | 0 | 9855 | 9855 | 9855 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8-02220 | 2494 | Site Lighting - Fixtures | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 11500 | 11500 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
SURV-S8-E-01015 | 2495 | Site Survey | 64000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
SG2-02050 | 2496 | Conduit - Risers (2" & Larger) | 788400 | 78840 | 0 | 0 | 0 | 0 | 0 | 0 | 177390 | 177390 | 177390 | 177390 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-S8-E-01015 | 2497 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02125 | 2498 | Switches and Receptacles | 10000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02520 | 2499 | Switchgear & Panelboard Energization | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02520 | 2500 | Switchgear & Panelboard Installation | 360000 | 270000 | 0 | 0 | 0 | 0 | 0 | 25714.2857 | 64285.7143 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02520 | 2501 | Switchgear & Panelboard Terminations | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02525 | 2502 | Switchgear & Panelboard Testing | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02020 | 2503 | Temp Light & Power | 50000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 6989.5288 | 6989.5288 | 6020.9424 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02415 | 2504 | Underground Electric Service - Cable | 410625 | 0 | 58660.7143 | 58660.7143 | 58660.7143 | 78214.2857 | 78214.2857 | 78214.2857 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8-01155 | 2505 | Underground Electric Service - Conduit | 328500 | 328500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8E-02030 | 2506 | Fire Alarm Conduit | 32850 | 0 | 4692.8571 | 4692.8571 | 4692.8571 | 6257.1429 | 6257.1429 | 6257.1429 | 0 | 0 | 0 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02015 | 2507 | Demolition/Temp Light & Power | 54750 | 30112.5 | 0 | 0 | 0 | 0 | 0 | 0 | 6159.375 | 6159.375 | 6159.375 | 6159.375 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02380 | 2508 | Fire Alarm Wiring | 31500 | 0 | 0 | 0 | 0 | 15750 | 0 | 0 | 5250 | 5250 | 5250 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02380 | 2509 | Fire Alarm Devices | 57000 | 28500 | 0 | 0 | 0 | 14250 | 0 | 0 | 4750 | 4750 | 4750 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02380 | 2510 | Fire Alarm Programming & Pretest | 2500 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02505 | 2511 | Fire Alarm FDNY Approval | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01705 | 2512 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 74861 | 7486.1 | 18715.25 | 18715.25 | 9981.4667 | 9981.4667 | 9981.4667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 271 - S81 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01580 | 2513 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 28908 | 4336.2 | 0 | 0 | 8190.6 | 8190.6 | 8190.6 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 271 - S81 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01580 | 2514 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - S8 | 417 | 0 | 0 | 0 | 0 | 208.5 | 208.5 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 271 - S81 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01070 | 2515 | FORMWORK NEW BUILDING - S8 | 317228 | 317228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01175 | 2516 | SET ANCHOR BOLTS FOR STEEL COLUMNS - S8 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01040 | 2517 | POUR CONCRETE NEW BUILDINGS - S8 | 147088 | 147088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02125 | 2518 | Firestopping | 5250 | 0 | 4666.6667 | 0 | 0 | 0 | 0 | 0 | 145.8333 | 145.8333 | 145.8333 | 145.8333 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01135 | 2519 | FINISH SLABS - S8 | 15940 | 15940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01075 | 2520 | Footing/Pier | 43103 | 43103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01075 | 2521 | Grade Beams | 2298 | 2298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01130 | 2522 | Floor Slabs | 23287 | 23287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01130 | 2523 | Equipment Pads | 109 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01130 | 2524 | First Floor Plumbing Shaft Slab | 1034 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01035 | 2525 | Plumbing Shafts | 28192 | 28192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01170 | 2526 | Concrete Bench | 890 | 0 | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01205 | 2527 | WWM-Slabs | 4933 | 4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01305 | 2528 | Layout | 5109 | 0 | 0 | 0 | 0 | 4014.2143 | 729.8571 | 364.9286 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02050 | 2529 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01305 | 2530 | Loading | 13137 | 0 | 0 | 0 | 0 | 2000 | 7424.6667 | 3712.3333 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01305 | 2531 | Exterior Framing, Insulation & Drywall - Materials | 46709 | 0 | 0 | 0 | 0 | 15000 | 21139.3333 | 10569.6667 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01305 | 2532 | Exterior Framing- Labor | 54445 | 0 | 0 | 0 | 0 | 20000 | 22963.3333 | 11481.6667 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01125 | 2533 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - S8 | 12569 | 12569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-02395 | 2534 | PENETRATION FIRESTOPPING NEW BLDG - S8 | 11505 | 0 | 9587.5 | 0 | 0 | 0 | 639.1667 | 639.1667 | 639.1667 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
S8E-01320 | 2535 | JOINT SEALANTS NEW BLDGS - S8 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
S8A-01305 | 2536 | Insulation- Labor | 4740 | 0 | 0 | 0 | 0 | 3724.2857 | 677.1429 | 338.5714 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01025 | 2537 | Crystalline Waterproofing at plumbing shaft | 3514 | 3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01072 | 2538 | Waterproofing at foundation | 66700 | 66700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01225 | 2539 | Fireproofing | 46200 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02065 | 2540 | Lighting Controls | 24150 | 12075 | 0 | 0 | 9660 | 0 | 0 | 0 | 603.75 | 603.75 | 603.75 | 603.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01265 | 2541 | P&I Cold Applied Roof Membrane | 68145 | 0 | 0 | 68145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01265 | 2542 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 70092 | 0 | 0 | 70092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01265 | 2543 | P&I Aluminum Coping | 3102 | 0 | 0 | 3102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01260 | 2544 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S8 | 14378 | 1437.8 | 0 | 0 | 0 | 6470.1 | 6470.1 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 275 - S82 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01245 | 2545 | Doors, Frames & Hardware - Labor | 26968 | 0 | 26968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 275 - S82 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 2546 | Furnish Doors | 22996 | 0 | 5749 | 5749 | 5749 | 2874.5 | 2874.5 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
S8A-01305 | 2547 | Sheathing & Drywall - Labor | 33946 | 0 | 0 | 0 | 0 | 10000 | 15964 | 7982 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01245 | 2548 | Tape/ Spackle finishes | 13372 | 0 | 13372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01280 | 2549 | Direct Applied Stucco | 31684 | 0 | 15842 | 15842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2550 | EXCAVATION NEW BLDGS - S8-2 | 70840 | 70840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02015 | 2551 | Lighting Remove & Re-install | 22667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5666.75 | 5666.75 | 5666.75 | 5666.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01055 | 2552 | BACKFILL NEW BLDGS - S8 | 35192 | 35192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2553 | DEWATERING COVERAGE FOR NEW BUILDINGS - S8 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2554 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - S8 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2555 | DRIVE PILES AND INSTALL LAGGING FOR SOE - S8 | 68282 | 68282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
0 | 2556 | CON EDISON ELECTRICAL UTILITY SERVICE FEE | 51926.66 | 2449.46 | 24738.6 | 24738.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALLOWANCE | 278 - Allowance - Division 1 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
0 | 2557 | NATIONAL GRID GAS UTILITY -CIAC | 141408 | 0 | 70704 | 70704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALLOWANCE | 278 - Allowance - Division 1 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG2-02015 | 2558 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02025 | 2559 | Mechanical Terminations(Dampers, Heaters, Motors) | 43800 | 0 | 0 | 0 | 35040 | 0 | 0 | 0 | 2190 | 2190 | 2190 | 2190 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-E-01030 | 2560 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02110 | 2561 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 2737.5 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02675 | 2562 | Switchgear & Panelboard Energization | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02375 | 2563 | Switchgear & Panelboard Installation | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 16425 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02375 | 2564 | Switchgear & Panelboard Terminations | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02680 | 2565 | Switchgear & Panelboard Testing | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01405 | 2566 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 12713 | 12713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 027 - SG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01480 | 2567 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 5028 | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 027 - SG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01480 | 2568 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-2 | 486 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 027 - SG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01005 | 2569 | Gaskets | 36000 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01010 | 2570 | Wire Insulation | 37500 | 0 | 0 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2571 | Assumed Flooring Material (Slab Penetrations) | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2572 | Vinyl Membrane and Mastic | 53652 | 0 | 0 | 26826 | 26826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2573 | Caulk | 103500 | 103500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2574 | Fibrous Slate | 14025 | 0 | 0 | 7012.5 | 7012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01020 | 2575 | Waterproofing | 9942 | 0 | 0 | 4971 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01020 | 2576 | Underground Utility Materials | 46800 | 0 | 0 | 23400 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2577 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01220 | 2578 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2579 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2580 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01115 | 2581 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01115 | 2582 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01115 | 2583 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2584 | Saw cut openings through slab for cellar ventilation / exhaust ducts | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01105 | 2585 | Remove window sill - 1st floor | 10000 | 5000 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01205 | 2586 | Remove Existing Ramp - 1st floor | 80000 | 40000 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 8000 | 8000 | 8000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01205 | 2587 | Existing Ramp railing to be be removed - 1st floor | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2588 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01210 | 2589 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2590 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2591 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2592 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2593 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2594 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 5000 | 5000 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01210 | 2595 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01105 | 2596 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2597 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2598 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2599 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01410 | 2600 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-3 | 52908 | 16072.4 | 0 | 0 | 0 | 18417.8 | 18417.8 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01450 | 2601 | DRILL & GROUT DOWELS - SG-3 | 7874 | 7874 | -2.8422e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01450 | 2602 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-3 | 42713 | 42713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01470 | 2603 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-3 | 30285 | 7571.25 | 0 | 18928.125 | 0 | 1892.8125 | 1892.8125 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01440 | 2604 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-3 | 30854 | 27748.6 | 0 | 0 | 1035.1333 | 1035.1333 | 1035.1333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01440 | 2605 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-3 | 4329 | 0 | 1082.25 | 1082.25 | 1082.25 | 541.125 | 541.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01320 | 2606 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-3 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01415 | 2607 | Footing/Pier | 17233 | 0 | 8616.5 | 8616.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01435 | 2608 | Retaining Walls | 2856 | 2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01535 | 2609 | Entrance Slab | 13291 | 0 | 11629.625 | 1661.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01810 | 2610 | Concrete Shelf | 6304 | 6304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01350 | 2611 | New Concrete Curb Next to Existing Wall | 242 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01350 | 2612 | Boiler Room Concrete Curb | 4178 | 0 | 0 | 4178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2613 | GFRP Sikawrap 100 G | 60346 | 0 | 10222.5464 | 9233.2678 | 13630.0619 | 13630.0619 | 13630.0619 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01440 | 2614 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-3 | 378 | 0 | 94.5 | 94.5 | 94.5 | 47.25 | 47.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01015 | 2615 | Overhead protection for Masonry | 24710 | 2471 | 0 | 0 | 0 | 11119.5 | 11119.5 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01820 | 2616 | 6" vertically reinforced CMU | 132685 | 112782.25 | 0 | 0 | 6634.25 | 6634.25 | 6634.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2617 | 2" Face brick | 410182 | 41018.2 | 69484.3825 | 62760.0874 | 78973.11 | 78973.11 | 78973.11 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2618 | 2" rigid Insulation | 19418 | 0 | 3289.388 | 2971.0601 | 4385.8506 | 4385.8506 | 4385.8506 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01820 | 2619 | Coping Stone C1/A-300 | 22968 | 2296.8 | 0 | 0 | 6890.4 | 6890.4 | 6890.4 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05530 | 2620 | MATERIAL AND FABRICATION | 21224 | 21224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01315 | 2621 | INSTALLATION | 37400 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01860 | 2622 | Temporary Aluminum Over Pass Stairs | 57196 | 0 | 0 | 0 | 0 | 0 | 0 | 14299 | 42897 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-02145 | 2623 | PENETRATION FIRESTOPPING EXTG BLDG - SG-3 | 11505 | 0 | 0 | 0 | 0 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01320 | 2624 | JOINT SEALANTS EXTG BLDGS - SG-3 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01830 | 2625 | Bituthene 4000 waterproofing membrane | 17281 | 0 | 2927.3825 | 2644.0874 | 3903.1767 | 3903.1767 | 3903.1767 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2626 | GE Elemax 2600 Silicone air and vapor barrier | 25531 | 0 | 4324.9235 | 3906.3825 | 5766.5647 | 5766.5647 | 5766.5647 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01370 | 2627 | Crystalline Waterproofing at perimeter walls | 50313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01825 | 2628 | Waterproofing at foundation walls | 17020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01330 | 2629 | Doors, Frames & Hardware - Labor | 5838 | 5838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 033 - SG3 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 2630 | Furnish Doors | 8362 | 8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2631 | Layout | 5658 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2632 | Loading | 8744 | 8744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2633 | Framing & Drywall - Materials | 13115 | 13115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2634 | Framing- Labor | 20060 | 20060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01330 | 2635 | Drywall - Labor | 23660 | 23660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01330 | 2636 | Tape/ Spackle finishes | 18517 | 18517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01855 | 2637 | Stucco | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01340 | 2638 | Resilient Flooring and base - SG-3 | 15640 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01860 | 2639 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-3 | 45295 | 22647.5 | 0 | 0 | 0 | 0 | 7549.1667 | 7549.1667 | 7549.1667 | 0 | 0 | 0 | 0 | SG3 | 035 - SG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01820 | 2640 | Wiper wall panel | 4851 | 0 | 0 | 0 | 1617 | 1617 | 1617 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 035 - SG3 - Division 10 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01865 | 2641 | Address Signs | 4950 | 0 | 0 | 0 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 035 - SG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01380 | 2642 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2643 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2644 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2645 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2646 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2647 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2648 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2649 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2650 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2651 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2652 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2653 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2654 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2655 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2656 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2657 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2658 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2659 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2660 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2661 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2662 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 0 | 0 | 1134.0833 | 1134.0833 | 1134.0833 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2663 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1056 | 105.6 | 0 | 0 | 316.8 | 316.8 | 316.8 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2664 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 0 | 0 | 0 | 365.3333 | 365.3333 | 365.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2665 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 5940 | 4158 | 0 | 0 | 594 | 594 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2666 | HANGERS AND SUPPORTS | 11512 | 9209.6 | 0 | 0 | 767.4667 | 767.4667 | 767.4667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2667 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2668 | DOMESTIC WATER PIPING | 137444 | 109955.2 | 0 | 0 | 9162.9333 | 9162.9333 | 9162.9333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2669 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 13838 | 0 | 0 | 814 | 814 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2670 | SANITARY WASTE PIPING | 135254 | 108203.2 | 0 | 0 | 9016.9333 | 9016.9333 | 9016.9333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2671 | SANITARY WASTE PIPING SPECIALTIES | 47078 | 42370.2 | 0 | 0 | 1569.2667 | 1569.2667 | 1569.2667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2672 | STORM DRAINAGE PIPING SPECIALTIES | 47078 | 18831.2 | 0 | 0 | 9415.6 | 9415.6 | 9415.6 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03030 | 2673 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 417998 | 376198.2 | 0 | 0 | 13933.2667 | 13933.2667 | 13933.2667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2674 | GAS SERVICE AND PIPING | 2261 | 0 | 0 | 0 | 753.6667 | 753.6667 | 753.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2675 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13266 | 13266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2676 | Plumbing Pipe Insulation | 35750 | 0 | 0 | 17875 | 17875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02040 | 2677 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-M-01005 | 2678 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 2679 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2680 | Exhaust Fans: Install | 14795 | 7397.5 | 2465.8333 | 2465.8333 | 2465.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2681 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2682 | Steam Unit Heaters: Install | 17600 | 0 | 5866.6667 | 5866.6667 | 5866.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2683 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2684 | Condensate Return Unit: Install | 24200 | 0 | 8066.6667 | 8066.6667 | 8066.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2685 | Heating and Ventilation Unit: Furnish | 7150 | 0 | 2383.3333 | 2383.3333 | 2383.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2686 | Heating and Ventilation Unit: Install | 25300 | 0 | 8433.3333 | 8433.3333 | 8433.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2687 | Steam Traps: Furnish | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2688 | Steam Traps: Install | 25850 | 0 | 8616.6667 | 8616.6667 | 8616.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2689 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2690 | Vacuum Pump Unit: Install | 27500 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2691 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 290565 | 232452 | 14528.25 | 14528.25 | 14528.25 | 14528.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2692 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 445500 | 378675 | 16706.25 | 16706.25 | 16706.25 | 16706.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2693 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 176000 | 0 | 58666.6667 | 58666.6667 | 58666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03015 | 2694 | Mechanical Pipe: Hydrostatic Testing | 6435 | 0 | 2145 | 2145 | 2145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2695 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 33000 | 30360 | 0 | 0 | 2572.8814 | 0 | 0 | 0 | 67.1186 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 2696 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 93500 | 86020 | 0 | 0 | 7289.8305 | 0 | 0 | 0 | 190.1695 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03235 | 2697 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 0 | 257.2881 | 0 | 0 | 0 | 3042.7119 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2698 | Controls: Furnish and Install: Devices | 82500 | 78375 | 0 | 0 | 3946.9424 | 0 | 0 | 178.0576 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2699 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 0 | 2105.036 | 0 | 0 | 94.964 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2700 | Controls: Furnish and Install: Controls Wiring | 11000 | 10450 | 0 | 0 | 526.259 | 0 | 0 | 23.741 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2701 | Controls: Connect to Final Termination Points | 8800 | 8360 | 0 | 0 | 421.0072 | 0 | 0 | 18.9928 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03310 | 2702 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 315.7554 | 0 | 0 | 6284.2446 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2703 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 0 | 0 | 0 | 0 | 4125 | 0 | 10725 | 1650 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2704 | Insulation: Furnish and Install: Piping Insulation | 33000 | 0 | 0 | 0 | 0 | 8250 | 0 | 21450 | 3300 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2705 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 0 | 0 | 0 | 0 | 4125 | 0 | 10725 | 1650 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2706 | ATS Energization | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 11406.6667 | 570.3333 | 570.3333 | 570.3333 | 570.3333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2707 | ATS Installation | 194250 | 97125 | 0 | 0 | 0 | 0 | 0 | 80937.5 | 4046.875 | 4046.875 | 4046.875 | 4046.875 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2708 | ATS Terminations | 13875 | 0 | 0 | 0 | 0 | 0 | 0 | 11562.5 | 578.125 | 578.125 | 578.125 | 578.125 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2709 | ATS Testing | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 11406.6667 | 570.3333 | 570.3333 | 570.3333 | 570.3333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02010 | 2710 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3421.875 | 3421.875 | 3421.875 | 3421.875 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02035 | 2711 | Cabling - Interior Branch (1/0 & Smaller) | 164250 | 0 | 23464.2857 | 23464.2857 | 23464.2857 | 31285.7143 | 31285.7143 | 31285.7143 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-02105 | 2712 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98550 | 98550 | 98550 | 98550 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02015 | 2713 | Conduit - Branch Circuits (1 1/2" & Smaller) | 222000 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 27750 | 27750 | 27750 | 27750 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02115 | 2714 | Conduit - Risers (2" & Larger) | 399600 | 359640 | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | 9990 | 9990 | 9990 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02020 | 2715 | Demolition/Temp Light & Power | 54750 | 46537.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2053.125 | 2053.125 | 2053.125 | 2053.125 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02145 | 2716 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02025 | 2717 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02125 | 2718 | Lighting Controls | 31500 | 15750 | 13500 | 0 | 0 | 0 | 0 | 0 | 562.5 | 562.5 | 562.5 | 562.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02020 | 2719 | Lighting Remove & Re-install | 54203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13550.75 | 13550.75 | 13550.75 | 13550.75 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02020 | 2720 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02045 | 2721 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 19053 | 38106 | 0 | 0 | 0 | 0 | 0 | 1587.75 | 1587.75 | 1587.75 | 1587.75 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-E-01030 | 2722 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02515 | 2723 | Switchgear & Panelboard Energization | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02265 | 2724 | Switchgear & Panelboard Installation | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98550 | 98550 | 98550 | 98550 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02265 | 2725 | Switchgear & Panelboard Terminations | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02510 | 2726 | Switchgear & Panelboard Testing | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02015 | 2727 | Fire Alarm Conduit | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6843.75 | 6843.75 | 6843.75 | 6843.75 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02120 | 2728 | Fire Alarm Wiring | 24638 | 0 | 18478.5 | 0 | 0 | 0 | 0 | 0 | 1539.875 | 1539.875 | 1539.875 | 1539.875 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02120 | 2729 | Fire Alarm Devices | 19710 | 9855 | 7391.25 | 0 | 0 | 0 | 0 | 0 | 615.9375 | 615.9375 | 615.9375 | 615.9375 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02120 | 2730 | Fire Alarm Programming & Pretest | 2738 | 0 | 2053.5 | 0 | 0 | 0 | 0 | 0 | 171.125 | 171.125 | 171.125 | 171.125 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02535 | 2731 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684.5 | 684.5 | 684.5 | 684.5 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01405 | 2732 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 15538 | 15538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 041 - SG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01480 | 2733 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 6285 | 942.75 | 0 | 5387.1429 | 0 | 0 | -14.9643 | -14.9643 | -14.9643 | 0 | 0 | 0 | 0 | SG3 | 041 - SG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01480 | 2734 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-3 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 041 - SG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01005 | 2735 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 9000 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01010 | 2736 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2737 | Assumed Flooring Material (Slab Penetrations) | 46800 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01020 | 2738 | Pipe Insulation | 15750 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2739 | Vinyl Membrane and Mastic | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2740 | Caulk | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2741 | Fibrous Slate | 14535 | 14535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01020 | 2742 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01020 | 2743 | Underground Utility Materials | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2744 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01220 | 2745 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2746 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2747 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01115 | 2748 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01115 | 2749 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01115 | 2750 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2751 | Saw cut openings through slab for cellar ventilation / exhaust ducts | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01105 | 2752 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01205 | 2753 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01205 | 2754 | Existing Ramp railing to be be removed - 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2755 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01210 | 2756 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2757 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2758 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2759 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2760 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2761 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01210 | 2762 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01105 | 2763 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2764 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2765 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2766 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01410 | 2767 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-4 | 106025 | 106025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01450 | 2768 | DRILL & GROUT DOWELS - SG-4 | 25962 | 25962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01450 | 2769 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-4 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01470 | 2770 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-4 | 49048 | 49048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01440 | 2771 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-4 | 23998 | 23998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01440 | 2772 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-4 | 4137 | 0 | 2068.5 | 2068.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01320 | 2773 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-4 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01415 | 2774 | Footing/Pier | 20904 | 20904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01435 | 2775 | Retaining Walls | 4692 | 4692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01665 | 2776 | Entrance Slab | 20706 | 5176.5 | 15529.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01810 | 2777 | Concrete Shelf | 4320 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01350 | 2778 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01350 | 2779 | Boiler Room Concrete Curb | 3354 | 3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2780 | GFRP Sikawrap 100 G | 87230 | 87230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01440 | 2781 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-4 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01015 | 2782 | Overhead protection for Masonry | 35611 | 33830.45 | 890.275 | 890.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01820 | 2783 | 6" vertically reinforced CMU | 126280 | 126280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2784 | 2" Face brick | 538422 | 484579.8 | 53842.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2785 | 2" rigid Insulation | 18480 | 18480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01820 | 2786 | Coping Stone C1/A-300 | 18586 | 18586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05350 | 2787 | MATERIAL AND FABRICATION | 21224 | 21224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01315 | 2788 | INSTALLATION | 37400 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01860 | 2789 | Temporary Aluminum Over Pass Stairs | 57196 | 0 | 28598 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-02345 | 2790 | PENETRATION FIRESTOPPING EXTG BLDG - SG-4 | 11505 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01320 | 2791 | JOINT SEALANTS EXTG BLDGS - SG-4 | 11505 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01830 | 2792 | Bituthene 4000 waterproofing membrane | 21142 | 21142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2793 | GE Elemax 2600 Silicone air and vapor barrier | 36905 | 36905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01370 | 2794 | Crystalline Waterproofing at perimeter walls | 42694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01825 | 2795 | Waterproofing at foundation walls | 17020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01860 | 2796 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-4 | 1050 | 0 | 525 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 047 - SG4 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01330 | 2797 | Doors, Frames & Hardware - Labor | 13066 | 13066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 047 - SG4 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 2798 | Furnish Doors | 8362 | 2759.46 | 2801.27 | 2801.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2799 | Layout | 7715 | 7715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2800 | Loading | 9001 | 9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2801 | Framing & Drywall - Materials | 17638 | 17638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2802 | Framing- Labor | 7458 | 7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01330 | 2803 | Drywall - Labor | 15944 | 15944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01330 | 2804 | Tape/ Spackle finishes | 23660 | 23660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01855 | 2805 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01340 | 2806 | Resilient Flooring and base - SG-4 | 27600 | 0 | 13800 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01860 | 2807 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-4 | 51471 | 25735.5 | 12867.75 | 12867.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01860 | 2808 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-4 | 11690 | 0 | 5845 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01860 | 2809 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-4 | 140863 | 84517.8 | 28172.6 | 28172.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01820 | 2810 | Wiper wall panel | 3234 | 3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01865 | 2811 | Temporary Egress Stair Storage Sign | 2640 | 0 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01865 | 2812 | Address Signs | 4950 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01380 | 2813 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2814 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2815 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2816 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2817 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2818 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2819 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2820 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2821 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2822 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2823 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2824 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2825 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2826 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2827 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2828 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2829 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2830 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2831 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2832 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2833 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10887.2 | 680.45 | 680.45 | 680.45 | 680.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2834 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1056 | 950.4 | 0 | 105.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2835 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 986.4 | 0 | 109.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2836 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4620 | 2772 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2837 | HANGERS AND SUPPORTS | 11509 | 9207.2 | 0 | 2301.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2838 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2839 | DOMESTIC WATER PIPING | 140998 | 126898.2 | 0 | 14099.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 2840 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 | 0 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2841 | SANITARY WASTE PIPING | 122074 | 122074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2842 | SANITARY WASTE PIPING SPECIALTIES | 45569 | 45569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2843 | STORM DRAINAGE PIPING SPECIALTIES | 45569 | 45569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03030 | 2844 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 324500 | 308275 | 0 | 16225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2845 | GAS SERVICE AND PIPING | 6369 | 5732.1 | 0 | 636.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2846 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2847 | Plumbing Pipe Insulation | 35464 | 24824.8 | 0 | 5319.6 | 5319.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02260 | 2848 | Heat Trace | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-M-01005 | 2849 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 2850 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03112 | 2851 | Exhaust Fans: Install | 11495 | 0 | 2873.75 | 2873.75 | 2873.75 | 2873.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2852 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03032 | 2853 | Steam Unit Heaters: Install | 14300 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2854 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03032 | 2855 | Condensate Return Unit: Install | 20900 | 20900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03112 | 2856 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03112 | 2857 | Heating and Ventilation Unit: Install | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03310 | 2858 | Steam Traps: Furnish | 2420 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03310 | 2859 | Steam Traps: Install | 18150 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2860 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03032 | 2861 | Vacuum Pump Unit: Install | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03107 | 2862 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 189613 | 189613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03007 | 2863 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 312400 | 312400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03007 | 2864 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 96250 | 96250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03025 | 2865 | Mechanical Pipe: Hydrostatic Testing | 3163 | 3163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03107 | 2866 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 19250 | 13475 | 1854.3578 | 0 | 1306.8807 | 1306.8807 | 1306.8807 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 2867 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 26950 | 3708.7156 | 0 | 2613.7615 | 2613.7615 | 2613.7615 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03140 | 2868 | HVAC Ductwork: Testing & Balancing | 2200 | 0 | 211.9266 | 0 | 662.6911 | 662.6911 | 662.6911 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2869 | Controls: Furnish and Install: Devices | 82500 | 79200 | 1809.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2870 | Controls: Furnish and Install: Controls Conduit | 44000 | 42240 | 965.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2871 | Controls: Furnish and Install: Controls Wiring | 11000 | 10560 | 241.2903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2872 | Controls: Connect to Final Termination Points | 88000 | 74800 | 0 | 0 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03310 | 2873 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2874 | Insulation: Furnish and Install: Ductwork Insulation | 12650 | 8855 | 1897.5 | 1897.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2875 | Insulation: Furnish and Install: Piping Insulation | 25300 | 24035 | 632.5 | 632.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2876 | Insulation: Furnish and Install: Equipment Insulation | 12650 | 12017.5 | 632.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2877 | ATS Energization | 13688 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2878 | ATS Installation | 191625 | 191625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2879 | ATS Terminations | 13688 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2880 | ATS Testing | 13688 | 13003.6 | 0 | 0 | 0 | 228.1333 | 228.1333 | 228.1333 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02225 | 2881 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 26006.25 | 0 | 0 | 0 | 456.25 | 456.25 | 456.25 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02245 | 2882 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-02125 | 2883 | Cabling - Risers & Feeders (2/0 & Larger) | 473040 | 449388 | 0 | 0 | 0 | 7884 | 7884 | 7884 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02230 | 2884 | Conduit - Branch Circuits (1 1/2" & Smaller) | 273750 | 260062.5 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02305 | 2885 | Conduit - Risers (2" & up) | 542025 | 542025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02210 | 2886 | Demolition/Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02345 | 2887 | Firestopping | 5250 | 4987.5 | 0 | 0 | 0 | 87.5 | 87.5 | 87.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02215 | 2888 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02250 | 2889 | Lighting Controls | 25200 | 23940 | 0 | 0 | 0 | 420 | 420 | 420 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02210 | 2890 | Lighting Remove & Re-install | 54945 | 52197.75 | 0 | 0 | 0 | 915.75 | 915.75 | 915.75 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02210 | 2891 | Lighting System Program & Energize | 5475 | 2737.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02270 | 2892 | Mechanical Terminations(Dampers, Heaters, Motors) | 56940 | 54093 | 0 | 0 | 0 | 949 | 949 | 949 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-E-01000 | 2893 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02425 | 2894 | Switches and Receptacles | 10950 | 10402.5 | 0 | 0 | 0 | 182.5 | 182.5 | 182.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02515 | 2895 | Switchgear & Panelboard Energization | 30113 | 27101.7 | 0 | 0 | 0 | 1003.7667 | 1003.7667 | 1003.7667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02455 | 2896 | Switchgear & Panelboard Installation | 361350 | 361350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02455 | 2897 | Switchgear & Panelboard Terminations | 30113 | 28607.35 | 0 | 0 | 1505.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02520 | 2898 | Switchgear & Panelboard Testing | 30113 | 24090.4 | 860.3714 | 860.3714 | 860.3714 | 1147.1619 | 1147.1619 | 1147.1619 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02230 | 2899 | Fire Alarm Conduit | 16650 | 15817.5 | 0 | 0 | 0 | 277.5 | 277.5 | 277.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02325 | 2900 | Fire Alarm Wiring | 13140 | 12483 | 0 | 0 | 0 | 219 | 219 | 219 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02325 | 2901 | Fire Alarm Devices | 21900 | 20805 | 0 | 0 | 0 | 365 | 365 | 365 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02325 | 2902 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02505 | 2903 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01405 | 2904 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 17656 | 17656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 055 - SG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01480 | 2905 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 7542 | 7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 055 - SG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01480 | 2906 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-4 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 055 - SG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01005 | 2907 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01010 | 2908 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2909 | Assumed Flooring Material (Slab Penetrations) | 43200 | 43200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01020 | 2910 | Pipe Insulation | 151200 | 151200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2911 | Mudded Joint Packing | 25086 | 25086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2912 | Vinyl Membrane and Mastic | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2913 | Caulk | 108000 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2914 | Fibrous Slate | 15810 | 15810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01020 | 2915 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01020 | 2916 | Underground Utility Materials | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2917 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01220 | 2918 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2919 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2920 | Remove existing door, frame and hardware | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01115 | 2921 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01115 | 2922 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01115 | 2923 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2924 | Prepare existing wall surface for paint | 6000 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01210 | 2925 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01105 | 2926 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01205 | 2927 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01205 | 2928 | Existing Ramp railing to be be removed - 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2929 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01210 | 2930 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2931 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2932 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2933 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2934 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2935 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01210 | 2936 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01105 | 2937 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2938 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2939 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2940 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01410 | 2941 | FORM FLOOD BARRIER FOUNDATIONS - SG-5 | 86514 | 86514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01450 | 2942 | DRILL & GROUT DOWELS - SG-5 | 26772 | 26772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01450 | 2943 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-5 | 41980 | 41980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01470 | 2944 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-5 | 45756 | 45756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01440 | 2945 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-5 | 23998 | 23998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01440 | 2946 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-5 | 3591 | 3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01320 | 2947 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-5 | 168000 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01435 | 2948 | Footing/Pier | 24258 | 19406.4 | 4851.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01465 | 2949 | Retaining Walls | 4692 | 4692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01665 | 2950 | Entrance Slab | 20400 | 16320 | 2040 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01810 | 2951 | Concrete Shelf | 4320 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01415 | 2952 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01415 | 2953 | Boiler Room Concrete Curb | 3354 | 3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2954 | GFRP Sikawrap 100 G | 83226 | 83226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01440 | 2955 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-5 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01015 | 2956 | Overhead protection for Masonry | 34158 | 34158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01820 | 2957 | 6" vertically reinforced CMU | 123200 | 123200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2958 | 2" Face brick | 530612 | 477550.8 | 53061.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2959 | 2" rigid Insulation | 18480 | 18480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01820 | 2960 | Coping Stone C1/A-300 | 17319 | 17319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05380 | 2961 | MATERIAL AND FABRICATION | 38589 | 38589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01315 | 2962 | INSTALLATION | 68000 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01860 | 2963 | Temporary Aluminum Over Pass Stairs | 103992 | 0 | 51996 | 51996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-02345 | 2964 | PENETRATION FIRESTOPPING EXTG BLDG - SG-5 | 19222 | 0 | 9611 | 9611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01320 | 2965 | JOINT SEALANTS EXTG BLDGS - SG-5 | 19222 | 0 | 9611 | 9611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01830 | 2966 | Bituthene 4000 waterproofing membrane | 21362 | 21362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2967 | GE Elemax 2600 Silicone air and vapor barrier | 35211 | 35211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01825 | 2968 | Crystalline Waterproofing at perimeter walls | 42694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01835 | 2969 | Waterproofing at foundation walls | 17020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01860 | 2970 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-5 | 1200 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 061 - SG5 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01330 | 2971 | Doors, Frames & Hardware - Labor | 5004 | 5004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 061 - SG5 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 2972 | Furnish Doors | 6780 | 3390 | 1695 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2973 | Layout | 4170 | 4170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2974 | Loading | 6950 | 6950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2975 | Framing & Drywall - Materials | 14456 | 14456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2976 | Framing- Labor | 16680 | 16680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01330 | 2977 | Drywall - Labor | 28914 | 28914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01330 | 2978 | Tape/ Spackle finishes | 13344 | 13344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01855 | 2979 | Stucco | 11008 | 0 | 5504 | 5504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01340 | 2980 | Resilient Flooring and base - SG-5 | 27600 | 0 | 13800 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01860 | 2981 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-5 | 49413 | 24706.5 | 12353.25 | 12353.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01860 | 2982 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-5 | 27072 | 27072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01860 | 2983 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-5 | 140863 | 84517.8 | 28172.6 | 28172.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01820 | 2984 | Wiper wall panel | 3333 | 3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01865 | 2985 | Temporary Egress Stair Storage Sign | 2400 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01865 | 2986 | Address Signs | 9000 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01370 | 2987 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2988 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2989 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2990 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2991 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01380 | 2992 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2993 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2994 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2995 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2996 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01380 | 2997 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01380 | 2998 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2999 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3000 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3001 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3002 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3003 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3004 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3005 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3006 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3007 | COMMON WORK RESULTS FOR PLUMBING | 14846 | 11876.8 | 742.3 | 742.3 | 742.3 | 742.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3008 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 864 | 777.6 | 21.6 | 21.6 | 21.6 | 21.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3009 | ESCUTCHEONS FOR PLUMBING PIPING | 1196 | 837.2 | 89.7 | 89.7 | 89.7 | 89.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3010 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4080 | 0 | 1020 | 1020 | 1020 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3011 | HANGERS AND SUPPORTS | 12555 | 2511 | 2511 | 2511 | 2511 | 2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3012 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2394 | 0 | 598.5 | 598.5 | 598.5 | 598.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3013 | DOMESTIC WATER PIPING | 108372 | 86697.6 | 5418.6 | 5418.6 | 5418.6 | 5418.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3014 | DOMESTIC WATER PIPING SPECIALTIES | 17760 | 13320 | 1110 | 1110 | 1110 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3015 | SANITARY WASTE PIPING | 107844 | 86275.2 | 5392.2 | 5392.2 | 5392.2 | 5392.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3016 | SANITARY WASTE PIPING SPECIALTIES | 22562 | 20305.8 | 564.05 | 564.05 | 564.05 | 564.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3017 | STORM DRAINAGE PIPING SPECIALTIES | 46560 | 39576 | 1746 | 1746 | 1746 | 1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03030 | 3018 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 270000 | 256500 | 3375 | 3375 | 3375 | 3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3019 | GAS SERVICE AND PIPING | 2112 | 0 | 528 | 528 | 528 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3020 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 10714 | 10714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 3021 | Plumbing Pipe Insulation | 35464 | 35464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02240 | 3022 | Heat Trace | 6000 | 4800 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-M-01005 | 3023 | Survey | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 3024 | Exhaust Fans: Furnish | 4320 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03112 | 3025 | Exhaust Fans: Install | 8940 | 0 | 0 | 0 | 8940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 3026 | Steam Unit Heaters: Furnish | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03032 | 3027 | Steam Unit Heaters: Install | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 3028 | Condensate Return Unit: Furnish | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03032 | 3029 | Condensate Return Unit: Install | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03112 | 3030 | Heating and Ventilation Unit: Furnish | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03112 | 3031 | Heating and Ventilation Unit: Install | 20400 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03015 | 3032 | Steam Traps: Furnish | 1920 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03015 | 3033 | Steam Traps: Install | 15600 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 3034 | Vacuum Pump Unit: Furnish | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03032 | 3035 | Vacuum Pump Unit: Install | 22800 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03107 | 3036 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 104700 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03007 | 3037 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 167200 | 167200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03007 | 3038 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 50400 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03025 | 3039 | Mechanical Pipe: Hydrostatic Testing | 1925 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03107 | 3040 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 10800 | 10584 | 0 | 0 | 407.0769 | 0 | -191.0769 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 3041 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 16720 | 0 | 0 | 663.3846 | 0 | 216.6154 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03035 | 3042 | HVAC Ductwork: Testing & Balancing | 1200 | 0 | 0 | 0 | 45.2308 | 0 | 1154.7692 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3043 | Controls: Furnish and Install: Devices | 90000 | 83500 | 0 | 0 | 3250 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3044 | Controls: Furnish and Install: Controls Conduit | 42000 | 40320 | 560 | 560 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3045 | Controls: Furnish and Install: Controls Wiring | 12000 | 11520 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3046 | Controls: Connect to Final Termination Points | 9000 | 8550 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03235 | 3047 | Controls: Controls Testing | 7200 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 3048 | Insulation: Furnish and Install: Ductwork Insulation | 12650 | 0 | 6325 | 6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 3049 | Insulation: Furnish and Install: Piping Insulation | 25300 | 24035 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 3050 | Insulation: Furnish and Install: Equipment Insulation | 13800 | 0 | 6900 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3051 | ATS Energization | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3052 | ATS Installation | 168000 | 151200 | 0 | 0 | 0 | 5600 | 5600 | 5600 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3053 | ATS Terminations | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3054 | ATS Testing | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02210 | 3055 | Bypass Connections (Misc Panels, Re-routes, etc) | 30000 | 15000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02235 | 3056 | Cabling - Interior Branch (1/0 & Smaller) | 160000 | 0 | 22857.1429 | 22857.1429 | 22857.1429 | 30476.1905 | 30476.1905 | 30476.1905 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02475 | 3057 | Cabling - Risers & Feeders (2/0 & Larger) | 354780 | 266085 | 50682.8571 | 38012.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02215 | 3058 | Conduit - Branch Circuits (1 1/2" & Smaller) | 219000 | 175200 | 0 | 0 | 0 | 14600 | 14600 | 14600 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02325 | 3059 | Conduit - Risers (2" & Larger) | 394200 | 374490 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02220 | 3060 | Demolition/Temp Light & Power | 60000 | 51000 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02345 | 3061 | Firestopping | 6000 | 4500 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02225 | 3062 | Foundation Coring | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02265 | 3063 | Lighting Controls | 33600 | 0 | 0 | 0 | 0 | 11200 | 11200 | 11200 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02220 | 3064 | Lighting Remove & Re-install | 60480 | 0 | 0 | 0 | 0 | 20160 | 20160 | 20160 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02220 | 3065 | Lighting System Program & Energize | 6000 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02245 | 3066 | Mechanical Terminations(Dampers, Heaters, Motors) | 62400 | 28080 | 0 | 0 | 0 | 11440 | 11440 | 11440 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-E-01000 | 3067 | Survey | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02460 | 3068 | Switches and Receptacles | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02515 | 3069 | Switchgear & Panelboard Energization | 33000 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02405 | 3070 | Switchgear & Panelboard Installation | 396000 | 356400 | 11314.2857 | 11314.2857 | 11314.2857 | 1885.7143 | 1885.7143 | 1885.7143 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02405 | 3071 | Switchgear & Panelboard Terminations | 33000 | 0 | 20625 | 0 | 0 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02530 | 3072 | Switchgear & Panelboard Testing | 33000 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02215 | 3073 | Fire Alarm Conduit | 16650 | 11655 | 0 | 0 | 0 | 1665 | 1665 | 1665 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02315 | 3074 | Fire Alarm Wiring | 13140 | 0 | 0 | 0 | 0 | 4380 | 4380 | 4380 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02315 | 3075 | Fire Alarm Devices | 24000 | 0 | 0 | 0 | 0 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02315 | 3076 | Fire Alarm Programming & Pretest | 3000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02505 | 3077 | Fire Alarm FDNY Approval | 3000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01405 | 3078 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 17656 | 17656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 069 - SG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01480 | 3079 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 7542 | 7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 069 - SG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01480 | 3080 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-5 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 069 - SG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG6-01070 | 3081 | FORMWORK NEW BUILDING - SG-6 | 469701 | 469701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01175 | 3082 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-6 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01040 | 3083 | POUR CONCRETE NEW BUILDINGS - SG-6 | 179646 | 179646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01135 | 3084 | FINISH SLABS - SG-6 | 10746 | 10746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01075 | 3085 | Footing/Pier | 69927 | 69927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01075 | 3086 | Grade Beams | 4634 | 4634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01130 | 3087 | First Floor Slab | 29856 | 29856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01130 | 3088 | Equipment Pads | 1690 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01035 | 3089 | First Floor Plumbing Shaft Slab | 1373 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01035 | 3090 | Second Floor Plumbing Shaft Slab | 898 | 898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01035 | 3091 | Plumbing Shafts | 22737 | 22737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01155 | 3092 | Fuel Oil Tank Room | 11970 | 11970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01205 | 3093 | WWM-Slabs | 4173 | 4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01230 | 3094 | 8" CMU (3 hour rated) | 349751 | 349751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01275 | 3095 | 4" CMU | 61023 | 61023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01275 | 3096 | Face Brick 3-5/8" | 158400 | 158400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01275 | 3097 | 3-1/8" Rigid insulation | 15840 | 15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01250 | 3098 | Cast Stone with SS letters | 8521 | 6390.75 | 0 | 710.0833 | 710.0833 | 710.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01230 | 3099 | Steel Channel | 18876 | 18876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01230 | 3100 | Cont. Shelf angle | 11616 | 11616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3101 | STEEL (MATERIAL ONLY) | 165824 | 165824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3102 | FABRICATION COSTS | 246972 | 246972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3103 | METAL DECK (BUY-OUT) | 14113 | 14113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3104 | ANCHORS & EMBEDS | 9410 | 9410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3105 | SURVEYING | 11762 | 11762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3106 | STEEL & DECK ERECTION | 576267 | 576267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3107 | BOLTS AND HARDWARE | 23522 | 23522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3108 | TRUCKING | 11762 | 11762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01270 | 3109 | Dunnage Grating Galvanized | 60521 | 60521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01270 | 3110 | Dunnage Guard Rail | 28968 | 28968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01270 | 3111 | Dunnage Platform Stair with Guard Rail | 13035 | 13035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01290 | 3112 | Stair A: Ground to Roof Floor Stair and Landing with and Hand & Guard Rail | 136365 | 136365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01290 | 3113 | Stair B: Ground to 2nd Floor Stair and Landing with Hand & Guard Rail | 64143 | 64143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01295 | 3114 | 1st to 2nd Floor Ship Ladder with Cage and Platform | 27106 | 27106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01120 | 3115 | Egress Stair: Stair & Landing with Hand & Guard Rail | 64143 | 64143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3116 | Layout | 5109 | 5109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3117 | Loading | 18391 | 18391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3118 | Exterior Framing, Insulation & Drywall - Materials | 74880 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3119 | Exterior Framing- Labor | 87871 | 87871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01125 | 3120 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-6 | 1444 | 1444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-02425 | 3121 | PENETRATION FIRESTOPPING NEW BLDG - SG-6 | 11505 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG5-01320 | 3122 | JOINT SEALANTS NEW BLDGS - S6 | 11505 | 5752.5 | 0 | 0 | 0 | 2876.25 | 2876.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01230 | 3123 | Air Film | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3124 | Insulation- Labor | 6422 | 6422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01025 | 3125 | Crystalline Waterproofing at plumbing shaft | 5486 | 5486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01072 | 3126 | Waterproofing at foundation | 10040 | 10040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3127 | Layout | 86622 | 86622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3128 | Framing | 196161 | 196161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3129 | Insulation | 35133 | 35133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3130 | Cladding Install | 245934 | 221340.6 | 0 | 12296.7 | 12296.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01225 | 3131 | Fireproofing | 41800 | 41800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01265 | 3132 | P&I Cold Applied Roof Membrane | 102076 | 102076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01265 | 3133 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 123891 | 123891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01265 | 3134 | P&I Aluminum Coping | 8547 | 0 | 0 | 8547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01260 | 3135 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S6 | 12324 | 9859.2 | 0 | 0 | 0 | 1232.4 | 1232.4 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01245 | 3136 | Doors, Frames & Hardware - Labor | 22798 | 22798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01317 | 3137 | Louvers Install | 61342 | 0 | 0 | 30671 | 30671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 3138 | Furnish Doors | 33448 | 33448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01305 | 3139 | Sheathing & Drywall - Labor | 40634 | 40634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01245 | 3140 | Tape/ Spackle finishes | 13372 | 13372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01315 | 3141 | ACT ceilings - Materials | 1029 | 0 | 0 | 1029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01315 | 3142 | ACT ceilings - Labor | 4629 | 0 | 2314.5 | 2314.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01280 | 3143 | Direct Applied Stucco | 18722 | 0 | 9361 | 9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01325 | 3144 | Painting SG-6 | 110000 | 55000 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01310 | 3145 | Cermic Tile and Base - SG-6 | 7564 | 7564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01260 | 3146 | FIRE EXTINGUISHERS NEW BLDGS - SG-6 | 2931 | 0 | 732.75 | 732.75 | 732.75 | 366.375 | 366.375 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01260 | 3147 | TOILET ACCESSORIES NEW BLDGS - SG-6 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3148 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3149 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3150 | Room Sign | 2750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3151 | Exit Sign | 1100 | 0 | 0 | 0 | 366.6667 | 366.6667 | 366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3152 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3153 | Stairway Flood Access Door | 550 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3154 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 5176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3155 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3156 | ESCUTCHEONS FOR PLUMBING PIPING | 2178 | 2069.1 | 27.225 | 27.225 | 27.225 | 27.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3157 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 19800 | 18810 | 247.5 | 247.5 | 247.5 | 247.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3158 | HANGERS AND SUPPORTS | 21995 | 20895.25 | 274.9375 | 274.9375 | 274.9375 | 274.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3159 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2728 | 0 | 682 | 682 | 682 | 682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3160 | DOMESTIC WATER PIPING | 224153 | 212945.35 | 2801.9125 | 2801.9125 | 2801.9125 | 2801.9125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3161 | DOMESTIC WATER PIPING SPECIALTIES | 39863 | 37869.85 | 498.2875 | 498.2875 | 498.2875 | 498.2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3162 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 78375 | 1031.25 | 1031.25 | 1031.25 | 1031.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3163 | SANITARY WASTE PIPING | 118800 | 118800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3164 | SANITARY WASTE PIPING SPECIALTIES | 21998 | 21998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3165 | STORM DRAINAGE PIPING SPECIALTIES | 32997 | 32997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3166 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 13094.4 | 818.4 | 818.4 | 818.4 | 818.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3167 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 3009.6 | 3009.6 | 3009.6 | 3009.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3168 | GAS SERVICE AND PIPING | 277970 | 266851.2 | 2779.7 | 2779.7 | 2779.7 | 2779.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3169 | PLUMBING FIXTURES | 14167 | 10625.25 | 885.4375 | 885.4375 | 885.4375 | 885.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3170 | EMERGENCY PLUMBING FIXTURES | 5104 | 2552 | 638 | 638 | 638 | 638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3171 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 45430 | 45430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3172 | Plumbing Pipe Insulation | 3032 | 3032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02140 | 3173 | Heat Trace | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGN-M-01005 | 3174 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 3175 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3176 | Exhaust Fans: Install | 23045 | 23045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 3177 | Steam Unit Heaters: Furnish | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3178 | Steam Unit Heaters: Install | 45650 | 45650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 3179 | Electric Unit Heaters: Furnish | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 3180 | Condensate Return Unit: Furnish | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3181 | Condensate Return Unit: Install | 45650 | 45650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3182 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3183 | Heating and Ventilation Unit: Install | 33550 | 33550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3184 | Steam Traps: Furnish | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3185 | Steam Traps: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3186 | Steam Separator: Furnish | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3187 | Steam Separator: Install | 195250 | 195250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3188 | Low Pressure Steam Boilers: Install | 107250 | 107250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 3189 | Boiler Feed Unit: Furnish | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 3190 | Boiler Feed Unit: Install | 52250 | 52250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 3191 | Fuel Oil Pump: Furnish | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03130 | 3192 | Fuel Oil Pump: Install | 52250 | 52250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 3193 | Fuel Oil Storage Tank: Furnish | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03130 | 3194 | Fuel Oil Storage Tank: Install | 52250 | 52250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03110 | 3195 | Rigging | 145750 | 145750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03107 | 3196 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 433895 | 433895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03107 | 3197 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 682000 | 682000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03207 | 3198 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 187000 | 187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03135 | 3199 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 181500 | 181500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03135 | 3200 | Mechanical Pipe: Hydrostatic Testing | 6105 | 6105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03207 | 3201 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 55000 | 53900 | 1064.5161 | 0 | 0 | 0 | 35.4839 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 3202 | HVAC Ductwork:Furnish and Install: Sheetmetal and RGDs | 110000 | 107800 | 2129.0323 | 0 | 0 | 0 | 70.9677 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03245 | 3203 | HVAC Ductwork:Testing & Balancing | 5500 | 0 | 106.4516 | 0 | 0 | 0 | 5393.5484 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3204 | Controls: Furnish and Install: Devices | 209000 | 198550 | 3483.3333 | 3483.3333 | 3483.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3205 | Controls: Furnish and Install: Controls Conduit | 93500 | 88825 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3206 | Controls: Furnish and Install: Controls Wiring | 27500 | 26125 | 458.3333 | 458.3333 | 458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3207 | Controls: Connect to Final Termination Points | 18700 | 12155 | 2181.6667 | 2181.6667 | 2181.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03510 | 3208 | Controls Testing | 14575 | 0 | 4858.3333 | 4858.3333 | 4858.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 3209 | Furnish and Install: Ductwork Insulation | 29700 | 0 | 11062.5688 | 0 | 18637.4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 3210 | Furnish and Install: Piping Insulation | 60500 | 48400 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 3211 | Furnish and Install: Equipment Insulation | 29700 | 23760 | 5940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 3212 | Furnish and Install: Chemical Feed Equipment | 10230 | 10230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3213 | Chemical Cleaning | 8250 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3214 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3215 | ATS Installation | 153300 | 145635 | 0 | 0 | 0 | 7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3216 | ATS Terminations | 10950 | 10402.5 | 0 | 0 | 0 | 547.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3217 | ATS Testing | 10950 | 5475 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02120 | 3218 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02410 | 3219 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 468112.5 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02110 | 3220 | Conduit - Branch Circuits (1 1/2" & Smaller) | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02155 | 3221 | Conduit - In-Slab | 216810 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02210 | 3222 | Conduit - Risers (2" & Larger) | 295650 | 280867.5 | 0 | 0 | 0 | 4927.5 | 4927.5 | 4927.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02425 | 3223 | Firestopping | 5250 | 4987.5 | 0 | 0 | 0 | 87.5 | 87.5 | 87.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG6-01025 | 3224 | Generator Delivery | 52500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG6-01010 | 3225 | Generator Release | 315000 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02385 | 3226 | Generator Terminations | 52500 | 47250 | 0 | 0 | 0 | 1750 | 1750 | 1750 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02510 | 3227 | Generator Test | 52500 | 26250 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02160 | 3228 | Lighting Controls | 25200 | 22680 | 0 | 0 | 0 | 840 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02130 | 3229 | Lighting Install | 88830 | 84388.5 | 0 | 0 | 0 | 1480.5 | 1480.5 | 1480.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02130 | 3230 | Lighting Rough | 92637 | 92637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02130 | 3231 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02395 | 3232 | Lightning Protection | 21900 | 13140 | 0 | 0 | 0 | 2920 | 2920 | 2920 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02135 | 3233 | Mechanical Terminations(Dampers, Heaters, Motors) | 142350 | 128115 | 0 | 0 | 0 | 4745 | 4745 | 4745 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGN-E-01000 | 3234 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
CO | CO-01 | Second floor Apartment Removals | 17585 | 17585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-02 | National Grid Additional Allowance | 199883 | 199883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-03 | SG6 Additional Strobe | 2486 | 2486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-04 | CO#2-GC - PCOCO 2 Site 8 Basement Deteriorated Slab Shoring | 39587 | 39587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-05 | First Floor Move | 61418 | 61418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-06 | Site 8 Electrical Hazards | 22438.52 | 22438.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-07 | PCO-4 Door Hardware Changes | 25825.5 | 25825.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-08 | PCO-7 Boiler Accessories Supply | 195313 | 195313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-09 | PCO-9 Irma Pagan Move | 2603 | 2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-10 | PCO-14 National Grid Gas Line Work | 21598 | 21598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-11 | PCO-15 Additional Windows | 7011 | 7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-12 | PCO 11 - Concrete Pads for Mechanical Equipment | 39740 | 39740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-13 | PCO 19 - Window Infill | 3598.42 | 3598.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-14 | PCO 64 - OG10 Additional 3-Way Switch | 2494.4 | 2494.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-15 | PCO-21 Site 8 Fire Stand Pipe | 81400.51 | 81400.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-16 | PCO 42 - Tank in OG8 | 22925.66 | 22925.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-17 | PCO 46 - Sanitary Venting | 74242.32 | 74242.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-18 | PCO 52 - Relocation of Playground OGE | 12810.32 | 12810.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-19 | PCO 53 - SG6 and OG8 Boiler Stack Support | 72889.74 | 72889.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-20 | PCO 54 - ACM Abatement Waterproofing | 377117 | 377117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-21 | PCO 66 - Electric Ductbank Conflict | 25899.61 | 25899.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-22 | PCO 85 - OG5 OG4 Tank Insulation | 133560 | 133560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-23 | PCO 62 - O'Dwyer Fence Install | 159967.11 | 159967.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-24 | PCO 76 - Additional Fire Extinguishers | 4609.81 | 4609.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-25 | PCO 77 - SGS Steam Pipe Abatement | 117169.94 | 117169.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-26 | PCO 63 Support for Concrete Encasement of Electrical Conduits | 194900.63 | 194900.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-27 | PCO 93 Roof Access and ATS Room Door Issue | 97988.19 | 97988.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-28 | PCO 100 Exterior Metal Panel Support OG8/OG9/OG10 | 158262.1 | 158262.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
CO | CO-29 | PCO 102 SGS Outage Temporary Lighting | 12743.73 | 12743.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order | 0 | 0% | MLJ | Change Orders | 0 | Change Order | 0
0 | 0 | 0 | 188988067.51 | 133689925.23 | 6760911.375 | 7993164.5261 | 7381505.4665 | 8347308.2383 | 6805699.2392 | 4772404.6508 | 3617235.7104 | 2903196.7827 | 2466119.9313 | 1745487.0318 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0

## Sub Cost Forecast
Schedule Act | Item # | Description | Cost | Current Commitment | Previous Total | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | Total | SOV Level 1 | SOV Level 2 | Percent Complete | Sub | Total>Commitment? | Category
SG1-01005 | 47 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 7500 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01010 | 48 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 49 | Assumed Flooring Material (Slab Penetrations) | 3600 | 10800 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01020 | 50 | Pipe Insulation | 44100 | 132300 | 44100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44100 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01005 | 51 | Duct Seal | 14400 | 43200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 52 | Vinyl Membrane and Mastic | 12240 | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 53 | Caulk | 36750 | 110250 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 54 | Fibrous Slate | 4080 | 12240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01020 | 55 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01020 | 56 | Underground Utility Materials | 15600 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01820 | 82 | 6" vertically reinforced CMU | 179000 | 230912 | 170050 | 0 | 0 | 8950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179000 | SG1 | 004 - SG1 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG1-01830 | 83 | 2" Face brick | 195000 | 597520 | 58500 | 0 | 32634.8909 | 34621.703 | 34621.703 | 34621.703 | 0 | 0 | 0 | 0 | 0 | 195000 | SG1 | 004 - SG1 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG1-01820 | 85 | Coping Stone C1/A-300 | 142000 | 13200 | 127800 | 0 | 0 | 4733.3333 | 4733.3333 | 4733.3333 | 0 | 0 | 0 | 0 | 0 | 142000 | SG1 | 004 - SG1 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05440 | 86 | MATERIAL AND FABRICATION | 5000 | 5824 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG1 | 005 - SG1 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG1-01315 | 87 | INSTALLATION | 6000 | 6600 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | SG1 | 005 - SG1 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG1-01860 | 88 | Temporary Aluminum Over Pass Stairs | 51996 | 57196 | 0 | 25998 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51996 | SG1 | 005 - SG1 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG1-01330 | 96 | Doors, Frames & Hardware - Labor | 3000 | 6672 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | SG1 | 007 - SG1 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01325 | 98 | Layout | 3375 | 2829 | 3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3375 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01325 | 99 | Loading | 1875 | 3858 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01325 | 100 | Framing & Drywall - Materials | 4875 | 2829 | 0 | 1625 | 1625 | 1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4875 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01325 | 101 | Framing- Labor | 2250 | 4629 | 0 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01330 | 102 | Drywall - Labor | 2250 | 4629 | 0 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01330 | 103 | Tape/ Spackle finishes | 1500 | 3086 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-01855 | 104 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | SG1 | 008 - SG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG6-02150 | 110 | Switches and Receptacles | 10000 | 10950 | 9500 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 0 | 0 | 0 | 0 | 10000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02525 | 111 | Switchgear & Panelboard Energization | 17500 | 19163 | 8750 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 17500 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02405 | 112 | Switchgear & Panelboard Installation | 210000 | 229950 | 199500 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02405 | 113 | Switchgear & Panelboard Terminations | 17500 | 19163 | 16625 | 0 | 0 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02530 | 114 | Switchgear & Panelboard Testing | 17500 | 19163 | 13125 | 0 | 0 | 0 | 1458.3333 | 1458.3333 | 1458.3333 | 0 | 0 | 0 | 0 | 17500 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02025 | 115 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 50000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02110 | 116 | Fire Alarm Conduit | 62500 | 68438 | 59375 | 0 | 0 | 0 | 1041.6667 | 1041.6667 | 1041.6667 | 0 | 0 | 0 | 0 | 62500 | SG6 | 081 - SG6 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02365 | 117 | Fire Alarm Wiring | 60000 | 65700 | 57000 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 60000 | SG6 | 081 - SG6 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02365 | 118 | Fire Alarm Devices | 85000 | 93075 | 80750 | 0 | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 85000 | SG6 | 081 - SG6 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02365 | 119 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | SG6 | 081 - SG6 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02505 | 121 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | SG6 | 081 - SG6 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-01230 | 140 | 8" CMU (3 hour rated) | 407500 | 171133 | 387125 | 20375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407500 | SG7 | 084 - SG7 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
SG7-01275 | 144 | Face Brick 3-5/8" | 225500 | 235521 | 180400 | 45100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225500 | SG7 | 084 - SG7 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
SG7-01250 | 146 | Cast Stone with SS letters | 6300.7 | 8521 | 2520.2726 | 0 | 1260.1425 | 1260.1425 | 1260.1425 | 0 | 0 | 0 | 0 | 0 | 0 | 6300.7 | SG7 | 084 - SG7 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
SG7-01105 | 149 | STEEL (MATERIAL ONLY) | 152000 | 178532 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 150 | FABRICATION COSTS | 325000 | 303034 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 151 | METAL DECK (BUY-OUT) | 13000 | 15270 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 152 | ANCHORS & EMBEDS | 8000 | 9398 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 154 | SURVEYING | 12000 | 14096 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 155 | STEEL & DECK ERECTION | 520000 | 610764 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 156 | BOLTS AND HARDWARE | 20000 | 23492 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01105 | 157 | TRUCKING | 12000 | 11746 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SG7 | 085 - SG7 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG7-01270 | 158 | Dunnage Grating Galvanized | 58687 | 64556 | 0 | 29343.5 | 29343.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58687 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01270 | 159 | Dunnage Guard Rail | 27650 | 30415 | 27650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27650 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01270 | 160 | Dunnage Stair and Guard Rail | 11850 | 13035 | 11850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11850 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01290 | 161 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 106861 | 128548 | 98548.0741 | 4156.463 | 4156.463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106861 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01295 | 162 | 1st to 2nd Floor Ship Ladder with Cages | 23409 | 25750 | 14045.4 | 7022.7 | 2340.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23409 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01295 | 163 | Bulkhead Ship Ladder to Roof at 2 Locations | 11257 | 12383 | 1125.7 | 5065.65 | 5065.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11257 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01305 | 165 | Layout | 8875 | 8028 | 0 | 0 | 0 | 1267.8571 | 7607.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 8875 | SG7 | 086 - SG7 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01305 | 166 | Loading | 16125 | 15326 | 0 | 0 | 0 | 2104.2673 | 3156.4009 | 7242.8879 | 3621.444 | 0 | 0 | 0 | 0 | 16125 | SG7 | 086 - SG7 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01305 | 167 | Exterior Framing, Insulation & Drywall - Materials | 61814 | 67511 | 61814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61814 | SG7 | 086 - SG7 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01305 | 168 | Exterior Framing- Labor | 58711 | 58049 | 0 | 0 | 0 | 8387.2857 | 10114.0416 | 26806.4485 | 13403.2242 | 0 | 0 | 0 | 0 | 58711 | SG7 | 086 - SG7 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01305 | 173 | Insulation- Labor | 6375 | 7798 | 0 | 0 | 0 | 910.7143 | 5464.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | SG7 | 087 - SG7 - Division 7 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01255 | 177 | Layout | 83212 | 87373 | 0 | 0 | 0 | 27737.3333 | 27737.3333 | 27737.3333 | 0 | 0 | 0 | 0 | 0 | 83212 | SG7 | 087 - SG7 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG7-01255 | 178 | Framing | 188663 | 198097 | 188663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188663 | SG7 | 087 - SG7 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG7-01255 | 179 | Insulation | 33790 | 35480 | 33790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33790 | SG7 | 087 - SG7 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG7-01255 | 180 | Cladding Install | 236533 | 248360 | 0 | 0 | 0 | 78844.3333 | 78844.3333 | 78844.3333 | 0 | 0 | 0 | 0 | 0 | 236533 | SG7 | 087 - SG7 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG7-01225 | 181 | Fireproofing | 38000 | 41800 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | SG7 | 087 - SG7 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
SG7-01265 | 182 | P&I Cold Applied Roof Membrane | 96705 | 99622 | 0 | 0 | 96705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96705 | SG7 | 087 - SG7 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
SG7-01265 | 183 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 98847 | 101829 | 0 | 0 | 98847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98847 | SG7 | 087 - SG7 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
SG7-01265 | 184 | P&I Aluminum Coping | 7684 | 7458 | 0 | 0 | 7684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7684 | SG7 | 087 - SG7 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
SG7-01245 | 187 | Doors, Frames & Hardware - Labor | 8125 | 18070 | 2031.25 | 6093.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8125 | SG7 | 088 - SG7 - Division 8 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01317 | 188 | Louvers Install | 30974 | 61948 | 0 | 0 | 0 | 10324.6667 | 10324.6667 | 10324.6667 | 0 | 0 | 0 | 0 | 0 | 30974 | SG7 | 088 - SG7 - Division 8 | 0% | Navillus | 0 | NEW BUILDINGS
SG7-01305 | 190 | Sheathing & Drywall - Labor | 24125 | 49634 | 0 | 0 | 0 | 3446.4286 | 9721.1589 | 7304.9417 | 3652.4708 | 0 | 0 | 0 | 0 | 24125 | SG7 | 089 - SG7 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01245 | 191 | Tape/ Spackle finishes | 6875 | 14144 | 0 | 6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6875 | SG7 | 089 - SG7 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01315 | 192 | ACT ceilings - Materials | 1875 | 3858 | 0 | 0 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | SG7 | 089 - SG7 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01315 | 193 | ACT ceilings - Labor | 6250 | 12788 | 0 | 0 | 0 | 0 | 977.4789 | 3515.0141 | 1757.507 | 0 | 0 | 0 | 0 | 6250 | SG7 | 089 - SG7 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01280 | 194 | Direct Applied Stucco | 26750 | 53251 | 0 | 13375 | 13375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750 | SG7 | 089 - SG7 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG7-01325 | 195 | Painting SG-7 | 55000 | 110000 | 0 | 0 | 0 | 0 | 0 | 17500 | 37500 | 0 | 0 | 0 | 0 | 55000 | SG7 | 089 - SG7 - Division 9 | 0% | GG Paint | 0 | NEW BUILDINGS
SG7-03105 | 206 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 2117.25 | 2587.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4705 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 207 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 2400 | 2290.9091 | 109.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 209 | ESCUTCHEONS FOR PLUMBING PIPING | 1980 | 2178 | 0 | 1890 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 210 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 20000 | 22000 | 0 | 19090.9091 | 909.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 211 | HANGERS AND SUPPORTS | 19680 | 21648 | 13776 | 5904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19680 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 212 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2480 | 2728 | 0 | 2367.2727 | 112.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2480 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 213 | DOMESTIC WATER PIPING | 232190 | 255409 | 104485.5 | 90909.0909 | 36795.4091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232190 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 214 | DOMESTIC WATER PIPING SPECIALTIES | 27440 | 30184 | 10976 | 16464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27440 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 215 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 82500 | 15000 | 27272.7273 | 32727.2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 216 | SANITARY WASTE PIPING | 94944 | 104439 | 71208 | 18181.7137 | 5554.2863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94944 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 217 | SANITARY WASTE PIPING SPECIALTIES | 18640 | 20504 | 17708 | 932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18640 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 218 | STORM DRAINAGE PIPING SPECIALTIES | 48640 | 53504 | 41344 | 7296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48640 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03140 | 220 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 19840 | 21824 | 0 | 6613.3333 | 13226.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19840 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03140 | 221 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 292804 | 322085 | 117121.6 | 18181.7843 | 0 | 68181.6912 | 68181.6912 | 14091.4889 | 7045.7445 | 0 | 0 | 0 | 0 | 292804 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 222 | GAS SERVICE AND PIPING | 246950 | 271645 | 61737.5 | 90909.0909 | 0 | 13331.3636 | 26990.6818 | 26990.6818 | 26990.6818 | 0 | 0 | 0 | 0 | 246950 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03140 | 223 | PLUMBING FIXTURES | 16720 | 18392 | 0 | 5573.3333 | 11146.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16720 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 224 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 71529 | 78682 | 71529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71529 | SG7 | 091 - SG7 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG7-03105 | 225 | Plumbing Pipe Insulation | 9800 | 2374 | 0 | 9354.5455 | 445.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800 | SG7 | 091 - SG7 - Division 22 | 0% | Tristan | 0 | NEW BUILDINGS
SG7-02145 | 226 | Heat Trace | 5000 | 5475 | 0 | 0 | 3333.3333 | 0 | 0 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 5000 | SG7 | 091 - SG7 - Division 22 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-SGS-M-01005 | 227 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03112 | 228 | Exhaust Fans: Furnish | 6000 | 6600 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 229 | Exhaust Fans: Install | 17000 | 18700 | 12750 | 3642.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16392.8571 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 231 | Electric Unit Heaters: Furnish | 4500 | 4950 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 232 | Steam Unit Heaters: Furnish | 3000 | 3300 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 233 | Steam Unit Heaters: Install | 29250 | 32175 | 0 | 0 | 0 | 13504.9945 | 15745.0055 | 0 | 0 | 0 | 0 | 0 | 0 | 29250 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 234 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 235 | Heating and Ventilation Unit: Install | 24250 | 26675 | 0 | 0 | 0 | 11196.4484 | 13053.5516 | 0 | 0 | 0 | 0 | 0 | 0 | 24250 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 236 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 237 | Condensate Return Unit: Install | 23250 | 25575 | 0 | 0 | 0 | 10734.7392 | 12515.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 23250 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 238 | Steam Traps: Furnish | 1400 | 1540 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03142 | 239 | Steam Traps: Install | 13000 | 14300 | 0 | 0 | 0 | 6002.2198 | 6997.7802 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 240 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 143150 | 157465 | 14315 | 0 | 0 | 66952.9534 | 57035.5699 | 4846.4767 | 0 | 0 | 0 | 0 | 0 | 143150 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 242 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 247000 | 271700 | 0 | 0 | 0 | 115524.8305 | 98412.7542 | 24603.1886 | 8459.2267 | 0 | 0 | 0 | 0 | 247000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 243 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 80000 | 88000 | 0 | 0 | 0 | 37416.9492 | 31874.5763 | 7968.6441 | 2739.8305 | 0 | 0 | 0 | 0 | 80000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03135 | 244 | Mechanical Pipe: Hydrostatic Testing | 1850 | 2035 | 0 | 0 | 0 | 865.2669 | 737.0996 | 184.2749 | 63.3586 | 0 | 0 | 0 | 0 | 1850 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03110 | 245 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 17500 | 19250 | 15750 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03110 | 246 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 35000 | 38500 | 31500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03145 | 247 | HVAC Ductwork: Testing & Balancing | 2000 | 2200 | 0 | 0 | 0 | 288.9908 | 0 | 0 | 1711.0092 | 0 | 0 | 0 | 0 | 2000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 248 | Controls: Furnish and Install: Devices | 100000 | 110000 | 15000 | 0 | 0 | 0 | 0 | 36315.7895 | 48245.614 | 438.5965 | 0 | 0 | 0 | 100000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 249 | Controls: Furnish and Install: Controls Conduit | 45000 | 49500 | 5400 | 0 | 0 | 0 | 0 | 16342.1053 | 21710.5263 | 1547.3684 | 0 | 0 | 0 | 45000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 250 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 0 | 0 | 3631.5789 | 4824.5614 | 1543.8596 | 0 | 0 | 0 | 10000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 251 | Controls: Connect to Final Termination Points | 10000 | 11000 | 0 | 0 | 0 | 0 | 0 | 3631.5789 | 4824.5614 | 1543.8596 | 0 | 0 | 0 | 10000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-03510 | 253 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 0 | 0 | 2178.9474 | 2894.7368 | 926.3158 | 0 | 0 | 0 | 6000 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 254 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 3300 | 0 | 0 | 16500 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 255 | Insulation: Furnish and Install: Piping Insulation | 27500 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 5500 | 0 | 0 | 27500 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 256 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 3300 | 0 | 0 | 16500 | SG7 | 092 - SG7 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG7-02280 | 257 | ATS Energization | 22500 | 24638 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 2812.5 | 2812.5 | 2812.5 | 2812.5 | 22500 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02280 | 258 | ATS Installation | 315000 | 344925 | 157500 | 0 | 78750 | 0 | 0 | 0 | 0 | 19687.5 | 19687.5 | 19687.5 | 19687.5 | 315000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02280 | 259 | ATS Terminations | 22500 | 24638 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 2812.5 | 2812.5 | 2812.5 | 2812.5 | 22500 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02280 | 260 | ATS Testing | 22500 | 24638 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 2812.5 | 2812.5 | 2812.5 | 2812.5 | 22500 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02125 | 261 | Cabling - Interior Branch (1/0 & Smaller) | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 100000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SGS-02125 | 262 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 0 | 0 | 0 | 0 | 501428.5714 | 0 | 0 | 9642.8571 | 9642.8571 | 9642.8571 | 9642.8571 | 540000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02115 | 264 | Conduit - Branch Circuits (1 1/2" & Smaller) | 112500 | 123188 | 39375 | 0 | 0 | 0 | 0 | 0 | 0 | 18281.25 | 18281.25 | 18281.25 | 18281.25 | 112500 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02105 | 265 | Conduit - In-Slab | 148500 | 162608 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148500 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02010 | 266 | Conduit - Risers (2" & Larger) | 540000 | 591300 | 432000 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 540000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02475 | 267 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02010 | 268 | Foundation Coring | 10000 | 10500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-SG7-01040 | 269 | Generator Delivery | 75000 | 78750 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 9375 | 9375 | 9375 | 9375 | 75000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-SG7-01030 | 270 | Generator Release | 450000 | 472500 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02415 | 271 | Generator Terminations | 75000 | 78750 | 0 | 0 | 0 | 69642.8571 | 0 | 0 | 0 | 1339.2857 | 1339.2857 | 1339.2857 | 1339.2857 | 75000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02615 | 272 | Generator Test | 75000 | 78750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | 18750 | 18750 | 18750 | 75000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02150 | 273 | Lighting Controls | 11000 | 11550 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 1375 | 1375 | 1375 | 1375 | 11000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02135 | 275 | Lighting Install | 75000 | 82125 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 9375 | 9375 | 9375 | 9375 | 75000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02135 | 276 | Lighting Rough | 75000 | 82125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | 18750 | 18750 | 18750 | 75000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02135 | 277 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02425 | 278 | Lightning Protection | 20000 | 21900 | 10000 | 0 | 0 | 0 | 8571.4286 | 0 | 0 | 357.1429 | 357.1429 | 357.1429 | 357.1429 | 20000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02140 | 279 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 0 | 0 | 49714.2857 | 0 | 0 | 0 | 0 | 2071.4286 | 2071.4286 | 2071.4286 | 2071.4286 | 58000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-SGS-E-01030 | 280 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02160 | 281 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 10000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02655 | 282 | Switchgear & Panelboard Energization | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 11250 | 11250 | 45000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02330 | 283 | Switchgear & Panelboard Installation | 540000 | 591300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 135000 | 135000 | 135000 | 540000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02330 | 284 | Switchgear & Panelboard Terminations | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 11250 | 11250 | 45000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02650 | 286 | Switchgear & Panelboard Testing | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 11250 | 11250 | 45000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02005 | 287 | Temp Light & Power | 50000 | 54750 | 32500 | 0 | 0 | 0 | 0 | 0 | 0 | 4375 | 4375 | 4375 | 4375 | 50000 | SG7 | 093 - SG7 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02115 | 288 | Fire Alarm Conduit | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 30000 | SG7 | 094 - SG7 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02250 | 289 | Fire Alarm Wiring | 30000 | 32850 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 3750 | 3750 | 30000 | SG7 | 094 - SG7 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02250 | 290 | Fire Alarm Devices | 49000 | 53655 | 24500 | 12250 | 0 | 0 | 0 | 0 | 0 | 3062.5 | 3062.5 | 3062.5 | 3062.5 | 49000 | SG7 | 094 - SG7 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02250 | 291 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 312.5 | 312.5 | 312.5 | 312.5 | 2500 | SG7 | 094 - SG7 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG7-02625 | 292 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 625 | 625 | 625 | 2500 | SG7 | 094 - SG7 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SGN-01155 | 323 | Manhole Installation | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SGN-02215 | 324 | Site Lighting - Cable | 50000 | 54750 | 5000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 50000 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SGN-02210 | 325 | Site Lighting - Conduit | 60000 | 65700 | 57000 | 1285.7143 | 1285.7143 | 428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SGN-02220 | 326 | Site Lighting - Fixtures | 50600 | 55407 | 0 | 0 | 0 | 0 | 0 | 16866.6667 | 16866.6667 | 16866.6667 | 0 | 0 | 0 | 50600 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SURV-SGN-E-01000 | 327 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SGN-02125 | 328 | Underground Electric Service - Cable | 750000 | 821250 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SGN-01155 | 330 | Underground Electric Service - Conduit | 600000 | 657000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | SGN | 099 - SGN - Division 26 | 0% | Five Star | 0 | SITE
SG1-03005 | 340 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 10515.35 | 0 | 0 | 0 | 618.55 | 618.55 | 618.55 | 0 | 0 | 0 | 0 | 12371 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGN-01640 | 345 | 4' Steel Bar Fence with Double Gates | 79007.7519 | 88000 | 0 | 0 | 0 | 0 | 67720.9302 | 11286.8217 | 0 | 0 | 0 | 0 | 0 | 79007.7519 | SGN | 101 - SGN - Division 32 | 0% | Atlas | 0 | SITE
SGN-01645 | 346 | 6' Chain Link Fence | 11357.3643 | 12650 | 0 | 0 | 0 | 0 | 0 | 11357.3643 | 0 | 0 | 0 | 0 | 0 | 11357.3643 | SGN | 101 - SGN - Division 32 | 0% | Atlas | 0 | SITE
SGN-01610 | 348 | 4" CONCRETE | 65000 | 100100 | 0 | 0 | 32500 | 27857.1429 | 4642.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01610 | 349 | 7" CONCRETE RAMP | 2000 | 3080 | 0 | 0 | 1000 | 857.1429 | 142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01610 | 350 | 5" POROUS CONCRETE | 300000 | 462000 | 75000 | 0 | 112500 | 96428.5714 | 16071.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SG1-03005 | 351 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGN-01630 | 352 | 5" COLOR CONCRETE | 50000 | 77000 | 30000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01605 | 353 | CONCRETE CURB | 12000 | 18480 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01605 | 354 | SFC -STELL FACING CURB | 12000 | 18480 | 0 | 8571.4286 | 2857.1429 | 571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01680 | 356 | Deciduous Trees | 14175.0087 | 14884 | 0 | 0 | 0 | 0 | 14175.0087 | 0 | 0 | 0 | 0 | 0 | 0 | 14175.0087 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01680 | 357 | Evergreen Trees | 3374.6826 | 3544 | 0 | 0 | 0 | 0 | 3374.6826 | 0 | 0 | 0 | 0 | 0 | 0 | 3374.6826 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01680 | 358 | Deciduous Shrubs | 2800 | 2940 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01680 | 359 | Evergreen Shrubs | 990.2344 | 1040 | 0 | 0 | 0 | 0 | 990.2344 | 0 | 0 | 0 | 0 | 0 | 0 | 990.2344 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01680 | 360 | Perennials | 7796.0859 | 8080 | 0 | 0 | 0 | 0 | 7796.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 7796.0859 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01675 | 361 | Grasses | 17652.3627 | 18295 | 0 | 0 | 0 | 8826.1814 | 8826.1814 | 0 | 0 | 0 | 0 | 0 | 0 | 17652.3627 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SG1-03005 | 362 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 747 | 0 | 0 | 0 | 0 | 166 | 83 | 0 | 0 | 0 | 0 | 996 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGN-01025 | 363 | Tree Removal | 6566.8979 | 41580 | 6566.8979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6566.8979 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01675 | 364 | Lawn Seeding (not including topsoil) | 17277.4815 | 14810 | 8638.7407 | 0 | 0 | 4319.3704 | 4319.3704 | 0 | 0 | 0 | 0 | 0 | 0 | 17277.4815 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01025 | 365 | Soil Erosion Mat | 3189.4866 | 2791 | 2707.921 | 0 | 0 | 240.7828 | 240.7828 | 0 | 0 | 0 | 0 | 0 | 0 | 3189.4866 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01675 | 366 | Topsoil Stockpile/Spread | 97333.6079 | 101317 | 63266.8451 | 0 | 0 | 17033.3814 | 17033.3814 | 0 | 0 | 0 | 0 | 0 | 0 | 97333.6079 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01675 | 367 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 2553.5586 | SGN | 101 - SGN - Division 32 | 0% | Aspen | 0 | SITE
SGN-01110 | 370 | INSTALL HW, CW PIPE - SGN | 183333.34 | 403279 | 183333.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183333.34 | SGN | 102 - SGN - Division 33 | 0% | Welkin | 0 | SITE
SGN-01130 | 372 | INSTALL CONDENSATE AND STEAM PIPE - SGN | 130000 | 308238 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | SGN | 102 - SGN - Division 33 | 0% | Welkin | 0 | SITE
SG1-03005 | 373 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3000 | 3300 | 2250 | 0 | 0 | 0 | 0 | 500 | 250 | 0 | 0 | 0 | 0 | 3000 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03005 | 384 | HANGERS AND SUPPORTS | 10477.5 | 11526 | 8905.875 | 0 | 0 | 0 | 0 | 1047.75 | 523.875 | 0 | 0 | 0 | 0 | 10477.5 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03005 | 395 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 0 | 0 | 0 | 1330 | 665 | 0 | 0 | 0 | 0 | 1995 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGS-02010 | 398 | Manhole Work | 50000 | 54750 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 50000 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SGS-02215 | 399 | Site Lighting - Cable | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 45000 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SGS-02210 | 400 | Site Lighting - Conduit | 60000 | 65700 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 0 | 60000 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SGS-02220 | 401 | Site Lighting - Fixtures | 57500 | 62963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19166.6667 | 19166.6667 | 19166.6667 | 0 | 57500 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SURV-SGS-E-01030 | 402 | Survey | 64000 | 70080 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SGS-02135 | 403 | Underground Electric Service - Cable | 750000 | 821250 | 0 | 0 | 0 | 187500 | 187500 | 187500 | 187500 | 0 | 0 | 0 | 0 | 750000 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SGS-01155 | 404 | Underground Electric Service - Conduit | 600000 | 657000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | SGS | 105 - SGS - Division 26 | 0% | Five Star | 0 | SITE
SG1-03005 | 406 | DOMESTIC WATER PIPING | 115200 | 126720 | 86400 | 0 | 0 | 0 | 0 | 19200 | 9600 | 0 | 0 | 0 | 0 | 115200 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03005 | 417 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 11100 | 0 | 0 | 0 | 0 | 2466.6667 | 1233.3333 | 0 | 0 | 0 | 0 | 14800 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGS-01745 | 421 | Ametco Fence | 126166.6667 | 138050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63083.3333 | 63083.3333 | 0 | 0 | 126166.6667 | SGS | 107 - SGS - Division 32 | 0% | Atlas | 0 | SITE
SGS-01710 | 422 | 4" CONCRETE | 65000 | 71500 | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29250 | 19500 | 0 | 65000 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01710 | 423 | 5"POROUS CONCRETE | 424200 | 466620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254520 | 169680 | 0 | 424200 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01730 | 424 | 5" COLOR CONCRETE | 140000 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | 140000 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01705 | 425 | CONCRETE CURB | 35000 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21666.6667 | 11666.6667 | 1666.6667 | 0 | 35000 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01705 | 426 | SFC -STELL FACING CURB | 12000 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7428.5714 | 4000 | 571.4286 | 0 | 12000 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01760 | 427 | Deciduous Trees | 26325.2883 | 27642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13162.6442 | 13162.6442 | 0 | 26325.2883 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SG1-03005 | 428 | SANITARY WASTE PIPING | 108000 | 118800 | 91800 | 0 | 0 | 0 | 0 | 10800 | 5400 | 0 | 0 | 0 | 0 | 108000 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGS-01760 | 429 | Evergreen Trees | 2025.3809 | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6904 | 1012.6904 | 0 | 2025.3809 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01760 | 430 | Deciduous Shrubs | 1400 | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 1400 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01760 | 431 | Perennials | 4273.3743 | 4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2136.6871 | 2136.6871 | 0 | 4273.3743 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01755 | 432 | Grasses | 7699.6914 | 7980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3849.8457 | 3849.8457 | 0 | 7699.6914 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01025 | 433 | Tree Removal | 7619.6863 | 48246 | 6987.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631.7362 | 0 | 0 | 7619.6863 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01755 | 434 | Lawn Seeding (not including topsoil) | 16346.5274 | 14012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8173.2637 | 8173.2637 | 0 | 16346.5274 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01755 | 435 | Topsoil Stockpile/Spread | 92388.968 | 96170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46194.484 | 46194.484 | 0 | 92388.968 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SGS-01755 | 436 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 2553.5586 | SGS | 107 - SGS - Division 32 | 0% | Aspen | 0 | SITE
SG1-03005 | 439 | SANITARY WASTE PIPING SPECIALTIES | 27336 | 30070 | 24602.4 | 0 | 0 | 0 | 0 | 1822.4 | 911.2 | 0 | 0 | 0 | 0 | 27336 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SGS-01355 | 440 | INSTALL HW, CW PIPE - SGS | 293333.33 | 504915 | 293333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293333.33 | SGS | 108 - SGS - Division 33 | 0% | Welkin | 0 | SITE
SGS-01330 | 442 | INSTALL CONDENSATE AND STEAM PIPE - SGS | 173333.34 | 516372 | 173333.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173333.34 | SGS | 108 - SGS - Division 33 | 0% | Welkin | 0 | SITE
SG1-03005 | 450 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 27000 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 30000 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-01005 | 452 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 15000 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01010 | 453 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01015 | 454 | Assumed Flooring Material (Slab Penetrations) | 20400 | 61200 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 455 | Pipe Insulation | 50400 | 151200 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 456 | Tank Insulation | 3250 | 9750 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01015 | 457 | Fireproofing | 57040 | 171120 | 57040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57040 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01015 | 458 | Fibrous Slate | 3060 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 459 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 460 | Underground Utility Materials | 3848 | 11544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-03030 | 461 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 230000 | 253000 | 218500 | 0 | 0 | 0 | 3833.3333 | 3833.3333 | 3833.3333 | 0 | 0 | 0 | 0 | 230000 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03005 | 472 | GAS SERVICE AND PIPING | 1920 | 2112 | 0 | 0 | 0 | 0 | 0 | 1280 | 640 | 0 | 0 | 0 | 0 | 1920 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03005 | 483 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | SG1 | 011 - SG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03005 | 494 | Plumbing Pipe Insulation | 21600 | 34034 | 0 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | SG1 | 011 - SG1 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG1-01830 | 502 | 2" Face brick | 98000 | 153384 | 88200 | 0 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98000 | OG1 | 111 - OG1 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG1-01820 | 503 | 6" vertically reinforced CMU | 58000 | 38368 | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000 | OG1 | 111 - OG1 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG1-02015 | 505 | Heat Trace | 5000 | 5475 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG1 | 011 - SG1 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-01820 | 506 | Coping stone C1/A-300 | 56000 | 24909 | 42000 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | 0 | 56000 | OG1 | 111 - OG1 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05230 | 507 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG1 | 112 - OG1 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG1-01315 | 508 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG1 | 112 - OG1 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG1-01860 | 509 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | OG1 | 112 - OG1 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SURV-SGS-M-01005 | 516 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-01330 | 517 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG1 | 114 - OG1 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01325 | 519 | Layout | 2500 | 5143 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01325 | 520 | Loading | 3625 | 7458 | 3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3625 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01325 | 521 | Framing & Drywall - Materials | 7875 | 12087 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01325 | 522 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9625 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01330 | 523 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8875 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01330 | 524 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-01855 | 525 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | OG1 | 115 - OG1 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-03112 | 527 | Exhaust Fans: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03112 | 538 | Exhaust Fans: Install | 4150 | 4565 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4150 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 549 | Steam Unit Heaters: Furnish | 3000 | 3300 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03005 | 554 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 1030.9167 | 1030.9167 | 1030.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 555 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 500 | 550 | 450 | 16.6667 | 16.6667 | 16.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 556 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 557 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2200 | 2420 | 1760 | 146.6667 | 146.6667 | 146.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 558 | HANGERS AND SUPPORTS | 10500.1 | 11551 | 7875.075 | 875.0083 | 875.0083 | 875.0083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500.1 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 559 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-03032 | 560 | Steam Unit Heaters: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03005 | 561 | DOMESTIC WATER PIPING | 98200 | 108020 | 73650 | 8183.3333 | 8183.3333 | 8183.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98200 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 562 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 13079.25 | 1453.25 | 1453.25 | 1453.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17439 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 563 | SANITARY WASTE PIPING | 86520 | 95172 | 77868 | 2884 | 2884 | 2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86520 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 564 | SANITARY WASTE PIPING SPECIALTIES | 31080 | 34188 | 29526 | 518 | 518 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31080 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 565 | STORM DRAINAGE PIPING SPECIALTIES | 31080 | 34188 | 15540 | 5180 | 5180 | 5180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31080 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03030 | 566 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 170000 | 187000 | 127500 | 14875 | 0 | 0 | 9208.3333 | 9208.3333 | 9208.3333 | 0 | 0 | 0 | 0 | 170000 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 567 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | OG1 | 118 - OG1 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03005 | 568 | Plumbing Pipe Insulation | 27600 | 41899 | 24840 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | OG1 | 118 - OG1 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG1-02040 | 569 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG1 | 118 - OG1 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGE-M-01005 | 570 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 571 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 572 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 573 | Exhaust Fans: Install | 7600 | 8360 | 0 | 3800 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 574 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 575 | Steam Unit Heaters: Install | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 576 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 577 | Condensate Return Unit: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 578 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 579 | Heating and Ventilation Unit: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03015 | 580 | Steam Traps: Furnish | 1800 | 1980 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03015 | 581 | Steam Traps: Install | 13000 | 14300 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03032 | 582 | Condensate Return Unit: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 583 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 584 | Vacuum Pump Unit: Install | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 585 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 81000 | 89100 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 586 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 110000 | 121000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 587 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03025 | 588 | Mechanical Pipe: Hydrostatic Testing | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03107 | 589 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 590 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03135 | 591 | HVAC Ductwork: Testing & Balancing | 1000 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 592 | Controls: Furnish and Install: Devices | 70000 | 77000 | 64400 | 5414.0625 | 185.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03112 | 593 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 594 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 595 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 7500 | 773.4375 | 132.8125 | 0 | 0 | 1593.75 | 0 | 0 | 0 | 0 | 0 | 10000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 596 | Controls: Connect to Final Termination Points | 7000 | 7700 | 3500 | 541.4062 | 92.9688 | 0 | 0 | 2865.625 | 0 | 0 | 0 | 0 | 0 | 7000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03025 | 597 | Controls: Controls Testing | 6000 | 6600 | 0 | 464.0625 | 79.6875 | 0 | 0 | 5456.25 | 0 | 0 | 0 | 0 | 0 | 6000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 598 | Insulation: Furnish and Install: Ductwork Insulation | 9000 | 9900 | 0 | 7200 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 599 | Insulation: Furnish and Install: Piping Insulation | 16000 | 17600 | 2400 | 12800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 600 | Insulation: Furnish and Install: Equipment Insulation | 9000 | 9900 | 1350.9091 | 7200 | 449.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | OG1 | 119 - OG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-02210 | 601 | ATS Energization | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 12500 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02210 | 602 | ATS Installation | 175000 | 191625 | 157500 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 175000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02210 | 603 | ATS Terminations | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 12500 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-03112 | 604 | Heating and Ventilation Unit: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-02210 | 605 | ATS Testing | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 12500 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02010 | 606 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 25000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02035 | 607 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 200000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG10-02395 | 608 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 270000 | 0 | 0 | 135000 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 540000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02015 | 609 | Conduit - Branch Circuits (1 1/2" & Smaller) | 225000 | 246375 | 168750 | 0 | 0 | 0 | 0 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 225000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02125 | 610 | Conduit - Risers (2" & Larger) | 540000 | 591300 | 513000 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | 0 | 0 | 540000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02020 | 611 | Demolition/Temp Light & Power | 50000 | 54750 | 45000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02145 | 612 | Firestopping | 5000 | 5250 | 0 | 4375 | 0 | 0 | 0 | 208.3333 | 208.3333 | 208.3333 | 0 | 0 | 0 | 5000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02025 | 613 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02065 | 614 | Lighting Controls | 24000 | 25200 | 12000 | 10500 | 0 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 24000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-03015 | 615 | Steam Traps: Furnish | 1600 | 1760 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-02120 | 616 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 30857.1429 | 0 | 0 | 0 | 1714.2857 | 1714.2857 | 1714.2857 | 0 | 0 | 0 | 36000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG10-02160 | 617 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02070 | 618 | Mechanical Terminations(Dampers, Heaters, Motors) | 60000 | 65700 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 60000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGE-01020 | 619 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02250 | 620 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02515 | 621 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 27500 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02215 | 622 | Switchgear & Panelboard Installation | 330000 | 361350 | 297000 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 330000 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02265 | 623 | Switchgear & Panelboard Terminations | 27500 | 30113 | 6875 | 20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02510 | 624 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 27500 | OG1 | 120 - OG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02015 | 625 | Fire Alarm Conduit | 20000 | 21900 | 0 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 20000 | OG1 | 121 - OG1 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-03015 | 626 | Steam Traps: Install | 12000 | 13200 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-02130 | 627 | Fire Alarm Wiring | 18000 | 19710 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 18000 | OG1 | 121 - OG1 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02115 | 628 | Fire Alarm Devices | 22000 | 24090 | 11000 | 0 | 0 | 0 | 0 | 3666.6667 | 3666.6667 | 3666.6667 | 0 | 0 | 0 | 22000 | OG1 | 121 - OG1 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02535 | 629 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG1 | 121 - OG1 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-02535 | 630 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG1 | 121 - OG1 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-01005 | 634 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 5000 | 0 | 0 | 15000 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01010 | 635 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01015 | 636 | Assumed Flooring Material (Slab Penetrations) | 19200 | 57600 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-03032 | 637 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-01020 | 638 | Pipe Insulation | 37800 | 113400 | 37800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37800 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01015 | 639 | Fibrous Slate | 3060 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01020 | 640 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01020 | 641 | Underground Utility Materials | 3848 | 11544 | 3848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3848 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-03032 | 648 | Vacuum Pump Unit: Install | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03107 | 659 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 80625 | 88688 | 80625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80625 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03007 | 670 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 115000 | 126500 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03007 | 681 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 41000 | 45100 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-01820 | 684 | 6" vertically reinforced CMU | 38000 | 38368 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | OG2 | 125 - OG2 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG2-01830 | 685 | 2" Face brick | 95000 | 153384 | 90250 | 0 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | OG2 | 125 - OG2 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG2-01820 | 687 | Coping stone C1/A-300 | 45000 | 25245 | 38250 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | OG2 | 125 - OG2 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05080 | 688 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG2 | 126 - OG2 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG2-01315 | 689 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG2 | 126 - OG2 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG2-01860 | 690 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | OG2 | 126 - OG2 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG1-03025 | 692 | Mechanical Pipe: Hydrostatic Testing | 1375 | 1513 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-01330 | 698 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG2 | 128 - OG2 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG2-01325 | 700 | Layout | 2500 | 5143 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG2-01325 | 701 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG2-01325 | 702 | Framing & Drywall - Materials | 7875 | 12087 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-03107 | 703 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-01325 | 704 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9625 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG2-01330 | 705 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8875 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG2-01330 | 706 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG2-01855 | 707 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | OG2 | 129 - OG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG1-03110 | 714 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03310 | 725 | HVAC Ductwork: Testing & Balancing | 1000 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03005 | 735 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 7422.6 | 0 | 4948.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03120 | 736 | Controls: Furnish and Install: Devices | 65000 | 71500 | 61750 | 0 | 0 | 1083.3333 | 1083.3333 | 1083.3333 | 0 | 0 | 0 | 0 | 0 | 65000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03005 | 737 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 500 | 550 | 450 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 738 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 739 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3399 | 3739 | 2209.35 | 0 | 1189.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3399 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 740 | HANGERS AND SUPPORTS | 10500.1 | 11551 | 7875.075 | 0 | 2625.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500.1 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 741 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 742 | DOMESTIC WATER PIPING | 103400 | 113740 | 77550 | 0 | 25850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103400 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 743 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 13079.25 | 0 | 4359.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17439 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 744 | SANITARY WASTE PIPING | 89300 | 98230 | 71440 | 0 | 17860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89300 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 745 | SANITARY WASTE PIPING SPECIALTIES | 27330 | 30063 | 24597 | 0 | 2733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27330 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 746 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03120 | 747 | Controls: Furnish and Install: Controls Conduit | 30000 | 33000 | 28500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 30000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03030 | 748 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 240000 | 264000 | 204000 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 749 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | OG2 | 132 - OG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG2-03005 | 750 | Plumbing Pipe Insulation | 16350 | 28886 | 14715 | 817.5 | 817.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16350 | OG2 | 132 - OG2 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG2-02035 | 751 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG2 | 132 - OG2 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGW-M-01005 | 752 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 753 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03112 | 754 | Exhaust Fans: Install | 8100 | 8910 | 0 | 2025 | 2025 | 2025 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 755 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03032 | 756 | Steam Unit Heaters: Install | 9500 | 10450 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 757 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 758 | Controls: Furnish and Install: Controls Wiring | 9000 | 9900 | 8550 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 9000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03032 | 759 | Condensate Return Unit: Install | 15500 | 17050 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15500 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03112 | 760 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03112 | 761 | Heating and Ventilation Unit: Install | 16500 | 18150 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03015 | 762 | Steam Traps: Furnish | 1600 | 1760 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03015 | 763 | Steam Traps: Install | 11000 | 12100 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 764 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03032 | 765 | Vacuum Pump Unit: Install | 18500 | 20350 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03107 | 766 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 78225 | 86048 | 78225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78225 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03007 | 767 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 105500 | 116050 | 105500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105500 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03007 | 768 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 31000 | 34100 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 769 | Controls: Connect to Final Termination Points | 6000 | 6600 | 5400 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 6000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03025 | 770 | Mechanical Pipe: Hydrostatic Testing | 2775 | 3053 | 2775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 771 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 38500 | 34300 | 674.3119 | 0 | 0 | 0 | 0 | 25.6881 | 0 | 0 | 0 | 0 | 35000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 772 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 70000 | 77000 | 68600 | 1348.6239 | 0 | 0 | 0 | 0 | 51.3761 | 0 | 0 | 0 | 0 | 70000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03135 | 773 | HVAC Ductwork: Testing & Balancing | 4000 | 4400 | 0 | 77.0642 | 0 | 0 | 0 | 0 | 3922.9358 | 0 | 0 | 0 | 0 | 4000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 774 | Controls: Furnish and Install: Devices | 70000 | 77000 | 66500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 775 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 776 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 7500 | 0 | 1417.9104 | 0 | 1082.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 777 | Controls: Connect to Final Termination Points | 8000 | 8800 | 4000 | 0 | 1134.3284 | 0 | 2865.6716 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-03025 | 778 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 850.7463 | 0 | 5149.2537 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 779 | Insulation: Furnish and Install: Ductwork Insulation | 9000 | 9900 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-03310 | 780 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 781 | Insulation: Furnish and Install: Piping Insulation | 16000 | 17600 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 782 | Insulation: Furnish and Install: Equipment Insulation | 9000 | 9900 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | OG2 | 133 - OG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-02210 | 783 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02210 | 784 | ATS Installation | 140000 | 153300 | 126000 | 0 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 140000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02210 | 785 | ATS Terminations | 10000 | 10950 | 5000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 10000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02210 | 786 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02010 | 787 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 17500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 25000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02025 | 788 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 125000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OGW-02115 | 789 | Cabling - Risers & Feeders (2/0 & Larger) | 360000 | 394200 | 270000 | 51428.5714 | 38571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02020 | 790 | Conduit - Branch Circuits (1 1/2" & Smaller) | 212500 | 232688 | 180625 | 0 | 0 | 0 | 0 | 10625 | 10625 | 10625 | 0 | 0 | 0 | 212500 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-03040 | 791 | Insulation: Furnish and Install: Ductwork Insulation | 9000 | 9900 | 0 | 0 | 4500 | 2700 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-02130 | 792 | Conduit - Risers (2" & Larger) | 360000 | 394200 | 342000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 360000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02015 | 793 | Demolition/Temp Light & Power | 50000 | 54750 | 37500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 50000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02145 | 794 | Firestopping | 5000 | 5250 | 2500 | 2187.5 | 0 | 0 | 0 | 104.1667 | 104.1667 | 104.1667 | 0 | 0 | 0 | 5000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02030 | 795 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02240 | 796 | Lighting Controls | 31000 | 32550 | 15500 | 0 | 0 | 0 | 0 | 5166.6667 | 5166.6667 | 5166.6667 | 0 | 0 | 0 | 31000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02015 | 797 | Lighting Remove & Re-install | 36900 | 40406 | 0 | 0 | 0 | 0 | 0 | 12300 | 12300 | 12300 | 0 | 0 | 0 | 36900 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02015 | 798 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02070 | 799 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 0 | 0 | 0 | 0 | 0 | 19333.3333 | 19333.3333 | 19333.3333 | 0 | 0 | 0 | 58000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGW-E-01015 | 800 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02245 | 801 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-03040 | 802 | Insulation: Furnish and Install: Piping Insulation | 16000 | 17600 | 0 | 0 | 8000 | 4800 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG2-02515 | 803 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 27500 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02260 | 804 | Switchgear & Panelboard Installation | 330000 | 361350 | 313500 | 14142.8571 | 2357.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02260 | 805 | Switchgear & Panelboard Terminations | 27500 | 30113 | 6875 | 23571.4286 | 0 | 0 | 0 | -982.1429 | -982.1429 | -982.1429 | 0 | 0 | 0 | 27500 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02510 | 806 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 27500 | OG2 | 134 - OG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02020 | 807 | Fire Alarm Conduit | 20000 | 21900 | 15000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 20000 | OG2 | 135 - OG2 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02115 | 808 | Fire Alarm Wiring | 15000 | 16425 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 15000 | OG2 | 135 - OG2 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02115 | 809 | Fire Alarm Devices | 21000 | 22995 | 10500 | 0 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 21000 | OG2 | 135 - OG2 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02115 | 810 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG2 | 135 - OG2 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG2-02535 | 811 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG2 | 135 - OG2 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-03040 | 813 | Insulation: Furnish and Install: Equipment Insulation | 9000 | 9900 | 0 | 0 | 4500 | 2700 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | SG1 | 012 - SG1 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-01005 | 816 | Gaskets | 26250 | 78750 | 0 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 26250 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01010 | 817 | Wire Insulation | 12500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01015 | 818 | Assumed Flooring Material (Slab Penetrations) | 15600 | 46800 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01005 | 819 | Duct Seal | 1200 | 3600 | 0 | 0 | 0 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | 0 | 1200 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01015 | 820 | Fibrous Slate | 3060 | 9180 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01020 | 821 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01020 | 822 | Underground Utility Materials | 3796 | 11388 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-02010 | 824 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 18750 | 3125 | 3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02065 | 835 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 150000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02130 | 846 | Cabling - Risers & Feeders (2/0 & Larger) | 270000 | 295650 | 0 | 0 | 0 | 0 | 9132.4201 | 9132.4201 | 9132.4201 | 60650.6849 | 60650.6849 | 60650.6849 | 60650.6849 | 270000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02035 | 857 | Conduit - Branch Circuits (1 1/2" & Smaller) | 225000 | 246375 | 22500 | 36529.6804 | 18409.0909 | 0 | 0 | 0 | 0 | 36890.3072 | 36890.3072 | 36890.3072 | 36890.3072 | 225000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-01820 | 863 | 6" vertically reinforced CMU | 60000 | 38368 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG3 | 139 - OG3 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG3-01830 | 864 | 2" Face brick | 100000 | 153384 | 90000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | OG3 | 139 - OG3 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG3-01820 | 866 | Coping stone C1/A-300 | 57000 | 25245 | 42750 | 0 | 0 | 4750 | 4750 | 4750 | 0 | 0 | 0 | 0 | 0 | 57000 | OG3 | 139 - OG3 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05110 | 867 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG3 | 140 - OG3 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG1-02030 | 868 | Conduit - Risers (2" & Larger) | 270000 | 295650 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 60750 | 60750 | 60750 | 60750 | 270000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-01315 | 869 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG3 | 140 - OG3 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG3-01860 | 870 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | OG3 | 140 - OG3 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG3-01330 | 877 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG3 | 142 - OG3 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-02025 | 879 | Demolition/Temp Light & Power | 50000 | 54750 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 50000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-01325 | 880 | Layout | 2625 | 5401 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG3-01325 | 881 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG3-01325 | 882 | Framing & Drywall - Materials | 11250 | 11829 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG3-01325 | 883 | Framing- Labor | 6625 | 13629 | 6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6625 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG3-01330 | 884 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8875 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG3-01330 | 885 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG3-01855 | 886 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | OG3 | 143 - OG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG1-02120 | 890 | Firestopping | 5000 | 5250 | 0 | 4375 | 0 | 0 | 0 | 0 | 0 | 156.25 | 156.25 | 156.25 | 156.25 | 5000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02030 | 901 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02115 | 912 | Lighting Controls | 25000 | 26250 | 12500 | 3571.4286 | 0 | 0 | 0 | 0 | 0 | 2232.1429 | 2232.1429 | 2232.1429 | 2232.1429 | 25000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-03005 | 915 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 7422.6 | 0 | 4948.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 916 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 714 | 786 | 499.8 | 0 | 214.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 917 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 300 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 918 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2397 | 2637 | 1438.2 | 0 | 958.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2397 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 919 | HANGERS AND SUPPORTS | 10477.5 | 11526 | 8905.875 | 0 | 1571.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10477.5 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 920 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 921 | DOMESTIC WATER PIPING | 117070 | 128777 | 99509.5 | 0 | 17560.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117070 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 922 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 16567.05 | 0 | 871.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17439 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG1-02025 | 923 | Lighting Remove & Re-install | 25200 | 27972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 6300 | 6300 | 6300 | 25200 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-03005 | 924 | SANITARY WASTE PIPING | 133651 | 147017 | 106920.8 | 0 | 0 | 13365.1 | 13365.1 | 0 | 0 | 0 | 0 | 0 | 0 | 133651 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 925 | SANITARY WASTE PIPING SPECIALTIES | 30720 | 33792 | 27648 | 0 | 3072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30720 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 926 | STORM DRAINAGE PIPING SPECIALTIES | 30720 | 33792 | 15360 | 0 | 15360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30720 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03030 | 927 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 240000 | 264000 | 204000 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 928 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 8470 | 9317 | 8470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8470 | OG3 | 146 - OG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG3-03005 | 929 | Plumbing Pipe Insulation | 30350 | 35464 | 7587.5 | 0 | 11381.25 | 11381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30350 | OG3 | 146 - OG3 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG3-02030 | 930 | Heat Trace | 5000 | 5475 | 0 | 4000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | 0 | 5000 | OG3 | 146 - OG3 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGW-M-01005 | 931 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 932 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03112 | 933 | Exhaust Fans: Install | 13600 | 14960 | 6800 | 297.0736 | 6502.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13600 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-02025 | 934 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-03032 | 935 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03032 | 936 | Steam Unit Heaters: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 937 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03032 | 938 | Condensate Return Unit: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03112 | 939 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03112 | 940 | Heating and Ventilation Unit: Install | 22000 | 24200 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03015 | 941 | Steam Traps: Furnish | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03015 | 942 | Steam Traps: Install | 22750 | 25025 | 22750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22750 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 943 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03032 | 944 | Vacuum Pump Unit: Install | 24000 | 26400 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG1-02040 | 945 | Mechanical Terminations(Dampers, Heaters, Motors) | 36000 | 39420 | 0 | 0 | 30857.1429 | 0 | 0 | 0 | 0 | 1285.7143 | 1285.7143 | 1285.7143 | 1285.7143 | 36000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-03007 | 946 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 300950 | 331045 | 300950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300950 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03007 | 947 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 383000 | 421300 | 383000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 948 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 130000 | 143000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03025 | 949 | Mechanical Pipe: Hydrostatic Testing | 4050 | 4455 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4050 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03107 | 950 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 30000 | 33000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 951 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 60000 | 66000 | 57000 | 0 | 1935.4839 | 0 | 0 | 0 | 1064.5161 | 0 | 0 | 0 | 0 | 60000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03135 | 952 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 96.7742 | 0 | 0 | 0 | 2903.2258 | 0 | 0 | 0 | 0 | 3000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 953 | Controls: Furnish and Install: Devices | 70000 | 77000 | 59500 | 0 | 9768.6567 | 0 | 731.3433 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 954 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 955 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 7800 | 0 | 1395.5224 | 0 | 804.4776 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SURV-SGS-E-01030 | 956 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-03120 | 957 | Controls: Connect to Final Termination Points | 8000 | 8800 | 4000 | 0 | 1116.4179 | 0 | 2883.5821 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-03025 | 958 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 837.3134 | 0 | 5162.6866 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 959 | Insulation: Furnish and Install: Ductwork Insulation | 18000 | 19800 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 960 | Insulation: Furnish and Install: Piping Insulation | 36000 | 39600 | 25200 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 961 | Insulation: Furnish and Install: Equipment Insulation | 18000 | 19800 | 12600 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG3 | 147 - OG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG3-02210 | 962 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02210 | 963 | ATS Installation | 140000 | 153300 | 126000 | 0 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 140000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02210 | 964 | ATS Terminations | 10000 | 10950 | 2500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 10000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02210 | 965 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02010 | 966 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 25000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02105 | 967 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 10000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02025 | 968 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 150000 | 0 | 42857.1429 | 0 | 0 | 0 | 35714.2857 | 35714.2857 | 35714.2857 | 0 | 0 | 0 | 150000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02260 | 969 | Cabling - Risers & Feeders (2/0 & Larger) | 360000 | 394200 | 270000 | 51428.5714 | 38571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02020 | 970 | Conduit - Branch Circuits (1 1/2" & Smaller) | 200000 | 219000 | 160000 | 0 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 200000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02130 | 971 | Conduit - Risers (2" & Larger) | 360000 | 394200 | 342000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 360000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02015 | 972 | Demolition/Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 50000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02150 | 973 | Firestopping | 5000 | 5250 | 2500 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 5000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02035 | 974 | Foundation Coring | 10000 | 10500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02240 | 975 | Lighting Controls | 32000 | 33600 | 16000 | 0 | 0 | 0 | 0 | 5333.3333 | 5333.3333 | 5333.3333 | 0 | 0 | 0 | 32000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02015 | 976 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 36000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02015 | 977 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG7-02655 | 978 | Switchgear & Panelboard Energization | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02070 | 979 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 14500 | 38062.5 | 0 | 0 | 0 | 1812.5 | 1812.5 | 1812.5 | 0 | 0 | 0 | 58000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGW-E-01015 | 980 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02245 | 981 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02515 | 982 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 27500 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02265 | 983 | Switchgear & Panelboard Installation | 330000 | 361350 | 313500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02265 | 984 | Switchgear & Panelboard Terminations | 27500 | 30525 | 6875 | 24062.5 | 0 | 0 | 0 | -1145.8333 | -1145.8333 | -1145.8333 | 0 | 0 | 0 | 27500 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02510 | 985 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 27500 | OG3 | 148 - OG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02020 | 986 | Fire Alarm Conduit | 20000 | 21900 | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 20000 | OG3 | 149 - OG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02115 | 987 | Fire Alarm Wiring | 15000 | 16425 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 15000 | OG3 | 149 - OG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02115 | 988 | Fire Alarm Devices | 19000 | 20805 | 9500 | 0 | 0 | 0 | 0 | 3166.6667 | 3166.6667 | 3166.6667 | 0 | 0 | 0 | 19000 | OG3 | 149 - OG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG7-02330 | 989 | Switchgear & Panelboard Installation | 60000 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 60000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02115 | 990 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG3 | 149 - OG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG3-02535 | 991 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG3 | 149 - OG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-01005 | 995 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2500 | 0 | 7500 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01010 | 996 | Wire Insulation | 12500 | 37500 | 11875 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01015 | 997 | Assumed Flooring Material (Slab Penetrations) | 25200 | 75600 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 998 | Pipe Insulation | 42000 | 126000 | 40000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 999 | Tank Insulation | 3250 | 9750 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG7-02330 | 1000 | Switchgear & Panelboard Terminations | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-01015 | 1001 | Fireproofing | 10850 | 32550 | 10850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10850 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01015 | 1002 | Fibrous Slate | 3060 | 9180 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 1003 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 1004 | Underground Utility Materials | 3796 | 11388 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG7-02650 | 1011 | Switchgear & Panelboard Testing | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG1 | 013 - SG1 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-01820 | 1047 | 6" vertically reinforced CMU | 58000 | 44875 | 55100 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000 | OG4 | 153 - OG4 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG4-01830 | 1048 | 2" Face brick | 99000 | 198275 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | OG4 | 153 - OG4 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG4-01820 | 1050 | Coping stone C1/A-300 | 57000 | 28328 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000 | OG4 | 153 - OG4 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05140 | 1051 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG4 | 154 - OG4 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG4-01315 | 1052 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG4 | 154 - OG4 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG4-01860 | 1053 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | OG4 | 154 - OG4 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG2-01005 | 1055 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 7500 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01330 | 1061 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG4 | 156 - OG4 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG4-01325 | 1063 | Layout | 2625 | 5401 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG4-01325 | 1064 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG4-01325 | 1065 | Framing & Drywall - Materials | 8125 | 12601 | 8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8125 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG2-01010 | 1066 | Wire Insulation | 12500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01325 | 1067 | Framing- Labor | 10000 | 13372 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG4-01330 | 1068 | Drywall - Labor | 7625 | 15687 | 7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7625 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG4-01330 | 1069 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG4-01855 | 1070 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | OG4 | 157 - OG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG2-01015 | 1077 | Assumed Flooring Material (Slab Penetrations) | 3600 | 10800 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG2-01020 | 1088 | Pipe Insulation | 37800 | 113400 | 32592 | 0 | 0 | 5208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37800 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03005 | 1098 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 6185.5 | 1546.375 | 1546.375 | 1546.375 | 1546.375 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG2-01020 | 1099 | Tank Insulation | 5200 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03005 | 1100 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 714 | 786 | 428.4 | 71.4 | 71.4 | 71.4 | 71.4 | 0 | 0 | 0 | 0 | 0 | 0 | 714 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1101 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 400 | 150 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1102 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2983 | 3282 | 596.6 | 596.6 | 596.6 | 596.6 | 596.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2983 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1103 | HANGERS AND SUPPORTS | 10489.6 | 11539 | 7342.72 | 786.72 | 786.72 | 786.72 | 786.72 | 0 | 0 | 0 | 0 | 0 | 0 | 10489.6 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1104 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 498.75 | 498.75 | 498.75 | 498.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1105 | DOMESTIC WATER PIPING | 114134 | 125548 | 79893.8 | 8560.05 | 8560.05 | 8560.05 | 8560.05 | 0 | 0 | 0 | 0 | 0 | 0 | 114134 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1106 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 13951.2 | 871.95 | 871.95 | 871.95 | 871.95 | 0 | 0 | 0 | 0 | 0 | 0 | 17439 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1107 | SANITARY WASTE PIPING | 97194 | 106914 | 87474.6 | 2429.85 | 2429.85 | 2429.85 | 2429.85 | 0 | 0 | 0 | 0 | 0 | 0 | 97194 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1108 | SANITARY WASTE PIPING SPECIALTIES | 27333 | 30067 | 24599.7 | 683.325 | 683.325 | 683.325 | 683.325 | 0 | 0 | 0 | 0 | 0 | 0 | 27333 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1109 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 15000 | 3750 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG2-01005 | 1110 | Duct Seal | 6000 | 18000 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 6000 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03030 | 1111 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 170000 | 187000 | 136000 | 17000 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1112 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 8460 | 9306 | 8460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8460 | OG4 | 160 - OG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG4-03005 | 1113 | Plumbing Pipe Insulation | 20600 | 35464 | 12360 | 4120 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20600 | OG4 | 160 - OG4 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG4-02045 | 1114 | Heat Trace | 5000 | 5475 | 0 | 0 | 4285.7143 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | 0 | 5000 | OG4 | 160 - OG4 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGP1-M-01005 | 1115 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 1116 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03112 | 1117 | Exhaust Fans: Install | 12600 | 13860 | 0 | 1512.5084 | 11087.4916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12600 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1118 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03032 | 1119 | Steam Unit Heaters: Install | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1120 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-01015 | 1121 | Vinyl Membrane and Mastic | 12240 | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03032 | 1122 | Condensate Return Unit: Install | 20000 | 22000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03112 | 1123 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03112 | 1124 | Heating and Ventilation Unit: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03015 | 1125 | Steam Traps: Furnish | 1800 | 1980 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03015 | 1126 | Steam Traps: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1127 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03032 | 1128 | Vacuum Pump Unit: Install | 23000 | 25300 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1129 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 246300 | 270930 | 246300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246300 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1130 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 320000 | 352000 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1131 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 120000 | 132000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-01015 | 1132 | Caulk | 37500 | 112500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03025 | 1133 | Mechanical Pipe: Hydrostatic Testing | 3700 | 4070 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 1134 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 25000 | 27500 | 23750 | 0 | 721.1538 | 0 | 176.2821 | 176.2821 | 176.2821 | 0 | 0 | 0 | 0 | 25000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 1135 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 50000 | 55000 | 49500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03032 | 1136 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 86.5385 | 0 | 0 | 0 | 2913.4615 | 0 | 0 | 0 | 0 | 3000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1137 | Controls: Furnish and Install: Devices | 70000 | 77000 | 63000 | 0 | 5171.6418 | 0 | 1828.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1138 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1139 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 9500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1140 | Controls: Connect to Final Termination Points | 8000 | 8800 | 7600 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-03025 | 1141 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 443.2836 | 0 | 5556.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1142 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-01015 | 1143 | Fibrous Slate | 4675 | 14025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-03040 | 1144 | Insulation: Furnish and Install: Piping Insulation | 34500 | 37950 | 20700 | 11116.6667 | 2683.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1145 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 18150 | 9900 | 5316.6667 | 1283.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | OG4 | 161 - OG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG4-02210 | 1146 | ATS Energization | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 12500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02210 | 1147 | ATS Installation | 175000 | 191625 | 157500 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 175000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02210 | 1148 | ATS Terminations | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 12500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02210 | 1149 | ATS Testing | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 12500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02015 | 1150 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 6250 | 0 | 0 | 0 | 0 | 6250 | 6250 | 6250 | 0 | 0 | 0 | 25000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02040 | 1151 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 200000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OGP1-02010 | 1152 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 270000 | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02020 | 1153 | Conduit - Branch Circuits (1 1/2" & Smaller) | 237500 | 260063 | 190000 | 0 | 0 | 0 | 0 | 15833.3333 | 15833.3333 | 15833.3333 | 0 | 0 | 0 | 237500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-01020 | 1154 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-02130 | 1155 | Conduit - Risers (2" & Larger) | 450000 | 492750 | 427500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 450000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02025 | 1156 | Demolition/Temp Light & Power | 50000 | 54750 | 47500 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02145 | 1157 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02030 | 1158 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02240 | 1159 | Lighting Controls | 25000 | 26250 | 12500 | 0 | 10714.2857 | 0 | 0 | 595.2381 | 595.2381 | 595.2381 | 0 | 0 | 0 | 25000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02025 | 1160 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 36000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02025 | 1161 | Lighting System Program & Energize | 5000 | 5550 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02050 | 1162 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 14500 | 0 | 0 | 0 | 0 | 14500 | 14500 | 14500 | 0 | 0 | 0 | 58000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGP1-E-01010 | 1163 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02245 | 1164 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-01020 | 1165 | Underground Utility Materials | 15600 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-02515 | 1166 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 27500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02260 | 1167 | Switchgear & Panelboard Installation | 330000 | 361350 | 297000 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02260 | 1168 | Switchgear & Panelboard Terminations | 27500 | 30525 | 6875 | 0 | 0 | 0 | 0 | 6875 | 6875 | 6875 | 0 | 0 | 0 | 27500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02510 | 1169 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 27500 | OG4 | 162 - OG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02020 | 1170 | Fire Alarm Conduit | 25000 | 27375 | 17500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 25000 | OG4 | 163 - OG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02115 | 1171 | Fire Alarm Wiring | 18000 | 19710 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 18000 | OG4 | 163 - OG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02115 | 1172 | Fire Alarm Devices | 20000 | 21900 | 10000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 20000 | OG4 | 163 - OG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02115 | 1173 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG4 | 163 - OG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG4-02535 | 1174 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG4 | 163 - OG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-01005 | 1179 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 15000 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01010 | 1180 | Wire Insulation | 12500 | 37500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 12500 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01015 | 1181 | Assumed Flooring Material (Slab Penetrations) | 19200 | 57600 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1182 | Pipe Insulation | 37800 | 113400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1183 | Tank Insulation | 3250 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01015 | 1184 | Fireproofing | 42625 | 127875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01015 | 1185 | Fibrous Slate | 3060 | 9180 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1186 | Waterproofing | 1657 | 4971 | 1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1657 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1188 | Underground Utility Materials | 3796 | 11388 | 3036.8 | 0 | 759.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01820 | 1230 | 6" vertically reinforced CMU | 58000 | 44875 | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000 | OG5 | 167 - OG5 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG5-01830 | 1232 | 2" Face brick | 85500 | 198275 | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500 | OG5 | 167 - OG5 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG5-01820 | 1234 | Coping stone C1/A-300 | 57000 | 28002 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000 | OG5 | 167 - OG5 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05260 | 1235 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG5 | 168 - OG5 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG5-01315 | 1236 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG5 | 168 - OG5 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG5-01860 | 1237 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | OG5 | 168 - OG5 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG5-01330 | 1245 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG5 | 170 - OG5 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01325 | 1247 | Layout | 1875 | 3858 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01325 | 1248 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01325 | 1249 | Framing & Drywall - Materials | 7750 | 11829 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01325 | 1250 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9625 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01330 | 1251 | Drywall - Labor | 8125 | 16715 | 8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8125 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01330 | 1252 | Tape/ Spackle finishes | 5875 | 12087 | 5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5875 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-01855 | 1254 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | OG5 | 171 - OG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG5-03005 | 1282 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 0 | 3092.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1283 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 500 | 550 | 400 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1284 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 750 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1285 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2600 | 2860 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1287 | HANGERS AND SUPPORTS | 10491 | 11541 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10491 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1288 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1289 | DOMESTIC WATER PIPING | 109926 | 120919 | 109926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109926 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1290 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 11100 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14800 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1291 | SANITARY WASTE PIPING | 101808 | 111989 | 91627.2 | 0 | 10180.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101808 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1292 | SANITARY WASTE PIPING SPECIALTIES | 27335 | 30069 | 24601.5 | 0 | 2733.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27335 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1293 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03030 | 1294 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 169998 | 186998 | 135998.4 | 0 | 0 | 16999.8 | 16999.8 | 0 | 0 | 0 | 0 | 0 | 0 | 169998 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1295 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | OG5 | 174 - OG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 1296 | Plumbing Pipe Insulation | 27500 | 35464 | 24750 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | OG5 | 174 - OG5 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG5-02045 | 1298 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG5 | 174 - OG5 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGP1-M-01005 | 1299 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 1300 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03112 | 1301 | Exhaust Fans: Install | 15600 | 17160 | 0 | 5200 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1302 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03032 | 1303 | Steam Unit Heaters: Install | 17000 | 18700 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1304 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03032 | 1305 | Condensate Return Unit: Install | 23000 | 25300 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03112 | 1306 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03112 | 1307 | Heating and Ventilation Unit: Install | 24000 | 26400 | 0 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03015 | 1309 | Steam Traps: Furnish | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03015 | 1310 | Steam Traps: Install | 23000 | 25300 | 11500 | 1594.3339 | 1414.1049 | 8491.5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1311 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03032 | 1312 | Vacuum Pump Unit: Install | 26000 | 28600 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03107 | 1313 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 318700 | 350570 | 239025 | 47533.7297 | 32141.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318700 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03007 | 1314 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 410000 | 451000 | 205000 | 102500 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1315 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 200000 | 220000 | 100000 | 29829.7645 | 70170.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03025 | 1316 | Mechanical Pipe: Hydrostatic Testing | 5300 | 5830 | 0 | 2650 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5300 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1317 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 38500 | 34300 | 0 | 0 | 674.3119 | 0 | 0 | 25.6881 | 0 | 0 | 0 | 0 | 35000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1318 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 70000 | 77000 | 68600 | 0 | 0 | 1348.6239 | 0 | 0 | 51.3761 | 0 | 0 | 0 | 0 | 70000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03310 | 1320 | HVAC Ductwork: Testing & Balancing | 4000 | 4400 | 0 | 0 | 0 | 77.0642 | 0 | 0 | 3922.9358 | 0 | 0 | 0 | 0 | 4000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1321 | Controls: Furnish and Install: Devices | 70000 | 77000 | 50400 | 0 | 18597.0149 | 0 | 1002.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1322 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1323 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 4000 | 0 | 2656.7164 | 0 | 3343.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1324 | Controls: Connect to Final Termination Points | 8000 | 8800 | 0 | 0 | 2125.3731 | 0 | 5874.6269 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-03025 | 1325 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 1594.0299 | 0 | 4405.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1326 | Insulation: Furnish and Install: Ductwork Insulation | 20000 | 22000 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1327 | Insulation: Furnish and Install: Piping Insulation | 40000 | 44000 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1328 | Insulation: Furnish and Install: Equipment Insulation | 20000 | 22000 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG5 | 175 - OG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG5-02210 | 1329 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02210 | 1331 | ATS Installation | 140000 | 153300 | 126000 | 0 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 140000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02210 | 1332 | ATS Terminations | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02210 | 1333 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02010 | 1334 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 25000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02040 | 1335 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 125000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OGP1-02025 | 1336 | Cabling - Risers & Feeders (2/0 & Larger) | 450000 | 492750 | 225000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02015 | 1337 | Conduit - Branch Circuits (1 1/2" & Smaller) | 212500 | 232688 | 180625 | 0 | 0 | 0 | 0 | 10625 | 10625 | 10625 | 0 | 0 | 0 | 212500 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02125 | 1338 | Conduit - Risers (2" & Larger) | 450000 | 492750 | 427500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 450000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02025 | 1339 | Demolition/Temp Light & Power | 50000 | 54750 | 40000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 50000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02145 | 1340 | Firestopping | 5000 | 5250 | 2500 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 5000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02030 | 1342 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02240 | 1343 | Lighting Controls | 31000 | 32550 | 15500 | 0 | 13285.7143 | 0 | 0 | 738.0952 | 738.0952 | 738.0952 | 0 | 0 | 0 | 31000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02025 | 1344 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 36000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02025 | 1345 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 5000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02050 | 1346 | Mechanical Terminations(Dampers, Heaters, Motors) | 60000 | 65700 | 15000 | 39375 | 0 | 0 | 0 | 1875 | 1875 | 1875 | 0 | 0 | 0 | 60000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGP1-E-01010 | 1347 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02250 | 1348 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 10000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02515 | 1349 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 23571.4286 | 0 | 1309.5238 | 1309.5238 | 1309.5238 | 0 | 0 | 0 | 27500 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02265 | 1350 | Switchgear & Panelboard Installation | 330000 | 366300 | 297000 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02265 | 1351 | Switchgear & Panelboard Terminations | 27500 | 30113 | 6875 | 0 | 0 | 0 | 0 | 6875 | 6875 | 6875 | 0 | 0 | 0 | 27500 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02510 | 1353 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 3928.5714 | 3928.5714 | 3928.5714 | 5238.0952 | 5238.0952 | 5238.0952 | 0 | 0 | 0 | 0 | 27500 | OG5 | 176 - OG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02015 | 1354 | Fire Alarm Conduit | 20000 | 21900 | 15000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 20000 | OG5 | 177 - OG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02115 | 1355 | Fire Alarm Wiring | 18000 | 19710 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 18000 | OG5 | 177 - OG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02115 | 1356 | Fire Alarm Devices | 19000 | 20805 | 9500 | 0 | 0 | 0 | 0 | 3166.6667 | 3166.6667 | 3166.6667 | 0 | 0 | 0 | 19000 | OG5 | 177 - OG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02115 | 1357 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG5 | 177 - OG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG5-02535 | 1358 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG5 | 177 - OG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-01005 | 1362 | Gaskets | 19500 | 58500 | 14625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4875 | 0 | 19500 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01010 | 1364 | Wire Insulation | 25000 | 75000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01015 | 1365 | Assumed Flooring Material (Slab Penetrations) | 21600 | 64800 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01020 | 1366 | Pipe Insulation | 30240 | 90720 | 30240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30240 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01005 | 1367 | Duct Seal | 1200 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01015 | 1368 | Asbestos Panels | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01015 | 1369 | Fibrous Slate | 4760 | 14280 | 4760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4760 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01020 | 1370 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01020 | 1371 | Underground Utility Materials | 3796 | 11388 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3796 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01820 | 1413 | 6" vertically reinforced CMU | 62000 | 34760 | 46500 | 0 | 0 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | OG6 | 181 - OG6 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG6-01830 | 1414 | 2" Face brick | 107000 | 161546 | 0 | 53500 | 53500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107000 | OG6 | 181 - OG6 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG6-01820 | 1416 | Coping stone C1/A-300 | 66000 | 12375 | 0 | 0 | 0 | 22000 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 66000 | OG6 | 181 - OG6 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05290 | 1417 | MATERIAL AND FABRICATION | 15000 | 16765 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG6 | 182 - OG6 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG6-01315 | 1419 | INSTALLATION | 18000 | 19800 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | OG6 | 182 - OG6 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG6-01860 | 1420 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | OG6 | 182 - OG6 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG6-01330 | 1428 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG6 | 184 - OG6 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01325 | 1431 | Layout | 1875 | 3858 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01325 | 1432 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01325 | 1433 | Framing & Drywall - Materials | 7750 | 11829 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01325 | 1434 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9625 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01330 | 1435 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8875 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01330 | 1436 | Tape/ Spackle finishes | 5750 | 11829 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG6-01855 | 1437 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | OG6 | 185 - OG6 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG2-01820 | 1440 | 6" vertically reinforced CMU | 166000 | 125840 | 157700 | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166000 | SG2 | 017 - SG2 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG2-01830 | 1451 | 2" Face brick | 177000 | 357280 | 141600 | 0 | 0 | 35400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177000 | SG2 | 017 - SG2 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG6-03005 | 1466 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 7422.6 | 1649.4667 | 1649.4667 | 1649.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1467 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 2394 | 2634 | 1915.2 | 159.6 | 159.6 | 159.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2394 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1468 | ESCUTCHEONS FOR PLUMBING PIPING | 1500 | 1650 | 1200 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1469 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3791 | 4171 | 2274.6 | 505.4667 | 505.4667 | 505.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3791 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1470 | HANGERS AND SUPPORTS | 10477.5 | 11526 | 7858.125 | 873.125 | 873.125 | 873.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10477.5 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1471 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1472 | DOMESTIC WATER PIPING | 178020 | 195822 | 160218 | 5934 | 5934 | 5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178020 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG2-01820 | 1473 | Coping Stone C1/A-300 | 181000 | 30958 | 181000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181000 | SG2 | 017 - SG2 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG6-03005 | 1474 | DOMESTIC WATER PIPING SPECIALTIES | 14799 | 16279 | 12579.15 | 739.95 | 739.95 | 739.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14799 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1475 | SANITARY WASTE PIPING | 34117 | 37529 | 32411.15 | 568.6167 | 568.6167 | 568.6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34117 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1476 | SANITARY WASTE PIPING SPECIALTIES | 147470 | 162217 | 132723 | 4915.6667 | 4915.6667 | 4915.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147470 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1477 | STORM DRAINAGE PIPING SPECIALTIES | 48720 | 53592 | 31668 | 5684 | 5684 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48720 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03030 | 1478 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 210000 | 231000 | 115500 | 31500 | 31500 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1479 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 12070 | 13277 | 12070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12070 | OG6 | 188 - OG6 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG6-03005 | 1480 | Plumbing Pipe Insulation | 64100 | 35464 | 48075 | 0 | 8012.5 | 8012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64100 | OG6 | 188 - OG6 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OG6-02045 | 1481 | Heat Trace | 5000 | 5475 | 0 | 0 | 4285.7143 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | 0 | 5000 | OG6 | 188 - OG6 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGE-M-01005 | 1482 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 1483 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
05470 | 1484 | MATERIAL AND FABRICATION | 5000 | 5824 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG2 | 018 - SG2 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG6-03112 | 1485 | Exhaust Fans: Install | 11450 | 12595 | 5725 | 0 | 2024.4873 | 3700.5127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11450 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1486 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03032 | 1487 | Steam Unit Heaters: Install | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1488 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03032 | 1489 | Condensate Return Unit: Install | 20000 | 22000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03112 | 1490 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03112 | 1491 | Heating and Ventilation Unit: Install | 21000 | 23100 | 0 | 0 | 3713.0334 | 17286.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03015 | 1492 | Steam Traps: Furnish | 2600 | 2860 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03015 | 1493 | Steam Traps: Install | 25000 | 27500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 1494 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-01315 | 1495 | INSTALLATION | 6000 | 6600 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | SG2 | 018 - SG2 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG6-03032 | 1496 | Vacuum Pump Unit: Install | 23000 | 25300 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03107 | 1497 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 239800 | 263780 | 232606 | 3597 | 3597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239800 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03007 | 1498 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 310000 | 341000 | 300700 | 4650 | 4650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1499 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 150000 | 165000 | 145500 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03025 | 1500 | Mechanical Pipe: Hydrostatic Testing | 5200 | 5720 | 0 | 2600 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 1501 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 25000 | 27500 | 24500 | 0 | 0 | 480.7692 | 0 | 0 | 0 | 19.2308 | 0 | 0 | 0 | 25000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 1502 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 50000 | 55000 | 49000 | 0 | 0 | 961.5385 | 0 | 0 | 0 | 38.4615 | 0 | 0 | 0 | 50000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03135 | 1503 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 0 | 57.6923 | 0 | 0 | 0 | 2942.3077 | 0 | 0 | 0 | 3000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1504 | Controls: Furnish and Install: Devices | 65000 | 71500 | 52000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1505 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 33250 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-01860 | 1506 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 25998 | SG2 | 018 - SG2 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG1-03120 | 1507 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 3109.7561 | 6890.2439 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 1508 | Controls: Connect to Final Termination Points | 7000 | 7700 | 0 | 0 | 0 | 2176.8293 | 4823.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-03025 | 1509 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 1865.8537 | 4134.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1510 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 0 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1511 | Insulation: Furnish and Install: Piping Insulation | 30000 | 33000 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 1512 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 18150 | 0 | 0 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | OG6 | 189 - OG6 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG6-02210 | 1513 | ATS Energization | 12500 | 13688 | 0 | 5000 | 5000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 12500 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02210 | 1514 | ATS Installation | 175000 | 191625 | 140000 | 35000 | 35000 | 0 | 0 | -11666.6667 | -11666.6667 | -11666.6667 | 0 | 0 | 0 | 175000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02210 | 1515 | ATS Terminations | 12500 | 13688 | 0 | 5000 | 5000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 12500 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02210 | 1516 | ATS Testing | 12500 | 13688 | 0 | 5000 | 5000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 12500 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02015 | 1518 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27750 | 13750 | 0 | 0 | 0 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 25000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02040 | 1519 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 136875 | 0 | 100000 | 12500 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 125000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OGE-02115 | 1520 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 0 | 0 | 0 | 135000 | 135000 | 135000 | 135000 | 0 | 0 | 0 | 0 | 540000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02020 | 1521 | Conduit - Branch Circuits (1 1/2" & Smaller) | 250000 | 273750 | 0 | 35714.2857 | 35714.2857 | 35714.2857 | 47619.0476 | 47619.0476 | 47619.0476 | 0 | 0 | 0 | 0 | 250000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02115 | 1522 | Conduit - Risers (2" & Larger) | 630000 | 689850 | 126000 | 68828.1938 | 0 | 0 | 0 | 145057.2687 | 145057.2687 | 145057.2687 | 0 | 0 | 0 | 630000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02025 | 1523 | Demolition/Temp Light & Power | 50000 | 55500 | 32500 | 2857.1429 | 2857.1429 | 2857.1429 | 2976.1905 | 2976.1905 | 2976.1905 | 0 | 0 | 0 | 0 | 50000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02145 | 1524 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 4285.7143 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | 0 | 5000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02030 | 1525 | Foundation Coring | 20000 | 21000 | 13000 | 540.9091 | 0 | 0 | 0 | 2153.0303 | 2153.0303 | 2153.0303 | 0 | 0 | 0 | 20000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02240 | 1526 | Lighting Controls | 47000 | 49350 | 23500 | 0 | 0 | 0 | 10071.4286 | 4476.1905 | 4476.1905 | 4476.1905 | 0 | 0 | 0 | 47000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02025 | 1527 | Lighting Remove & Re-install | 36900 | 40406 | 0 | 10542.8571 | 0 | 0 | 0 | 8785.7143 | 8785.7143 | 8785.7143 | 0 | 0 | 0 | 36900 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02025 | 1529 | Lighting System Program & Energize | 5000 | 5550 | 0 | 1428.5714 | 0 | 0 | 0 | 1190.4762 | 1190.4762 | 1190.4762 | 0 | 0 | 0 | 5000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02050 | 1530 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 0 | 0 | 49714.2857 | 0 | 0 | 2761.9048 | 2761.9048 | 2761.9048 | 0 | 0 | 0 | 58000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-OGE-01020 | 1531 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02245 | 1532 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 8571.4286 | 476.1905 | 476.1905 | 476.1905 | 0 | 0 | 0 | 10000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02515 | 1533 | Switchgear & Panelboard Energization | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 30000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02260 | 1534 | Switchgear & Panelboard Installation | 450000 | 492750 | 360000 | 0 | 0 | 0 | 192857.1429 | -34285.7143 | -34285.7143 | -34285.7143 | 0 | 0 | 0 | 450000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02260 | 1535 | Switchgear & Panelboard Terminations | 30000 | 32850 | 0 | 0 | 0 | 0 | 25714.2857 | 1428.5714 | 1428.5714 | 1428.5714 | 0 | 0 | 0 | 30000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02510 | 1536 | Switchgear & Panelboard Testing | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 30000 | OG6 | 190 - OG6 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02020 | 1537 | Fire Alarm Conduit | 25000 | 27375 | 0 | 3571.4286 | 3571.4286 | 3571.4286 | 4761.9048 | 4761.9048 | 4761.9048 | 0 | 0 | 0 | 0 | 25000 | OG6 | 191 - OG6 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02120 | 1538 | Fire Alarm Wiring | 22500 | 24638 | 0 | 0 | 0 | 11250 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 22500 | OG6 | 191 - OG6 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02120 | 1540 | Fire Alarm Devices | 22000 | 24090 | 11000 | 0 | 0 | 5500 | 0 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 22000 | OG6 | 191 - OG6 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02120 | 1541 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 1250 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | 0 | 2500 | OG6 | 191 - OG6 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG6-02535 | 1542 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 2500 | OG6 | 191 - OG6 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG10-01013 | 1546 | Caulk | 3000 | 9000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG10-01013 | 1547 | Fibrous Slate | 170 | 510 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG10-01015 | 1548 | Demo Existing Building/Temp Light & Power | 32100 | 35150 | 32100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32100 | OG7 | 194 - OG7 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG8-01230 | 1562 | 8" CMU (3 hour rated) | 787500 | 434720 | 787500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787500 | OG8 | 196 - OG8 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
OG8-01275 | 1565 | Face Brick 3-5/8" | 205500 | 373450 | 205500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205500 | OG8 | 196 - OG8 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
OG8-01250 | 1567 | Cast Stone with SS letters | 6700 | 8650 | 0 | 6700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | OG8 | 196 - OG8 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG8-01105 | 1570 | STEEL (MATERIAL ONLY) | 210000 | 245175 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1571 | FABRICATION COSTS | 368000 | 338575 | 368000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1573 | METAL DECK (BUY-OUT) | 21000 | 24518 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1574 | ANCHORS & EMBEDS | 10000 | 11676 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1575 | SURVEYING | 15000 | 17514 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1576 | STEEL & DECK ERECTION | 700000 | 817248 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1577 | BOLTS AND HARDWARE | 20000 | 23351 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01105 | 1578 | TRUCKING | 10000 | 11676 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG8 | 197 - OG8 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG8-01270 | 1579 | Dunnage Grating Galvanized | 66023 | 72626 | 16505.75 | 49517.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66023 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01270 | 1580 | Dunnage Guard Rail | 29625 | 32588 | 29625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29625 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01270 | 1581 | Dunnage Stair and Railing (1) | 12038 | 13242 | 10834.2 | 0 | 1203.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12038 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01290 | 1582 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 144130 | 172065 | 144130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144130 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01290 | 1584 | Stair B: Stair, Landing and Hand & Guard Rail | 74111 | 81523 | 74111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74111 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01295 | 1585 | 1st to 2nd Floor Ship Ladder with Cage and Platform Landing | 24641 | 27106 | 20944.85 | 0 | 3696.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24641 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01290 | 1586 | Egress Stair: Stair & Landing with Hand & Guard Rail | 43263 | 47590 | 10815.75 | 0 | 0 | 32447.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43263 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01305 | 1587 | Layout | 11875 | 9195 | 11875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11875 | OG8 | 198 - OG8 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01305 | 1588 | Loading | 34000 | 26857 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | OG8 | 198 - OG8 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01305 | 1589 | Exterior Framing, Insulation & Drywall - Materials | 102500 | 116188 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102500 | OG8 | 198 - OG8 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01305 | 1590 | Exterior Framing- Labor | 55500 | 64809 | 55500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55500 | OG8 | 198 - OG8 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG2-01330 | 1594 | Doors, Frames & Hardware - Labor | 3500 | 7784 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | SG2 | 020 - SG2 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-01305 | 1596 | Insulation- Labor | 8500 | 10399 | 6375 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | OG8 | 199 - OG8 - Division 7 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01255 | 1599 | Layout | 131466 | 138040 | 0 | 0 | 43822 | 43822 | 43822 | 0 | 0 | 0 | 0 | 0 | 0 | 131466 | OG8 | 199 - OG8 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG8-01255 | 1600 | Framing | 313010 | 328661 | 313010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313010 | OG8 | 199 - OG8 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG8-01255 | 1601 | Insulation | 56061 | 58865 | 56061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56061 | OG8 | 199 - OG8 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG8-01255 | 1602 | Cladding Install | 392430 | 412052 | 19621.5 | 0 | 124269.5 | 124269.5 | 124269.5 | 0 | 0 | 0 | 0 | 0 | 0 | 392430 | OG8 | 199 - OG8 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG8-01225 | 1603 | Fireproofing | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG8 | 199 - OG8 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
OG8-01265 | 1604 | P&I Cold Applied Roof Membrane | 152230 | 151996 | 106561 | 0 | 0 | 45669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152230 | OG8 | 199 - OG8 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG8-01265 | 1606 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 160940 | 160693 | 70454.6291 | 0 | 0 | 90485.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160940 | OG8 | 199 - OG8 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG8-01265 | 1607 | P&I Aluminum Coping | 9660 | 9240 | 0 | 0 | 0 | 9660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9660 | OG8 | 199 - OG8 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG8-01245 | 1609 | Doors, Frames & Hardware - Labor | 15750 | 35030 | 5395.3754 | 2406.9354 | 4496.1462 | 3451.543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750 | OG8 | 200 - OG8 - Division 8 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01317 | 1610 | Louvers Install | 51389 | 102778 | 0 | 0 | 17129.6667 | 17129.6667 | 17129.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 51389 | OG8 | 200 - OG8 - Division 8 | 0% | Navillus | 0 | NEW BUILDINGS
08080 | 1611 | Overhead Door | 11316 | 16000 | 0 | 0 | 0 | 5658 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 11316 | OG8 | 200 - OG8 - Division 8 | 0% | Loading Dock | 0 | NEW BUILDINGS
OG8-01305 | 1613 | Sheathing & Drywall - Labor | 42375 | 87184 | 0 | 0 | 14581.2305 | 14581.2305 | 13212.539 | 0 | 0 | 0 | 0 | 0 | 0 | 42375 | OG8 | 201 - OG8 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01245 | 1614 | Tape/ Spackle finishes | 20125 | 41405 | 0 | 7290.7861 | 7290.7861 | 5543.4277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20125 | OG8 | 201 - OG8 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01315 | 1615 | ACT ceilings - Materials | 625 | 1286 | 0 | 0 | 468.75 | 156.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | OG8 | 201 - OG8 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG2-01325 | 1616 | Layout | 3125 | 2315 | 0 | 1041.6667 | 1041.6667 | 1041.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-01315 | 1617 | ACT ceilings - Labor | 1500 | 3086 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | OG8 | 201 - OG8 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01280 | 1618 | Direct Applied Stucco | 12800 | 26335 | 0 | 6400 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | OG8 | 201 - OG8 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG8-01325 | 1619 | Painting OG-8 | 55000 | 110000 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | OG8 | 201 - OG8 - Division 9 | 0% | GG Paint | 0 | NEW BUILDINGS
SG2-01325 | 1627 | Loading | 1750 | 3601 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-03105 | 1630 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 3764 | 294.0625 | 294.0625 | 0 | 117.625 | 117.625 | 117.625 | 0 | 0 | 0 | 0 | 4705 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1631 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4560 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1632 | ESCUTCHEONS FOR PLUMBING PIPING | 2000 | 2200 | 1900 | 0 | 0 | 0 | 33.3333 | 33.3333 | 33.3333 | 0 | 0 | 0 | 0 | 2000 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1633 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 13800 | 15180 | 13110 | 345 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1634 | HANGERS AND SUPPORTS | 19803 | 21784 | 18812.85 | 495.075 | 495.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19803 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1635 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2490 | 2739 | 0 | 830 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1636 | DOMESTIC WATER PIPING | 188497 | 207347 | 179072.15 | 6126.1525 | 0 | 0 | 1099.5658 | 1099.5658 | 1099.5658 | 0 | 0 | 0 | 0 | 188497 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1637 | DOMESTIC WATER PIPING SPECIALTIES | 13040 | 14344 | 12648.8 | 195.6 | 195.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13040 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG2-01325 | 1638 | Framing & Drywall - Materials | 5375 | 3858 | 0 | 1791.6667 | 1791.6667 | 1791.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5375 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-03105 | 1639 | SANITARY WASTE PIPING | 133476 | 146824 | 129471.72 | 2002.14 | 2002.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133476 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1640 | SANITARY WASTE PIPING SPECIALTIES | 27034 | 29738 | 25682.3 | 450.5667 | 450.5667 | 450.5667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27034 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1641 | STORM DRAINAGE PIPING SPECIALTIES | 67032 | 73736 | 67032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67032 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03140 | 1642 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 14880 | 16368 | 4464 | 3472 | 3472 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14880 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03140 | 1643 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 3648 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218880 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1644 | GAS SERVICE AND PIPING | 362208 | 398429 | 325987.2 | 13582.8 | 0 | 0 | 7546 | 7546 | 7546 | 0 | 0 | 0 | 0 | 362208 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03140 | 1645 | PLUMBING FIXTURES | 16720 | 18392 | 0 | 5573.3333 | 5573.3333 | 5573.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16720 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03140 | 1646 | EMERGENCY PLUMBING FIXTURES | 4640 | 5104 | 0 | 1546.6667 | 1546.6667 | 1546.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4640 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1647 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13728 | 15101 | 13728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13728 | OG8 | 203 - OG8 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG8-03105 | 1648 | Plumbing Pipe Insulation | 7600 | 8895 | 0 | 0 | 0 | 3800 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | OG8 | 203 - OG8 - Division 22 | 0% | Tristan | 0 | NEW BUILDINGS
SG2-01325 | 1649 | Framing- Labor | 2750 | 5658 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-02150 | 1650 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | OG8 | 203 - OG8 - Division 22 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-OGP1-M-01005 | 1651 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03112 | 1652 | Exhaust Fans: Furnish | 7200 | 7920 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1653 | Exhaust Fans: Install | 36400 | 40040 | 36400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36400 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1654 | Steam Unit Heaters: Furnish | 8000 | 8800 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1655 | Steam Unit Heaters: Install | 77500 | 85250 | 38750 | 38750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1656 | Electric Heaters: Furnish | 5000 | 5500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1657 | Condensate Return Unit: Furnish | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1658 | Condensate Return Unit: Install | 53500 | 58850 | 53500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1659 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG2-01330 | 1660 | Drywall - Labor | 2625 | 5401 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-03142 | 1661 | Heating and Ventilation Unit: Install | 42500 | 46750 | 0 | 21250 | 21250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1662 | Steam Traps: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1663 | Steam Traps: Install | 46000 | 50600 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1664 | Steam Separator: Furnish | 48000 | 52800 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1665 | Steam Separator: Install | 349500 | 384450 | 349500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03210 | 1666 | Low Pressure Steam Boilers: Install | 189500 | 208450 | 189500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1667 | Boiler Feed Unit: Furnish | 75000 | 82500 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03242 | 1668 | Boiler Feed Unit: Install | 49500 | 54450 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1669 | Fuel Oil Pump: Furnish | 70000 | 77000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 1670 | Fuel Oil Pump: Install | 49500 | 54450 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG2-01330 | 1671 | Tape/ Spackle finishes | 2250 | 4629 | 0 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-03142 | 1672 | Fuel Oil Storage Tank: Furnish | 65000 | 71500 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03110 | 1673 | Fuel Oil Storage Tank: Install | 59500 | 65450 | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03110 | 1674 | Rigging | 259500 | 285450 | 259500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03107 | 1675 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 654000 | 719400 | 654000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 1676 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 863000 | 949300 | 863000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 1677 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 345000 | 379500 | 338100 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03242 | 1678 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 350000 | 385000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03135 | 1679 | Mechanical Pipe: Hydrostatic Testing | 11000 | 12100 | 9350 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 1680 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 90000 | 99000 | 81000 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03110 | 1681 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 175000 | 192500 | 157500 | 4375 | 4375 | 4375 | 4375 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG2-01855 | 1682 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | SG2 | 021 - SG2 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
OG8-03245 | 1683 | HVAC Ductwork: Testing & Balancing | 10000 | 11000 | 0 | 481.8182 | 0 | 0 | 3172.7273 | 3172.7273 | 3172.7273 | 0 | 0 | 0 | 0 | 10000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1684 | Controls: Furnish and Install: Devices | 250000 | 275000 | 125000 | 41666.6667 | 41666.6667 | 41666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1685 | Controls: Furnish and Install: Controls Conduit | 110000 | 121000 | 82500 | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1686 | Controls: Furnish and Install: Controls Wiring | 30000 | 33000 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1687 | Controls: Connect to Final Termination Points | 20000 | 22000 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03135 | 1688 | Controls: Controls Testing | 17300 | 19030 | 0 | 5766.6667 | 5766.6667 | 5766.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17300 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 1689 | Insulation: Furnish and Install: Ductwork Insulation | 55000 | 60500 | 0 | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 1690 | Insulation: Furnish and Install: Piping Insulation | 115000 | 126500 | 23000 | 34244.4444 | 57755.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 1691 | Insulation: Furnish and Install: Equipment Insulation | 55000 | 60500 | 0 | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03242 | 1692 | Furnish and Install: Chemical Feed Equipment | 9300 | 10230 | 4650 | 1550 | 1550 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9300 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03242 | 1694 | Chemical Cleaning | 7500 | 8250 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | OG8 | 204 - OG8 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-02255 | 1695 | ATS Energization | 15000 | 16425 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 15000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02255 | 1696 | ATS Installation | 210000 | 229950 | 189000 | 0 | 0 | 0 | 7000 | 7000 | 7000 | 0 | 0 | 0 | 0 | 210000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02255 | 1697 | ATS Terminations | 15000 | 16425 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 15000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02255 | 1698 | ATS Testing | 15000 | 16425 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 15000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02130 | 1699 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 219000 | 100000 | 0 | 0 | 0 | 33333.3333 | 33333.3333 | 33333.3333 | 0 | 0 | 0 | 0 | 200000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02490 | 1700 | Cabling - Risers & Feeders (2/0 & Larger) | 450000 | 492750 | 0 | 0 | 429545.4545 | 20454.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02115 | 1701 | Conduit - Branch Circuits (1 1/2" & Smaller) | 150000 | 164250 | 127500 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 150000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02205 | 1702 | Conduit - In-Slab | 198000 | 216810 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02010 | 1703 | Conduit - Risers (2" & Larger) | 405000 | 443475 | 384750 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 0 | 0 | 0 | 0 | 405000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02495 | 1705 | Firestopping | 5000 | 5250 | 3000 | 0 | 1000 | 500 | 166.6667 | 166.6667 | 166.6667 | 0 | 0 | 0 | 0 | 5000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-OG8-01170 | 1706 | Generator Delivery | 75000 | 78750 | 0 | 37500 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 75000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-OG8-01010 | 1707 | Generator Release | 450000 | 472500 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02420 | 1708 | Generator Terminations | 75000 | 78750 | 0 | 0 | 0 | 69642.8571 | 1785.7143 | 1785.7143 | 1785.7143 | 0 | 0 | 0 | 0 | 75000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02730 | 1709 | Generator Test | 75000 | 78750 | 37500 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 75000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02120 | 1710 | Lighting Controls | 14000 | 14700 | 7000 | 0 | 0 | 0 | 2333.3333 | 2333.3333 | 2333.3333 | 0 | 0 | 0 | 0 | 14000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02140 | 1711 | Lighting Install | 138000 | 144900 | 124200 | 6960.5263 | 0 | 0 | 2279.8246 | 2279.8246 | 2279.8246 | 0 | 0 | 0 | 0 | 138000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02140 | 1712 | Lighting Rough | 138000 | 151110 | 131100 | 2784.2105 | 0 | 0 | 1371.9298 | 1371.9298 | 1371.9298 | 0 | 0 | 0 | 0 | 138000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02140 | 1713 | Lighting System Program & Energize | 5000 | 5475 | 0 | 1008.7719 | 0 | 0 | 1330.4094 | 1330.4094 | 1330.4094 | 0 | 0 | 0 | 0 | 5000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02425 | 1714 | Lightning Protection | 20000 | 21900 | 10000 | 0 | 0 | 8571.4286 | 476.1905 | 476.1905 | 476.1905 | 0 | 0 | 0 | 0 | 20000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02145 | 1716 | Mechanical Terminations(Dampers, Heaters, Motors) | 150000 | 164250 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 150000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-OGP1-E-01010 | 1717 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02160 | 1718 | Switches and Receptacles | 20000 | 21900 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 20000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02725 | 1719 | Switchgear & Panelboard Energization | 22500 | 24638 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 22500 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02275 | 1720 | Switchgear & Panelboard Installation | 270000 | 295650 | 202500 | 9642.8571 | 9642.8571 | 9642.8571 | 12857.1429 | 12857.1429 | 12857.1429 | 0 | 0 | 0 | 0 | 270000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02275 | 1721 | Switchgear & Panelboard Terminations | 22500 | 24638 | 0 | 11250 | 0 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 22500 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02720 | 1722 | Switchgear & Panelboard Testing | 22500 | 24638 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 22500 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02005 | 1723 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 50000 | OG8 | 205 - OG8 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02115 | 1724 | Fire Alarm Conduit | 62500 | 68438 | 53125 | 0 | 0 | 0 | 3125 | 3125 | 3125 | 0 | 0 | 0 | 0 | 62500 | OG8 | 206 - OG8 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02480 | 1725 | Fire Alarm Wiring | 60000 | 65700 | 30000 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 60000 | OG8 | 206 - OG8 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02480 | 1727 | Fire Alarm Devices | 128000 | 140160 | 108800 | 0 | 0 | 0 | 6400 | 6400 | 6400 | 0 | 0 | 0 | 0 | 128000 | OG8 | 206 - OG8 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02480 | 1728 | Fire Alarm Programming & Pretest | 2500 | 2750 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | OG8 | 206 - OG8 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02740 | 1729 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | OG8 | 206 - OG8 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-01230 | 1749 | 8" CMU (3 hour rated) | 301500 | 101420 | 301500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301500 | OG9 | 209 - OG9 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
OG9-01275 | 1752 | Face Brick 3-5/8" | 70500 | 99578 | 70500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70500 | OG9 | 209 - OG9 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
OG9-01250 | 1754 | Cast Stone with SS letters | 105000 | 142454 | 81078.8044 | 20503.882 | 3417.3137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | OG9 | 209 - OG9 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG9-01105 | 1757 | STEEL (MATERIAL ONLY) | 88000 | 101945 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1758 | FABRICATION COSTS | 180000 | 173771 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1760 | METAL DECK (BUY-OUT) | 6500 | 7531 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1761 | ANCHORS & EMBEDS | 6000 | 6951 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1762 | SURVEYING | 8500 | 9848 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1763 | STEEL & DECK ERECTION | 300000 | 347540 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1764 | BOLTS AND HARDWARE | 6000 | 6951 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01105 | 1765 | TRUCKING | 5000 | 5793 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | OG9 | 210 - OG9 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG9-01270 | 1766 | Dunnage Grating | 21443 | 23588 | 21443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21443 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01290 | 1767 | Railing | 10698 | 11768 | 10698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10698 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01270 | 1768 | Dunnage Stair and Railing | 15800 | 17380 | 15800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15800 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01290 | 1769 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 128933 | 141827 | 128933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128933 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01295 | 1771 | 1st to 2nd Floor Ship Ladder with Safety Cage and Landing Platform with Rail | 22760 | 25036 | 22760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22760 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01295 | 1772 | Ship Ladder Bulkhead Roof | 6395 | 7035 | 6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6395 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01305 | 1773 | Layout | 7625 | 3065 | 7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7625 | OG9 | 211 - OG9 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01305 | 1774 | Loading | 12750 | 10218 | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12750 | OG9 | 211 - OG9 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01305 | 1775 | Exterior Framing, Insulation & Drywall - Materials | 40875 | 37221 | 40875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40875 | OG9 | 211 - OG9 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01305 | 1776 | Exterior Framing- Labor | 48125 | 56196 | 48125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48125 | OG9 | 211 - OG9 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01305 | 1782 | Insulation- Labor | 2375 | 2906 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375 | OG9 | 212 - OG9 - Division 7 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01255 | 1785 | Layout | 52396 | 55016 | 52396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52396 | OG9 | 212 - OG9 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG9-01255 | 1786 | Framing | 109253 | 114716 | 109253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109253 | OG9 | 212 - OG9 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG9-01255 | 1787 | Insulation | 19567 | 20546 | 19567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19567 | OG9 | 212 - OG9 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG9-01255 | 1788 | Cladding Install | 136974 | 143823 | 102730.5 | 0 | 8560.875 | 8560.875 | 8560.875 | 8560.875 | 0 | 0 | 0 | 0 | 0 | 136974 | OG9 | 212 - OG9 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG9-01225 | 1789 | Fireproofing | 27000 | 29700 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | OG9 | 212 - OG9 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
OG9-01265 | 1790 | P&I Cold Applied Roof Membrane | 56806 | 54257 | 56806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56806 | OG9 | 212 - OG9 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG9-01265 | 1791 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 72352 | 69054 | 72352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72352 | OG9 | 212 - OG9 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG9-01265 | 1793 | P&I Aluminum Coping | 6375 | 6592 | 0 | 0 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | OG9 | 212 - OG9 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG9-01245 | 1795 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 6975.7194 | 599.5204 | 299.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | OG9 | 213 - OG9 - Division 8 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01317 | 1796 | Louvers Install | 17937 | 35874 | 0 | 0 | 4484.25 | 4484.25 | 4484.25 | 4484.25 | 0 | 0 | 0 | 0 | 0 | 17937 | OG9 | 213 - OG9 - Division 8 | 0% | Navillus | 0 | NEW BUILDINGS
OG9-01305 | 1798 | Sheathing & Drywall - Labor | 9125 | 18774 | 7666.8664 | 729.0668 | 729.0668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9125 | OG9 | 214 - OG9 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01245 | 1799 | Tape/ Spackle finishes | 4500 | 9258 | 4050 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | OG9 | 214 - OG9 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01315 | 1800 | ACT ceilings - Materials | 1000 | 2058 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | OG9 | 214 - OG9 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01315 | 1801 | ACT ceilings - Labor | 2125 | 4372 | 0 | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125 | OG9 | 214 - OG9 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01280 | 1802 | Direct Applied Stucco | 6400 | 13167 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | OG9 | 214 - OG9 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG9-01325 | 1804 | Painting OG-9 | 55000 | 110000 | 0 | 0 | 0 | 23571.4286 | 31428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | OG9 | 214 - OG9 - Division 9 | 0% | GG Paint | 0 | NEW BUILDINGS
OG9-03105 | 1812 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 4469.75 | 117.625 | 117.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4705 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1813 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4656 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1815 | ESCUTCHEONS FOR PLUMBING PIPING | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1816 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 13400 | 14740 | 12998 | 134 | 134 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13400 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1817 | HANGERS AND SUPPORTS | 19936 | 21930 | 19337.92 | 199.36 | 199.36 | 199.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19936 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1818 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2490 | 2739 | 0 | 830 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1819 | DOMESTIC WATER PIPING | 153867 | 169254 | 146173.65 | 2564.45 | 2564.45 | 2564.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153867 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1820 | DOMESTIC WATER PIPING SPECIALTIES | 3120 | 3432 | 3026.4 | 31.2 | 31.2 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3120 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1821 | SANITARY WASTE PIPING | 116480 | 128128 | 112985.6 | 1456 | 1456 | 582.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116480 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1822 | SANITARY WASTE PIPING SPECIALTIES | 17318 | 19050 | 17318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17318 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1823 | STORM DRAINAGE PIPING SPECIALTIES | 37320 | 41052 | 37320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37320 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03140 | 1824 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 9200 | 10120 | 4600 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03140 | 1826 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 3648 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218880 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1827 | GAS SERVICE AND PIPING | 204340 | 224774 | 194123 | 3405.6667 | 3405.6667 | 3405.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204340 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03140 | 1828 | PLUMBING FIXTURES | 12879 | 14167 | 1287.9 | 3863.7 | 3863.7 | 3863.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12879 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1829 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG9 | 216 - OG9 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG9-03105 | 1830 | Plumbing Pipe Insulation | 12500 | 3175 | 0 | 0 | 0 | 6250 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | OG9 | 216 - OG9 - Division 22 | 0% | Tristan | 0 | NEW BUILDINGS
OG9-02130 | 1831 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | OG9 | 216 - OG9 - Division 22 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-OGW-M-01005 | 1832 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03112 | 1833 | Exhaust Fans: Furnish | 6000 | 6600 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03142 | 1834 | Exhaust Fans: Install | 19750 | 21725 | 19750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19750 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1835 | Electric Unit Heaters: Furnish | 2500 | 2750 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1837 | Steam Unit Heater: Furnish | 5000 | 5500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03142 | 1838 | Steam Unit Heater: Install | 44000 | 48400 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1839 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03142 | 1840 | Condensate Return Unit: Install | 26000 | 28600 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03142 | 1841 | Steam Traps: Furnish | 600 | 660 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03142 | 1842 | Steam Traps: Install | 10000 | 11000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03107 | 1843 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 165250 | 181775 | 165250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165250 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03107 | 1844 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 193500 | 212850 | 193500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193500 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 1845 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 91500 | 100650 | 91500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91500 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03135 | 1846 | Mechanical Pipe: Hydrostatic Testing | 2750 | 3025 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03107 | 1848 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 17250 | 18975 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17250 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03110 | 1849 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03145 | 1850 | HVAC Ductwork: Testing & Balancing | 2000 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1851 | Controls: Furnish and Install: Devices | 90000 | 99000 | 28800 | 0 | 0 | 45243.2432 | 12952.7027 | 3004.0541 | 0 | 0 | 0 | 0 | 0 | 90000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1852 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 17500 | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1853 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 5027.027 | 1439.1892 | 3533.7838 | 0 | 0 | 0 | 0 | 0 | 10000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 1854 | Controls: Connect to Final Termination Points | 7000 | 7700 | 0 | 0 | 0 | 3518.9189 | 1007.4324 | 2473.6486 | 0 | 0 | 0 | 0 | 0 | 7000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-03135 | 1855 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 3016.2162 | 863.5135 | 2120.2703 | 0 | 0 | 0 | 0 | 0 | 6000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 1856 | Insulation: Furnish and Install: Ductwork Insulation | 11000 | 12100 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 1857 | Insulation: Furnish and Install: Piping Insulation | 23000 | 25300 | 0 | 0 | 0 | 11500 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 1859 | Insulation: Furnish and Install: Equipment Insulation | 11000 | 12100 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OG9 | 217 - OG9 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG9-02275 | 1860 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02275 | 1861 | ATS Installation | 140000 | 153300 | 133000 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02275 | 1862 | ATS Terminations | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02275 | 1863 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02125 | 1864 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 75000 | 30000 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 75000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02255 | 1865 | Cabling - Risers & Feeders (2/0 & Larger) | 324000 | 354780 | 0 | 46285.7143 | 46285.7143 | 46285.7143 | 61714.2857 | 61714.2857 | 61714.2857 | 0 | 0 | 0 | 0 | 324000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02115 | 1866 | Conduit - Branch Circuits (1 1/2" & Smaller) | 75000 | 83250 | 63750 | 0 | 0 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 75000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02105 | 1867 | Conduit - In-Slab | 115500 | 126473 | 115500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115500 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02010 | 1868 | Conduit - Risers (2" & Larger) | 270000 | 299700 | 256500 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 270000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02400 | 1870 | Firestopping | 5000 | 5250 | 2500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 5000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-OG9-01046 | 1871 | Generator Delivery | 50000 | 52500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-OG9-01010 | 1872 | Generator Release | 300000 | 315000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02335 | 1873 | Generator Terminations | 50000 | 52500 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | 0 | 0 | 50000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02530 | 1874 | Generator Test | 50000 | 52500 | 25000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 50000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02160 | 1875 | Lighting Controls | 8000 | 8400 | 4800 | 0 | 0 | 0 | 1066.6667 | 1066.6667 | 1066.6667 | 0 | 0 | 0 | 0 | 8000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02140 | 1876 | Lighting Install | 68400 | 71820 | 54720 | 0 | 0 | 0 | 4560 | 4560 | 4560 | 0 | 0 | 0 | 0 | 68400 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02140 | 1877 | Lighting Rough | 68400 | 74898 | 64980 | 1710 | 1710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68400 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02140 | 1878 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG8-02310 | 1879 | Lightning Protection | 20000 | 21900 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02145 | 1881 | Mechanical Terminations(Dampers, Heaters, Motors) | 60000 | 66600 | 18000 | 0 | 0 | 0 | 14000 | 14000 | 14000 | 0 | 0 | 0 | 0 | 60000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-OGW-E-01015 | 1882 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02155 | 1883 | Switches and Receptacles | 10000 | 10950 | 1500 | 0 | 0 | 0 | 2833.3333 | 2833.3333 | 2833.3333 | 0 | 0 | 0 | 0 | 10000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02515 | 1884 | Switchgear & Panelboard Energization | 17500 | 19163 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 17500 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02260 | 1885 | Switchgear & Panelboard Installation | 210000 | 229950 | 199500 | 9000 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02260 | 1886 | Switchgear & Panelboard Terminations | 17500 | 19163 | 0 | 15000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 17500 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02510 | 1887 | Switchgear & Panelboard Testing | 17500 | 19425 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 17500 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02005 | 1888 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 50000 | OG9 | 218 - OG9 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02115 | 1889 | Fire Alarm Conduit | 25000 | 27375 | 22500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 25000 | OG9 | 219 - OG9 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02365 | 1890 | Fire Alarm Wiring | 22500 | 24638 | 2250 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 0 | 0 | 0 | 0 | 22500 | OG9 | 219 - OG9 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02365 | 1892 | Fire Alarm Devices | 33000 | 36135 | 16500 | 0 | 0 | 0 | 5500 | 5500 | 5500 | 0 | 0 | 0 | 0 | 33000 | OG9 | 219 - OG9 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02365 | 1893 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | OG9 | 219 - OG9 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG9-02535 | 1894 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | OG9 | 219 - OG9 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-01230 | 1914 | 6" CMU (2 hour rated) | 520500 | 140624 | 520500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520500 | OG10 | 222 - OG10 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
OG10-01275 | 1916 | Face Brick 3-5/8" | 190500 | 93486 | 190500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190500 | OG10 | 222 - OG10 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
OG10-01250 | 1918 | Cast Stone with SS letters | 5228.3 | 6487 | 2614.15 | 0 | 871.3833 | 871.3833 | 871.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 5228.3 | OG10 | 222 - OG10 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG10-01105 | 1921 | STEEL (MATERIAL ONLY) | 88000 | 102320 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1922 | FABRICATION COSTS | 229500 | 226149 | 229500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229500 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1923 | METAL DECK (BUY-OUT) | 10000 | 11629 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1925 | ANCHORS & EMBEDS | 6000 | 6978 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1926 | SURVEYING | 8500 | 9884 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1927 | STEEL & DECK ERECTION | 300000 | 348817 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1928 | BOLTS AND HARDWARE | 6000 | 6978 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01105 | 1929 | TRUCKING | 6000 | 6978 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | OG10 | 223 - OG10 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
OG10-01270 | 1930 | Dunnage Grating Galvanized | 18151 | 19967 | 18151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18151 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01270 | 1931 | Dunnage Stair with Guard Railing | 19938 | 21932 | 19938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19938 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01290 | 1932 | Stair B: First Floor to Roof Stair and Landing with Hand & Guard Rail | 112703 | 123974 | 112703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112703 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01295 | 1933 | Ship Ladder First Floor to Second Floor with Cage and Upper Platform | 15236 | 16760 | 15236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15236 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01295 | 1934 | Ship Ladder Bulkhead | 6395 | 7035 | 6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6395 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01305 | 1936 | Layout | 7375 | 6292 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375 | OG10 | 224 - OG10 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01305 | 1937 | Loading | 17875 | 17370 | 17875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17875 | OG10 | 224 - OG10 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01305 | 1938 | Exterior Framing, Insulation & Drywall - Materials | 53375 | 57656 | 53375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53375 | OG10 | 224 - OG10 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01305 | 1939 | Exterior Framing- Labor | 81375 | 84514 | 81375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81375 | OG10 | 224 - OG10 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01305 | 1944 | Insulation- Labor | 3875 | 4740 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3875 | OG10 | 225 - OG10 - Division 7 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01255 | 1948 | Layout | 84988 | 89238 | 84988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84988 | OG10 | 225 - OG10 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG10-01255 | 1949 | Framing | 193240 | 202902 | 193240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193240 | OG10 | 225 - OG10 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG10-01255 | 1950 | Insulation | 34610 | 36341 | 34610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34610 | OG10 | 225 - OG10 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG10-01255 | 1951 | Cladding Install | 242272 | 254386 | 230158.4 | 4037.8667 | 4037.8667 | 4037.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242272 | OG10 | 225 - OG10 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
OG10-01225 | 1952 | Fireproofing | 34000 | 37400 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | OG10 | 225 - OG10 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
OG10-01265 | 1953 | P&I Cold Applied Roof Membrane | 48880 | 48805 | 48880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48880 | OG10 | 225 - OG10 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG10-01265 | 1954 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 59800 | 59708 | 59800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59800 | OG10 | 225 - OG10 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG10-01265 | 1955 | P&I Aluminum Coping | 6417 | 6138 | 0 | 0 | 6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6417 | OG10 | 225 - OG10 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
OG10-01245 | 1958 | Doors, Frames & Hardware - Labor | 8500 | 18906 | 7600.8146 | 599.457 | 0 | 299.7285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | OG10 | 226 - OG10 - Division 8 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01317 | 1959 | Louvers Install | 31726 | 63452 | 0 | 15863 | 15863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31726 | OG10 | 226 - OG10 - Division 8 | 0% | Navillus | 0 | NEW BUILDINGS
OG10-01305 | 1961 | Sheathing & Drywall - Labor | 17750 | 36519 | 17750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17750 | OG10 | 227 - OG10 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01245 | 1962 | Tape/ Spackle finishes | 6875 | 14144 | 6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6875 | OG10 | 227 - OG10 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01315 | 1963 | ACT ceilings - Materials | 1500 | 3086 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | OG10 | 227 - OG10 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01315 | 1964 | ACT ceilings - Labor | 7250 | 14915 | 0 | 0 | 7250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7250 | OG10 | 227 - OG10 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01280 | 1965 | Direct Applied Stucco | 20200 | 41559 | 0 | 10478.8806 | 9721.1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20200 | OG10 | 227 - OG10 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
OG10-01325 | 1966 | Painting OG-10 | 55000 | 110000 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | OG10 | 227 - OG10 - Division 9 | 0% | GG Paint | 0 | NEW BUILDINGS
SG2-03005 | 1968 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 0 | 0 | 1030.9167 | 1030.9167 | 1030.9167 | 0 | 0 | 0 | 0 | 0 | 12371 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-03105 | 1974 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 4234.5 | 235.25 | 235.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4705 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1975 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4560 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1976 | ESCUTCHEONS FOR PLUMBING PIPING | 2000 | 2200 | 1940 | 25 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1977 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 17200 | 18920 | 16340 | 215 | 215 | 215 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 17200 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1978 | HANGERS AND SUPPORTS | 19936 | 21930 | 19337.92 | 598.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19936 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG2-03005 | 1979 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1000 | 1100 | 700 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 1000 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-03105 | 1980 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2490 | 2739 | 2241 | 0 | 0 | 0 | 0 | 166 | 83 | 0 | 0 | 0 | 0 | 2490 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1981 | DOMESTIC WATER PIPING | 199920 | 219912 | 189924 | 9996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199920 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1982 | DOMESTIC WATER PIPING SPECIALTIES | 27440 | 30184 | 26068 | 1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27440 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1983 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 82500 | 71250 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1984 | SANITARY WASTE PIPING | 119990 | 131989 | 117590.2 | 799.9333 | 799.9333 | 799.9333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119990 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1985 | SANITARY WASTE PIPING SPECIALTIES | 18240 | 20064 | 18240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18240 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1986 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03140 | 1987 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 14880 | 16368 | 4910.4 | 3720 | 3720 | 2529.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14880 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03140 | 1988 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 3648 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218880 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1989 | GAS SERVICE AND PIPING | 222480 | 244728 | 211356 | 5562 | 5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222480 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG2-03005 | 1990 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 498 | 0 | 0 | 166 | 166 | 166 | 0 | 0 | 0 | 0 | 0 | 996 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-03140 | 1991 | PLUMBING FIXTURES | 16720 | 18392 | 1672 | 5016 | 5016 | 5016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16720 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1992 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 29000 | 31900 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | OG10 | 229 - OG10 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
OG10-03105 | 1993 | Plumbing Pipe Insulation | 7800 | 2317 | 0 | 0 | 0 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | OG10 | 229 - OG10 - Division 22 | 0% | Tristan | 0 | NEW BUILDINGS
OG10-02145 | 1994 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | OG10 | 229 - OG10 - Division 22 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-OGE-M-01005 | 1995 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03112 | 1996 | Exhaust Fans: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03410 | 1997 | Exhaust Fans: Install | 15750 | 17325 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1998 | Electric Unit Heaters: Furnish | 3500 | 3850 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 1999 | Steam Unit Heater: Furnish | 4000 | 4400 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03142 | 2000 | Steam Unit Heater: Install | 34000 | 37400 | 25500 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG2-03005 | 2001 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2600 | 2860 | 1300 | 0 | 0 | 433.3333 | 433.3333 | 433.3333 | 0 | 0 | 0 | 0 | 0 | 2600 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03032 | 2002 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03142 | 2003 | Condensate Return Unit: Install | 22000 | 24200 | 11000 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03142 | 2004 | Steam Traps: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03142 | 2005 | Steam Traps: Install | 10500 | 11550 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03107 | 2006 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 123450 | 135795 | 123450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123450 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03107 | 2007 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 140000 | 154000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03007 | 2008 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 75000 | 82500 | 67500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03135 | 2009 | Mechanical Pipe: Hydrostatic Testing | 1550 | 1705 | 0 | 775 | 775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03107 | 2010 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 12500 | 13750 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03110 | 2011 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 25000 | 27500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG2-03005 | 2012 | HANGERS AND SUPPORTS | 10462.5 | 11509 | 8893.125 | 0 | 0 | 523.125 | 523.125 | 523.125 | 0 | 0 | 0 | 0 | 0 | 10462.5 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-03145 | 2013 | HVAC Ductwork: Testing & Balancing | 1500 | 1650 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 2014 | Controls: Furnish and Install: Devices | 90000 | 99000 | 45000 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 90000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 2015 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 21000 | 0 | 0 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 2016 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 2925.6757 | 3358.1081 | 3716.2162 | 0 | 0 | 0 | 0 | 0 | 10000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 2017 | Controls: Connect to Final Termination Points | 7000 | 7700 | 0 | 0 | 0 | 2047.973 | 2350.6757 | 2601.3514 | 0 | 0 | 0 | 0 | 0 | 7000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-03135 | 2018 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 1755.4054 | 2014.8649 | 2229.7297 | 0 | 0 | 0 | 0 | 0 | 6000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 2019 | Insulation: Furnish and Install: Ductwork Insulation | 11000 | 12100 | 0 | 0 | 0 | 2200 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 2020 | Insulation: Furnish and Install: Piping Insulation | 22000 | 24200 | 0 | 0 | 0 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 2021 | Insulation: Furnish and Install: Equipment Insulation | 11000 | 12100 | 0 | 0 | 0 | 2200 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OG10 | 230 - OG10 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG10-02335 | 2022 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG2-03005 | 2023 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 1995 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-02335 | 2024 | ATS Installation | 140000 | 153300 | 133000 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02335 | 2025 | ATS Terminations | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02335 | 2026 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02125 | 2027 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 75000 | 37500 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 75000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02395 | 2028 | Cabling - Risers & Feeders (2/0 & Larger) | 270000 | 295650 | 0 | 0 | 0 | 67500 | 67500 | 67500 | 67500 | 0 | 0 | 0 | 0 | 270000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02115 | 2029 | Conduit - Branch Circuits (1 1/2" & Smaller) | 75000 | 82125 | 67500 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 75000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02105 | 2030 | Conduit - In-Slab | 115500 | 126473 | 115500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115500 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02110 | 2031 | Conduit - Risers (2" & Larger) | 288000 | 315360 | 273600 | 0 | 0 | 0 | 4800 | 4800 | 4800 | 0 | 0 | 0 | 0 | 288000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02400 | 2032 | Firestopping | 5000 | 5250 | 3750 | 0 | 0 | 937.5 | 104.1667 | 104.1667 | 104.1667 | 0 | 0 | 0 | 0 | 5000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-OG10-01145 | 2033 | Generator Delivery | 50000 | 52500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG2-03005 | 2034 | DOMESTIC WATER PIPING | 105165 | 115682 | 89390.25 | 0 | 0 | 5258.25 | 5258.25 | 5258.25 | 0 | 0 | 0 | 0 | 0 | 105165 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
P-OG10-01010 | 2035 | Generator Release | 300000 | 315000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02315 | 2036 | Generator Terminations | 50000 | 52500 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | 0 | 0 | 50000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02535 | 2037 | Generator Test | 50000 | 52500 | 25000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 50000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02160 | 2038 | Lighting Controls | 20000 | 21000 | 10000 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 20000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02135 | 2039 | Lighting Install | 54000 | 56700 | 40500 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 54000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02240 | 2040 | Lighting Rough | 54000 | 59940 | 48600 | 2700 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02160 | 2041 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02325 | 2042 | Lightning Protection | 20000 | 21900 | 10000 | 3750 | 0 | 0 | 2083.3333 | 2083.3333 | 2083.3333 | 0 | 0 | 0 | 0 | 20000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02140 | 2043 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 17400 | 0 | 0 | 0 | 13533.3333 | 13533.3333 | 13533.3333 | 0 | 0 | 0 | 0 | 58000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-OGE-01020 | 2044 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG2-03005 | 2045 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 12580 | 0 | 0 | 740 | 740 | 740 | 0 | 0 | 0 | 0 | 0 | 14800 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-02155 | 2046 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02525 | 2047 | Switchgear & Panelboard Energization | 17500 | 19163 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 17500 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02405 | 2048 | Switchgear & Panelboard Installation | 210000 | 229950 | 199499.0868 | 0 | 0 | 6000.5219 | 4500.3914 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02405 | 2049 | Switchgear & Panelboard Terminations | 17500 | 19163 | 0 | 0 | 0 | 10000 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 17500 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02520 | 2050 | Switchgear & Panelboard Testing | 17500 | 19163 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 17500 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02005 | 2051 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 50000 | OG10 | 231 - OG10 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02115 | 2052 | Fire Alarm Conduit | 30000 | 32850 | 24000 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 30000 | OG10 | 232 - OG10 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02385 | 2053 | Fire Alarm Wiring | 30000 | 32850 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 30000 | OG10 | 232 - OG10 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02385 | 2054 | Fire Alarm Devices | 46000 | 50370 | 23000 | 0 | 0 | 0 | 7666.6667 | 7666.6667 | 7666.6667 | 0 | 0 | 0 | 0 | 46000 | OG10 | 232 - OG10 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
OG10-02385 | 2055 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | OG10 | 232 - OG10 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG2-03005 | 2056 | SANITARY WASTE PIPING | 123120 | 135432 | 110808 | 0 | 0 | 4104 | 4104 | 4104 | 0 | 0 | 0 | 0 | 0 | 123120 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG10-02540 | 2057 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | OG10 | 232 - OG10 - Division 28 | 0% | Five Star | 0 | NEW BUILDINGS
SG2-03005 | 2067 | SANITARY WASTE PIPING SPECIALTIES | 17625 | 19388 | 16743.75 | 0 | 0 | 293.75 | 293.75 | 293.75 | 0 | 0 | 0 | 0 | 0 | 17625 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG2-03005 | 2078 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 12000 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 30000 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OGE-02010 | 2081 | Manhole Work | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
OGE-02215 | 2082 | Site Lighting - Cable | 62500 | 68438 | 0 | 0 | 0 | 0 | 0 | 20833.3333 | 20833.3333 | 20833.3333 | 0 | 0 | 0 | 62500 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
OGE-02210 | 2083 | Site Lighting - Conduit | 80000 | 87600 | 60000 | 2857.1429 | 2857.1429 | 2857.1429 | 3809.5238 | 3809.5238 | 3809.5238 | 0 | 0 | 0 | 0 | 80000 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
OGE-02220 | 2084 | Site Lighting - Fixtures | 98900 | 108296 | 0 | 0 | 0 | 0 | 0 | 32966.6667 | 32966.6667 | 32966.6667 | 0 | 0 | 0 | 98900 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
SURV-OGE-01020 | 2085 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
OGE-02115 | 2086 | Underground Electric Service - Cable | 950000 | 1040250 | 617500 | 0 | 0 | 110833.3333 | 110833.3333 | 110833.3333 | 0 | 0 | 0 | 0 | 0 | 950000 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
OGE-01155 | 2087 | Underground Electric Service - Conduit | 750000 | 821250 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | OGE | 236 - OGE - Division 26 | 0% | Five Star | 0 | SITE
SG2-03030 | 2089 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 169998 | 186998 | 144498.3 | 0 | 0 | 8499.9 | 8499.9 | 8499.9 | 0 | 0 | 0 | 0 | 0 | 169998 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG2-03005 | 2100 | GAS SERVICE AND PIPING | 1920 | 2112 | 0 | 0 | 0 | 640 | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 1920 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OGE-01740 | 2104 | 4' Chain Link Fence | 21233.3333 | 23650 | 0 | 0 | 0 | 0 | 0 | 19817.7778 | 1415.5556 | 0 | 0 | 0 | 0 | 21233.3333 | OGE | 238 - OGE - Division 32 | 0% | Atlas | 0 | SITE
OGE-01745 | 2105 | 10' Chain Link Fence | 22220.9302 | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 22220.9302 | 0 | 0 | 0 | 0 | 22220.9302 | OGE | 238 - OGE - Division 32 | 0% | Atlas | 0 | SITE
OGE-01745 | 2107 | Ametco Fence | 126166.6667 | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63083.3333 | 63083.3333 | 0 | 0 | 126166.6667 | OGE | 238 - OGE - Division 32 | 0% | Atlas | 0 | SITE
OGE-01710 | 2108 | 4" CONCRETE | 45000 | 49500 | 22500 | 0 | 0 | 0 | 20892.8571 | 1607.1429 | 0 | 0 | 0 | 0 | 0 | 45000 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01710 | 2109 | 5"POROUS CONCRETE | 501200 | 551320 | 200480 | 0 | 0 | 100240 | 100240 | 100240 | 0 | 0 | 0 | 0 | 0 | 501200 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01730 | 2110 | 5" COLOR CONCRETE | 35000 | 38500 | 33250 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
SG2-03005 | 2111 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | SG2 | 024 - SG2 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OGE-01705 | 2112 | CONCRETE CURB | 35000 | 38500 | 21000 | 0 | 0 | 13333.3333 | 666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01705 | 2113 | SFC -STELL FACING CURB | 4000 | 4400 | 0 | 0 | 0 | 3809.5238 | 190.4762 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01710 | 2114 | CONCRETE STEPS | 33600 | 36960 | 25200 | 0 | 0 | 0 | 7800 | 600 | 0 | 0 | 0 | 0 | 0 | 33600 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01760 | 2118 | Deciduous Trees | 13499.7816 | 14175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749.8908 | 6749.8908 | 0 | 13499.7816 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01760 | 2119 | Evergreen Trees | 2699.5556 | 2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349.7778 | 1349.7778 | 0 | 2699.5556 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01760 | 2120 | Deciduous Shrubs | 420 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 0 | 420 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01025 | 2121 | Tree Removal | 5514.1095 | 34914 | 5514.1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5514.1095 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
SG2-03005 | 2122 | Plumbing Pipe Insulation | 25100 | 35464 | 22590 | 0 | 1255 | 1255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25100 | SG2 | 024 - SG2 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
OGE-01755 | 2123 | Lawn Seeding (not including topsoil) | 11282.2771 | 9671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5641.1385 | 5641.1385 | 0 | 11282.2771 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01025 | 2124 | Soil Erosion Mat | 7664.5957 | 6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3832.2978 | 3832.2978 | 0 | 7664.5957 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01755 | 2125 | Topsoil Stockpile/Spread | 65322.6606 | 67996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32661.3303 | 32661.3303 | 0 | 65322.6606 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01755 | 2126 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 2553.5586 | OGE | 238 - OGE - Division 32 | 0% | Aspen | 0 | SITE
OGE-01380 | 2129 | INSTALL HW, CW PIPE - OGE | 73333.33 | 231845 | 73333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73333.33 | OGE | 239 - OGE - Division 33 | 0% | Welkin | 0 | SITE
OGE-01280 | 2131 | INSTALL CONDENSATE AND STEAM PIPE - OGE | 260000 | 427171 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000 | OGE | 239 - OGE - Division 33 | 0% | Welkin | 0 | SITE
SG2-02040 | 2133 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 5000 | SG2 | 024 - SG2 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGS-M-01005 | 2144 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 2155 | Exhaust Fans: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-03112 | 2166 | Exhaust Fans: Install | 4150 | 4565 | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4150 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OGW-02010 | 2167 | Manhole Installation | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
OGW-02215 | 2168 | Site Lighting - Cable | 75000 | 82125 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 75000 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
OGW-02210 | 2169 | Site Lighting - Conduit | 70000 | 76650 | 63000 | 1500 | 1500 | 1500 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 70000 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
OG5-02250 | 2170 | Site Lighting - Fixtures | 78200 | 85629 | 0 | 0 | 0 | 0 | 0 | 26066.6667 | 26066.6667 | 26066.6667 | 0 | 0 | 0 | 78200 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
SURV-OGW-E-01015 | 2171 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
OGW-02115 | 2172 | Underground Electric Service - Cable | 1000000 | 1095000 | 750000 | 142857.1429 | 107142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
OGW-01155 | 2173 | Underground Electric Service - Conduit | 825000 | 903375 | 825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825000 | OGW | 243 - OGW - Division 26 | 0% | Five Star | 0 | SITE
OG1-03032 | 2177 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-03032 | 2188 | Steam Unit Heaters: Install | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OGW-01740 | 2191 | 4' Chain Link Fence | 88883.7209 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88883.7209 | 0 | 0 | 0 | 88883.7209 | OGW | 245 - OGW - Division 32 | 0% | Atlas | 0 | SITE
OGW-01745 | 2192 | 10' Chain Link Fence | 17282.9457 | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17282.9457 | 0 | 0 | 0 | 17282.9457 | OGW | 245 - OGW - Division 32 | 0% | Atlas | 0 | SITE
OGW-01745 | 2194 | Ametco Fence | 126166.6667 | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63083.3333 | 63083.3333 | 0 | 0 | 126166.6667 | OGW | 245 - OGW - Division 32 | 0% | Atlas | 0 | SITE
OGW-01710 | 2195 | 4" CONCRETE | 130000 | 143000 | 19500 | 0 | 36833.3333 | 36833.3333 | 36833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01710 | 2196 | 7" CONCRETE RAMP | 2500 | 2750 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01710 | 2197 | 5" POROUS CONCRETE | 417300 | 459030 | 0 | 139100 | 139100 | 139100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417300 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01730 | 2198 | 5" COLOR CONCRETE | 36000 | 39600 | 16200 | 0 | 6600 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OG2-03032 | 2199 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OGW-01705 | 2200 | CONCRETE CURB | 36000 | 39600 | 14400 | 0 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01705 | 2201 | SFC -STELL FACING CURB | 25000 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 0 | 25000 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01710 | 2202 | CONCRETE STEPS | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01760 | 2205 | Deciduous Trees | 8775.0961 | 9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4387.5481 | 4387.5481 | 0 | 8775.0961 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01760 | 2206 | Deciduous Shrubs | 2660 | 2793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330 | 1330 | 0 | 2660 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01760 | 2207 | Evergreen Shrubs | 3509.6191 | 3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754.8096 | 1754.8096 | 0 | 3509.6191 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01760 | 2208 | Perennials | 7892.5721 | 8180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.286 | 3946.286 | 0 | 7892.5721 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01755 | 2209 | Grasses | 15592.3576 | 16160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7796.1788 | 7796.1788 | 0 | 15592.3576 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
SG2-03032 | 2210 | Condensate Return Unit: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OGW-01025 | 2211 | Tree Removal | 6214.8629 | 39351 | 6214.8629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6214.8629 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01755 | 2212 | Lawn Seeding (not including topsoil) | 11191.2815 | 9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5595.6408 | 5595.6408 | 0 | 11191.2815 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01025 | 2213 | Soil Erosion Mat | 1151.9178 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575.9589 | 575.9589 | 0 | 1151.9178 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01755 | 2214 | Topsoil Stockpile/Spread | 65062.3153 | 67725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32531.1576 | 32531.1576 | 0 | 65062.3153 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
OGW-01755 | 2215 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 2553.5586 | OGW | 245 - OGW - Division 32 | 0% | Aspen | 0 | SITE
SGS-01355 | 2218 | INSTALL HW, CW PIPE - OGW | 183333.33 | 452669 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183333.33 | OGW | 246 - OGW - Division 33 | 0% | Welkin | 0 | SITE
OGW-01280 | 2220 | INSTALL CONDENSATE AND STEAM PIPE - OGW | 260000 | 622421 | 254800 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260000 | OGW | 246 - OGW - Division 33 | 0% | Welkin | 0 | SITE
SG2-03112 | 2221 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-03112 | 2232 | Heating and Ventilation Unit: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8E-01005 | 2241 | Gaskets | 33750 | 101250 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 6750 | 6750 | 33750 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01010 | 2242 | Wire Insulation | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG2-03015 | 2243 | Steam Traps: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8E-01015 | 2244 | Assumed Flooring Material (Slab Penetrations) | 3600 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 720 | 720 | 720 | 3600 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01015 | 2245 | Vinyl Membrane and Mastic | 24038 | 72114 | 0 | 0 | 0 | 0 | 0 | 0 | 4807.6 | 4807.6 | 4807.6 | 4807.6 | 4807.6 | 24038 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01015 | 2246 | Caulk | 61500 | 184500 | 17250 | 0 | 0 | 0 | 0 | 0 | 8850 | 8850 | 8850 | 8850 | 8850 | 61500 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01015 | 2247 | Fibrous Slate | 8500 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 1700 | 1700 | 1700 | 1700 | 8500 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01020 | 2248 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 662.8 | 662.8 | 662.8 | 662.8 | 662.8 | 3314 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01020 | 2249 | Underground Utility Materials | 1560 | 4680 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 312 | 312 | 312 | 312 | 1560 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG2-03015 | 2254 | Steam Traps: Install | 11000 | 12100 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-01250 | 2264 | Cast Stone with SS letters | 5370.7 | 6870 | 0 | 5370.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5370.7 | S82 | 249 - S8 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG1-03032 | 2265 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-01270 | 2266 | Dunnage Grating Galvanized | 18339 | 20173 | 18339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18339 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01270 | 2267 | Dunnage Stair and Guard Rail at 1 Location | 11850 | 13035 | 0 | 0 | 0 | 11850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11850 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01290 | 2268 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 103538 | 124892 | 93184.2 | 10353.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103538 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01295 | 2269 | Ship Ladder with Cage and Platform | 23136 | 25450 | 0 | 11568 | 11568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23136 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01295 | 2270 | Bulkhead Roof Access Ship Ladder at 2 Locations | 13919 | 15311 | 0 | 6959.5 | 6959.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13919 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8E-01860 | 2271 | Temporary Aluminum Over Pass Stair | 103992 | 114392 | 0 | 0 | 0 | 0 | 0 | 103992 | 0 | 0 | 0 | 0 | 0 | 103992 | S81 | 250 - S8 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
08080 | 2272 | Overhead Door | 11316 | 16000 | 0 | 0 | 0 | 5658 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 11316 | S82 | 251 - S8 - Division 8 | 0% | Loading Dock | 0 | NEW BUILDINGS
S8A-01325 | 2273 | Painting S8-2 | 55000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 17500 | 0 | 0 | 0 | 55000 | S82 | 252 - S8 - Division 9 | 0% | GG Paint | 0 | NEW BUILDINGS
SG2-03032 | 2276 | Vacuum Pump Unit: Install | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-03107 | 2287 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 83500 | 91850 | 83500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83500 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-03007 | 2298 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 111000 | 122100 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-03007 | 2309 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 41000 | 45100 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8E-03005 | 2313 | Plumbing Pipe Insulation | 40800 | 53797 | 0 | 0 | 0 | 20400 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 40800 | S81 | 256 - S8 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
SG2-03025 | 2320 | Mechanical Pipe: Hydrostatic Testing | 1500 | 1650 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8-01740 | 2329 | 4' High Steel Bar Fence | 78513.9535 | 87450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78513.9535 | 0 | 0 | 0 | 78513.9535 | S8 | 258 - S8 - Division 32 | 0% | Atlas | 0 | SITE
OG1-03007 | 2331 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 9900 | 8820 | 0 | 0 | 173.0769 | 0 | 0 | 6.9231 | 0 | 0 | 0 | 0 | 9000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8-01710 | 2332 | 4" CONCRETE | 35000 | 38500 | 0 | 0 | 0 | 0 | 0 | 17500 | 17500 | 0 | 0 | 0 | 0 | 35000 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01710 | 2333 | 5"POROUS CONCRETE | 135400 | 148940 | 0 | 0 | 0 | 0 | 0 | 67700 | 67700 | 0 | 0 | 0 | 0 | 135400 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01730 | 2334 | 5" COLOR CONCRETE | 110000 | 121000 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 0 | 0 | 0 | 0 | 110000 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01705 | 2335 | CONCRETE CURB | 35000 | 38500 | 0 | 0 | 0 | 0 | 0 | 17500 | 17500 | 0 | 0 | 0 | 0 | 35000 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01705 | 2336 | SFC -STELL FACING CURB | 8000 | 8800 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 8000 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01710 | 2337 | CONCRETE STEPS | 8000 | 9240 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 8000 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01760 | 2339 | Deciduous Trees | 10799.8253 | 11340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5399.9126 | 5399.9126 | 0 | 10799.8253 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01760 | 2340 | Evergreen Trees | 2025.3809 | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6904 | 1012.6904 | 0 | 2025.3809 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01760 | 2341 | Deciduous Shrubs | 840 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 420 | 0 | 840 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
OG1-03110 | 2342 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 15680 | 0 | 0 | 307.6923 | 0 | 0 | 12.3077 | 0 | 0 | 0 | 0 | 16000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8-01760 | 2343 | Evergreen Shrubs | 1350.1465 | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675.0732 | 675.0732 | 0 | 1350.1465 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01760 | 2344 | Perennials | 3234.2178 | 3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617.1089 | 1617.1089 | 0 | 3234.2178 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01755 | 2345 | Grasses | 6006.3382 | 6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003.1691 | 3003.1691 | 0 | 6006.3382 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01025 | 2346 | Tree Removal | 5164.4435 | 32700 | 789.6703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2582.2217 | 1792.5515 | 0 | 5164.4435 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01755 | 2347 | Lawn Seeding (not including topsoil) | 3057.6826 | 2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528.8413 | 1528.8413 | 0 | 3057.6826 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01755 | 2348 | Topsoil Stockpile/Spread | 18217.4483 | 18963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9108.7241 | 9108.7241 | 0 | 18217.4483 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
S8-01755 | 2349 | Maintenance | 2535.7657 | 2659.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267.8828 | 1267.8828 | 0 | 2535.7657 | S8 | 258 - S8 - Division 32 | 0% | Aspen | 0 | SITE
SGN-01135 | 2352 | INSTALL CONDENSATE AND STEAM PIPE - S8 | 43333.33 | 55999 | 0 | 0 | 0 | 20000 | 23333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 43333.33 | S8 | 259 - S8 - Division 33 | 0% | Welkin | 0 | SITE
SG2-03135 | 2353 | HVAC Ductwork: Testing & Balancing | 1000 | 1100 | 0 | 0 | 0 | 19.2308 | 0 | 0 | 980.7692 | 0 | 0 | 0 | 0 | 1000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2364 | Controls: Furnish and Install: Devices | 65000 | 71500 | 61750 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 65000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2375 | Controls: Furnish and Install: Controls Conduit | 30000 | 33000 | 28500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 30000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-01275 | 2378 | 2" Face Brick | 343000 | 346786 | 0 | 171500 | 171500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343000 | S81 | 261 - S81 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
S8A-01230 | 2380 | 6" CMU (2 hour rated) | 387000 | 249945 | 0 | 0 | 77417.0317 | 103194.3228 | 103194.3228 | 103194.3228 | 0 | 0 | 0 | 0 | 0 | 387000 | S81 | 261 - S81 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
OG1-03120 | 2386 | Controls: Furnish and Install: Controls Wiring | 9000 | 9900 | 8550 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 9000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-01105 | 2389 | STEEL (MATERIAL ONLY) | 110000 | 117614 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2390 | FABRICATION COSTS | 265000 | 226674 | 265000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2391 | METAL DECK (BUY-OUT) | 10000 | 10693 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2392 | ANCHORS & EMBEDS | 8000 | 8554 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2393 | SURVEYING | 6000 | 6416 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2394 | STEEL & DECK ERECTION | 400000 | 433032 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2395 | BOLTS AND HARDWARE | 10000 | 9623 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
S8A-01105 | 2396 | TRUCKING | 12000 | 10693 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | S81 | 262 - S81 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
OG1-03120 | 2397 | Controls: Connect to Final Termination Points | 6000 | 6600 | 5700 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 6000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-01255 | 2405 | Layout | 53137 | 55794 | 0 | 0 | 0 | 0 | 26568.5 | 26568.5 | 0 | 0 | 0 | 0 | 0 | 53137 | S82 | 263 - S81 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
S8A-01255 | 2406 | Framing | 111161 | 116720 | 111161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111161 | S82 | 263 - S81 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
S8A-01255 | 2407 | Insulation | 19909 | 20905 | 19909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19909 | S82 | 263 - S81 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG2-03135 | 2408 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-01255 | 2409 | Cladding Install | 139366 | 146335 | 0 | 0 | 0 | 0 | 69683 | 69683 | 0 | 0 | 0 | 0 | 0 | 139366 | S82 | 263 - S81 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
S8A-01317 | 2410 | Louvers Install | 18250 | 36500 | 0 | 0 | 0 | 0 | 9125 | 9125 | 0 | 0 | 0 | 0 | 0 | 18250 | S82 | 264 - S81 - Division 8 | 0% | Navillus | 0 | NEW BUILDINGS
S8E-03005 | 2414 | COMMON WORK RESULTS FOR PLUMBING | 15371 | 15371 | 8454.05 | 0 | 0 | 2305.65 | 2305.65 | 2305.65 | 0 | 0 | 0 | 0 | 0 | 15371 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2415 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 6000 | 6000 | 4500 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 6000 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2416 | ESCUTCHEONS FOR PLUMBING PIPING | 2500 | 2500 | 750 | 0 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 2500 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2417 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 12200 | 12200 | 1220 | 0 | 0 | 3660 | 3660 | 3660 | 0 | 0 | 0 | 0 | 0 | 12200 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2418 | HANGERS AND SUPPORTS | 21800 | 21800 | 10900 | 0 | 0 | 3633.3333 | 3633.3333 | 3633.3333 | 0 | 0 | 0 | 0 | 0 | 21800 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03040 | 2419 | Insulation: Furnish and Install: Ductwork Insulation | 7000 | 7700 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 7000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8E-03005 | 2420 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2975 | 2975 | 0 | 0 | 0 | 991.6667 | 991.6667 | 991.6667 | 0 | 0 | 0 | 0 | 0 | 2975 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2421 | DOMESTIC WATER PIPING | 258984 | 284883 | 90644.4 | 0 | 0 | 0 | 56113.2 | 56113.2 | 56113.2 | 0 | 0 | 0 | 0 | 258984 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2422 | DOMESTIC WATER PIPING SPECIALTIES | 38000 | 38000 | 0 | 0 | 0 | 12666.6667 | 12666.6667 | 12666.6667 | 0 | 0 | 0 | 0 | 0 | 38000 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2423 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 75000 | 18750 | 0 | 0 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 75000 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2424 | SANITARY WASTE PIPING | 155246 | 170771 | 131959.1 | 0 | 0 | 7762.3 | 7762.3 | 7762.3 | 0 | 0 | 0 | 0 | 0 | 155246 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2425 | SANITARY WASTE PIPING SPECIALTIES | 58485 | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 58485 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2426 | STORM DRAINAGE PIPING SPECIALTIES | 58485 | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 58485 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03030 | 2427 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 359996 | 359996 | 269997 | 0 | 0 | 29999.6667 | 29999.6667 | 29999.6667 | 0 | 0 | 0 | 0 | 0 | 359996 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03030 | 2428 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 145920 | 145920 | 58368 | 0 | 0 | 29184 | 29184 | 29184 | 0 | 0 | 0 | 0 | 0 | 145920 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2429 | GAS SERVICE AND PIPING | 239050 | 262955 | 59762.5 | 0 | 0 | 0 | 59762.5 | 59762.5 | 59762.5 | 0 | 0 | 0 | 0 | 239050 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG1-03040 | 2430 | Insulation: Furnish and Install: Piping Insulation | 16500 | 18150 | 0 | 0 | 8250 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 16500 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8E-03030 | 2431 | PLUMBING FIXTURES | 5200 | 5200 | 0 | 0 | 0 | 1733.3333 | 1733.3333 | 1733.3333 | 0 | 0 | 0 | 0 | 0 | 5200 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-03005 | 2432 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 57428 | 63171 | 28714 | 0 | 0 | 9571.3333 | 9571.3333 | 9571.3333 | 0 | 0 | 0 | 0 | 0 | 57428 | S81 | 267 - S81 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
S8E-02055 | 2433 | Heat Trace | 5000 | 5000 | 0 | 0 | 4285.7143 | 0 | 0 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 5000 | S81 | 267 - S81 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-S8-M-01005 | 2434 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 2435 | Exhaust Fans: Furnish | 8400 | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2436 | Exhaust Fans: Install | 19050 | 19050 | 0 | 2625.354 | 1539.2486 | 13596.0968 | 1289.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 19050 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2437 | Electric Unit Heaters: Furnish | 3500 | 3500 | 0 | 482.3485 | 282.8016 | 2497.9705 | 236.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2438 | Steam Unit Heater: Install | 20000 | 20000 | 0 | 2756.2771 | 1616.0091 | 14274.1174 | 1353.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2439 | Steam Unit Heater: Furnish | 54000 | 54000 | 0 | 7441.9483 | 4363.2245 | 38540.117 | 3654.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2440 | Condensate Return Unit: Furnish | 14000 | 14000 | 0 | 1929.394 | 1131.2063 | 9991.8822 | 947.5175 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2441 | Insulation: Furnish and Install: Equipment Insulation | 7000 | 7700 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 7000 | SG2 | 025 - SG2 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2442 | Condensate Return Unit: Install | 35000 | 35000 | 0 | 4823.485 | 2828.0159 | 24979.7055 | 2368.7937 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2443 | Steam Traps: Furnish | 4400 | 4400 | 0 | 606.381 | 355.522 | 3140.3058 | 297.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2444 | Steam Traps: Install | 34000 | 34000 | 0 | 4685.6711 | 2747.2154 | 24265.9996 | 2301.1138 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2445 | Heating and Ventilation Unit: Furnish | 6500 | 6500 | 0 | 895.7901 | 525.2029 | 4639.0882 | 439.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2446 | Heating and Ventilation Unit: Install | 24000 | 24000 | 0 | 3307.5326 | 1939.2109 | 17128.9409 | 1624.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2447 | Vacuum Pump Unit: Furnish | 16000 | 16000 | 0 | 2205.0217 | 1292.8072 | 11419.2939 | 1082.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03142 | 2448 | Vacuum Pump Unit : Install | 26000 | 26000 | 0 | 3583.1603 | 2100.8118 | 18556.3527 | 1759.6753 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2449 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 250500 | 250500 | 25050 | 41140.3551 | 62304.7585 | 61230.1705 | 49843.8068 | 10930.9091 | 0 | 0 | 0 | 0 | 0 | 250500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2450 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 465000 | 511500 | 9300 | 76368.3239 | 115655.5398 | 113660.7955 | 92524.4318 | 57490.9091 | 0 | 0 | 0 | 0 | 0 | 465000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2451 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 160000 | 0 | 26277.2727 | 39795.4545 | 39109.0909 | 31836.3636 | 22981.8182 | 0 | 0 | 0 | 0 | 0 | 160000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-02010 | 2452 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 25000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-03135 | 2453 | Mechanical Pipe: Hydrostatic Testing | 4500 | 4950 | 0 | 739.0483 | 1119.2472 | 1099.9432 | 895.3977 | 646.3636 | 0 | 0 | 0 | 0 | 0 | 4500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2454 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 35000 | 17500 | 0 | 8467.7419 | 8467.7419 | 8467.7419 | -2634.4086 | -2634.4086 | -2634.4086 | 0 | 0 | 0 | 35000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 2455 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 70000 | 77000 | 35000 | 0 | 16935.4839 | 16935.4839 | 16935.4839 | -5268.8172 | -5268.8172 | -5268.8172 | 0 | 0 | 0 | 70000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03145 | 2456 | HVAC Ductwork: Testing & Balancing | 3500 | 3500 | 0 | 0 | 846.7742 | 846.7742 | 846.7742 | 846.7742 | 0 | 112.9032 | 0 | 0 | 0 | 3500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2457 | Controls: Furnish and Install: Devices | 115000 | 115000 | 42550 | 0 | 0 | 0 | 0 | 22406.3625 | 50043.6375 | 0 | 0 | 0 | 0 | 115000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2458 | Controls: Furnish and Install: Controls Conduit | 60000 | 60000 | 18000 | 0 | 0 | 0 | 0 | 11690.2761 | 29135.6543 | 1174.0696 | 0 | 0 | 0 | 60000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2459 | Controls: Furnish and Install: Controls Wiring | 17250 | 17250 | 0 | 0 | 0 | 0 | 0 | 3360.9544 | 8376.5006 | 5512.545 | 0 | 0 | 0 | 17250 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2460 | Controls: Connect to Final Termination Points | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 1948.3794 | 4855.9424 | 3195.6783 | 0 | 0 | 0 | 10000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-03135 | 2461 | Controls: Controls Testing | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 1169.0276 | 2913.5654 | 1917.407 | 0 | 0 | 0 | 6000 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2462 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 4950 | 3300 | 0 | 0 | 16500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG2-02035 | 2463 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 175000 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 8750 | 175000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
OG1-03040 | 2464 | Insulation: Furnish and Install: Piping Insulation | 27500 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 13750 | 8250 | 5500 | 0 | 0 | 27500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2465 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 4950 | 3300 | 0 | 0 | 16500 | S81 | 268 - S81 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
S8A-02345 | 2466 | ATS Energization | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 15000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02345 | 2467 | ATS Installation | 210000 | 210000 | 168000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02345 | 2468 | ATS Terminations | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 15000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02345 | 2469 | ATS Testing | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 15000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02010 | 2470 | Bypass Connections (Misc Panels, Re-routes, etc) | 5000 | 5000 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 5000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02040 | 2471 | Cabling - Interior Branch (1/0 & Smaller) | 225000 | 225000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 225000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02115 | 2472 | Cabling - Risers & Feeders (2/0 & Larger) | 810000 | 886950 | 0 | 0 | 0 | 202500 | 202500 | 202500 | 202500 | 0 | 0 | 0 | 0 | 810000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02030 | 2473 | Conduit - Branch Circuits (1 1/2" & Smaller) | 125000 | 136875 | 12500 | 16071.4286 | 16071.4286 | 16071.4286 | 21428.5714 | 21428.5714 | 21428.5714 | 0 | 0 | 0 | 0 | 125000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02135 | 2474 | Cabling - Risers & Feeders (2/0 & Larger) | 630000 | 689850 | 0 | 27397.2603 | 90000 | 90000 | 18264.8402 | 18264.8402 | 18264.8402 | 91952.0548 | 91952.0548 | 91952.0548 | 91952.0548 | 630000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02155 | 2475 | Conduit - In-Slab | 198000 | 216810 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02105 | 2476 | Conduit - Risers (2" & Larger) | 900000 | 985500 | 630000 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02010 | 2477 | Demolition | 20000 | 20000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 5666.6667 | 5666.6667 | 5666.6667 | 0 | 20000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02130 | 2478 | Firestopping | 5000 | 5000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 5000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02025 | 2479 | Foundation Coring | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
P-S8A-01100 | 2480 | Generator Delivery | 50000 | 50000 | 0 | 0 | 0 | 0 | 28571.4286 | 14285.7143 | 0 | 2380.9524 | 2380.9524 | 2380.9524 | 0 | 50000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
P-S8A-01030 | 2481 | Generator Release | 300000 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02310 | 2482 | Generator Terminations | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 46428.5714 | 0 | 1190.4762 | 1190.4762 | 1190.4762 | 0 | 50000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02510 | 2483 | Generator Test | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 50000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02160 | 2484 | Lighting Controls | 50000 | 50000 | 25000 | 0 | 0 | 12500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 50000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02020 | 2485 | Conduit - Branch Circuits (1 1/2" & Smaller) | 175000 | 191625 | 17500 | 0 | 0 | 7159.0909 | 0 | 0 | 0 | 37585.2273 | 37585.2273 | 37585.2273 | 37585.2273 | 175000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02110 | 2486 | Lighting Install | 67800 | 67800 | 33900 | 0 | 0 | 27120 | 0 | 0 | 0 | 2260 | 2260 | 2260 | 0 | 67800 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02365 | 2487 | Lighting Rough | 67800 | 67800 | 0 | 0 | 0 | 0 | 54240 | 0 | 0 | 4520 | 4520 | 4520 | 0 | 67800 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG1-02025 | 2488 | Lighting System Program & Energize | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 5000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02370 | 2489 | Lightning Protection | 20000 | 20000 | 10000 | 0 | 0 | 0 | 0 | 8333.3333 | 0 | 555.5556 | 555.5556 | 555.5556 | 0 | 20000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8-02010 | 2490 | Manhole Work | 25000 | 25000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 25000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02045 | 2491 | Mechanical Terminations(Dampers, Heaters, Motors) | 100000 | 100000 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 100000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8-02215 | 2492 | Site Lighting - Cable | 22500 | 24638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 22500 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8-02210 | 2493 | Site Lighting - Conduit | 30000 | 32850 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | 30000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8-02220 | 2494 | Site Lighting - Fixtures | 34500 | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 11500 | 11500 | 0 | 34500 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-S8-E-01015 | 2495 | Site Survey | 64000 | 64000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02050 | 2496 | Conduit - Risers (2" & Larger) | 720000 | 788400 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 162000 | 162000 | 162000 | 162000 | 720000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-S8-E-01015 | 2497 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02125 | 2498 | Switches and Receptacles | 10000 | 10000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 10000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02520 | 2499 | Switchgear & Panelboard Energization | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 30000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02520 | 2500 | Switchgear & Panelboard Installation | 360000 | 360000 | 270000 | 0 | 0 | 0 | 0 | 0 | 25714.2857 | 64285.7143 | 0 | 0 | 0 | 360000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02520 | 2501 | Switchgear & Panelboard Terminations | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 30000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02525 | 2502 | Switchgear & Panelboard Testing | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 5000 | 5000 | 5000 | 0 | 30000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02020 | 2503 | Temp Light & Power | 50000 | 50000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 6989.5288 | 6989.5288 | 6020.9424 | 0 | 50000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02415 | 2504 | Underground Electric Service - Cable | 375000 | 410625 | 0 | 53571.4286 | 53571.4286 | 53571.4286 | 71428.5714 | 71428.5714 | 71428.5714 | 0 | 0 | 0 | 0 | 375000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8-01155 | 2505 | Underground Electric Service - Conduit | 300000 | 328500 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | S81 | 269 - S81 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8E-02030 | 2506 | Fire Alarm Conduit | 30000 | 32850 | 0 | 4285.7143 | 4285.7143 | 4285.7143 | 5714.2857 | 5714.2857 | 5714.2857 | 0 | 0 | 0 | 0 | 30000 | S81 | 270 - S81 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02015 | 2507 | Demolition/Temp Light & Power | 50000 | 54750 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 5625 | 5625 | 5625 | 5625 | 50000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02380 | 2508 | Fire Alarm Wiring | 30000 | 31500 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 30000 | S81 | 270 - S81 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02380 | 2509 | Fire Alarm Devices | 57000 | 57000 | 28500 | 0 | 0 | 0 | 14250 | 0 | 0 | 4750 | 4750 | 4750 | 0 | 57000 | S81 | 270 - S81 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02380 | 2510 | Fire Alarm Programming & Pretest | 2500 | 2500 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 2500 | S81 | 270 - S81 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-02505 | 2511 | Fire Alarm FDNY Approval | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 2500 | S81 | 270 - S81 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02125 | 2518 | Firestopping | 5000 | 5250 | 0 | 4444.4444 | 0 | 0 | 0 | 0 | 0 | 138.8889 | 138.8889 | 138.8889 | 138.8889 | 5000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-01305 | 2528 | Layout | 6375 | 5109 | 0 | 0 | 0 | 0 | 5008.9286 | 910.7143 | 455.3571 | 0 | 0 | 0 | 0 | 6375 | S82 | 273 - S82 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG2-02050 | 2529 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-01305 | 2530 | Loading | 14250 | 13137 | 0 | 0 | 0 | 0 | 2169.4451 | 8053.7033 | 4026.8516 | 0 | 0 | 0 | 0 | 14250 | S82 | 273 - S82 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01305 | 2531 | Exterior Framing, Insulation & Drywall - Materials | 44000 | 46709 | 0 | 0 | 0 | 0 | 14130.0392 | 19913.3072 | 9956.6536 | 0 | 0 | 0 | 0 | 44000 | S82 | 273 - S82 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01305 | 2532 | Exterior Framing- Labor | 55625 | 54445 | 0 | 0 | 0 | 0 | 20433.465 | 23461.0234 | 11730.5117 | 0 | 0 | 0 | 0 | 55625 | S82 | 273 - S82 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01305 | 2536 | Insulation- Labor | 3875 | 4740 | 0 | 0 | 0 | 0 | 3044.6429 | 553.5714 | 276.7857 | 0 | 0 | 0 | 0 | 3875 | S82 | 274 - S82 - Division 7 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01225 | 2539 | Fireproofing | 42000 | 46200 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | S82 | 274 - S82 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
SG2-02065 | 2540 | Lighting Controls | 23000 | 24150 | 11500 | 0 | 0 | 9200 | 0 | 0 | 0 | 575 | 575 | 575 | 575 | 23000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
S8A-01265 | 2541 | P&I Cold Applied Roof Membrane | 63000 | 68145 | 0 | 0 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63000 | S82 | 274 - S82 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
S8A-01265 | 2542 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 64800 | 70092 | 0 | 0 | 64800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64800 | S82 | 274 - S82 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
S8A-01265 | 2543 | P&I Aluminum Coping | 2867 | 3102 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2867 | S82 | 274 - S82 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
S8A-01245 | 2545 | Doors, Frames & Hardware - Labor | 12125 | 26968 | 0 | 12125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12125 | S82 | 275 - S82 - Division 8 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01305 | 2547 | Sheathing & Drywall - Labor | 16500 | 33946 | 0 | 0 | 0 | 0 | 4860.661 | 7759.5593 | 3879.7797 | 0 | 0 | 0 | 0 | 16500 | S82 | 276 - S82 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01245 | 2548 | Tape/ Spackle finishes | 6500 | 13372 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | S82 | 276 - S82 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
S8A-01280 | 2549 | Direct Applied Stucco | 15400 | 31684 | 0 | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15400 | S82 | 276 - S82 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG2-02015 | 2551 | Lighting Remove & Re-install | 20700 | 22667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175 | 5175 | 5175 | 5175 | 20700 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02015 | 2558 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02025 | 2559 | Mechanical Terminations(Dampers, Heaters, Motors) | 40000 | 43800 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 40000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGS-E-01030 | 2560 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG2-02110 | 2561 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 10000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG7-02675 | 2562 | Switchgear & Panelboard Energization | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG7-02375 | 2563 | Switchgear & Panelboard Installation | 60000 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 60000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG7-02375 | 2564 | Switchgear & Panelboard Terminations | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG7-02680 | 2565 | Switchgear & Panelboard Testing | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG2 | 026 - SG2 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-01005 | 2569 | Gaskets | 12000 | 36000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 12000 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01010 | 2570 | Wire Insulation | 12500 | 37500 | 0 | 0 | 6250 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2571 | Assumed Flooring Material (Slab Penetrations) | 12000 | 36000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2572 | Vinyl Membrane and Mastic | 17884 | 53652 | 0 | 0 | 8942 | 8942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17884 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2573 | Caulk | 34500 | 103500 | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2574 | Fibrous Slate | 4675 | 14025 | 0 | 0 | 2337.5 | 2337.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4675 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01020 | 2575 | Waterproofing | 3314 | 9942 | 0 | 0 | 1657 | 1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3314 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01020 | 2576 | Underground Utility Materials | 15600 | 46800 | 0 | 0 | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01820 | 2616 | 6" vertically reinforced CMU | 198000 | 132685 | 168300 | 0 | 0 | 9900 | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 198000 | SG3 | 030 - SG3 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG3-01830 | 2617 | 2" Face brick | 223000 | 410182 | 22300 | 37775.9563 | 34120.2186 | 42934.6084 | 42934.6084 | 42934.6084 | 0 | 0 | 0 | 0 | 0 | 223000 | SG3 | 030 - SG3 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG3-01820 | 2619 | Coping Stone C1/A-300 | 274000 | 22968 | 27400 | 0 | 0 | 82200 | 82200 | 82200 | 0 | 0 | 0 | 0 | 0 | 274000 | SG3 | 030 - SG3 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05530 | 2620 | MATERIAL AND FABRICATION | 19000 | 21224 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | SG3 | 031 - SG3 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG3-01315 | 2621 | INSTALLATION | 34000 | 37400 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | SG3 | 031 - SG3 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG3-01860 | 2622 | Temporary Aluminum Over Pass Stairs | 51996 | 57196 | 0 | 0 | 0 | 0 | 0 | 0 | 12999 | 38997 | 0 | 0 | 0 | 51996 | SG3 | 031 - SG3 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG3-01330 | 2629 | Doors, Frames & Hardware - Labor | 2625 | 5838 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | SG3 | 033 - SG3 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01325 | 2631 | Layout | 4750 | 5658 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01325 | 2632 | Loading | 4250 | 8744 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01325 | 2633 | Framing & Drywall - Materials | 9875 | 13115 | 9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9875 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01325 | 2634 | Framing- Labor | 9750 | 20060 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9750 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01330 | 2635 | Drywall - Labor | 11500 | 23660 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01330 | 2636 | Tape/ Spackle finishes | 9000 | 18517 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-01855 | 2637 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 4950 | SG3 | 034 - SG3 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG3-03005 | 2662 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 0 | 0 | 1030.9167 | 1030.9167 | 1030.9167 | 0 | 0 | 0 | 0 | 0 | 12371 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2663 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 960 | 1056 | 96 | 0 | 0 | 288 | 288 | 288 | 0 | 0 | 0 | 0 | 0 | 960 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2664 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 0 | 0 | 0 | 332 | 332 | 332 | 0 | 0 | 0 | 0 | 0 | 996 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2665 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 5400 | 5940 | 3780 | 0 | 0 | 540 | 540 | 540 | 0 | 0 | 0 | 0 | 0 | 5400 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2666 | HANGERS AND SUPPORTS | 10465 | 11512 | 8372 | 0 | 0 | 697.6667 | 697.6667 | 697.6667 | 0 | 0 | 0 | 0 | 0 | 10465 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2667 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 1995 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2668 | DOMESTIC WATER PIPING | 124949 | 137444 | 99959.2 | 0 | 0 | 8329.9333 | 8329.9333 | 8329.9333 | 0 | 0 | 0 | 0 | 0 | 124949 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2669 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 12580 | 0 | 0 | 740 | 740 | 740 | 0 | 0 | 0 | 0 | 0 | 14800 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2670 | SANITARY WASTE PIPING | 122958 | 135254 | 98366.4 | 0 | 0 | 8197.2 | 8197.2 | 8197.2 | 0 | 0 | 0 | 0 | 0 | 122958 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2671 | SANITARY WASTE PIPING SPECIALTIES | 42798 | 47078 | 38518.2 | 0 | 0 | 1426.6 | 1426.6 | 1426.6 | 0 | 0 | 0 | 0 | 0 | 42798 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2672 | STORM DRAINAGE PIPING SPECIALTIES | 42798 | 47078 | 17119.2 | 0 | 0 | 8559.6 | 8559.6 | 8559.6 | 0 | 0 | 0 | 0 | 0 | 42798 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03030 | 2673 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 379998 | 417998 | 341998.2 | 0 | 0 | 12666.6 | 12666.6 | 12666.6 | 0 | 0 | 0 | 0 | 0 | 379998 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2674 | GAS SERVICE AND PIPING | 2055 | 2261 | 0 | 0 | 0 | 685 | 685 | 685 | 0 | 0 | 0 | 0 | 0 | 2055 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2675 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 12060 | 13266 | 12060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12060 | SG3 | 037 - SG3 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG3-03005 | 2676 | Plumbing Pipe Insulation | 35100 | 35750 | 0 | 0 | 17550 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35100 | SG3 | 037 - SG3 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
SG3-02040 | 2677 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG3 | 037 - SG3 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGS-M-01005 | 2678 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 2679 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2680 | Exhaust Fans: Install | 13450 | 14795 | 6725 | 2241.6667 | 2241.6667 | 2241.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13450 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2681 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2682 | Steam Unit Heaters: Install | 16000 | 17600 | 0 | 5333.3333 | 5333.3333 | 5333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2683 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2684 | Condensate Return Unit: Install | 22000 | 24200 | 0 | 7333.3333 | 7333.3333 | 7333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2685 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 0 | 2166.6667 | 2166.6667 | 2166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2686 | Heating and Ventilation Unit: Install | 23000 | 25300 | 0 | 7666.6667 | 7666.6667 | 7666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2687 | Steam Traps: Furnish | 2800 | 3080 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03112 | 2688 | Steam Traps: Install | 23500 | 25850 | 0 | 7833.3333 | 7833.3333 | 7833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2689 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2690 | Vacuum Pump Unit: Install | 25000 | 27500 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2691 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 264150 | 290565 | 211320 | 13207.5 | 13207.5 | 13207.5 | 13207.5 | 0 | 0 | 0 | 0 | 0 | 0 | 264150 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2692 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 405000 | 445500 | 344250 | 15187.5 | 15187.5 | 15187.5 | 15187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2693 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 176000 | 0 | 53333.3333 | 53333.3333 | 53333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03015 | 2694 | Mechanical Pipe: Hydrostatic Testing | 5850 | 6435 | 0 | 1950 | 1950 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5850 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03007 | 2695 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 30000 | 33000 | 27600 | 0 | 0 | 2338.9831 | 0 | 0 | 0 | 61.0169 | 0 | 0 | 0 | 30000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 2696 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 85000 | 93500 | 78200 | 0 | 0 | 6627.1186 | 0 | 0 | 0 | 172.8814 | 0 | 0 | 0 | 85000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03235 | 2697 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 0 | 233.8983 | 0 | 0 | 0 | 2766.1017 | 0 | 0 | 0 | 3000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2698 | Controls: Furnish and Install: Devices | 75000 | 82500 | 71250 | 0 | 0 | 3588.1295 | 0 | 0 | 161.8705 | 0 | 0 | 0 | 0 | 75000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2699 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 0 | 1913.6691 | 0 | 0 | 86.3309 | 0 | 0 | 0 | 0 | 40000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2700 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 9500 | 0 | 0 | 478.4173 | 0 | 0 | 21.5827 | 0 | 0 | 0 | 0 | 10000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2701 | Controls: Connect to Final Termination Points | 8000 | 8800 | 7600 | 0 | 0 | 382.7338 | 0 | 0 | 17.2662 | 0 | 0 | 0 | 0 | 8000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03310 | 2702 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 287.0504 | 0 | 0 | 5712.9496 | 0 | 0 | 0 | 0 | 6000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2703 | Insulation: Furnish and Install: Ductwork Insulation | 15000 | 16500 | 0 | 0 | 0 | 0 | 3750 | 0 | 9750 | 1500 | 0 | 0 | 0 | 15000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2704 | Insulation: Furnish and Install: Piping Insulation | 30000 | 33000 | 0 | 0 | 0 | 0 | 7500 | 0 | 19500 | 3000 | 0 | 0 | 0 | 30000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2705 | Insulation: Furnish and Install: Equipment Insulation | 15000 | 16500 | 0 | 0 | 0 | 0 | 3750 | 0 | 9750 | 1500 | 0 | 0 | 0 | 15000 | SG3 | 038 - SG3 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-02210 | 2706 | ATS Energization | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 10416.6667 | 520.8333 | 520.8333 | 520.8333 | 520.8333 | 12500 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02210 | 2707 | ATS Installation | 175000 | 194250 | 87500 | 0 | 0 | 0 | 0 | 0 | 72916.6667 | 3645.8333 | 3645.8333 | 3645.8333 | 3645.8333 | 175000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02210 | 2708 | ATS Terminations | 12500 | 13875 | 0 | 0 | 0 | 0 | 0 | 0 | 10416.6667 | 520.8333 | 520.8333 | 520.8333 | 520.8333 | 12500 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02210 | 2709 | ATS Testing | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 10416.6667 | 520.8333 | 520.8333 | 520.8333 | 520.8333 | 12500 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02010 | 2710 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 3125 | 3125 | 3125 | 3125 | 25000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02035 | 2711 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 164250 | 0 | 21428.5714 | 21428.5714 | 21428.5714 | 28571.4286 | 28571.4286 | 28571.4286 | 0 | 0 | 0 | 0 | 150000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SGS-02105 | 2712 | Cabling - Risers & Feeders (2/0 & Larger) | 360000 | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | 360000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02015 | 2713 | Conduit - Branch Circuits (1 1/2" & Smaller) | 200000 | 222000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 200000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02115 | 2714 | Conduit - Risers (2" & Larger) | 360000 | 399600 | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 9000 | 360000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02020 | 2715 | Demolition/Temp Light & Power | 50000 | 54750 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | 1875 | 1875 | 1875 | 50000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02145 | 2716 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02025 | 2717 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02125 | 2718 | Lighting Controls | 30000 | 31500 | 15000 | 12857.1429 | 0 | 0 | 0 | 0 | 0 | 535.7143 | 535.7143 | 535.7143 | 535.7143 | 30000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02020 | 2719 | Lighting Remove & Re-install | 49500 | 54203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 12375 | 12375 | 12375 | 49500 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02020 | 2720 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 5000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02045 | 2721 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 17400 | 34800 | 0 | 0 | 0 | 0 | 0 | 1450 | 1450 | 1450 | 1450 | 58000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGS-E-01030 | 2722 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02515 | 2723 | Switchgear & Panelboard Energization | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 30000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02265 | 2724 | Switchgear & Panelboard Installation | 360000 | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | 360000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02265 | 2725 | Switchgear & Panelboard Terminations | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 30000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02510 | 2726 | Switchgear & Panelboard Testing | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 30000 | SG3 | 039 - SG3 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02015 | 2727 | Fire Alarm Conduit | 25000 | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 6250 | 6250 | 6250 | 25000 | SG3 | 040 - SG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02120 | 2728 | Fire Alarm Wiring | 22500 | 24638 | 0 | 16875 | 0 | 0 | 0 | 0 | 0 | 1406.25 | 1406.25 | 1406.25 | 1406.25 | 22500 | SG3 | 040 - SG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02120 | 2729 | Fire Alarm Devices | 18000 | 19710 | 9000 | 6750 | 0 | 0 | 0 | 0 | 0 | 562.5 | 562.5 | 562.5 | 562.5 | 18000 | SG3 | 040 - SG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02120 | 2730 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 156.25 | 156.25 | 156.25 | 156.25 | 2500 | SG3 | 040 - SG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG3-02535 | 2731 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 625 | 625 | 625 | 2500 | SG3 | 040 - SG3 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-01005 | 2735 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 3000 | 0 | 0 | 0 | 15000 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01010 | 2736 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2737 | Assumed Flooring Material (Slab Penetrations) | 15600 | 46800 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01020 | 2738 | Pipe Insulation | 5250 | 15750 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2739 | Vinyl Membrane and Mastic | 14416 | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2740 | Caulk | 30000 | 90000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2741 | Fibrous Slate | 4845 | 14535 | 4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01020 | 2742 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01020 | 2743 | Underground Utility Materials | 18200 | 54600 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01820 | 2783 | 6" vertically reinforced CMU | 210000 | 126280 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | SG4 | 044 - SG4 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG4-01830 | 2784 | 2" Face brick | 226000 | 538422 | 203400 | 22600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226000 | SG4 | 044 - SG4 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG4-01820 | 2786 | Coping Stone C1/A-300 | 213000 | 18586 | 213000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213000 | SG4 | 044 - SG4 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05350 | 2787 | MATERIAL AND FABRICATION | 19000 | 21224 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | SG4 | 045 - SG4 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG4-01315 | 2788 | INSTALLATION | 34000 | 37400 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | SG4 | 045 - SG4 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG4-01860 | 2789 | Temporary Aluminum Over Pass Stairs | 51996 | 57196 | 0 | 25998 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51996 | SG4 | 045 - SG4 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG4-01330 | 2797 | Doors, Frames & Hardware - Labor | 5875 | 13066 | 5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5875 | SG4 | 047 - SG4 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01325 | 2799 | Layout | 5750 | 7715 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01325 | 2800 | Loading | 7875 | 9001 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01325 | 2801 | Framing & Drywall - Materials | 8500 | 17638 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01325 | 2802 | Framing- Labor | 3625 | 7458 | 3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3625 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01330 | 2803 | Drywall - Labor | 7750 | 15944 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01330 | 2804 | Tape/ Spackle finishes | 11500 | 23660 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-01855 | 2805 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | SG4 | 048 - SG4 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG4-03005 | 2833 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9896.8 | 618.55 | 618.55 | 618.55 | 618.55 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2834 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 960 | 1056 | 864 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2835 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 896.4 | 0 | 99.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 996 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2836 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4200 | 4620 | 2520 | 0 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2837 | HANGERS AND SUPPORTS | 10462.5 | 11509 | 8370 | 0 | 2092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10462.5 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2838 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2839 | DOMESTIC WATER PIPING | 128180 | 140998 | 115362 | 0 | 12818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128180 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 2840 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 11100 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14800 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2841 | SANITARY WASTE PIPING | 110976 | 122074 | 110976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110976 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2842 | SANITARY WASTE PIPING SPECIALTIES | 41426 | 45569 | 41426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41426 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2843 | STORM DRAINAGE PIPING SPECIALTIES | 41426 | 45569 | 41426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41426 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03030 | 2844 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 295000 | 324500 | 280250 | 0 | 14750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2845 | GAS SERVICE AND PIPING | 5790 | 6369 | 5211 | 0 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5790 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2846 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | SG4 | 051 - SG4 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG4-03005 | 2847 | Plumbing Pipe Insulation | 29800 | 35464 | 20860 | 0 | 4470 | 4470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29800 | SG4 | 051 - SG4 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
SG4-02260 | 2848 | Heat Trace | 5000 | 5475 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG4 | 051 - SG4 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGN-M-01005 | 2849 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 2850 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03112 | 2851 | Exhaust Fans: Install | 10450 | 11495 | 0 | 2612.5 | 2612.5 | 2612.5 | 2612.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10450 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2852 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03032 | 2853 | Steam Unit Heaters: Install | 13000 | 14300 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2854 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03032 | 2855 | Condensate Return Unit: Install | 19000 | 20900 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03112 | 2856 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03112 | 2857 | Heating and Ventilation Unit: Install | 20000 | 22000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03310 | 2858 | Steam Traps: Furnish | 2200 | 2420 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG3-03310 | 2859 | Steam Traps: Install | 16500 | 18150 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 2860 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03032 | 2861 | Vacuum Pump Unit: Install | 22000 | 24200 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03107 | 2862 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 172375 | 189613 | 172375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172375 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03007 | 2863 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 284000 | 312400 | 284000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03007 | 2864 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 87500 | 96250 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87500 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03025 | 2865 | Mechanical Pipe: Hydrostatic Testing | 2875 | 3163 | 2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03107 | 2866 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 17500 | 19250 | 12250 | 1685.7798 | 0 | 1188.0734 | 1188.0734 | 1188.0734 | 0 | 0 | 0 | 0 | 0 | 17500 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 2867 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 35000 | 38500 | 24500 | 3371.5596 | 0 | 2376.1468 | 2376.1468 | 2376.1468 | 0 | 0 | 0 | 0 | 0 | 35000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03140 | 2868 | HVAC Ductwork: Testing & Balancing | 2000 | 2200 | 0 | 192.6606 | 0 | 602.4465 | 602.4465 | 602.4465 | 0 | 0 | 0 | 0 | 0 | 2000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2869 | Controls: Furnish and Install: Devices | 75000 | 82500 | 72000 | 1645.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73645.1613 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2870 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38400 | 877.4194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39277.4194 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2871 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 9600 | 219.3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9819.3548 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 2872 | Controls: Connect to Final Termination Points | 80000 | 88000 | 68000 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-03310 | 2873 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2874 | Insulation: Furnish and Install: Ductwork Insulation | 11500 | 12650 | 8050 | 1725 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2875 | Insulation: Furnish and Install: Piping Insulation | 23000 | 25300 | 21850 | 575 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 2876 | Insulation: Furnish and Install: Equipment Insulation | 11500 | 12650 | 10925 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | SG4 | 052 - SG4 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG4-02430 | 2877 | ATS Energization | 12500 | 13688 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02430 | 2878 | ATS Installation | 175000 | 191625 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02430 | 2879 | ATS Terminations | 12500 | 13688 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02430 | 2880 | ATS Testing | 12500 | 13688 | 11875 | 0 | 0 | 0 | 208.3333 | 208.3333 | 208.3333 | 0 | 0 | 0 | 0 | 12500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02225 | 2881 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 23750 | 0 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | 0 | 0 | 25000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02245 | 2882 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 175000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SGN-02125 | 2883 | Cabling - Risers & Feeders (2/0 & Larger) | 432000 | 473040 | 410400 | 0 | 0 | 0 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 0 | 432000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02230 | 2884 | Conduit - Branch Circuits (1 1/2" & Smaller) | 250000 | 273750 | 237500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 250000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02305 | 2885 | Conduit - Risers (2" & up) | 495000 | 542025 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02210 | 2886 | Demolition/Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 50000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02345 | 2887 | Firestopping | 5000 | 5250 | 4750 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 0 | 0 | 0 | 0 | 5000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02215 | 2888 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02250 | 2889 | Lighting Controls | 24000 | 25200 | 22800 | 0 | 0 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | 0 | 24000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02210 | 2890 | Lighting Remove & Re-install | 49500 | 54945 | 47025 | 0 | 0 | 0 | 825 | 825 | 825 | 0 | 0 | 0 | 0 | 49500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02210 | 2891 | Lighting System Program & Energize | 5000 | 5475 | 2500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 5000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02270 | 2892 | Mechanical Terminations(Dampers, Heaters, Motors) | 52000 | 56940 | 49400 | 0 | 0 | 0 | 866.6667 | 866.6667 | 866.6667 | 0 | 0 | 0 | 0 | 52000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGN-E-01000 | 2893 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02425 | 2894 | Switches and Receptacles | 10000 | 10950 | 9500 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 0 | 0 | 0 | 0 | 10000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02515 | 2895 | Switchgear & Panelboard Energization | 27500 | 30113 | 24750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 27500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02455 | 2896 | Switchgear & Panelboard Installation | 330000 | 361350 | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02455 | 2897 | Switchgear & Panelboard Terminations | 27500 | 30113 | 26125 | 0 | 0 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02520 | 2898 | Switchgear & Panelboard Testing | 27500 | 30113 | 22000 | 785.7143 | 785.7143 | 785.7143 | 1047.619 | 1047.619 | 1047.619 | 0 | 0 | 0 | 0 | 27500 | SG4 | 053 - SG4 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02230 | 2899 | Fire Alarm Conduit | 15000 | 16650 | 14250 | 0 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 15000 | SG4 | 054 - SG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02325 | 2900 | Fire Alarm Wiring | 12000 | 13140 | 11400 | 0 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 12000 | SG4 | 054 - SG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02325 | 2901 | Fire Alarm Devices | 20000 | 21900 | 19000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | 0 | 0 | 20000 | SG4 | 054 - SG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02325 | 2902 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | SG4 | 054 - SG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG4-02505 | 2903 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | SG4 | 054 - SG4 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-01005 | 2907 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01010 | 2908 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2909 | Assumed Flooring Material (Slab Penetrations) | 14400 | 43200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01020 | 2910 | Pipe Insulation | 50400 | 151200 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2911 | Mudded Joint Packing | 8362 | 25086 | 8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8362 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2912 | Vinyl Membrane and Mastic | 14416 | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2913 | Caulk | 36000 | 108000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2914 | Fibrous Slate | 5270 | 15810 | 5270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5270 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01020 | 2915 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01020 | 2916 | Underground Utility Materials | 18200 | 54600 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01820 | 2957 | 6" vertically reinforced CMU | 244000 | 123200 | 244000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244000 | SG5 | 058 - SG5 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG5-01830 | 2958 | 2" Face brick | 229000 | 530612 | 206100 | 22900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229000 | SG5 | 058 - SG5 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
SG5-01820 | 2960 | Coping Stone C1/A-300 | 204000 | 17319 | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204000 | SG5 | 058 - SG5 - Division 4 | 0% | Faxa | 0 | EXISTING BUILDINGS
05380 | 2961 | MATERIAL AND FABRICATION | 19000 | 38589 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | SG5 | 059 - SG5 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG5-01315 | 2962 | INSTALLATION | 34000 | 68000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | SG5 | 059 - SG5 - Division 5 | 0% | Weir Welding | 0 | EXISTING BUILDINGS
SG5-01860 | 2963 | Temporary Aluminum Over Pass Stairs | 51996 | 103992 | 0 | 25998 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51996 | SG5 | 059 - SG5 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG5-01330 | 2971 | Doors, Frames & Hardware - Labor | 2250 | 5004 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | SG5 | 061 - SG5 - Division 8 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01325 | 2973 | Layout | 3875 | 4170 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3875 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01325 | 2974 | Loading | 6625 | 6950 | 6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6625 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01325 | 2975 | Framing & Drywall - Materials | 6500 | 14456 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01325 | 2976 | Framing- Labor | 7500 | 16680 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01330 | 2977 | Drywall - Labor | 13000 | 28914 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01330 | 2978 | Tape/ Spackle finishes | 6000 | 13344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-01855 | 2979 | Stucco | 4950 | 11008 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | SG5 | 062 - SG5 - Division 9 | 0% | Custom Carpentry | 0 | EXISTING BUILDINGS
SG5-03005 | 3007 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 14846 | 9896.8 | 618.55 | 618.55 | 618.55 | 618.55 | 0 | 0 | 0 | 0 | 0 | 0 | 12371 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3008 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 720 | 864 | 648 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3009 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1196 | 697.2 | 74.7 | 74.7 | 74.7 | 74.7 | 0 | 0 | 0 | 0 | 0 | 0 | 996 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3010 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3400 | 4080 | 0 | 850 | 850 | 850 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3011 | HANGERS AND SUPPORTS | 10462.5 | 12555 | 2092.5 | 2092.5 | 2092.5 | 2092.5 | 2092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10462.5 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3012 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2394 | 0 | 498.75 | 498.75 | 498.75 | 498.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3013 | DOMESTIC WATER PIPING | 98520 | 108372 | 78816 | 4926 | 4926 | 4926 | 4926 | 0 | 0 | 0 | 0 | 0 | 0 | 98520 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3014 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 17760 | 11100 | 925 | 925 | 925 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 14800 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3015 | SANITARY WASTE PIPING | 98040 | 107844 | 78432 | 4902 | 4902 | 4902 | 4902 | 0 | 0 | 0 | 0 | 0 | 0 | 98040 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3016 | SANITARY WASTE PIPING SPECIALTIES | 18801 | 22562 | 16920.9 | 470.025 | 470.025 | 470.025 | 470.025 | 0 | 0 | 0 | 0 | 0 | 0 | 18801 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3017 | STORM DRAINAGE PIPING SPECIALTIES | 38800 | 46560 | 32980 | 1455 | 1455 | 1455 | 1455 | 0 | 0 | 0 | 0 | 0 | 0 | 38800 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03030 | 3018 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 237697.2 | 270000 | 225812.34 | 2971.215 | 2971.215 | 2971.215 | 2971.215 | 0 | 0 | 0 | 0 | 0 | 0 | 237697.2 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3019 | GAS SERVICE AND PIPING | 1920 | 2112 | 0 | 480 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
SG5-03005 | 3020 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9740 | 10714 | 9740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9740 | SG5 | 065 - SG5 - Division 22 | 0% | Vital | 0 | EXISTING BUILDINGS
OG5-03005 | 3021 | Plumbing Pipe Insulation | 15800 | 35464 | 15800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15800 | SG5 | 065 - SG5 - Division 22 | 0% | Tristan | 0 | EXISTING BUILDINGS
SG5-02240 | 3022 | Heat Trace | 5000 | 6000 | 4000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG5 | 065 - SG5 - Division 22 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGN-M-01005 | 3023 | Survey | 60000 | 72000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03112 | 3024 | Exhaust Fans: Furnish | 3600 | 4320 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03112 | 3025 | Exhaust Fans: Install | 7450 | 8940 | 0 | 0 | 0 | 7450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7450 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 3026 | Steam Unit Heaters: Furnish | 1000 | 1200 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03032 | 3027 | Steam Unit Heaters: Install | 10000 | 12000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 3028 | Condensate Return Unit: Furnish | 7000 | 8400 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03032 | 3029 | Condensate Return Unit: Install | 16000 | 19200 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03112 | 3030 | Heating and Ventilation Unit: Furnish | 6500 | 7800 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03112 | 3031 | Heating and Ventilation Unit: Install | 17000 | 20400 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03015 | 3032 | Steam Traps: Furnish | 1600 | 1920 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03015 | 3033 | Steam Traps: Install | 13000 | 15600 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03032 | 3034 | Vacuum Pump Unit: Furnish | 16000 | 19200 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03032 | 3035 | Vacuum Pump Unit: Install | 19000 | 22800 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03107 | 3036 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 87250 | 104700 | 87250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87250 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03007 | 3037 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 152000 | 167200 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03007 | 3038 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 42000 | 50400 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03025 | 3039 | Mechanical Pipe: Hydrostatic Testing | 1750 | 1925 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03107 | 3040 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 10800 | 8820 | 0 | 0 | 339.2308 | 0 | -159.2308 | 0 | 0 | 0 | 0 | 0 | 9000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03110 | 3041 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 15200 | 0 | 0 | 603.0769 | 0 | 196.9231 | 0 | 0 | 0 | 0 | 0 | 16000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03035 | 3042 | HVAC Ductwork: Testing & Balancing | 1000 | 1200 | 0 | 0 | 0 | 37.6923 | 0 | 962.3077 | 0 | 0 | 0 | 0 | 0 | 1000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 3043 | Controls: Furnish and Install: Devices | 75000 | 90000 | 69583.3333 | 0 | 0 | 2708.3333 | 2708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 3044 | Controls: Furnish and Install: Controls Conduit | 35000 | 42000 | 33600 | 466.6667 | 466.6667 | 466.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 3045 | Controls: Furnish and Install: Controls Wiring | 10000 | 12000 | 9600 | 133.3333 | 133.3333 | 133.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03120 | 3046 | Controls: Connect to Final Termination Points | 7500 | 9000 | 7125 | 125 | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-03235 | 3047 | Controls: Controls Testing | 6000 | 7200 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 3048 | Insulation: Furnish and Install: Ductwork Insulation | 11500 | 12650 | 0 | 5750 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 3049 | Insulation: Furnish and Install: Piping Insulation | 23000 | 25300 | 21850 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
OG1-03040 | 3050 | Insulation: Furnish and Install: Equipment Insulation | 11500 | 13800 | 0 | 5750 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | SG5 | 066 - SG5 - Division 23 | 0% | Welkin | 0 | EXISTING BUILDINGS
SG5-02420 | 3051 | ATS Energization | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02420 | 3052 | ATS Installation | 140000 | 168000 | 126000 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | 140000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02420 | 3053 | ATS Terminations | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02420 | 3054 | ATS Testing | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02210 | 3055 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 30000 | 12500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 25000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02235 | 3056 | Cabling - Interior Branch (1/0 & Smaller) | 160000 | 160000 | 0 | 22857.1429 | 22857.1429 | 22857.1429 | 30476.1905 | 30476.1905 | 30476.1905 | 0 | 0 | 0 | 0 | 160000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02475 | 3057 | Cabling - Risers & Feeders (2/0 & Larger) | 324000 | 354780 | 243000 | 46285.7143 | 34714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02215 | 3058 | Conduit - Branch Circuits (1 1/2" & Smaller) | 200000 | 219000 | 160000 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | 200000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02325 | 3059 | Conduit - Risers (2" & Larger) | 360000 | 394200 | 342000 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 360000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02220 | 3060 | Demolition/Temp Light & Power | 50000 | 60000 | 42500 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 50000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02345 | 3061 | Firestopping | 5000 | 6000 | 3750 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02225 | 3062 | Foundation Coring | 20000 | 24000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02265 | 3063 | Lighting Controls | 28000 | 33600 | 0 | 0 | 0 | 0 | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 28000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02220 | 3064 | Lighting Remove & Re-install | 50400 | 60480 | 0 | 0 | 0 | 0 | 16800 | 16800 | 16800 | 0 | 0 | 0 | 0 | 50400 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02220 | 3065 | Lighting System Program & Energize | 5000 | 6000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02245 | 3066 | Mechanical Terminations(Dampers, Heaters, Motors) | 52000 | 62400 | 23400 | 0 | 0 | 0 | 9533.3333 | 9533.3333 | 9533.3333 | 0 | 0 | 0 | 0 | 52000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SURV-SGN-E-01000 | 3067 | Survey | 60000 | 72000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02460 | 3068 | Switches and Receptacles | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02515 | 3069 | Switchgear & Panelboard Energization | 27500 | 33000 | 0 | 0 | 0 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 27500 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02405 | 3070 | Switchgear & Panelboard Installation | 330000 | 396000 | 297000 | 9428.5714 | 9428.5714 | 9428.5714 | 1571.4286 | 1571.4286 | 1571.4286 | 0 | 0 | 0 | 0 | 330000 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02405 | 3071 | Switchgear & Panelboard Terminations | 27500 | 33000 | 0 | 17187.5 | 0 | 0 | 3437.5 | 3437.5 | 3437.5 | 0 | 0 | 0 | 0 | 27500 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02530 | 3072 | Switchgear & Panelboard Testing | 27500 | 33000 | 0 | 0 | 0 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 27500 | SG5 | 067 - SG5 - Division 26 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02215 | 3073 | Fire Alarm Conduit | 15000 | 16650 | 10500 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 15000 | SG5 | 068 - SG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02315 | 3074 | Fire Alarm Wiring | 12000 | 13140 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 12000 | SG5 | 068 - SG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02315 | 3075 | Fire Alarm Devices | 20000 | 24000 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 20000 | SG5 | 068 - SG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02315 | 3076 | Fire Alarm Programming & Pretest | 2500 | 3000 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | SG5 | 068 - SG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG5-02505 | 3077 | Fire Alarm FDNY Approval | 2500 | 3000 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 2500 | SG5 | 068 - SG5 - Division 28 | 0% | Five Star | 0 | EXISTING BUILDINGS
SG6-01230 | 3094 | 8" CMU (3 hour rated) | 478000 | 349751 | 478000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478000 | SG6 | 071 - SG6 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
SG6-01275 | 3096 | Face Brick 3-5/8" | 191380 | 158400 | 191380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191380 | SG6 | 071 - SG6 - Division 4 | 0% | Faxa | 0 | NEW BUILDINGS
SG6-01250 | 3098 | Cast Stone with SS letters | 6400.3 | 8521 | 4800.225 | 0 | 533.3583 | 533.3583 | 533.3583 | 0 | 0 | 0 | 0 | 0 | 0 | 6400.3 | SG6 | 071 - SG6 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
SG6-01105 | 3101 | STEEL (MATERIAL ONLY) | 141000 | 165824 | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3102 | FABRICATION COSTS | 272000 | 246972 | 272000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3103 | METAL DECK (BUY-OUT) | 12000 | 14113 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3104 | ANCHORS & EMBEDS | 8000 | 9410 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3105 | SURVEYING | 10000 | 11762 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3106 | STEEL & DECK ERECTION | 490000 | 576267 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3107 | BOLTS AND HARDWARE | 20000 | 23522 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01105 | 3108 | TRUCKING | 10000 | 11762 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | SG6 | 072 - SG6 - Division 5 | 0% | Weir Welding | 0 | NEW BUILDINGS
SG6-01270 | 3109 | Dunnage Grating Galvanized | 55019 | 60521 | 55019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55019 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01270 | 3110 | Dunnage Guard Rail | 26334 | 28968 | 26334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26334 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01270 | 3111 | Dunnage Platform Stair with Guard Rail | 11850 | 13035 | 11850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11850 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01290 | 3112 | Stair A: Ground to Roof Floor Stair and Landing with and Hand & Guard Rail | 103968 | 136365 | 103968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103968 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01290 | 3113 | Stair B: Ground to 2nd Floor Stair and Landing with Hand & Guard Rail | 53311 | 64143 | 53311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53311 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01295 | 3114 | 1st to 2nd Floor Ship Ladder with Cage and Platform | 24641 | 27106 | 24641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24641 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01120 | 3115 | Egress Stair: Stair & Landing with Hand & Guard Rail | 58311 | 64143 | 58311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58311 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01305 | 3116 | Layout | 6375 | 5109 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | SG6 | 073 - SG6 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01305 | 3117 | Loading | 18750 | 18391 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | SG6 | 073 - SG6 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01305 | 3118 | Exterior Framing, Insulation & Drywall - Materials | 68125 | 74880 | 68125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68125 | SG6 | 073 - SG6 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01305 | 3119 | Exterior Framing- Labor | 84250 | 87871 | 84250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84250 | SG6 | 073 - SG6 - Division 6 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01305 | 3124 | Insulation- Labor | 5250 | 6422 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250 | SG6 | 074 - SG6 - Division 7 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01255 | 3127 | Layout | 82513 | 86622 | 82513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82513 | SG6 | 074 - SG6 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG6-01255 | 3128 | Framing | 186820 | 196161 | 186820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186820 | SG6 | 074 - SG6 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG6-01255 | 3129 | Insulation | 33460 | 35133 | 33460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33460 | SG6 | 074 - SG6 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG6-01255 | 3130 | Cladding Install | 234222 | 245934 | 210799.8 | 0 | 11711.1 | 11711.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234222 | SG6 | 074 - SG6 - Division 7 | 0% | Navillus | 0 | NEW BUILDINGS
SG6-01225 | 3131 | Fireproofing | 38000 | 41800 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000 | SG6 | 074 - SG6 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
SG6-01265 | 3132 | P&I Cold Applied Roof Membrane | 99066 | 102076 | 99066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99066 | SG6 | 074 - SG6 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
SG6-01265 | 3133 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 120238 | 123891 | 120238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120238 | SG6 | 074 - SG6 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
SG6-01265 | 3134 | P&I Aluminum Coping | 8333 | 8547 | 0 | 0 | 8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8333 | SG6 | 074 - SG6 - Division 7 | 0% | Triangle GC | 0 | NEW BUILDINGS
SG6-01245 | 3136 | Doors, Frames & Hardware - Labor | 10250 | 22798 | 10250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10250 | SG6 | 075 - SG6 - Division 8 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01317 | 3137 | Louvers Install | 30671 | 61342 | 0 | 0 | 15335.5 | 15335.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30671 | SG6 | 075 - SG6 - Division 8 | 0% | Navillus | 0 | NEW BUILDINGS
SG6-01305 | 3139 | Sheathing & Drywall - Labor | 19750 | 40634 | 19750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19750 | SG6 | 076 - SG6 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01245 | 3140 | Tape/ Spackle finishes | 6500 | 13372 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG6 | 076 - SG6 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01315 | 3141 | ACT ceilings - Materials | 500 | 1029 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | SG6 | 076 - SG6 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01315 | 3142 | ACT ceilings - Labor | 2250 | 4629 | 0 | 1125 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | SG6 | 076 - SG6 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01280 | 3143 | Direct Applied Stucco | 9100 | 18722 | 0 | 4550 | 4550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9100 | SG6 | 076 - SG6 - Division 9 | 0% | Custom Carpentry | 0 | NEW BUILDINGS
SG6-01325 | 3144 | Painting SG-6 | 55000 | 110000 | 27500 | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | SG6 | 076 - SG6 - Division 9 | 0% | GG Paint | 0 | NEW BUILDINGS
SG6-03105 | 3154 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 4705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4705 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3155 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3156 | ESCUTCHEONS FOR PLUMBING PIPING | 1980 | 2178 | 1881 | 24.75 | 24.75 | 24.75 | 24.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3157 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 18000 | 19800 | 17100 | 225 | 225 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3158 | HANGERS AND SUPPORTS | 19995 | 21995 | 18995.25 | 249.9375 | 249.9375 | 249.9375 | 249.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 19995 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3159 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2480 | 2728 | 0 | 620 | 620 | 620 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 2480 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3160 | DOMESTIC WATER PIPING | 203775 | 224153 | 193586.25 | 2547.1875 | 2547.1875 | 2547.1875 | 2547.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 203775 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3161 | DOMESTIC WATER PIPING SPECIALTIES | 36239 | 39863 | 34427.05 | 452.9875 | 452.9875 | 452.9875 | 452.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 36239 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3162 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 82500 | 71250 | 937.5 | 937.5 | 937.5 | 937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3163 | SANITARY WASTE PIPING | 108000 | 118800 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108000 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3164 | SANITARY WASTE PIPING SPECIALTIES | 19998 | 21998 | 19998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19998 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3165 | STORM DRAINAGE PIPING SPECIALTIES | 29997 | 32997 | 29997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29997 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03140 | 3166 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 14880 | 16368 | 11904 | 744 | 744 | 744 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 14880 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03140 | 3167 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 2736 | 2736 | 2736 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 218880 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3168 | GAS SERVICE AND PIPING | 252700 | 277970 | 242592 | 2527 | 2527 | 2527 | 2527 | 0 | 0 | 0 | 0 | 0 | 0 | 252700 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03140 | 3169 | PLUMBING FIXTURES | 12879 | 14167 | 9659.25 | 804.9375 | 804.9375 | 804.9375 | 804.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 12879 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03140 | 3170 | EMERGENCY PLUMBING FIXTURES | 4640 | 5104 | 2320 | 580 | 580 | 580 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 4640 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3171 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 41300 | 45430 | 41300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41300 | SG6 | 078 - SG6 - Division 22 | 0% | Vital | 0 | NEW BUILDINGS
SG6-03105 | 3172 | Plumbing Pipe Insulation | 7600 | 3032 | 7600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | SG6 | 078 - SG6 - Division 22 | 0% | Tristan | 0 | NEW BUILDINGS
SG6-02140 | 3173 | Heat Trace | 5000 | 5475 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | SG6 | 078 - SG6 - Division 22 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-SGN-M-01005 | 3174 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03112 | 3175 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3176 | Exhaust Fans: Install | 20950 | 23045 | 20950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20950 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 3177 | Steam Unit Heaters: Furnish | 4000 | 4400 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3178 | Steam Unit Heaters: Install | 41500 | 45650 | 41500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 3179 | Electric Unit Heaters: Furnish | 4500 | 4950 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03032 | 3180 | Condensate Return Unit: Furnish | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3181 | Condensate Return Unit: Install | 41500 | 45650 | 41500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3182 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3183 | Heating and Ventilation Unit: Install | 30500 | 33550 | 30500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3184 | Steam Traps: Furnish | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3185 | Steam Traps: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3186 | Steam Separator: Furnish | 24000 | 26400 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3187 | Steam Separator: Install | 177500 | 195250 | 177500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3188 | Low Pressure Steam Boilers: Install | 97500 | 107250 | 97500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 3189 | Boiler Feed Unit: Furnish | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03242 | 3190 | Boiler Feed Unit: Install | 47500 | 52250 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 3191 | Fuel Oil Pump: Furnish | 50000 | 55000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03130 | 3192 | Fuel Oil Pump: Install | 47500 | 52250 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03142 | 3193 | Fuel Oil Storage Tank: Furnish | 40000 | 44000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03130 | 3194 | Fuel Oil Storage Tank: Install | 47500 | 52250 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03110 | 3195 | Rigging | 132500 | 145750 | 132500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03107 | 3196 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 394450 | 433895 | 394450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394450 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03107 | 3197 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 620000 | 682000 | 620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03207 | 3198 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 170000 | 187000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03135 | 3199 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 165000 | 181500 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03135 | 3200 | Mechanical Pipe: Hydrostatic Testing | 5550 | 6105 | 5550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03207 | 3201 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 50000 | 55000 | 49000 | 967.7419 | 0 | 0 | 0 | 32.2581 | 0 | 0 | 0 | 0 | 0 | 50000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03110 | 3202 | HVAC Ductwork:Furnish and Install: Sheetmetal and RGDs | 100000 | 110000 | 98000 | 1935.4839 | 0 | 0 | 0 | 64.5161 | 0 | 0 | 0 | 0 | 0 | 100000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03245 | 3203 | HVAC Ductwork:Testing & Balancing | 5000 | 5500 | 0 | 96.7742 | 0 | 0 | 0 | 4903.2258 | 0 | 0 | 0 | 0 | 0 | 5000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 3204 | Controls: Furnish and Install: Devices | 190000 | 209000 | 180500 | 3166.6667 | 3166.6667 | 3166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 3205 | Controls: Furnish and Install: Controls Conduit | 85000 | 93500 | 80750 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 3206 | Controls: Furnish and Install: Controls Wiring | 25000 | 27500 | 23750 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03120 | 3207 | Controls: Connect to Final Termination Points | 17000 | 18700 | 11050 | 1983.3333 | 1983.3333 | 1983.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03510 | 3208 | Controls Testing | 13250 | 14575 | 0 | 4416.6667 | 4416.6667 | 4416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13250 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 3209 | Furnish and Install: Ductwork Insulation | 27000 | 29700 | 0 | 10056.8807 | 0 | 16943.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 3210 | Furnish and Install: Piping Insulation | 55000 | 60500 | 44000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG1-03040 | 3211 | Furnish and Install: Equipment Insulation | 27000 | 29700 | 21600 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
OG8-03242 | 3212 | Furnish and Install: Chemical Feed Equipment | 9300 | 10230 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9300 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-03142 | 3213 | Chemical Cleaning | 7500 | 8250 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | SG6 | 079 - SG6 - Division 23 | 0% | Welkin | 0 | NEW BUILDINGS
SG6-02310 | 3214 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 10000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02310 | 3215 | ATS Installation | 140000 | 153300 | 133000 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02310 | 3216 | ATS Terminations | 10000 | 10950 | 9500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02310 | 3217 | ATS Testing | 10000 | 10950 | 5000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 10000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02120 | 3218 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 175000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02410 | 3219 | Cabling - Risers & Feeders (2/0 & Larger) | 450000 | 492750 | 427500 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 450000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02110 | 3220 | Conduit - Branch Circuits (1 1/2" & Smaller) | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 50000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02155 | 3221 | Conduit - In-Slab | 198000 | 216810 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02210 | 3222 | Conduit - Risers (2" & Larger) | 270000 | 295650 | 256500 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 270000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02425 | 3223 | Firestopping | 5000 | 5250 | 4750 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 0 | 0 | 0 | 0 | 5000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-SG6-01025 | 3224 | Generator Delivery | 50000 | 52500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
P-SG6-01010 | 3225 | Generator Release | 300000 | 315000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02385 | 3226 | Generator Terminations | 50000 | 52500 | 45000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 50000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02510 | 3227 | Generator Test | 50000 | 52500 | 25000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 50000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02160 | 3228 | Lighting Controls | 24000 | 25200 | 21600 | 0 | 0 | 0 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 24000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02130 | 3229 | Lighting Install | 84600 | 88830 | 80370 | 0 | 0 | 0 | 1410 | 1410 | 1410 | 0 | 0 | 0 | 0 | 84600 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02130 | 3230 | Lighting Rough | 84600 | 92637 | 84600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84600 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02130 | 3231 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 5000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02395 | 3232 | Lightning Protection | 20000 | 21900 | 12000 | 0 | 0 | 0 | 2666.6667 | 2666.6667 | 2666.6667 | 0 | 0 | 0 | 0 | 20000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SG6-02135 | 3233 | Mechanical Terminations(Dampers, Heaters, Motors) | 130000 | 142350 | 117000 | 0 | 0 | 0 | 4333.3333 | 4333.3333 | 4333.3333 | 0 | 0 | 0 | 0 | 130000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS
SURV-SGN-E-01000 | 3234 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | SG6 | 080 - SG6 - Division 26 | 0% | Five Star | 0 | NEW BUILDINGS

## Work Summary
Subcontractor | Category | Building | Type | February | March | April | May | June | July | August | September | October
ASPEN
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 1.757% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 25.97% | 25.97% | 0% | 0% | 0% | 10.47%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ATCO
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 72.86% | 0% | 0% | 0% | 0% | 0% | 0% | 27.14% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45.71%
|  | OG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 47.66% | 26.27% | 0% | 0% | 0% | 0% | 0% | 0% | 24.24%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ATLAS
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 47.06% | 0% | 0% | 0% | 0% | 50%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CCC
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.643% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.035% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.414% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 27.8% | 0% | 72.2% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.388% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 32% | 37.33% | 0% | 0% | 28.67% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 32% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 20.63% | 28.8% | 0% | 0% | 47.99% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 23.73% | 43.02% | 12.42% | 0% | 20.7% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 4.52% | 13.56% | 64.97% | 13.56% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 30.72% | 69.28% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 8.333% | 0% | 0% | 21.05% | 67.98% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.309% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CITYWIDE
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 32.28% | 67.72% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20.87% | 76.52%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 96.7% | 0%
CLOSEOUT
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.388% | 28.66% | 11.94% | 0% | 33.43% | 20% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 5.637% | 37.37% | 50.1% | 5.637% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 8.977% | 16.7% | 5.01% | 0% | 0% | 0% | 35.7% | 32.36%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 5.832% | 0% | 19.65% | 0% | 0% | 5.184% | 50.11%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 4.829% | 28.97% | 64.59% | 1.811%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 29.45% | 0% | 0% | 51.56% | 18.99%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 15.58% | 43.48% | 39.86% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 8.121% | 9.977% | 14.85% | 53.83% | 11.83% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 19.6% | 7.875% | 10.26% | 41.03% | 20.15% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 13.08% | 15.26% | 0% | 0% | 0% | 0% | 13.08% | 46.59% | 10.35%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 9.057% | 10.57% | 0% | 0% | 8.113% | 0% | 21.13% | 38.3% | 11.7%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.509% | 15.09% | 0% | 29.25% | 42.83% | 10.19% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 23.47% | 0% | 0% | 5.51% | 0% | 0% | 38.16% | 21.84%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 12.66% | 20.25% | 0% | 15.19% | 0% | 0% | 7.595% | 31.33%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 52.34% | 11.25% | 11.25% | 16.41%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 25.3% | 28.92% | 21.54% | 0% | 15.81%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 33.06% | 0% | 0% | 0% | 0% | 34.5% | 25.64%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 61.63% | 37.47% | 1.007%
SITE
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 73.53% | 23.53% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DSTAR
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 22.43% | 26.17% | 0% | 48.6% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Dynasty Elevator
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
E&Y
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.47% | 25% | 56.58% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 16.92% | 12.31% | 66.15% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ENGINEERING
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 20.7% | 40.67% | 12.11% | 0% | 0% | 8.133% | 17.28% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 44.2% | 41.85% | 12.84% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 16.76% | 40.67% | 16% | 7.619% | 17.81% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 17.92% | 35.2% | 19.84% | 3.84% | 16.24% | 5.76% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 28.41% | 29.32% | 30.66% | 11.37%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 6.378% | 28.21% | 20.01% | 22.78%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 17.27% | 77.7% | 2.878% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 2.963% | 85.93% | 8.889% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 75.19% | 23.7% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 53.54% | 45.28%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.17% | 12.95% | 14.34% | 18.5% | 24.68% | 3.237% | 5.087% | 10.35% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 12.01% | 15.28% | 22.92% | 31.31% | 17.67% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.56% | 13.45% | 14.89% | 19.21% | 25.81% | 0% | 0% | 0% | 12.67%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 8.552% | 10.88% | 12.05% | 15.55% | 21.14% | 11.66% | 7.532% | 0% | 1.944%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.51% | 13.38% | 14.81% | 19.12% | 25.69% | 0% | 1.912% | 14.04% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.67% | 13.58% | 15.03% | 19.39% | 25.88% | 0.4848% | 0% | 0% | 8.909%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.7% | 13.62% | 15.08% | 19.46% | 23.04% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.17% | 12.95% | 14.34% | 13.87% | 17.11% | 14.05% | 0% | 0% | 0%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.702% | 9.803% | 10.85% | 15.05% | 16.59% | 10.5% | 10.85% | 5.937% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.544% | 9.601% | 10.63% | 14.74% | 16.25% | 10.29% | 10.63% | 7.873% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 8.099% | 10.31% | 11.41% | 11.04% | 11.41% | 11.04% | 11.41% | 11.41% | 0.3682%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 20.76% | 19.86% | 58.59% | 0.9456%
Overhead
|  | ENG | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.8561% | 3.995% | 7.09% | 6.421% | 2.14% | 0.5707% | 0% | 1.525% | 0.7848%
FAXA
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 59.05% | 40.95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 29.63% | 59.26% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.231% | 0.9393% | 1.879% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.815% | 35.94% | 3.213% | 50.4% | 5.422% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 21.2% | 32.36% | 26.38% | 0% | 19.09% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 9.43% | 12.93% | 1.617% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.536% | 15.22% | 0% | 0% | 1.242% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 1.538% | 13.84% | 3.044% | 0% | 0% | 0%
FIVE STAR
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.3282% | 0.1313% | 0% | 1.017% | 0.7877% | 0.9436% | 0.3938% | 0.4595% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.9071% | 4.697% | 1.037% | 0.8755% | 9.398% | 7.816% | 9.124% | 5.19% | 1.129%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.8372% | 1.699% | 1.092% | 0.9944% | 1.157% | 1.067% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 21.27% | 4.99% | 0.8317% | 1.537% | 0.8678% | 1.079% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.319% | 4.268% | 0.3596% | 3.094% | 2.04% | 1.656% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.2237% | 5.761% | 9.341% | 9.341% | 10.18% | 3.738% | 1.566% | 3.132% | 0%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 21.61% | 0% | 0% | 0% | 25% | 53.39% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.15% | 7.346% | 0% | 0% | 4.995% | 48.78% | 0% | 1.567% | 21.74%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.12% | 1.348% | 2.378% | 0.2995% | 0.9548% | 0.8331% | 3.473% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 1.7% | 0.8679% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 26.57% | 15.03% | 0% | 0% | 0% | 2.147% | 55.55% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 11.61% | 20.14% | 13.84% | 0.248% | 1.623% | 0.9019% | 0% | 1.939% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.8114% | 9.076% | 2.293% | 1.049% | 0.8114% | 3.126% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.368% | 9.014% | 1.001% | 0.7244% | 1.919% | 1.337% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.2018% | 32.34% | 1.105% | 0.4893% | 1.296% | 0.903% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.335% | 6.614% | 1.328% | 1.371% | 0.6206% | 3.075% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.388% | 5.329% | 1.908% | 0.8408% | 0.3737% | 1.855% | 0.6406% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.6115% | 5% | 10.61% | 7.722% | 3.249% | 3.693% | 1.055% | 0% | 0%
|  | OG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 8.607% | 13.85% | 9.086% | 0.1838% | 1.203% | 0.6685% | 0% | 1.12% | 0.6685%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.104% | 6.266% | 5.157% | 3.194% | 3.61% | 1.726% | 4.647% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.4065% | 3.46% | 4.16% | 0% | 1.418% | 3.517% | 3.526% | 3.876% | 1.012%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.1108% | 0% | 0% | 0.7556% | 2.126% | 1.803% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.5783% | 4.183% | 0.1115% | 0.3553% | 2.39% | 1.247% | 0% | 0% | 0%
FLOORING
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
GG PAINT
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 14.31% | 85.88% | 0%
General Conditions
Overhead
|  | Overhead | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
JMC
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.416% | 5.665% | 4.602% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 33.26% | 23.91% | 34.93% | 6.653% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.152% | 15.81% | 0% | 0% | 0% | 0% | 5.381% | 9.686%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 4.082% | 23.13% | 18.2% | 38.1% | 15.48% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 19.95% | 18.14% | 0% | 42.4%
EXISTING BUILDINGS
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Loading Dock
NEW BUILDINGS
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
MEP
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.147% | 18.88% | 0% | 0% | 0% | 2.655% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 6.293% | 32.25% | 36.18% | 22.03% | 0% | 0% | 0% | 2.655% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 22.54% | 67.61% | 0% | 0% | 0% | 0% | 0% | 0% | 3.219%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 50.93% | 36.07% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 26.01% | 0% | 52.1% | 0% | 0% | 21.89%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 14.72% | 75.87% | 0% | 0% | 8.793%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 25.81% | 37.85% | 29.25% | 0% | 0% | 5.806% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 15.44% | 12.89% | 0% | 0% | 2.368% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 39.63% | 10.14% | 0% | 0% | 4.954% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 9.132% | 40.18% | 0.9132% | 0% | 0% | 4.909%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 45.9% | 17.49% | 0% | 17.49% | 12.02% | 0% | 0% | 0% | 5.874%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 21.56% | 56.29% | 16.77% | 0% | 4.042% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 34.29% | 41.14% | 17.14% | 0% | 0% | 0% | 6.143%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 24.96% | 60.14% | 7.943% | 0% | 0% | 0% | 6.099%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 25.65% | 46.84% | 23.42% | 0% | 3.764%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 14.68% | 79.95% | 0% | 5.506%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 66.59% | 22.59% | 0% | 0% | 0% | 0% | 10.12%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 44.24% | 14.22% | 33.18% | 0% | 8.492%
MLJ
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 12.86% | 27.51% | 31.25% | 0% | 0% | 0% | 0% | 14.3% | 12.62%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.555% | 35% | 12.28% | 7.864% | 9.662% | 3.289% | 0% | 0% | 5.499%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 15.64% | 37.54% | 23.36% | 0% | 0% | 11.16% | 11.68% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.263% | 7.908% | 2.4% | 0% | 0% | 2.446% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 4.062% | 13.39% | 5.669% | 1.562% | 0% | 4.776% | 0% | 4.776% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 16.05% | 29.41% | 29.38% | 6.373% | 0% | 0% | 0% | 4.914% | 12.52%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 21.47% | 26.09% | 5.993% | 0% | 0% | 0% | 23.97% | 8.989% | 11.99%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.36% | 10.38% | 12.92% | 11.58% | 6.481% | 4.802% | 0% | 0% | 2.304%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 5.93% | 35.25% | 17.76% | 13.25% | 10.83% | 10.27% | 2.538% | 0% | 2.928%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 5.737% | 25.19% | 20.32% | 12.62% | 3.162% | 0.204% | 2.805% | 4.479% | 3.952%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.203% | 8.774% | 5.413% | 6.857% | 10.35% | 2.526% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.071% | 1.827% | 6.405% | 5.04% | 7.455% | 5.04% | 2.184% | 0% | 0%
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.232% | 2.232% | 0.2665% | 4.264% | 4.264% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 9.942% | 21.77% | 2.144% | 4.678% | 0% | 0% | 11.5% | 39.51% | 9.357%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.94% | 3.293% | 0% | 0% | 0.6469% | 2.058% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.92% | 3.167% | 1.336% | 4.751% | 0.5444% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 22.71% | 18.98% | 0% | 41.69% | 5.424% | 9.153% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.19% | 7.093% | 16.41% | 18.22% | 0% | 7.093% | 0% | 13.31% | 23.32%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 19.02% | 12.5% | 14.54% | 13.86% | 12.36% | 22.15% | 0% | 4.755% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.655% | 29.89% | 28.09% | 7.41% | 0% | 8.713% | 4.56% | 7.41% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 6.277% | 18.16% | 11.71% | 7.96% | 2.805% | 3.191% | 1.227% | 1.122% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 6.631% | 24.36% | 15.12% | 13% | 4.598% | 9.593% | 4.951% | 14.41% | 3.89%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.563% | 14.53% | 4.9% | 0% | 1.127% | 3.014% | 9.576% | 3.915% | 0%
|  | ALLOWANCE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Change Orders
|  | Change Order | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overhead
|  | OH | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 1.452% | 2.5% | 2.419%
NATIONAL GRID
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 11.7% | 85.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 75.45% | 21.82% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 3.191% | 96.81% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 5.349% | 94.88% | 0% | 0%
NAVILLUS
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 62.7% | 0% | 0% | 4.688% | 32.81% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 50.7% | 22.54% | 24.65% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 39.26% | 58.9% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 28.15% | 43.7% | 26.89% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 29.45% | 68.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 29.45% | 68.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 47.9% | 51.2% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 11.98% | 81.44% | 4.79% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 26.99% | 71.17% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 5.442% | 92.52% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 29% | 70.09% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 51.46% | 46.78% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 29.45% | 68.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 65.78% | 0% | 0% | 0% | 34.22% | 0% | 0%
PUNCH LIST
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 64.08% | 0% | 0% | 35.92% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.27% | 52.59%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 86.62% | 11.27% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 64.08% | 0% | 0% | 0% | 35.92% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72% | 69.28%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.67% | 53.33%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.67% | 87.33%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 53.01% | 43.37% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
SITE
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 7.477% | 89.72% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.43%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SIG
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TONAGE
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 13.56% | 81.36% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 48.19% | 48.19% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 66.67% | 33.33% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 13.56% | 81.36% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SITE
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 42.11% | 42.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TRIANGLE
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 3.947% | 75% | 19.57% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 27.59% | 64.37% | 0% | 6.322% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.05% | 32.78% | 2.341% | 44.49% | 0% | 4.585% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TRISTAN
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VITAL
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 55.53% | 28.63% | 15.9% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 29.45% | 68.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 29.45% | 68.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 73.62% | 24.54% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 6.262% | 48.53% | 43.84% | 1.566% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
WEIR
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
WELKIN
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 16.4% | 26.9% | 18.38% | 21.92% | 15.63% | 0.708% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.8117% | 1.183% | 0.06957% | 2.667% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 62.66% | 35.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 41.4% | 57.21% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.709% | 3.845% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 10.51% | 48.29% | 21.94% | 17.74% | 0.5256% | 0% | 0% | 0%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 3.343% | 0% | 0% | 65.65% | 30.09% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.55% | 16.97% | 0% | 0% | 0% | 67.58% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 14.08% | 26.23% | 4.729% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 8.523% | 15.77% | 4.832% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.936% | 1.381% | 7.629% | 2.434% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.7501% | 6.188% | 7.392% | 1.875% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.301% | 16.63% | 19.35% | 24.53% | 1.553% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.828% | 1.877% | 6.331% | 2.084% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.455% | 9.551% | 2.183% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 17.11% | 29.41% | 31.12% | 8.408% | 13.81% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.4818% | 18.05% | 11.83% | 11.91% | 6.643% | 5.242% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 8.967% | 18.38% | 9.282% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.917% | 19.02% | 18.17% | 2.431% | 0% | 0% | 0% | 0% | 0%
Overhead
|  | OH | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0.7779% | 1.34% | 1.297%