## Cost Forecast
Code | Name | Projected Forecast | Spent to Date | February | March | April | May | June | July | August | September | October | Final Cost | Breakdown Type | Cost Type 1 | Cost Type 2 | Category 1 | Forecast Spent %
00-0001 | SECOND FLOOR APARTMENT REMOVALS | 14032 | 14032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0002 | SITE 8 SLAB SHORING | 15736.31 | 15736.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0003 | OG8 Obstruction Removal | 17042.53 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0004 | Floor Drain PCO | 0 | 17791.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0005 | Equipment Pad PCO | 15000 | 14912.24 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 543.8525 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0006 | PCO 15 Additional Windows PCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0007 | IRMA PAGAN APARTMENT MOVE | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0008 | National Grid Gas Line Relocation | 11667.88 | 11667.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0009 | Bracing for POE Penetration Through SG4 Wall | 7468.26 | 7468.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0010 | SG1 RELOCATE BELONGINGS | 21773.44 | 21773.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0011 | PERAMBULATOR ROOM DEMO | 18064.37 | 18064.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0012 | OG8 Tank Removal | 20378.14 | 372.43 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 2500.7137 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0013 | Exist Bldgs Bracing due to Penetrations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0014 | SG4 DEMO FOR STEEL BEAMS INSTALL | 1285.34 | 1285.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0015 | SG5 DEMO FOR STEEL BEAMS INSTALL | 1678.93 | 1678.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0016 | OG4 BRACING FOR POE PENETRATION | 164120.78 | 30850.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | Change Order | 0 | 0%
00-0017 | National Grid Additional Allowance | 205770.46 | 5887.46 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 24985.375 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0018 | SG6 Additional Strobe | 2387.08 | 0 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 298.385 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0019 | ODWYER FENCE INSTALL | 60000 | 62577.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0021 | MOVE PLAYGROUNDS | 1941.36 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0022 | SITE 8 CLEANING | 5968.61 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0023 | S8 FIRE STAND PIPE ACCESS | 59605.91 | 7156.91 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 6556.125 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0024 | Boiler Stack Support | 64820.84 | 1417 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 8003.0537 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0025 | Bulletin 1 Civil PCO 44 | 76640 | 30736.74 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 6206.225 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0026 | DOOR HARDWARE CHANGES | 21947.23 | 0 | 0 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0027 | BOILER ACCESSORY SUPPLY | 185547.35 | 0 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 23193.4188 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0028 | SITE 8 ELECTRICAL REPAIRS | 21203.36 | 0 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 2650.42 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0029 | PCO46 SANITARY VENTING OG5 & OG6 | 69207.97 | 0 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 8650.9963 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0030 | PCO 54 ACM ABATEMENT MASONRY WATERPROOFING | 120833.26 | 0 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 15104.1575 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0031 | PCO 55 ACM ABATEMENT UTILITY WATERPROOF | 241793.37 | 0 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 30224.1712 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0032 | PCO 64 OG10 ADDITIONAL SWITCH | 2369.68 | 0 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 296.21 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0033 | PCO 66 ELECTRICAL DB FOUNDATION CONFLICT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0034 | PCO 76 ADDITIONAL FIRE EXTINGUISHERS | 3809.76 | 0 | 0 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0035 | PCO 77 ACM ABATEMENT SGS STEAM PIPE | 111590.33 | 0 | 0 | 33000 | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0036 | PCO 99 SG5 APARTMENT RENO | 9892.17 | 9892.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0037 | JACOBS TRAILER MOVE | 2879.76 | -30038.69 | 32918.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0038 | PCO 59 SGS REDESIGN | 557295.88 | 4726.71 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 69071.1463 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0039 | AC UNIT DEMO | 7582.95 | 7582.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0040 | PCO 8 BULLETIN 1 ELECTRICAL | 38953 | 0 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 4869.125 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0041 | PCO 19 WINDOW INFILL | 5922.43 | 0 | 5922.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0042 | PCO 40 SG6 STUD RELOCATION | 10923.98 | 0 | 10923.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0043 | PCO 59 SGS ELECTRICAL CHANGES | 213.43 | 213.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0044 | PCO 74 OG9 AND S8 GENERATOR SUPPORTS | 60248.81 | 39449.71 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 2599.8875 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0045 | PCO 79 ACM FILING | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0046 | PCO 85 OG4 & OG5 TANK INSULATION ACM | 75690.92 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0047 | PCO 90 ODYWER TRAILER POWER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0048 | PCO 45 BULLETIN 1 MECHANICAL | 154900.73 | 0 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 19362.5913 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0049 | PCO 83 SG6 METAL PANEL SUPPORT | 70919.49 | 0 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 8864.9363 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0050 | PCO 63 Conduit Concrete Encasement | 225393.38 | 0 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 28174.1725 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0051 | PCO 49 Electrical Clash with LPS | 9430.53 | 0 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 1178.8163 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0052 | PCO 93 Roof Access and ATS Door | 125820.09 | 9185.52 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 14840.1912 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0053 | PCO 100 Exterior Framing OG8, OG9, OG10 | 204711.04 | 0 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 25588.88 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0054 | PCO 48 Restore Walkways | 5772.17 | 9506.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0055 | Pit Covers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0056 | PCO 27 OG8 Structural Steel | 94993.6 | 0 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 11874.2 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0057 | PCO 80 LPS Reroute OG6 | 10884.19 | 0 | 10884.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0058 | PCO 98 OG6 Structural Steel | 6536.32 | 1612.44 | 4923.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0059 | PCO 117 OG1 Ramp Restore | 9555.81 | 9555.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0060 | PCO 78 OG10 Clash | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0061 | PCO 108 STREET CROSSING | 290768 | 96922.67 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 36346 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0062 | PCO 143 SG2 SHELF SUPPORT | 0 | 2073.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0063 | PCO 144 SG3 BASEMENT CLEANING | 0 | 17678.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0064 | PCO 148 EB BACKWATER VALVES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0065 | PCO 17 PLUMBING PIT REINF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0066 | PCO 18 SG6 SHAFT BRACING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0067 | PCO 26 SG6 STAIR MOD | 16182.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0068 | PCO 86 OG1 MANHOLE REROUTE | 19514.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0069 | PCO 97 OG2 OG3 STEAM TUNNEL ACM | 14297.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0070 | PCO 102 SGS OUTAGE | 16182.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0071 | PCO 116 ROOF FLASHING AT BULKHEAD | 13624.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0072 | PCO 142 GENERATOR EQUIP | 28230.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Change Order | 0 | 0%
00-0073 | PCO 124 LOUVER SUPPORT | 0 | 3225.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
00-0074 | PCO 131 SG1 DRAINAGE | 0 | 1566.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
00-0075 | PCO 81 EB Structural Steel Fireproofing | 97275.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
00-0076 | PCO 106 TANK INSUALTION ACM | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
00-0077 | PCO 145 SG6 REVISED BULKHEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
00-0078 | PCO 152 OG4 STEAM LEAK | 1919.86 | 1919.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
00-1000 | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
01-6000 | BUILDING CONDITIONS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
01-6100 | CPM SUB | 73150 | 61170 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 0 | monthly | Sub | 0 | 0 | 0%
01-6200 | PHOTO SUB | 87990 | 46410 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 0 | monthly | Sub | 0 | 0 | 0%
01-6300 | OVERHEAD PROTECTION LABOR | 1472.69 | 1472.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
01-6310 | OVERHEAD PROTECTION MATERIALS | 4491.11 | 4491.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
01-6320 | OVERHEAD PROTECTION EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
01-6400 | RODENT CONTROL SUB | 28596.9 | 14953.9 | 2000 | 2000 | 1223 | 1000 | 1000 | 1000 | 1000 | 2900 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
01-6410 | RODENT CONTROL SUB SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1000 | EROSION CONTROL FABRIC | 970.55 | 970.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1100 | INLET PROTECTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1200 | SILT FENCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1300 | STABILIZED CONSTRUCTION ENTRANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1400 | MANTAIN EROSION CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1500 | REMOVE EROSION CONTROL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1600 | STOCKPILE | 4496.62 | 4496.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-1700 | REMOVE FENCE | 62785.26 | 24231.19 | 7879.8 | 7879.8 | 5000 | 9914.67 | 7879.8 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0%
02-1800 | REMOVE/REINSTALL BOLLARDS ODG EAST | 51378.15 | 627.92 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0%
02-1900 | REMOVE FULL DEPTH ASPHALT PVMT | 85977.83 | 82630 | 500 | 500 | 500 | 1070.7183 | 777.1117 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0%
02-2000 | REMOVE SITE FURNISHING | 77397.6 | 37619.77 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 5400.0133 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0%
02-2100 | REMOVE CONCRETE CURB & STEPS | 93000 | 85502.3 | 1833.3933 | 1833.3933 | 1833.3933 | 622.7967 | 1374.7233 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | SITE | 0%
02-2200 | REMOVE PVMTS | 97421.11 | 87670.24 | 4443.095 | 4721.06 | 586.715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-2300 | BASEMENT MAINTENANCE | 312373.79 | 249803.48 | 8640 | 8640 | 8640 | 8640 | 8640 | 4320 | 4320 | 4320 | 6410.31 | 0 | Phased | Labor | Site Maintenance | Overhead | 0%
02-3000 | CORE DRILLING | 578853.58 | 528822.04 | 10000 | 10000 | 10000 | 10000 | 10031.54 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6000 | OG-7 DEMO LABOR | 21560.01 | 21560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6001 | OG-7 DEMO EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6002 | OG-7 DEMO MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | 373189.17 | 333301.09 | 0 | 0 | 45221.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Site Demo | EXISTING BUILDINGS | 0%
02-6006 | LEAD CONSULTANT | 19466.75 | 19466.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6007 | LEAD DISPOSAL | 5400.21 | 5400.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6008 | LEAD TRAINING | 8413.33 | 8413.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6009 | Paint Removal Elevator Pits | 67036 | 1052.44 | 0 | 0 | 66147.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Site Demo | EXISTING BUILDINGS | 0%
02-6010 | REMOVE SUMP PUMPS | 36030 | 27496.03 | 1805.515 | 1805.515 | 1805.515 | 3117.43 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | 102770 | 73904.8 | 5369.995 | 5369.995 | 5369.995 | 5369.995 | 7385.22 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | 19766.24 | 6308.67 | 3112.9617 | 3112.9617 | 3112.9617 | 3112.9617 | 1005.7233 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6025 | REMOVE AREAWAYS LABOR | 82000 | 71381.46 | 2050.3233 | 2050.3233 | 2050.3233 | 2417.2467 | 2050.3233 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6026 | REMOVE AREAWAYS EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | 227761.46 | 385.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | 1520.48 | 0 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 253.41 | 253.4167 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | 15000 | 3487.09 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.82 | 1918.8167 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6050 | DEMO STAIRS AND RAMPS LABOR | 17116.64 | 12850.76 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | 2259.95 | 2259.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6060 | DEMO SECOND FLOOR APARTMENTS | 150000 | 130767.81 | 4808.0475 | 4808.0475 | 4808.05 | 4808.045 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6065 | DEMO FOR MECHANICAL | 200000 | 13880.04 | 2500 | 2500 | 45000 | 45000 | 45000 | 45000 | 1119.96 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6066 | FLOOR DRAIN DEMO | 70083.35 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6070 | DEMO FOR ELECTRICAL | 156200 | 29589.93 | 5000 | 5000 | 5000 | 40000 | 40000 | 31610.07 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6075 | DEMO FOR PLUMBING | 161879.62 | 16967.27 | 5000 | 5000 | 5000 | 40000 | 40000 | 49912.35 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6080 | ENTRANCE RAMP DEMO | 118800 | 46426.87 | 27937.11 | 25195.35 | 19240.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Demo | EXISTING BUILDINGS | 0%
02-6100 | ASBESTOS SUB | 1554903.14 | 1302498.98 | 27745.7 | 34819.5 | 34316.6667 | 34316.6667 | 75119.0667 | 41802.4 | 38802.4 | 36177.4 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
02-6110 | ASBESTOS SUB SUPPORT | 79333.7 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 9333.7 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
02-6120 | ASEBESTOS CONSULTANT | 23896.55 | 23896.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-6130 | ASBESTOS SUB ACCESS | 25543.46 | 21820.5 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | 1900.42 | 1900.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-7100 | STONE FOR EROSION CONTROL | 32382.03 | 32382.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
02-7200 | SOIL TESTING | 83535 | 83535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-1000 | FORMWORK NEW BUILDING | 2150000 | 2148203.85 | 12787.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
03-1100 | FORMWORK EXIST BLDGS | 786238.54 | 546850.51 | 40000 | 40000 | 40000 | 40000 | 40000 | 15006.95 | 24381.08 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-1105 | Conduit Encasement | 138600 | 97818.95 | 20000 | 20000 | 20000 | 5427.15 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-1200 | OPERATOR FOR CONCRETE WORK | 29756.82 | 29756.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-1300 | SET ANCHOR BOLTS FOR STEEL COLUMNS | 63065.21 | 63065.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-1400 | DRILL & GROUT DOWELS | 274808.11 | 263152.93 | 6475.152 | 6475.152 | 6475.152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-1500 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE | 162759.19 | 143861.99 | 6432.236 | 6432.236 | 3000 | 3032.728 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-1600 | FORMWORK SITE CONCRETE LABOR | 150000 | 126752.74 | 6500 | 6500 | 6500 | 3747.26 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
03-1610 | FORMWORK SITE CONCRETE MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-1700 | CONCRETE REINFORCEMENT NEW BUILDING UNLOAD | 56763.12 | 56763.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-1800 | CONCRETE REINFORCEMENT BARRIER FOUNDATIONS UNLOAD | 45000 | 38208.34 | 1455.676 | 1455.676 | 1455.676 | 1455.676 | 968.956 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
03-1900 | POUR CONCRETE NEW BUILDINGS | 530000 | 525785.09 | 4214.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
03-2000 | FINISH SLABS - NEW BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-2100 | POUR CONC EXIST BLDGS | 205190.25 | 189150.65 | 5000 | 5000 | 5000 | 1039.6 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-2110 | SHOTCRETE SUB | 166500 | 90593.84 | 25302.0533 | 25302.0533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
03-2120 | SHOTCRETE SUB CLEANUP | 30000 | 27911.35 | 2088.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
03-2200 | CONCRETE FOOTING FOR SITE FURNISHING | 13759.32 | 0 | 0 | 3439.83 | 3439.83 | 3439.83 | 3439.83 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
03-2300 | CONCRETE DUCTBANKS | 225000 | 218768.34 | 6231.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
03-2400 | CONCRETE SITE RETAINING WALL AND FOOTINGS | 36435.9 | 25421.31 | 11014.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
03-2500 | CONCRETE SHELF AND BOND BEAM EXTG BL (INCL FORMS) | 108745 | 103915.02 | 2658.22 | 2171.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-2600 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL | 13834.32 | 726.04 | 0 | 0 | 0 | 3277.07 | 3277.07 | 3277.07 | 3277.07 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-2700 | EXISTING BLDGS EQUIPMENT PAD WORK | 95.84 | 95.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-5000 | FURNISH CONCRETE | 1749303.72 | 1435171.81 | 40000 | 40000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
03-5100 | FURNISH INSULATION | 39414.64 | 39414.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-5200 | FURNISH REBAR | 14662.42 | 13710.55 | 200 | 118.9838 | 59.4919 | 373.3944 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
03-5250 | FURNISH WIREMESH | 47762.13 | 35283.88 | 2500 | 1559.7812 | 1200 | 4218.4688 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
03-5400 | FURNISH SAKCRETE | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 31500 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
03-5500 | FURNISH CONC PATCH MATERIAL | 9174.5 | 9174.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-6000 | FRP WORK | 420253.96 | 407746.27 | 12507.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
03-6010 | FRP Self Perform | 35296.6 | 35296.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-6100 | REBAR SUB | 1494408.08 | 1256293.37 | 41898.9371 | 41898.9371 | 41898.9371 | 94874.6514 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
03-6110 | REBAR SUB SUPPORT | 4416.84 | 3071.9 | 4069.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
03-6120 | REBAR DELIVERY SUPPORT | 4041.34 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
03-7000 | FORMWORK MATERIAL | 709305.66 | 551390.3 | 28000 | 28000 | 28000 | 28000 | 33397.62 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
03-7100 | MATERIAL FOR FLOWABLE FILL BACKFILL | 152745.59 | 152745.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
04-1000 | CLEAN CONC SURF FOUND WALL/PATCH VOIDS W/MORTAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
04-6000 | GROUT INJECTION SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
04-6100 | MASONRY SUB | 9090000 | 6613749.56 | 403372.1412 | 377150.6342 | 309000.6342 | 309000.6342 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
04-6110 | MASONRY SUB SUPPORT | 150000 | 25393.2 | 30000 | 30000 | 30000 | 30000 | 4606.8 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
04-6120 | MASON EUIP SUPPORT | 62569.54 | 62569.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
04-6130 | ANGLE FOR FACADE | 103266.58 | 69102.74 | 5000 | 5000 | 5000 | 19163.84 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
04-6200 | STONE SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
04-7000 | MASONRY CLEANER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
05-6000 | STRUCTURAL STEEL SUB | 5918133.95 | 5907478.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
05-6010 | STRUCTURAL STEEL SUB SUPPORT | 22760.18 | 15158.89 | 7601.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
05-6020 | GROUT STEEL COLUMNS | 30000 | 27222.11 | 2070.29 | 707.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
05-6030 | STEEL & CRANE DELIVERIES | 9097.96 | 9097.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
05-6040 | Ground Prep For Crane | 8898.32 | 8898.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
05-6050 | PREP COLUMNS FOR STEEL INSTALL | 2237.81 | 2237.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
05-6100 | MISC METALS SUB | 2010175 | 871189.78 | 142327.963 | 70295.25 | 155988 | 103992 | 12999 | 38997 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
05-6110 | MISC METALS SUB SUPPORT | 100040.22 | 7104.35 | 0 | 92935.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
05-6120 | BACKCHARGE E&Y | 1174.65 | 1174.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
05-6200 | SIGNAGE SUB | 138024 | 21000 | 0 | 11316 | 11316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
05-6210 | SIGNAGE SUB SUPPORT | 10000 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
06-6000 | CARPENTRY SUB | 1840000 | 1540449.87 | 117420.1925 | 67082.066 | 101775.2295 | 105521.171 | 57710.5855 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
06-6010 | CARPENTRY SUB SUPPORT | 50000 | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
06-6020 | EIFS | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
07-1000 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
07-1100 | 3 RIGID INSULATION UNDER GRADE NEW BLDGS | 34098.54 | 34098.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
07-1200 | PENETRATION FIRESTOPPING EXTG BLDGS | 55337.28 | 0 | 3458.58 | 6917.16 | 6917.16 | 13834.32 | 13834.32 | 3458.58 | 3458.58 | 3458.58 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
07-1300 | PENETRATION FIRESTOPPING NEW BLDGS | 27668.64 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
07-1400 | JOINT SEALANTS EXTG BLDGS | 55337.28 | 12860.73 | 2654.7844 | 5309.5688 | 5309.5688 | 10619.1375 | 10619.1375 | 2654.7844 | 2654.7844 | 2654.7844 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
07-1500 | JOINT SEALANTS NEW BLDGS | 27668.64 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
07-2000 | INSTALL WATERSTOP | 3491.54 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
07-5000 | FURNISH FIRESTOPPING | 90000 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
07-5100 | FURNISH JOINT SEALANT | 90000 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
07-6000 | WATERPROOFING SUB | 1007406.25 | 27305.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
07-6010 | WATERPROOFING SUB SUPPORT | 103510.13 | 1172.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
07-6020 | PREP SURFACE FOR WATERPROOFING | 51520.23 | 53225.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
07-6100 | METAL PANELS SUB | 3381506.41 | 1774255.81 | 245213.7583 | 346257.0917 | 420549.125 | 235327.9583 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
07-6110 | METAL PANELS SUB SUPPORT | 68493.59 | 10719.51 | 57774.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
07-6200 | ROOFING SUB | 1135000 | 705799.78 | 355028 | 145814.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
07-6210 | ROOFING SUB SUPPORT | 60000 | 1171.78 | 58828.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
07-6220 | PREP ROOF SURFACE FOR WORK | 40000 | 26323.7 | 0 | 13676.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
07-6300 | SPRAY ON FIREPROOFING SUB | 254755.38 | 247755.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | 21837.92 | 1377.92 | 20000 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0%
07-6320 | Maintain heat for Fireproofers | 9196.97 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
07-6330 | FIREPROOFING CLEANUP | 2771.84 | 2771.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
08-1600 | ACCESS HATCH | 114418.44 | 0 | 7151.1525 | 14302.305 | 14302.305 | 28604.61 | 28604.61 | 7151.1525 | 7151.1525 | 7151.1525 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
08-1700 | (1''4WX8H) S.S. FLOOD VENTS NEW BL (153) | 19069.74 | 0 | 1191.8588 | 2383.7175 | 2383.7175 | 4767.435 | 4767.435 | 1191.8588 | 1191.8588 | 1191.8587 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
08-1800 | 2'9"x8" SS FLOOD VENT W/SS SCRN NEW BLDG(8.06) | 6356.58 | 0 | 397.2862 | 794.5725 | 794.5725 | 1589.145 | 1589.145 | 397.2862 | 397.2862 | 397.2862 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
08-5000 | FURNISH HM DOORS | 191266.4 | 83834.36 | 26858.01 | 26858.01 | 26858.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
08-5010 | HM DOOR SUPPORT | 50313.29 | 313.29 | 3125 | 6250 | 6250 | 12500 | 12500 | 3125 | 3125 | 3125 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
08-5100 | FURNISH ACCESS HATCHES | 91781 | 91781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
08-6000 | OVERHEAD DOORS SUB | 22632 | 5658 | 0 | 0 | 0 | 0 | 16974 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
08-6010 | OVERHEAD DOORS SUB SUPPORT | 5000 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0%
08-6100 | GLAZING SUB | 28000 | 0 | 0 | 0 | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
08-6200 | LOUVERS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
09-6000 | STUCCO SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
09-6100 | TILE SUB | 34200 | 0 | 11400 | 11400 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
09-6110 | TILING SUB SUPPORT | 5000 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0%
09-6200 | VCT FLOORING SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
09-6300 | PAINT SUB | 533755 | 0 | 0 | 51071.4286 | 141428.5714 | 17500 | 75000 | 17500 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
09-6310 | PAINTING SUB SUPPORT | 40000 | 3160.89 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0%
09-6320 | EPOXY FLOORING | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
10-1000 | FIRE EXTINGUISHERS NEW BLDGS | 2772.14 | 935.19 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
10-1100 | TOILET ACCESSORIES NEW BLDGS | 11260.88 | 1407.61 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
10-1200 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) | 289147.86 | 14136.86 | 17188.1875 | 34376.375 | 34376.375 | 68752.75 | 68752.75 | 17188.1875 | 17188.1875 | 17188.1875 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
10-1300 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) | 22248.03 | 13400.37 | 693.415 | 1386.83 | 1386.83 | 2773.66 | 2773.66 | 693.415 | 693.415 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
10-1400 | WINDOW FLOODGATES (8.06 AND 8.14) | 50000.29 | 0 | 3125.0181 | 6250.0363 | 6250.0363 | 12500.0725 | 12500.0725 | 3125.0181 | 3125.0181 | 3125.0181 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
10-1500 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE | 19069.74 | 5523.22 | 846.6575 | 1693.315 | 1693.315 | 3386.63 | 3386.63 | 846.6575 | 846.6575 | 846.6575 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
10-5000 | FURNISH TOILET ACCESSORIES | 1488.1 | 1488.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
10-5100 | FURNISH FIRE EXTINGUISHERS | 2450 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
10-5200 | FURNISH AQUA FLOOD BARRIERS | 1682724.63 | 991858 | 186104.1575 | 186104.1575 | 186104.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
10-5300 | FURNISH 8.08 FLOOD DOORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
11-1000 | EXCAVATE & POUR CONCRETE FOOTINGS | 35505.12 | 0 | 5917.52 | 5917.52 | 0 | 0 | 5917.52 | 5917.52 | 5917.52 | 5917.52 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
11-6000 | PLAY AREA ITEMS SUB | 426718.49 | 251725.08 | 50675.1225 | 0 | 0 | 0 | 0 | 50675.1225 | 50675.1225 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
11-6010 | SUPPORT PLAY AREA | 50000 | 13225.17 | 0 | 0 | 0 | 0 | 6411.3733 | 6411.3733 | 23952.0833 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
14-6000 | ELEVATOR SUB | 1027903.5 | 31860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0%
14-6010 | ELEVATOR JUNCTION BOXES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
22-5000 | Purchase Yard Pumps | 99876.64 | 0 | 39876.64 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
22-6000 | PLUMBING SUB | 13100000 | 9558967.31 | 502610.633 | 514449.7498 | 550282.8988 | 415097.0032 | 192758.2754 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
22-6010 | PLUMBING BOND | 125426 | 125426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
22-6020 | PIPE INSULATION | 450000 | 173905 | 61606.7045 | 78393.75 | 34350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
22-6025 | PLUMBING INSULATION REMOVAL | 25000 | 8405.69 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.72 | 2765.7167 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
22-6030 | YARD PUMP SUPPLY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
22-6040 | YARD PUMP INSTALL | 209344 | 39010.84 | 10804.8838 | 21609.7675 | 21609.7675 | 43219.535 | 43219.535 | 10804.8838 | 10804.8838 | 8259.9037 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | 41078 | 41078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
22-6060 | PLUMBING SUB SUPPORT | 3359.95 | 3359.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
22-6070 | PLUMBING SCAFFOLD | 10000 | 9164.95 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 291.77 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
23-6000 | HVAC SUB | 24100000 | 20199921.02 | 1053107.6173 | 1288338.8215 | 796401.3526 | 319764.821 | 279375.7121 | 90559.3773 | 24200 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
23-6010 | HVAC SUB SUPPORT | 200000 | 0 | 33333.3333 | 33333.3333 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | sub | 0 | 0 | 0%
23-6020 | MECHANICAL LOUVERS | 0 | 8876.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
26-6000 | ELECTRICAL SUB | 50099472.19 | 26758199.8 | 2154626.4502 | 1779954.9915 | 2860913.6249 | 2713967.4611 | 2696110.3183 | 2304559.6893 | 1422455.9379 | 1421487.3515 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
26-6010 | TEMP ELECTRIC | 2449.46 | 2449.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
26-6020 | ELECTRICAL SUB SUPPORT | 50000 | 345.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub | 0 | 0 | 0%
26-6030 | EQUIPMENT INSTALLATION SUPPORT | 30000 | 22091.48 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.56 | 988.57 | 0 | 0 | Phased | Labor | Sub Support | Sub | 0%
31-1000 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND CONCRETE | 250000 | 187717.17 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 10897.9 | 7793.35 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
31-1100 | BACKFILL FOR FLOOD BARRIER FFTGS & CONCRETE SHELF | 152500 | 119707.21 | 7727.625 | 7727.625 | 7727.625 | 6475.63 | 3134.285 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Existing Buildings | EXISTING BUILDINGS | 0%
31-1200 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - ALL EXIST BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1300 | EXCAVATION NEW BLDGS | 205909.86 | 205909.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1400 | BACKFILL NEW BLDGS | 150000 | 148114.7 | 942.65 | 0 | 0 | 0 | 942.65 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
31-1500 | BACKFILL STONE/GRAVEL/CRUSHED STONE - ALL | 25000 | 23506.32 | 746.84 | 0 | 0 | 0 | 746.84 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | New Buildings | NEW BUILDINGS | 0%
31-1600 | PUMP OPERATOR FOR FLOOD BARRIERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1700 | DEWATER NEW BLDGS | 140469.48 | 140469.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1800 | INSTALL H PILES | 26802.94 | 26802.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1810 | SOE MATERIAL | 445577.25 | 445577.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1820 | INSTALL SHEETING | 210938.15 | 208728.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | New Buildings | NEW BUILDINGS | 0%
31-1830 | INSTALL LAGGING | 55626.32 | 55626.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1840 | MUD SLAB | 55578.77 | 55578.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1850 | SOE Sub | 402338.93 | 402338.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1860 | SOE Sub Support | 15201.85 | 15201.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-1900 | TREE PROTECTION | 50000 | 44097.39 | 0 | 0 | 0 | 0 | 5902.61 | 0 | 0 | 0 | 0 | 0 | hold | labor | Site Utilities | SITE | 0%
31-2000 | TEST PIT SUPPORT | 83241.53 | 83241.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-2010 | HAND EXCAVATION SUPPORT | 1978.47 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-2100 | EXCAVATION FOR SITE FURNISHING FOOTINGS | 40000 | 22024.13 | 3668.46 | 3668.46 | 3668.46 | 3668.46 | 3302.03 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-2200 | BACKFILL UTILITIES | 383288.4 | 313276.18 | 15940.65 | 15940.65 | 15940.65 | 8355.2 | 13835.07 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
31-2300 | EXCAVATION FOR PAVEMENTS | 10328.22 | 0 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-2400 | BACKFILL AND COMPACTION FOR PAVEMENTS | 7141.61 | 0 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.27 | 1190.2667 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-2500 | DENSE GRADED STONE BASE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-2600 | SITE FURNISHINGS | 38534.4 | 3313.85 | 0 | 0 | 8891.0525 | 8891.0525 | 8891.0525 | 8547.3925 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-2700 | BOLLARDS | 4816.8 | 0 | 0 | 0 | 2408.4 | 2408.4 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-2800 | DRINKING FOUNTAIN | 30000 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-2900 | LANDSCAPE BOULDERS | 80000 | 67325.84 | 5000 | 7674.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-3000 | BASKETBALL BACKSTOP | 3296.32 | 0 | 0 | 0 | 0 | 0 | 1648.16 | 1648.16 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
31-4000 | VAC TRUCKING SUB | 130000 | 118443.18 | 6556.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
31-5000 | FURNISH GRAVEL | 12744 | 0 | 0 | 0 | 12744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
31-5100 | FURNISH CLEAN FILL | 60000 | 7761.75 | 13059.5625 | 13059.5625 | 13059.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
31-6000 | DISPOSAL & TRUCKING SUB | 1710399 | 1485850.33 | 40000 | 40000 | 40000 | 20000 | 20000 | 10000 | 10757.67 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
31-6100 | DEWATERING SUB | 38820 | 38820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6120 | INSTALL SETTLING TANK AND DISCHARGE PIPING BEYOND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6130 | DISCHARGE LOCATIONS NOT INCLUDED WITHIN DEWATERING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6140 | DEEP WELL INSTALL SUPPORT & CLEANUP LABOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6180 | WATER TREATMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6190 | ELECTRIC SERVICE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6200 | DUMPSTERS FOR DEWATERING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-6210 | DEWATERING DISCHARGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-7000 | LUMBER - TREE PROTECTION | 22925.01 | 22925.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-7100 | DEWATERING PUMPS | 14.07 | 14.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-7200 | SOLDIER PILE & LAGGING BLDGS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-7300 | TRENCH BOX - UTILITY TRENCHES | 256261.83 | 197207.14 | 15000 | 15000 | 15000 | 5441.31 | 8613.38 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
31-7400 | PLATES - UTILITY TRENCHES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
31-7500 | LUMBER - UTILITY TRENCHES | 16396.43 | 16396.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-5000 | FURNISH BOLLARDS | 10010 | 10010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-5100 | FURNISH SUBBASE | 56700 | 0 | 0 | 10000 | 10000 | 20000 | 10000 | 6000 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-5200 | FURNISH BENCHES & TABLES | 393000 | 380785 | 50651.875 | 50651.875 | 50651.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-5300 | FURNISH PING PONG TABLE | 32700 | 22413 | 2571.75 | 2571.75 | 2571.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-5400 | FURNISH BIKE RACK | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-5500 | FURNISH DRINKING FOUNTAIN | 9000 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-5600 | FURNISH SHOWER EQUIPMENT | 26188.02 | 0 | 0 | 0 | 26188.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-5700 | FURNISH LANDSCAPE BOULDERS | 191092.5 | 191092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-5800 | FURNISH BASKETBALL BOARD AND POST | 5340 | 0 | 0 | 0 | 5340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
32-6000 | SAWCUTTING | 134276.38 | 134276.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-6100 | ASPHALT SUB | 210269.79 | 0 | 0 | 0 | 0 | 0 | 70089.93 | 70089.93 | 70089.93 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
32-6200 | FLATWORK SUB | 3075000 | 645550.02 | 355256.0073 | 436078.6937 | 204528.6937 | 268147.1429 | 165700 | 29095.2381 | 381936.6667 | 273918.0952 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
32-6210 | FLATWORK SUB SUPPORT | 131865.87 | 3898.15 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | Hold | Labor | Sub Support | Sub | 0%
32-6220 | JMC EQUIP BACKCHARGE | 9119.41 | 14635.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-6230 | GRADING FOR RESTORATION | 289044.39 | 99550.67 | 40000 | 40000 | 40000 | 40000 | 29493.72 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-6400 | COURT SURFACES SUB | 415000 | 0 | 0 | 0 | 0 | 0 | 141666.6667 | 141666.6667 | 131666.6667 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
32-6410 | Prep Basketball Courts | 10000 | 3129.11 | 0 | 0 | 0 | 0 | 6870.89 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
32-6500 | FENCING SUB | 1318652.5 | 757678.8 | 0 | 0 | 67720.9302 | 42461.9638 | 23636.4858 | 373930.6202 | 53223.7 | 0 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
32-6510 | FENCE MESH INSTALL | 99496.11 | 98618.38 | 1453.4117 | 1453.4117 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Maintenance | Overhead | 0%
32-6520 | FENCE INSTALL SELF PERFORM | 507000 | 350859 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 26612.24 | 9528.76 | 0 | 0 | Phased | Labor | Site Maintenance | Overhead | 0%
32-6600 | LANDSCAPING SUB | 635225.54 | 77215.59 | 0 | 31696.4952 | 60832.5068 | 0 | 0 | 0 | 214669.3285 | 213247.9221 | 0 | 0 | SOV | Sub | 0 | 0 | 0%
32-6610 | CLEAR AND GRUB | 87764.08 | 87764.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
32-6620 | SELF PERFORM TREE REMOVAL | 24373.2 | 27341.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Restoration | SITE | 0%
32-6630 | LANDSCAPING SUB SUPPORT | 50000 | 23531.37 | 0 | 12500 | 12500 | 1468.63 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Labor | Sub Support | Sub | 0%
32-6700 | Arbor Consultant | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1000 | MAINT & PROT EXIST PRIVATELY OWNED UTILITIES | 51626.6 | 44180.68 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1789.6557 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-1100 | TERMINATE AND DEMOLISH EXISTING UTILITIES | 56789.26 | 16146.65 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.38 | 3836.3157 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-1200 | WATER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1300 | WELDING OF WATER PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1310 | WATER PIPE FIT UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1400 | INSTALL JOJNT INSULATORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1500 | PRESSURE & AIR TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1600 | FIX 10% FAILURE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1700 | PRESSURE & AIR RE-TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1800 | CONDENSATE & STEAM PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1900 | WELDING OF STEAM AND CONDENSATE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-1910 | STEAM AND CONDENSATE PIPE FIT UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2000 | INSTALL JOJNT INSULATORS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2100 | PRESSURE & AIR TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2200 | FIX 10% FAILURE PIPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2210 | EXCAVATE UTILITIES | 2945.71 | 2945.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2300 | PRESSURE & AIR RE-TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2400 | DEWATER UTILITIES | 53037.69 | 53037.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-2500 | DUCTILE IRON PIPE SEWERS | 276988.13 | 203154.02 | 18158.716 | 18158.716 | 28016.082 | 9500.596 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-2510 | SEWER LINE WORK | 200000 | 60613.81 | 20000 | 28803.258 | 30000 | 20000 | 20582.932 | 20000 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-2600 | CATCH BASIN CONNECTIONS | 285541.31 | 212032.93 | 20000 | 31159 | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-2700 | STORM DETENTION TANK (I DON'T THINK THIS EXISTS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-2800 | DRAINAGE MANHOLES | 1485.51 | 1485.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-2900 | REMOVE AREA DRAINS | 32809.86 | 26769.12 | 1357.084 | 1357.084 | 1969.488 | 1357.084 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-3000 | ELECTRICAL MANHOLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-3100 | UTILITY TRENCHES | 716744.78 | 700923.75 | 5000 | 5000 | 10279.738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-3200 | FENCES & PLATES @ TRENCHES (THIS WILL BE DIFFERENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-3300 | ADD''L CRANE FOR SUBCONTRACTORS SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-4000 | SITE LIGHTING EXCAVATION | 211275.05 | 59306.6 | 10000 | 10000 | 10000 | 15000 | 15000 | 6523.03 | 85445.42 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | 881653.58 | 724386.41 | 40767.885 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
33-5100 | FURNISH 2 COPPER WATER PIPE | 115654.5 | 0 | 0 | 0 | 25000 | 25000 | 35000 | 30654.5 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
33-5200 | FURNISH DIP DRAINAGE PIPE | 276580.36 | 280874.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-5300 | FURNISH PRECAST AREA DRAINS & MHS | 126016 | 77921.81 | 12961.0475 | 12961.0475 | 12961.0475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material | 0 | 0 | 0%
33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-5500 | FURNISH DETENTION TANK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
33-5600 | CHLORINATION | 100000 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-6000 | UNDERGROUND UTILITY MATERIAL DELIVERY | 25000 | 20750.65 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-6010 | UTILITY PIPE PLACEMENT IN TRENCH | 115000 | 104182.59 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.34 | 1545.3486 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-7000 | WELDING MATERIALS | 32664 | 28362.57 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
33-9000 | GAS LINE DAMAGE | 110287.72 | 87073.27 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 3401.8063 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
97-6000 | Bulk ACM removal, hose wire insulation | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6200 | Bulk ACM removal, pipe insulation and assoc jack | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6300 | Bulk ACM removal, pipe insulation and braided wire | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6400 | Bulk ACM removal, ACM Contamined Debris | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | Hold | Labor | Change Order | 0 | 0%
97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | Hold | Labor | Change Order | 0 | 0%
97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | Hold | Labor | Change Order | 0 | 0%
98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | 51926.66 | 75219.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | 141408 | 397322.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Labor | Site Utilities | SITE | 0%
99-1000 | Supervision | 7270000 | 5487436.45 | 220000 | 242000 | 220000 | 220000 | 175000 | 175000 | 150000 | 100000 | 67763.55 | 0 | Phased | overhead | 0 | 0 | 0%
99-1010 | CLAIMS CONSULTANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-1020 | LEGAL COSTS | 50000 | 5030 | 0 | 0 | 0 | 0 | 4970 | 10000 | 10000 | 10000 | 10000 | 0 | Phased | overhead | 0 | 0 | 0%
99-1100 | TEAMSTER | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-1200 | OPER ENG MASTER MECH | 270000 | 82331.19 | 0 | 0 | 27974.1557 | 27974.1557 | 27974.1557 | 0 | 0 | 0 | 0 | 0 | Hold | Labor | Site Maintenance | Overhead | 0%
99-1300 | OPER ENG MECH | 260000 | 74008.48 | 0 | 0 | 27641.78 | 27641.78 | 27641.78 | 0 | 0 | 0 | 0 | 0 | Hold | Labor | Site Maintenance | Overhead | 0%
99-2000 | SURVEY SUB | 687620.75 | 558135 | 47573.75 | 20000 | 20000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
99-3000 | SECURITY SUB | 648295.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-3100 | CONTAINERS - 30 CY | 1150000 | 783597.85 | 60000 | 60000 | 50000 | 50000 | 50000 | 50000 | 30000 | 29031.59 | 0 | 0 | Phased | Material | 0 | 0 | 0%
99-4000 | YARD W/ TEMP ELECT | 138034 | 119118.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 8915.59 | 0 | Phased | Labor | Closeout | Closeout | 0%
99-4050 | COMPUTER/SOFTWARE | 90000 | 84407.41 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 607.054 | 0 | monthly | overhead | 0 | 0 | 0%
99-4100 | STATIONWORK DESK | 8710.4 | 6193.68 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 251.672 | 0 | monthly | overhead | 0 | 0 | 0%
99-4150 | IT SUPPORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-4200 | PHONE EQUIPMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-4250 | PHONE SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-4300 | PRINTERS/PLOTTER | 55000 | 45283.5 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 1270.174 | 0 | monthly | overhead | 0 | 0 | 0%
99-4350 | SUPPLIES | 90000 | 65350.32 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 2819.837 | 0 | monthly | overhead | 0 | 0 | 0%
99-4400 | TELEPHONE | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-4450 | CELL PHONES | 29506.48 | 20259 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 978.539 | 0 | monthly | overhead | 0 | 0 | 0%
99-4500 | ELECTRIC | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-4550 | SANITATION | 305000 | 168441.5 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 10000 | 5000 | 400.977 | 0 | Phased | overhead | 0 | 0 | 0%
99-4560 | SITE MAINTENANCE | 1110000 | 881914.01 | 34560 | 34560 | 34560 | 30000 | 25000 | 25000 | 17280 | 15000 | 12125.99 | 0 | Phased | Labor | Site Maintenance | Overhead | 0%
99-4570 | BASEMENT MAINTENANCE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-4600 | VEHICLES | 160347.74 | 87752.55 | 10000 | 10000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 2988.36 | 0 | Phased | Equipment | 0 | 0 | 0%
99-4650 | FUEL | 158001.22 | 154957.01 | 3044.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phased | Equipment | 0 | 0 | 0%
99-4700 | PETTY CASH | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-5000 | OFFICE RENT | 561000 | 466172.95 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13110.3144 | 0 | 0 | 0 | Phased | overhead | 0 | 0 | 0%
99-5100 | NYCHA OFFICE FURNITURE | 55000 | 38878.87 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 1612.113 | 0 | monthly | overhead | 0 | 0 | 0%
99-6000 | SMALL TOOLS | 640000 | 598973.36 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 9770.2436 | 0 | 0 | monthly | Material | 0 | 0 | 0%
99-7000 | LABOR ESCAL | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-7100 | PREMIUM COST | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency | 0 | 0 | 0%
99-7200 | HOLIDAY PAY | 265722.37 | 225352.8 | 9200 | 0 | 0 | 6440 | 0 | 4600 | 0 | 4600 | 0 | 0 | Phased | overhead | 0 | 0 | 0%
99-7210 | PAID TIME OFF | 68000 | 30333.77 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 3971.162 | 0 | monthly | overhead | 0 | 0 | 0%
99-7300 | LOST TIME | 150000 | 49377.75 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 18294.9545 | 0 | hold | overhead | 0 | 0 | 0%
99-7400 | PERMITS | 30000 | 18673.7 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 0 | 0 | 0 | 0 | Phased | overhead | 0 | 0 | 0%
99-7500 | ENGINEERING SUB | 183350 | 171007.28 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 0 | 0 | 0 | 0 | Phased | Sub | 0 | 0 | 0%
99-7510 | CADD SERVICES | 20000 | 14395.69 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 0 | 0 | 0 | 0 | Phased | overhead | 0 | 0 | 0%
99-7600 | SECTION 3 ADMINISTRATOR SUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-8000 | EQUIPMENT | 1561716.25 | 1193701.71 | 80000 | 60000 | 50000 | 40000 | 30000 | 20000 | 17725.98 | 85133.27 | 0 | 0 | Phased | Equipment | 0 | 0 | 0%
99-8050 | AID TO SUBS | 250000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | Phased | Sub | 0 | 0 | 0%
99-8100 | PROJECT SIGNS | 4000 | 3181.22 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 0 | 0 | monthly | Material | 0 | 0 | 0%
99-8200 | PUNCH LIST | 250000 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | Phased | Labor | Closeout | Closeout | 0%
99-9000 | BOND | 1170144 | 948765.41 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 22137.859 | 0 | monthly | overhead | 0 | 0 | 0%
99-9100 | INSURANCE | 3248000 | 1784034.35 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 132148.565 | 0 | monthly | overhead | 0 | 0 | 0%
99-9999 | Accruals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%
99-NY0001 | Supervision- Do Not Use | 22408.12 | 22408.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent | 0 | 0 | 0%

## Billing Forecast
Schedule Act | Item # | Description | Current Commitment | Previous Total | January | February | March | April | May | June | July | August | September | October | Final Total | SOV Level 1 | SOV Level 2 | Percent Complete | Sub | Category 1 | Category 2 | Billing Category | Total>Commitment?
MOBE-01005 | 11 | Mobilization | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
MOBE-01005 | 12 | Bond | 1170144 | 1170144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
MOBE-01005 | 13 | Insurance | 1057256 | 750651.76 | 41133.4242 | 42285.145 | 37330.9183 | 45389.2083 | 37549.2423 | 25657.4558 | 17820.7329 | 14508.8491 | 11855.6435 | 33073.6207 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
OGE-01010 | 14 | Project Management | 7740000 | 5495400 | 301131.139 | 309562.7004 | 273293.6088 | 332287.0449 | 274891.9234 | 187834.0796 | 130462.6999 | 106216.935 | 86793.2464 | 242126.6225 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
01500 | 15 | Noise Reduction Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
02160 | 16 | Lead Safe Work Practice Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
SGN-01010 | 17 | Rodent Control | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
01575 | 18 | Waste Management Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
01500 | 19 | Site Specific Safety Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
01500 | 20 | Site Safety Plan | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
01540 | 21 | Quality Plan | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
01500 | 22 | CPM - Baseline | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
OGE-01010 | 23 | CPM - Monthly Updates | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
MOBE-01005 | 24 | Field Office - Set Up | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
OGE-01010 | 25 | Field Office - Rent, Maintenance and Supplies | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
MOBE-01005 | 26 | Yard - Set Up | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
OGE-01010 | 27 | Yard - Maintenance | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
OGE-01010 | 28 | Photos | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-03315 | 29 | Filing Alt1 permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-03025 | 30 | Filing Alt2 permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-03005 | 31 | Filing NB permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-02005 | 32 | Filing CCD1 for Fence | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-02005 | 33 | Filing Fence Permit | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-04005 | 34 | Filing dewatering permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-01005 | 35 | Filing DOT permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-05005 | 36 | Filing Demo Permit | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-07010 | 37 | Filing Asbestos permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
PERMIT-06005 | 38 | Filing Electrical Permits | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
02020 | 39 | Shop Drawings / Submittals (exc O&M, As-Built and Warranty) | 218350 | 163762.5 | 10917.5 | 10917.5 | 10917.5 | 0 | 0 | 0 | 0 | 0 | 0 | 21835 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
M905 | 40 | O&M, As-Built and Warranty | 155650 | 0 | 0 | 0 | 0 | 0 | 31130 | 31130 | 31130 | 31130 | 31130 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
MOBE-01005 | 41 | Survey | 24000 | 17040 | 933.74 | 959.8843 | 847.422 | 1030.3474 | 852.3781 | 582.4313 | 404.5355 | 329.3548 | 269.1263 | 750.7802 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
MOBE-01005 | 42 | Engineering | 36000 | 25560 | 1400.6099 | 1439.8265 | 1271.1331 | 1545.5211 | 1278.5671 | 873.6469 | 606.8033 | 494.0323 | 403.6895 | 1126.1703 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
S8-01770 | 43 | Demobilization/Project Closeout | 36850 | 0 | 0 | 0 | 0 | 0 | 7370 | 7370 | 7370 | 7370 | 7370 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
SGN-01055 | 44 | Soil Testing and Management Plan | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
SG7-03520 | 45 | Punchlist | 51150 | 0 | 0 | 0 | 0 | 0 | 10230 | 10230 | 10230 | 10230 | 10230 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
S8E-03330 | 46 | Training | 61600 | 0 | 0 | 0 | 0 | 0 | 12320 | 12320 | 12320 | 12320 | 12320 | 0 | 0 | Overhead | 001 - General Conditions | 0% | General Conditions | Overhead |  | Overhead | 0
SG1-01005 | 47 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01010 | 48 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 49 | Assumed Flooring Material (Slab Penetrations) | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01020 | 50 | Pipe Insulation | 132300 | 132300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01005 | 51 | Duct Seal | 43200 | 43200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 52 | Vinyl Membrane and Mastic | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 53 | Caulk | 110250 | 110250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01015 | 54 | Fibrous Slate | 12240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01020 | 55 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01020 | 56 | Underground Utility Materials | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01105 | 57 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01220 | 58 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01105 | 59 | Remove existing vent / window and frame - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01105 | 60 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01115 | 61 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01115 | 62 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01115 | 63 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01210 | 64 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01105 | 65 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01205 | 66 | Remove existing stair - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01205 | 67 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01205 | 68 | Existing Ramp railing to be be removed - 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01410 | 69 | FORM FLOOD BARRIER FOUNDATIONS - SG-1 | 50095 | 30057 | 0 | 20038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01450 | 70 | DRILL & GROUT DOWELS - SG-1 | 6278 | 6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01450 | 71 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-1 | 30151 | 30151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01470 | 72 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-1 | 33906 | 16953 | 9687.4286 | 0 | 0 | 2421.8571 | 2421.8571 | 2421.8571 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01440 | 73 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-1 | 18856 | 18856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01415 | 74 | Footing/Pier | 17434 | 8717 | 4358.5 | 4358.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01435 | 75 | Retaining Walls | 4571 | 2285.5 | 1523.6667 | 761.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01535 | 76 | Entrance Slab | 21380 | 1069 | 10155.5 | 10155.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01810 | 77 | Concrete Shelf | 4895 | 4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01350 | 78 | New Concrete Curb Next to Existing Wall | 297 | 0 | 148.5 | 148.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 79 | GFRP Sikawrap 100 G | 58344 | 0 | 0 | 0 | 19448 | 19448 | 19448 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 003 - SG1 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01440 | 80 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-1 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01015 | 81 | Overhead protection for Masonry | 10175 | 7631.25 | 0 | 2543.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01820 | 82 | 6" vertically reinforced CMU | 230912 | 219366.4 | 0 | 0 | 11545.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 83 | 2" Face brick | 597520 | 179256 | 0 | 100000 | 106088 | 106088 | 106088 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 84 | 2" rigid Insulation | 39424 | 19712 | 0 | 0 | 6570.6667 | 6570.6667 | 6570.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01820 | 85 | Coping Stone C1/A-300 | 13200 | 11880 | 0 | 0 | 440 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05440 | 86 | MATERIAL AND FABRICATION | 5824 | 0 | 5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01315 | 87 | INSTALLATION | 6600 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01860 | 88 | Temporary Aluminum Over Pass Stairs | 57196 | 0 | 28598 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02120 | 89 | PENETRATION FIRESTOPPING EXTG BLDG - SG-1 | 11505 | 0 | 10066.875 | 0 | 0 | 479.375 | 479.375 | 479.375 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01320 | 90 | JOINT SEALANTS EXTG BLDGS - SG-1 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01830 | 91 | Bituthene 4000 waterproofing membrane | 37752 | 9438 | 0 | 0 | 9438 | 9438 | 9438 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01830 | 92 | GE Elemax 2600 Silicone air and vapor barrier | 31416 | 0 | 0 | 0 | 10472 | 10472 | 10472 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01370 | 93 | Crystalline Waterproofing at perimeter walls | 37260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01825 | 94 | Waterproofing at foundation walls | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 006 - SG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01860 | 95 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 007 - SG1 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01330 | 96 | Doors, Frames & Hardware - Labor | 6672 | 0 | 2224 | 2224 | 2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 007 - SG1 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 97 | Furnish Doors | 2091 | 0 | 522.75 | 522.75 | 522.75 | 261.375 | 261.375 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 98 | Layout | 2829 | 2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 99 | Loading | 3858 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 100 | Framing & Drywall - Materials | 2829 | 0 | 943 | 943 | 943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01325 | 101 | Framing- Labor | 4629 | 0 | 1543 | 1543 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01330 | 102 | Drywall - Labor | 4629 | 0 | 1543 | 1543 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01330 | 103 | Tape/ Spackle finishes | 3086 | 0 | 1028.6667 | 1028.6667 | 1028.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01855 | 104 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-01860 | 105 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-1 | 70001 | 35000.5 | 21875.3125 | 0 | 0 | 4375.0625 | 4375.0625 | 4375.0625 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01860 | 106 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-1 | 31714 | 0 | 19821.25 | 0 | 0 | 3964.25 | 3964.25 | 3964.25 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01860 | 107 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-1 | 68909 | 0 | 43068.125 | 0 | 0 | 8613.625 | 8613.625 | 8613.625 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01865 | 108 | Temporary Egress Stair Storage Sign | 2640 | 0 | 1760 | 0 | 0 | 293.3333 | 293.3333 | 293.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01865 | 109 | Address Signs | 4950 | 0 | 3300 | 0 | 0 | 550 | 550 | 550 | 0 | 0 | 0 | 0 | 0 | SG1 | 009 - SG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG6-02150 | 110 | Switches and Receptacles | 10950 | 10402.5 | 0 | 0 | 0 | 182.5 | 182.5 | 182.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02525 | 111 | Switchgear & Panelboard Energization | 19163 | 9581.5 | 0 | 0 | 0 | 3193.8333 | 3193.8333 | 3193.8333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02405 | 112 | Switchgear & Panelboard Installation | 229950 | 218452.5 | 0 | 0 | 11497.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02405 | 113 | Switchgear & Panelboard Terminations | 19163 | 18204.85 | 0 | 0 | 958.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02530 | 114 | Switchgear & Panelboard Testing | 19163 | 14372.25 | 0 | 0 | 0 | 1596.9167 | 1596.9167 | 1596.9167 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02025 | 115 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02110 | 116 | Fire Alarm Conduit | 68438 | 65016.1 | 0 | 0 | 0 | 1140.6333 | 1140.6333 | 1140.6333 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02365 | 117 | Fire Alarm Wiring | 65700 | 62415 | 0 | 0 | 0 | 1095 | 1095 | 1095 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02365 | 118 | Fire Alarm Devices | 93075 | 88421.25 | 0 | 0 | 0 | 1551.25 | 1551.25 | 1551.25 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02365 | 119 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 120 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG6-02505 | 121 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01005 | 122 | EXCAVATION NEW BLDGS - SG-6 | 38439 | 38439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01055 | 123 | BACKFILL NEW BLDGS - SG-6 | 18099 | 18099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01005 | 124 | DEWATERING COVERAGE FOR NEW BUILDINGS - SG-6 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01005 | 125 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-6 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01005 | 126 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-6 | 34172 | 34172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 082 - SG6 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01070 | 127 | FORMWORK NEW BUILDING - SG-7 | 353185 | 353185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01175 | 128 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-7 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01040 | 129 | POUR CONCRETE NEW BUILDINGS - SG-7 | 220248 | 220248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01135 | 130 | FINISH SLABS - SG-7 | 17896 | 17896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 131 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01075 | 132 | Footing/Pier | 174820 | 174820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 133 | Floor Slabs | 31988 | 31988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 134 | Cellar Pit First Floor Slab | 490 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 135 | Cellar Pit Second Floor Slab | 544 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01170 | 136 | Meter Room Second Floor Slab | 762 | 762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01130 | 137 | Cellar Pit | 47722 | 47721.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01155 | 138 | Gas Meter Room | 12726 | 12726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01205 | 139 | WWM-Slabs | 6648 | 6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 083 - SG7 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01230 | 140 | 8" CMU (3 hour rated) | 171133 | 162576.35 | 8556.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01275 | 141 | 4" CMU | 39402 | 37431.9 | 985.05 | 985.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 142 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01230 | 143 | 6" CMU (2 hour rated) | 38214 | 36303.3 | 1910.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01275 | 144 | Face Brick 3-5/8" | 235521 | 188416.8 | 47104.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01275 | 145 | 3-1/8" Rigid insulation | 30712 | 15356 | 7678 | 7678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01250 | 146 | Cast Stone with SS letters | 8521 | 3408.39 | 0 | 1704.2033 | 1704.2033 | 1704.2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01230 | 147 | Steel Channel | 16720 | 0 | 0 | 0 | 5573.3333 | 5573.3333 | 5573.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01230 | 148 | Cont. Shelf angle | 9240 | 0 | 0 | 0 | 3080 | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 149 | STEEL (MATERIAL ONLY) | 178532 | 178532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 150 | FABRICATION COSTS | 303034 | 303034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 151 | METAL DECK (BUY-OUT) | 15270 | 15270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 152 | ANCHORS & EMBEDS | 9398 | 9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 153 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01105 | 154 | SURVEYING | 14096 | 14096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 155 | STEEL & DECK ERECTION | 610764 | 610764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 156 | BOLTS AND HARDWARE | 23492 | 23492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01105 | 157 | TRUCKING | 11746 | 11746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01270 | 158 | Dunnage Grating Galvanized | 64556 | 0 | 32278 | 32278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01270 | 159 | Dunnage Guard Rail | 30415 | 30415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01270 | 160 | Dunnage Stair and Guard Rail | 13035 | 13035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01290 | 161 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 128548 | 118548 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01295 | 162 | 1st to 2nd Floor Ship Ladder with Cages | 25750 | 15450 | 7725 | 2575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01295 | 163 | Bulkhead Ship Ladder to Roof at 2 Locations | 12383 | 1238.3 | 5572.35 | 5572.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 164 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01305 | 165 | Layout | 8028 | 0 | 0 | 0 | 1146.8571 | 6881.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 166 | Loading | 15326 | 0 | 0 | 0 | 2000 | 3000 | 6884 | 3442 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 167 | Exterior Framing, Insulation & Drywall - Materials | 67511 | 67511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 168 | Exterior Framing- Labor | 58049 | 0 | 0 | 0 | 8292.7143 | 10000 | 26504.1905 | 13252.0952 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01125 | 169 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-7 | 7236 | 7236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-02475 | 170 | PENETRATION FIRESTOPPING NEW BLDG - SG-7 | 11505 | 0 | 0 | 0 | 0 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG3-01320 | 171 | JOINT SEALANTS NEW BLDGS - S7 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01230 | 172 | Air Film | 19195 | 0 | 0 | 0 | 6398.3333 | 6398.3333 | 6398.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01305 | 173 | Insulation- Labor | 7798 | 0 | 0 | 0 | 1114 | 6684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01025 | 174 | Crystalline Waterproofing at plumbing shaft | 4474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 175 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01072 | 176 | Waterproofing at foundation | 8522 | 8522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 177 | Layout | 87373 | 0 | 0 | 0 | 29124.3333 | 29124.3333 | 29124.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 178 | Framing | 198097 | 198097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 179 | Insulation | 35480 | 35480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01255 | 180 | Cladding Install | 248360 | 0 | 0 | 0 | 82786.6667 | 82786.6667 | 82786.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01225 | 181 | Fireproofing | 41800 | 41800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01265 | 182 | P&I Cold Applied Roof Membrane | 99622 | 0 | 0 | 99622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01265 | 183 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 101829 | 0 | 0 | 101829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01265 | 184 | P&I Aluminum Coping | 7458 | 0 | 0 | 7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01260 | 185 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S7 | 10270 | 0 | 2567.5 | 2567.5 | 2567.5 | 1283.75 | 1283.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 186 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01245 | 187 | Doors, Frames & Hardware - Labor | 18070 | 4517.5 | 13552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01317 | 188 | Louvers Install | 61948 | 0 | 0 | 0 | 20649.3333 | 20649.3333 | 20649.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 189 | Furnish Doors | 18815 | 0 | 4703.75 | 4703.75 | 4703.75 | 2351.875 | 2351.875 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01305 | 190 | Sheathing & Drywall - Labor | 49634 | 0 | 0 | 0 | 7090.5714 | 20000 | 15028.9524 | 7514.4762 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01245 | 191 | Tape/ Spackle finishes | 14144 | 0 | 14144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01315 | 192 | ACT ceilings - Materials | 3858 | 0 | 0 | 0 | 0 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01315 | 193 | ACT ceilings - Labor | 12788 | 0 | 0 | 0 | 0 | 2000 | 7192 | 3596 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01280 | 194 | Direct Applied Stucco | 53251 | 0 | 26625.5 | 26625.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01325 | 195 | Painting SG-7 | 110000 | 0 | 0 | 0 | 0 | 0 | 35000 | 75000 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01310 | 196 | Cermic Tile and Base - SG-7 | 5490 | 0 | 0 | 0 | 0 | 2745 | 2745 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 197 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01260 | 198 | FIRE EXTINGUISHERS NEW BLDGS - SG-7 | 733 | 0 | 183.25 | 183.25 | 183.25 | 91.625 | 91.625 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01260 | 199 | TOILET ACCESSORIES NEW BLDGS - SG-7 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 200 | Stair Identification Sign | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 201 | Stairway Floor number and ID Sign | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 202 | Room Sign | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 203 | Exit Sign | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 204 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01330 | 205 | Stairway Flood Access Door | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | SG7 | 090 - SG7 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 206 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 2329.2 | 2846.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 207 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 2640 | 2520 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 208 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-03105 | 209 | ESCUTCHEONS FOR PLUMBING PIPING | 2178 | 0 | 2079 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 210 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 22000 | 0 | 21000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 211 | HANGERS AND SUPPORTS | 21648 | 15153.6 | 6494.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 212 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2728 | 0 | 2604 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 213 | DOMESTIC WATER PIPING | 255409 | 114934.05 | 100000 | 40474.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 214 | DOMESTIC WATER PIPING SPECIALTIES | 30184 | 12073.6 | 18110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 215 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 16500 | 30000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 216 | SANITARY WASTE PIPING | 104439 | 78329.25 | 20000 | 6109.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 217 | SANITARY WASTE PIPING SPECIALTIES | 20504 | 19478.8 | 1025.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 218 | STORM DRAINAGE PIPING SPECIALTIES | 53504 | 45478.4 | 8025.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 219 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-03140 | 220 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 21824 | 0 | 7274.6667 | 14549.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03140 | 221 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 322085 | 128834 | 20000 | 0 | 75000 | 75000 | 15500.6667 | 7750.3333 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 222 | GAS SERVICE AND PIPING | 271645 | 67911.25 | 100000 | 0 | 14664.5 | 29689.75 | 29689.75 | 29689.75 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03140 | 223 | PLUMBING FIXTURES | 18392 | 0 | 6130.6667 | 12261.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 224 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 78682 | 78682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03105 | 225 | Plumbing Pipe Insulation | 2374 | 0 | 2266.0909 | 107.9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02145 | 226 | Heat Trace | 5475 | 0 | 0 | 3650 | 0 | 0 | 0 | 0 | 456.25 | 456.25 | 456.25 | 456.25 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGS-M-01005 | 227 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 228 | Exhaust Fans: Furnish | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 229 | Exhaust Fans: Install | 18700 | 14025 | 4007.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 230 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 231 | Electric Unit Heaters: Furnish | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 232 | Steam Unit Heaters: Furnish | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 233 | Steam Unit Heaters: Install | 32175 | 0 | 0 | 0 | 14855.4939 | 17319.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 234 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 235 | Heating and Ventilation Unit: Install | 26675 | 0 | 0 | 0 | 12316.0932 | 14358.9068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 236 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 237 | Condensate Return Unit: Install | 25575 | 0 | 0 | 0 | 11808.2131 | 13766.7869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 238 | Steam Traps: Furnish | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03142 | 239 | Steam Traps: Install | 14300 | 0 | 0 | 0 | 6602.4417 | 7697.5583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 240 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 157465 | 15746.5 | 0 | 0 | 73648.2487 | 62739.1269 | 5331.1244 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 241 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 242 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 271700 | 0 | 0 | 0 | 127077.3136 | 108254.0297 | 27063.5074 | 9305.1494 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 243 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 88000 | 0 | 0 | 0 | 41158.6441 | 35062.0339 | 8765.5085 | 3013.8136 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03135 | 244 | Mechanical Pipe: Hydrostatic Testing | 2035 | 0 | 0 | 0 | 951.7936 | 810.8095 | 202.7024 | 69.6944 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 245 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 19250 | 17325 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 246 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 34650 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-03145 | 247 | HVAC Ductwork: Testing & Balancing | 2200 | 0 | 0 | 0 | 317.8899 | 0 | 0 | 1882.1101 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 248 | Controls: Furnish and Install: Devices | 110000 | 16500 | 0 | 0 | 0 | 0 | 39947.3684 | 53070.1754 | 482.4561 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 249 | Controls: Furnish and Install: Controls Conduit | 49500 | 5940 | 0 | 0 | 0 | 0 | 17976.3158 | 23881.5789 | 1702.1053 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 250 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 0 | 0 | 3994.7368 | 5307.0175 | 1698.2456 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 251 | Controls: Connect to Final Termination Points | 11000 | 0 | 0 | 0 | 0 | 0 | 3994.7368 | 5307.0175 | 1698.2456 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 252 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-03510 | 253 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 0 | 0 | 2396.8421 | 3184.2105 | 1018.9474 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 254 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14520 | 3630 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 255 | Insulation: Furnish and Install: Piping Insulation | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24200 | 6050 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 256 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14520 | 3630 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 257 | ATS Energization | 24638 | 0 | 0 | 12319 | 0 | 0 | 0 | 0 | 3079.75 | 3079.75 | 3079.75 | 3079.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 258 | ATS Installation | 344925 | 172462.5 | 0 | 86231.25 | 0 | 0 | 0 | 0 | 21557.8125 | 21557.8125 | 21557.8125 | 21557.8125 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 259 | ATS Terminations | 24638 | 0 | 0 | 12319 | 0 | 0 | 0 | 0 | 3079.75 | 3079.75 | 3079.75 | 3079.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02280 | 260 | ATS Testing | 24638 | 0 | 0 | 12319 | 0 | 0 | 0 | 0 | 3079.75 | 3079.75 | 3079.75 | 3079.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02125 | 261 | Cabling - Interior Branch (1/0 & Smaller) | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SGS-02125 | 262 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 | 0 | 0 | 0 | 549064.2857 | 0 | 0 | 10558.9286 | 10558.9286 | 10558.9286 | 10558.9286 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 263 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02115 | 264 | Conduit - Branch Circuits (1 1/2" & Smaller) | 123188 | 43115.8 | 0 | 0 | 0 | 0 | 0 | 0 | 20018.05 | 20018.05 | 20018.05 | 20018.05 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02105 | 265 | Conduit - In-Slab | 162608 | 162608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02010 | 266 | Conduit - Risers (2" & Larger) | 591300 | 473040 | 0 | 0 | 0 | 0 | 0 | 0 | 29565 | 29565 | 29565 | 29565 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02475 | 267 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02010 | 268 | Foundation Coring | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG7-01040 | 269 | Generator Delivery | 78750 | 0 | 0 | 0 | 39375 | 0 | 0 | 0 | 9843.75 | 9843.75 | 9843.75 | 9843.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG7-01030 | 270 | Generator Release | 472500 | 472500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02415 | 271 | Generator Terminations | 78750 | 0 | 0 | 0 | 73125 | 0 | 0 | 0 | 1406.25 | 1406.25 | 1406.25 | 1406.25 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02615 | 272 | Generator Test | 78750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19687.5 | 19687.5 | 19687.5 | 19687.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02150 | 273 | Lighting Controls | 11550 | 5775 | 0 | 0 | 0 | 0 | 0 | 0 | 1443.75 | 1443.75 | 1443.75 | 1443.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 274 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02135 | 275 | Lighting Install | 82125 | 41062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10265.625 | 10265.625 | 10265.625 | 10265.625 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02135 | 276 | Lighting Rough | 82125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20531.25 | 20531.25 | 20531.25 | 20531.25 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02135 | 277 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02425 | 278 | Lightning Protection | 21900 | 10950 | 0 | 0 | 0 | 9385.7143 | 0 | 0 | 391.0714 | 391.0714 | 391.0714 | 391.0714 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02140 | 279 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 | 0 | 54437.1429 | 0 | 0 | 0 | 0 | 2268.2143 | 2268.2143 | 2268.2143 | 2268.2143 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGS-E-01030 | 280 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02160 | 281 | Switches and Receptacles | 10950 | 0 | 0 | 5475 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02655 | 282 | Switchgear & Panelboard Energization | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318.75 | 12318.75 | 12318.75 | 12318.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02330 | 283 | Switchgear & Panelboard Installation | 591300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147825 | 147825 | 147825 | 147825 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02330 | 284 | Switchgear & Panelboard Terminations | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318.75 | 12318.75 | 12318.75 | 12318.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG1-01380 | 285 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02650 | 286 | Switchgear & Panelboard Testing | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12318.75 | 12318.75 | 12318.75 | 12318.75 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02005 | 287 | Temp Light & Power | 54750 | 35587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4790.625 | 4790.625 | 4790.625 | 4790.625 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02115 | 288 | Fire Alarm Conduit | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02250 | 289 | Fire Alarm Wiring | 32850 | 0 | 16425 | 0 | 0 | 0 | 0 | 0 | 4106.25 | 4106.25 | 4106.25 | 4106.25 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02250 | 290 | Fire Alarm Devices | 53655 | 26827.5 | 13413.75 | 0 | 0 | 0 | 0 | 0 | 3353.4375 | 3353.4375 | 3353.4375 | 3353.4375 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02250 | 291 | Fire Alarm Programming & Pretest | 2738 | 0 | 1369 | 0 | 0 | 0 | 0 | 0 | 342.25 | 342.25 | 342.25 | 342.25 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-02625 | 292 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684.5 | 684.5 | 684.5 | 684.5 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG7-01005 | 293 | EXCAVATION NEW BLDGS - SG-7 | 42812 | 42812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01055 | 294 | BACKFILL NEW BLDGS - SG-7 | 18057 | 18057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01005 | 295 | DEWATERING COVERAGE FOR NEW BUILDINGS - SG-7 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG1-01380 | 296 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-01005 | 297 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - SG-7 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG7-01005 | 298 | DRIVE PILES AND INSTALL LAGGING FOR SOE - SG-7 | 34172 | 34172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 095 - SG7 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SGN-01035 | 299 | EROSION CONTROL FABRIC - SGN | 71660 | 71660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 300 | INLET PROTECTION - SGN | 31100 | 31100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 301 | SILT FENCE - SGN | 22950 | 22950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 302 | STABILIZED CONSTRUCTION ENTRANCE - SGN | 48300 | 48300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01035 | 303 | MANTAIN EROSION CONTROL - SGN | 42735 | 42735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01690 | 304 | REMOVE EROSION CONTROL - SGN | 29979 | 4496.85 | 0 | 0 | 0 | 8494.05 | 8494.05 | 8494.05 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 305 | REMOVE FENCE - SGN | 23500 | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 306 | REMOVE FULL DEPTH ASPHALT PVMT - SGN | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-01380 | 307 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01060 | 308 | REMOVE SITE FURNISHING - SGN | 181360 | 181360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 309 | REMOVE CONCRETE CURB & STEPS - SGN | 40100 | 40100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01000 | 310 | REMOVE PVMTS - SGN | 151850 | 151850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 096 - SGN - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01510 | 311 | FORMWORK SITE CONCRETE - SGN | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 312 | CONCRETE FOOTING FOR SITE FURNISHING - SGN | 5947 | 0 | 0 | 2973.5 | 2973.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 313 | CONCRETE DUCTBANKS - SGN | 40284 | 40284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01520 | 314 | CONCRETE SITE RETAINING WALL AND FOOTINGS - SGN | 25224 | 25224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 097 - SGN - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 315 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - SGN | 24647 | 6161.75 | 0 | 0 | 0 | 6161.75 | 6161.75 | 6161.75 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 316 | Crackle Corn | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 317 | Jet Spray | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-01380 | 318 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01635 | 319 | 2-5 year play equipment | 88000 | 44000 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 320 | 5-12 year play equipment | 88000 | 44000 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 321 | Splash Pad | 22000 | 11000 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01635 | 322 | Install Water Play Equipment and Piping | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 098 - SGN - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01155 | 323 | Manhole Installation | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02215 | 324 | Site Lighting - Cable | 54750 | 5475 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02210 | 325 | Site Lighting - Conduit | 65700 | 62415 | 1407.8571 | 1407.8571 | 469.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02220 | 326 | Site Lighting - Fixtures | 55407 | 0 | 0 | 0 | 0 | 0 | 18469 | 18469 | 18469 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-SGN-E-01000 | 327 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-02125 | 328 | Underground Electric Service - Cable | 821250 | 821250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SG1-01380 | 329 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 010 - SG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01155 | 330 | Underground Electric Service - Conduit | 657000 | 657000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGN-01020 | 331 | TREE PROTECTION - SGN | 14532 | 14532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01020 | 332 | HAND EXCAVATION AS NEEDED - SGN | 19751 | 19751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 333 | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGN | 4025 | 0 | 0 | 2012.5 | 2012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01120 | 334 | BACKFILL - SGN | 153869 | 153869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01650 | 335 | SITE FURNISHINGS - SGN | 37275 | 3727.5 | 0 | 0 | 0 | 11182.5 | 11182.5 | 11182.5 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 336 | DRINKING FOUNTAIN - SGN | 16059 | 1605.9 | 0 | 0 | 0 | 4817.7 | 4817.7 | 4817.7 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01650 | 337 | LANDSCAPE BOULDERS - SGN | 22319 | 16739.25 | 0 | 0 | 0 | 1859.9167 | 1859.9167 | 1859.9167 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01090 | 338 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01090 | 339 | Furnish and Install Deep Wells | 146250 | 146250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 340 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 11567.65 | 0 | 0 | 0 | 680.45 | 680.45 | 680.45 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01090 | 341 | Furnish and Install Pumps and Piping | 160800 | 160800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01090 | 342 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01090 | 343 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01090 | 344 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 100 - SGN - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01640 | 345 | 4' Steel Bar Fence with Double Gates | 88000 | 0 | 0 | 0 | 0 | 75428.5714 | 12571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGN-01645 | 346 | 6' Chain Link Fence | 12650 | 0 | 0 | 0 | 0 | 0 | 12650 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGN-01005 | 347 | 8' High Temporary Fence | 242250 | 242250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGN-01610 | 348 | 4" CONCRETE | 100100 | 0 | 0 | 50050 | 42900 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01610 | 349 | 7" CONCRETE RAMP | 3080 | 0 | 0 | 1540 | 1320 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01610 | 350 | 5" POROUS CONCRETE | 462000 | 115500 | 0 | 173250 | 148500 | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SG1-03005 | 351 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01630 | 352 | 5" COLOR CONCRETE | 77000 | 46200 | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01605 | 353 | CONCRETE CURB | 18480 | 18480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGN-01605 | 354 | SFC -STELL FACING CURB | 18480 | 0 | 13200 | 4400 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01709 | 355 | Asphalt Parking | 1161 | 0 | 0 | 0 | 0 | 1078.0714 | 82.9286 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
SGN-01680 | 356 | Deciduous Trees | 14884 | 0 | 0 | 0 | 0 | 14884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 357 | Evergreen Trees | 3544 | 0 | 0 | 0 | 0 | 3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 358 | Deciduous Shrubs | 2940 | 0 | 0 | 0 | 0 | 2940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 359 | Evergreen Shrubs | 1040 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01680 | 360 | Perennials | 8080 | 0 | 0 | 0 | 0 | 8080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 361 | Grasses | 18295 | 0 | 0 | 0 | 9147.5 | 9147.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG1-03005 | 362 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 822 | 0 | 0 | 0 | 0 | 182.6667 | 91.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01025 | 363 | Tree Removal | 41580 | 41580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 364 | Lawn Seeding (not including topsoil) | 14810 | 7405 | 0 | 0 | 3702.5 | 3702.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01025 | 365 | Soil Erosion Mat | 2791 | 2369.6 | 0 | 0 | 210.7 | 210.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 366 | Topsoil Stockpile/Spread | 101317 | 65856.05 | 0 | 0 | 17730.475 | 17730.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01675 | 367 | Maintenance | 2678 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGN-01120 | 368 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGN | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01110 | 369 | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGN | 25018 | 25018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01110 | 370 | INSTALL HW, CW PIPE - SGN | 403279 | 403279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SGN-01115 | 371 | TEST HW, CW - SGN | 17587 | 17587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01130 | 372 | INSTALL CONDENSATE AND STEAM PIPE - SGN | 308238 | 308238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SG1-03005 | 373 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3300 | 2475 | 0 | 0 | 0 | 0 | 550 | 275 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01135 | 374 | TEST CONDENSATE, STEAM - SGN | 12947 | 12947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01095 | 375 | DEWATERING COVERAGE FOR UTILITY WORK - SGN | 56118 | 56118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01380 | 376 | SEWER / DRAINAGE PIPE - SGN | 150607 | 150607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01375 | 377 | CATCH BASIN DRAINS AND CONNECTIONS - SGN | 165979 | 165979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01375 | 378 | REMOVE AREA DRAINS - SGN | 23320 | 23320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01255 | 379 | ELECTRICAL MANHOLES - SGN | 6377 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01255 | 380 | ELECTRICAL CONDUIT TRENCHES - SGN | 45340 | 45340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 381 | Equipment SUPPORT FOR SITE - SGN | 167754 | 167754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01035 | 382 | EROSION CONTROL FABRIC - SGS | 71650 | 71650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01035 | 383 | INLET PROTECTION - SGS | 23325 | 23325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 384 | HANGERS AND SUPPORTS | 11526 | 9797.1 | 0 | 0 | 0 | 0 | 1152.6 | 576.3 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01035 | 385 | SILT FENCE - SGS | 29100 | 29100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01035 | 386 | STABILIZED CONSTRUCTION ENTRANCE - SGS | 48390 | 48390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01035 | 387 | MANTAIN EROSION CONTROL - SGS | 42735 | 42735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01770 | 388 | REMOVE EROSION CONTROL - SGS | 29979 | 4496.85 | 0 | 25482.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 389 | REMOVE FENCE - SGS | 24400 | 24400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 390 | REMOVE FULL DEPTH ASPHALT PVMT - SGS | 68825 | 68825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01060 | 391 | REMOVE SITE FURNISHING - SGS | 64615 | 64615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 392 | REMOVE CONCRETE CURB & STEPS - SGS | 60250 | 60250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01000 | 393 | REMOVE PVMTS - SGS | 100625 | 100625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 103 - SGS - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGN-01510 | 394 | FORMWORK SITE CONCRETE - SGS | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 104 - SGS - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 395 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 0 | 0 | 0 | 1463.3333 | 731.6667 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01750 | 396 | CONCRETE FOOTING FOR SITE FURNISHING - SGS | 5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947 | 0 | 0 | SGS | 104 - SGS - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 397 | CONCRETE DUCTBANKS - SGS | 59916 | 59915 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 104 - SGS - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-02010 | 398 | Manhole Work | 54750 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 14600 | 14600 | 14600 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02215 | 399 | Site Lighting - Cable | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02210 | 400 | Site Lighting - Conduit | 65700 | 6570 | 0 | 0 | 0 | 0 | 0 | 0 | 19710 | 19710 | 19710 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02220 | 401 | Site Lighting - Fixtures | 62963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20987.6667 | 20987.6667 | 20987.6667 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-SGS-E-01030 | 402 | Survey | 70080 | 70080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-02135 | 403 | Underground Electric Service - Cable | 821250 | 0 | 0 | 0 | 205312.5 | 205312.5 | 205312.5 | 205312.5 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-01155 | 404 | Underground Electric Service - Conduit | 657000 | 657000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SGS-01020 | 405 | TREE PROTECTION - SGS | 5882 | 5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG1-03005 | 406 | DOMESTIC WATER PIPING | 126720 | 95040 | 0 | 0 | 0 | 0 | 21120 | 10560 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01020 | 407 | HAND EXCAVATION AS NEEDED - SGS | 21068 | 21068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01750 | 408 | EXCAVATION FOR SITE FURNISHING FOOTINGS - SGS | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4025 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01370 | 409 | BACKFILL - SGS | 195501 | 195501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01750 | 410 | SITE FURNISHINGS - SGS | 74550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74550 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01750 | 411 | BOLLARDS - SGS | 15581 | 1558.1 | 0 | 0 | 0 | 4674.3 | 4674.3 | 4674.3 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01750 | 412 | DRINKING FOUNTAIN - SGS | 8030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8030 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01090 | 413 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01090 | 414 | Furnish and Install Deep Wells | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01090 | 415 | Furnish and Install Pumps and Piping | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01090 | 416 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG1-03005 | 417 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 | 0 | 0 | 0 | 0 | 2713.3333 | 1356.6667 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01090 | 418 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01090 | 419 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 106 - SGS - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01005 | 420 | 8' High Temporary Fence | 372400 | 336200 | 36200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGS-01745 | 421 | Ametco Fence | 138050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69025 | 69025 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
SGS-01710 | 422 | 4" CONCRETE | 71500 | 17875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32175 | 21450 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01710 | 423 | 5"POROUS CONCRETE | 466620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279972 | 186648 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01730 | 424 | 5" COLOR CONCRETE | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000 | 77000 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01705 | 425 | CONCRETE CURB | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23833.3333 | 12833.3333 | 1833.3333 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01705 | 426 | SFC -STELL FACING CURB | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8171.4286 | 4400 | 628.5714 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SGS-01760 | 427 | Deciduous Trees | 27642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13821 | 13821 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG1-03005 | 428 | SANITARY WASTE PIPING | 118800 | 100980 | 0 | 0 | 0 | 0 | 11880 | 5940 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01760 | 429 | Evergreen Trees | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.5 | 1063.5 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01760 | 430 | Deciduous Shrubs | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735 | 735 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01760 | 431 | Perennials | 4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214.5 | 2214.5 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 432 | Grasses | 7980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3990 | 3990 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01025 | 433 | Tree Removal | 48246 | 44246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 434 | Lawn Seeding (not including topsoil) | 14012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7006 | 7006 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 435 | Topsoil Stockpile/Spread | 96170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48085 | 48085 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01755 | 436 | Maintenance | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SGS-01370 | 437 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - SGS | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01355 | 438 | TERMINATE AND DEMOLISH EXISTING UTILITIES - SGS | 25860 | 23274 | 0 | 2586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG1-03005 | 439 | SANITARY WASTE PIPING SPECIALTIES | 30070 | 27063 | 0 | 0 | 0 | 0 | 2004.6667 | 1002.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01355 | 440 | INSTALL HW, CW PIPE - SGS | 504915 | 504915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SGS-01360 | 441 | TEST HW, CW - SGS | 21983 | 21983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01330 | 442 | INSTALL CONDENSATE AND STEAM PIPE - SGS | 516372 | 516372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SGS-01335 | 443 | TEST CONDENSATE, STEAM - SGS | 19421 | 19421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01095 | 444 | DEWATERING COVERAGE FOR UTILITY WORK - SGS | 5612 | 5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01595 | 445 | SEWER / DRAINAGE PIPE - SGS | 132508 | 53003.2 | 0 | 0 | 0 | 26501.6 | 26501.6 | 26501.6 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01560 | 446 | CATCH BASIN DRAINS AND CONNECTIONS - SGS | 78622 | 47173.2 | 0 | 31448.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01560 | 447 | REMOVE AREA DRAINS - SGS | 23320 | 5830 | 0 | 0 | 0 | 5830 | 5830 | 5830 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01255 | 448 | ELECTRICAL MANHOLES - SGS | 31811 | 6000 | 0 | 0 | 0 | 8603.6667 | 8603.6667 | 8603.6667 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01255 | 449 | ELECTRICAL CONDUIT TRENCHES - SGS | 61478 | 61478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG1-03005 | 450 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 29700 | 0 | 0 | 0 | 1100 | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01010 | 451 | Equipment SUPPORT FOR SITE - SGS | 167754 | 159366.3 | 0 | 0 | 0 | 2795.9 | 2795.9 | 2795.9 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OG1-01005 | 452 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01010 | 453 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01015 | 454 | Assumed Flooring Material (Slab Penetrations) | 61200 | 61200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 455 | Pipe Insulation | 151200 | 151200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 456 | Tank Insulation | 9750 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01015 | 457 | Fireproofing | 171120 | 171120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01015 | 458 | Fibrous Slate | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 459 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01020 | 460 | Underground Utility Materials | 11544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03030 | 461 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 253000 | 240350 | 0 | 0 | 0 | 4216.6667 | 4216.6667 | 4216.6667 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 462 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 463 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 464 | Remove existing door, frame and hardware | 20000 | 10000 | 0 | 0 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01115 | 465 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01115 | 466 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01115 | 467 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 468 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 0 | 3000 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 469 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 470 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01105 | 471 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03005 | 472 | GAS SERVICE AND PIPING | 2112 | 0 | 0 | 0 | 0 | 0 | 1408 | 704 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 473 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 474 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 475 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 476 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 477 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 478 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 479 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01210 | 480 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 481 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 482 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03005 | 483 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01105 | 484 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01210 | 485 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-01410 | 486 | FORM FLOOD BARRIER FOUNDATIONS - OG-1 | 30105 | 30105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01450 | 487 | DRILL & GROUT DOWELS - OG-1 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01450 | 488 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-1 | 27638 | 27638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01770 | 489 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-1 | 18434 | 13825.5 | 0 | 0 | 2304.25 | 1152.125 | 1152.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01440 | 490 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-1 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01440 | 491 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-1 | 3113 | 3113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01320 | 492 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-1 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01415 | 493 | Footing/Pier | 8892 | 4446 | 0 | 2223 | 2223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-03005 | 494 | Plumbing Pipe Insulation | 34034 | 0 | 17017 | 17017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01435 | 495 | Retaining Walls | 1428 | 714 | 0 | 357 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01615 | 496 | Entrance Slab | 11730 | 8797.5 | 0 | 1466.25 | 1466.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01810 | 497 | Concrete Shelf | 6432 | 6432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01350 | 498 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01830 | 499 | GFRP Sikawrap 100 G | 27456 | 0 | 0 | 0 | 9152 | 9152 | 9152 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 110 - OG1 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01440 | 500 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-1 | 396 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01015 | 501 | Overhead protection for Masonry | 5088 | 3816 | 0 | 0 | 636 | 318 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01830 | 502 | 2" Face brick | 153384 | 138045.6 | 0 | 15338.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01820 | 503 | 6" vertically reinforced CMU | 38368 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01830 | 504 | 2" rigid Insulation | 6715 | 0 | 0 | 0 | 2238.3333 | 2238.3333 | 2238.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02015 | 505 | Heat Trace | 5475 | 0 | 0 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01820 | 506 | Coping stone C1/A-300 | 24909 | 18681.75 | 0 | 0 | 2075.75 | 2075.75 | 2075.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05230 | 507 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01315 | 508 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01860 | 509 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-02145 | 510 | PENETRATION FIRESTOPPING EXTG BLDG - OG-1 | 11505 | 0 | 10066.875 | 0 | 719.0625 | 359.5312 | 359.5312 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01320 | 511 | JOINT SEALANTS EXTG BLDGS - OG-1 | 11505 | 0 | 0 | 0 | 5752.5 | 2876.25 | 2876.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01830 | 512 | Bituthene 4000 waterproofing membrane | 10217 | 8684.45 | 0 | 1532.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01830 | 513 | GE Elemax 2600 Silicone air and vapor barrier | 13728 | 12355.2 | 0 | 1372.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01370 | 514 | Crystalline Waterproofing at perimeter walls | 30878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01825 | 515 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 113 - OG1 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SURV-SGS-M-01005 | 516 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01330 | 517 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 114 - OG1 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 518 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 519 | Layout | 5143 | 5143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 520 | Loading | 7458 | 7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 521 | Framing & Drywall - Materials | 12087 | 12087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01325 | 522 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01330 | 523 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01330 | 524 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01855 | 525 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01340 | 526 | Resilient Flooring and base - OG-1 | 12880 | 0 | 0 | 6440 | 6440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 527 | Exhaust Fans: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01860 | 528 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-1 | 57648 | 28824 | 0 | 0 | 9608 | 9608 | 9608 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01860 | 529 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-1 | 63427 | 0 | 0 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01865 | 530 | Temporary Egress Stair Storage Sign | 2640 | 0 | 0 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01865 | 531 | Address Signs | 4675 | 0 | 0 | 0 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 116 - OG1 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01380 | 532 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 533 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 534 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 535 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 536 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 537 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03112 | 538 | Exhaust Fans: Install | 4565 | 4565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 539 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 540 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 541 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 542 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 543 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 544 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 545 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 546 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 547 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 548 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 549 | Steam Unit Heaters: Furnish | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 550 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 551 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 552 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01380 | 553 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 117 - OG1 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 554 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 1134.0833 | 1134.0833 | 1134.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 555 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 495 | 18.3333 | 18.3333 | 18.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 556 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 557 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2420 | 1936 | 161.3333 | 161.3333 | 161.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 558 | HANGERS AND SUPPORTS | 11551 | 8663.25 | 962.5833 | 962.5833 | 962.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 559 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03032 | 560 | Steam Unit Heaters: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 561 | DOMESTIC WATER PIPING | 108020 | 81015 | 9001.6667 | 9001.6667 | 9001.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 562 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 14387.25 | 1598.5833 | 1598.5833 | 1598.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 563 | SANITARY WASTE PIPING | 95172 | 85654.8 | 3172.4 | 3172.4 | 3172.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 564 | SANITARY WASTE PIPING SPECIALTIES | 34188 | 32478.6 | 569.8 | 569.8 | 569.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 565 | STORM DRAINAGE PIPING SPECIALTIES | 34188 | 17094 | 5698 | 5698 | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03030 | 566 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 187000 | 140250 | 16362.5 | 0 | 0 | 10129.1667 | 10129.1667 | 10129.1667 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 567 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03005 | 568 | Plumbing Pipe Insulation | 41899 | 37709.1 | 2094.95 | 2094.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02040 | 569 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-M-01005 | 570 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 571 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 572 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 573 | Exhaust Fans: Install | 8360 | 0 | 4180 | 4180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 574 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 575 | Steam Unit Heaters: Install | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 576 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 577 | Condensate Return Unit: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 578 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 579 | Heating and Ventilation Unit: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03015 | 580 | Steam Traps: Furnish | 1980 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03015 | 581 | Steam Traps: Install | 14300 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03032 | 582 | Condensate Return Unit: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 583 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 584 | Vacuum Pump Unit: Install | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 585 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 89100 | 89100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 586 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 121000 | 121000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 587 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03025 | 588 | Mechanical Pipe: Hydrostatic Testing | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03107 | 589 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 590 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03135 | 591 | HVAC Ductwork: Testing & Balancing | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 592 | Controls: Furnish and Install: Devices | 77000 | 70840 | 5955.4688 | 204.5312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03112 | 593 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 594 | Controls: Furnish and Install: Controls Conduit | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 595 | Controls: Furnish and Install: Controls Wiring | 11000 | 8250 | 850.7812 | 146.0938 | 0 | 0 | 1753.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 596 | Controls: Connect to Final Termination Points | 7700 | 3850 | 595.5469 | 102.2656 | 0 | 0 | 3152.1875 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03025 | 597 | Controls: Controls Testing | 6600 | 0 | 510.4688 | 87.6562 | 0 | 0 | 6001.875 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 598 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 | 7920 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 599 | Insulation: Furnish and Install: Piping Insulation | 17600 | 2640 | 14080 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 600 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 1486 | 7920 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 601 | ATS Energization | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 602 | ATS Installation | 191625 | 172462.5 | 0 | 0 | 0 | 0 | 6387.5 | 6387.5 | 6387.5 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 603 | ATS Terminations | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03112 | 604 | Heating and Ventilation Unit: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02210 | 605 | ATS Testing | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02010 | 606 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02035 | 607 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02395 | 608 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 295650 | 0 | 0 | 147825 | 49275 | 49275 | 49275 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02015 | 609 | Conduit - Branch Circuits (1 1/2" & Smaller) | 246375 | 184781.25 | 0 | 0 | 0 | 0 | 20531.25 | 20531.25 | 20531.25 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02125 | 610 | Conduit - Risers (2" & Larger) | 591300 | 561735 | 0 | 0 | 0 | 0 | 9855 | 9855 | 9855 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02020 | 611 | Demolition/Temp Light & Power | 54750 | 49275 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02145 | 612 | Firestopping | 5250 | 0 | 4593.75 | 0 | 0 | 0 | 218.75 | 218.75 | 218.75 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02025 | 613 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02065 | 614 | Lighting Controls | 25200 | 12600 | 11025 | 0 | 0 | 0 | 525 | 525 | 525 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03015 | 615 | Steam Traps: Furnish | 1760 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02120 | 616 | Lighting Remove & Re-install | 39420 | 0 | 33788.5714 | 0 | 0 | 0 | 1877.1429 | 1877.1429 | 1877.1429 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02160 | 617 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02070 | 618 | Mechanical Terminations(Dampers, Heaters, Motors) | 65700 | 0 | 0 | 0 | 0 | 0 | 21900 | 21900 | 21900 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-01020 | 619 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02250 | 620 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02515 | 621 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02215 | 622 | Switchgear & Panelboard Installation | 361350 | 325215 | 0 | 0 | 0 | 0 | 12045 | 12045 | 12045 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02265 | 623 | Switchgear & Panelboard Terminations | 30113 | 7528.25 | 22584.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02510 | 624 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02015 | 625 | Fire Alarm Conduit | 21900 | 0 | 0 | 0 | 0 | 0 | 7300 | 7300 | 7300 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03015 | 626 | Steam Traps: Install | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02130 | 627 | Fire Alarm Wiring | 19710 | 0 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02115 | 628 | Fire Alarm Devices | 24090 | 12045 | 0 | 0 | 0 | 0 | 4015 | 4015 | 4015 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02535 | 629 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-02535 | 630 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-01405 | 631 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 122 - OG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01780 | 632 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-1 | 3981 | 3582.9 | 0 | 0 | 132.7 | 132.7 | 132.7 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 122 - OG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-01780 | 633 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-1 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 122 - OG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01005 | 634 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 15000 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01010 | 635 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01015 | 636 | Assumed Flooring Material (Slab Penetrations) | 57600 | 57600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-03032 | 637 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01020 | 638 | Pipe Insulation | 113400 | 113400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01015 | 639 | Fibrous Slate | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01020 | 640 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01020 | 641 | Underground Utility Materials | 11544 | 11544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 642 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01220 | 643 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 644 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 645 | Remove existing door, frame and hardware | 20000 | 10000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01115 | 646 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01115 | 647 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03032 | 648 | Vacuum Pump Unit: Install | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01115 | 649 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01115 | 650 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 651 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01105 | 652 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 653 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 654 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 655 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 656 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 657 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 658 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-03107 | 659 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 88688 | 88688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 660 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 661 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01210 | 662 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01105 | 663 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 664 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01105 | 665 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01210 | 666 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG2-01410 | 667 | FORM FLOOD BARRIER FOUNDATIONS - OG-2 | 30704 | 30704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01450 | 668 | DRILL & GROUT DOWELS - OG-2 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01450 | 669 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-2 | 27638 | 27638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-03007 | 670 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 126500 | 126500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01770 | 671 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-2 | 18763 | 18763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01440 | 672 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-2 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01440 | 673 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-2 | 3113 | 3113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01320 | 674 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-2 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01415 | 675 | Footing/Pier | 9009 | 9009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01435 | 676 | Retaining Walls | 1428 | 1428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01615 | 677 | Entrance Slab | 12342 | 9256.5 | 3085.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01810 | 678 | Concrete Shelf | 6624 | 6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01350 | 679 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01830 | 680 | GFRP Sikawrap 100 G | 26400 | 0 | 0 | 0 | 8800 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 124 - OG2 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-03007 | 681 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 45100 | 45100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01440 | 682 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-2 | 396 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01015 | 683 | Overhead protection for Masonry | 5088 | 3816 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01820 | 684 | 6" vertically reinforced CMU | 38368 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01830 | 685 | 2" Face brick | 153384 | 145714.8 | 0 | 7669.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01830 | 686 | 2" rigid Insulation | 6715 | 0 | 0 | 0 | 2238.3333 | 2238.3333 | 2238.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01820 | 687 | Coping stone C1/A-300 | 25245 | 21458.25 | 0 | 3786.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05080 | 688 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01315 | 689 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01860 | 690 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-02145 | 691 | PENETRATION FIRESTOPPING EXTG BLDG - OG-2 | 11505 | 0 | 10066.875 | 719.0625 | 719.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03025 | 692 | Mechanical Pipe: Hydrostatic Testing | 1513 | 1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01320 | 693 | JOINT SEALANTS EXTG BLDGS - OG-2 | 11505 | 0 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01830 | 694 | Bituthene 4000 waterproofing membrane | 10217 | 9195.3 | 0 | 1021.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01830 | 695 | GE Elemax 2600 Silicone air and vapor barrier | 13728 | 12355.2 | 0 | 1372.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01370 | 696 | Crystalline Waterproofing at perimeter walls | 30878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01825 | 697 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 127 - OG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01330 | 698 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 128 - OG2 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 699 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 700 | Layout | 5143 | 5143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 701 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 702 | Framing & Drywall - Materials | 12087 | 12087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03107 | 703 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01325 | 704 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01330 | 705 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01330 | 706 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01855 | 707 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01340 | 708 | Resilient Flooring and base - OG-2 | 12880 | 0 | 6440 | 6440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01860 | 709 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-2 | 57648 | 28824 | 9608 | 9608 | 9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01860 | 710 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-2 | 63427 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01865 | 711 | Temporary Egress Stair Storage Sign | 1320 | 0 | 440 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01865 | 712 | Address Signs | 4675 | 0 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 130 - OG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01380 | 713 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 714 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 715 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 716 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 717 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 718 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 719 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 720 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 721 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 722 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 723 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 724 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03310 | 725 | HVAC Ductwork: Testing & Balancing | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 726 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 727 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 728 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 729 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 730 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 731 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 732 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 733 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01380 | 734 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 131 - OG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 735 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 | 0 | 5443.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 736 | Controls: Furnish and Install: Devices | 71500 | 67925 | 0 | 0 | 1191.6667 | 1191.6667 | 1191.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 737 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 495 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 738 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 550 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 739 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3739 | 2430.35 | 0 | 1308.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 740 | HANGERS AND SUPPORTS | 11551 | 8663.25 | 0 | 2887.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 741 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 742 | DOMESTIC WATER PIPING | 113740 | 85305 | 0 | 28435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 743 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 14387.25 | 0 | 4795.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 744 | SANITARY WASTE PIPING | 98230 | 78584 | 0 | 19646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 745 | SANITARY WASTE PIPING SPECIALTIES | 30063 | 27056.7 | 0 | 3006.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 746 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 747 | Controls: Furnish and Install: Controls Conduit | 33000 | 31350 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03030 | 748 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 264000 | 224400 | 0 | 0 | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 749 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03005 | 750 | Plumbing Pipe Insulation | 28886 | 25997.4 | 1444.3 | 1444.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02035 | 751 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-M-01005 | 752 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 753 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03112 | 754 | Exhaust Fans: Install | 8910 | 0 | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 755 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03032 | 756 | Steam Unit Heaters: Install | 10450 | 10450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 757 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 758 | Controls: Furnish and Install: Controls Wiring | 9900 | 9405 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03032 | 759 | Condensate Return Unit: Install | 17050 | 17050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03112 | 760 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03112 | 761 | Heating and Ventilation Unit: Install | 18150 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03015 | 762 | Steam Traps: Furnish | 1760 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03015 | 763 | Steam Traps: Install | 12100 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 764 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03032 | 765 | Vacuum Pump Unit: Install | 20350 | 20350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03107 | 766 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 86048 | 86048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03007 | 767 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 116050 | 116050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03007 | 768 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 34100 | 34100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 769 | Controls: Connect to Final Termination Points | 6600 | 5940 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03025 | 770 | Mechanical Pipe: Hydrostatic Testing | 3053 | 3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 771 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 38500 | 37730 | 741.7431 | 0 | 0 | 0 | 0 | 28.2569 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 772 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 75460 | 1483.4862 | 0 | 0 | 0 | 0 | 56.5138 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03135 | 773 | HVAC Ductwork: Testing & Balancing | 4400 | 0 | 84.7706 | 0 | 0 | 0 | 0 | 4315.2294 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 774 | Controls: Furnish and Install: Devices | 77000 | 73150 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 775 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 776 | Controls: Furnish and Install: Controls Wiring | 11000 | 8250 | 0 | 1559.7015 | 0 | 1190.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 777 | Controls: Connect to Final Termination Points | 8800 | 4400 | 0 | 1247.7612 | 0 | 3152.2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-03025 | 778 | Controls: Controls Testing | 6600 | 0 | 0 | 935.8209 | 0 | 5664.1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 779 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-03310 | 780 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 781 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 782 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 783 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 784 | ATS Installation | 153300 | 137970 | 0 | 0 | 0 | 0 | 5110 | 5110 | 5110 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 785 | ATS Terminations | 10950 | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02210 | 786 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02010 | 787 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 19162.5 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02025 | 788 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-02115 | 789 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 295650 | 56314.2857 | 42235.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02020 | 790 | Conduit - Branch Circuits (1 1/2" & Smaller) | 232688 | 197784.8 | 0 | 0 | 0 | 0 | 11634.4 | 11634.4 | 11634.4 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 791 | Insulation: Furnish and Install: Ductwork Insulation | 9900 | 0 | 0 | 4950 | 2970 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02130 | 792 | Conduit - Risers (2" & Larger) | 394200 | 374490 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02015 | 793 | Demolition/Temp Light & Power | 54750 | 41062.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02145 | 794 | Firestopping | 5250 | 2625 | 2296.875 | 0 | 0 | 0 | 109.375 | 109.375 | 109.375 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02030 | 795 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02240 | 796 | Lighting Controls | 32550 | 16275 | 0 | 0 | 0 | 0 | 5425 | 5425 | 5425 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02015 | 797 | Lighting Remove & Re-install | 40406 | 0 | 0 | 0 | 0 | 0 | 13468.6667 | 13468.6667 | 13468.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02015 | 798 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02070 | 799 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 | 0 | 0 | 0 | 0 | 21170 | 21170 | 21170 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-E-01015 | 800 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02245 | 801 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 802 | Insulation: Furnish and Install: Piping Insulation | 17600 | 0 | 0 | 8800 | 5280 | 3520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02515 | 803 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02260 | 804 | Switchgear & Panelboard Installation | 361350 | 343282.5 | 15486.4286 | 2581.0714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02260 | 805 | Switchgear & Panelboard Terminations | 30113 | 7528.25 | 25811.1429 | 0 | 0 | 0 | -1075.4643 | -1075.4643 | -1075.4643 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02510 | 806 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02020 | 807 | Fire Alarm Conduit | 21900 | 16425 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02115 | 808 | Fire Alarm Wiring | 16425 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02115 | 809 | Fire Alarm Devices | 22995 | 11497.5 | 0 | 0 | 0 | 0 | 3832.5 | 3832.5 | 3832.5 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02115 | 810 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-02535 | 811 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01405 | 812 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 136 - OG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03040 | 813 | Insulation: Furnish and Install: Equipment Insulation | 9900 | 0 | 0 | 4950 | 2970 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG2-01780 | 814 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-2 | 3981 | 3981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 136 - OG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01780 | 815 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-2 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 136 - OG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01005 | 816 | Gaskets | 78750 | 0 | 0 | 0 | 0 | 26250 | 26250 | 26250 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01010 | 817 | Wire Insulation | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01015 | 818 | Assumed Flooring Material (Slab Penetrations) | 46800 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01005 | 819 | Duct Seal | 3600 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01015 | 820 | Fibrous Slate | 9180 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01020 | 821 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01020 | 822 | Underground Utility Materials | 11388 | 11388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 823 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-02010 | 824 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 20531.25 | 3421.875 | 3421.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01220 | 825 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 826 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 827 | Remove existing door, frame and hardware | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01115 | 828 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01115 | 829 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01115 | 830 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 831 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 832 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 833 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01210 | 834 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-02065 | 835 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01210 | 836 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 837 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 838 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 839 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 840 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01210 | 841 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01105 | 842 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 843 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01105 | 844 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG3-01210 | 845 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-02130 | 846 | Cabling - Risers & Feeders (2/0 & Larger) | 295650 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 66412.5 | 66412.5 | 66412.5 | 66412.5 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01410 | 847 | FORM FLOOD BARRIER FOUNDATIONS - OG-3 | 30704 | 23028 | 0 | 4605.6 | 3070.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01450 | 848 | DRILL & GROUT DOWELS - OG-3 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01450 | 849 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-3 | 27638 | 27638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01770 | 850 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-3 | 18763 | 14072.25 | 0 | 4690.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01440 | 851 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-3 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01440 | 852 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-3 | 3113 | 0 | 1037.6667 | 1037.6667 | 1037.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01320 | 853 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-3 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01415 | 854 | Footing/Pier | 9009 | 6756.75 | 2252.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01435 | 855 | Retaining Walls | 1428 | 714 | 357 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01615 | 856 | Entrance Slab | 11730 | 0 | 11730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02035 | 857 | Conduit - Branch Circuits (1 1/2" & Smaller) | 246375 | 24637.5 | 40000 | 20157.9545 | 0 | 0 | 0 | 0 | 40394.8864 | 40394.8864 | 40394.8864 | 40394.8864 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01810 | 858 | Concrete Shelf | 6768 | 6768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01350 | 859 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01830 | 860 | GFRP Sikawrap 100 G | 27456 | 0 | 0 | 0 | 9152 | 9152 | 9152 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 138 - OG3 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01440 | 861 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-3 | 396 | 0 | 132 | 132 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01015 | 862 | Overhead protection for Masonry | 5088 | 3816 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01820 | 863 | 6" vertically reinforced CMU | 38368 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01830 | 864 | 2" Face brick | 153384 | 138045.6 | 0 | 15338.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01830 | 865 | 2" rigid Insulation | 6715 | 1343 | 0 | 0 | 1790.6667 | 1790.6667 | 1790.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01820 | 866 | Coping stone C1/A-300 | 25245 | 18933.75 | 0 | 0 | 2103.75 | 2103.75 | 2103.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05110 | 867 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02030 | 868 | Conduit - Risers (2" & Larger) | 295650 | 29565 | 0 | 0 | 0 | 0 | 0 | 0 | 66521.25 | 66521.25 | 66521.25 | 66521.25 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01315 | 869 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01860 | 870 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-02150 | 871 | PENETRATION FIRESTOPPING EXTG BLDG - OG-3 | 11505 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01320 | 872 | JOINT SEALANTS EXTG BLDGS - OG-3 | 11505 | 0 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01830 | 873 | Bituthene 4000 waterproofing membrane | 10217 | 0 | 0 | 0 | 3405.6667 | 3405.6667 | 3405.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01830 | 874 | GE Elemax 2600 Silicone air and vapor barrier | 14784 | 0 | 0 | 0 | 4928 | 4928 | 4928 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01370 | 875 | Crystalline Waterproofing at perimeter walls | 29843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01825 | 876 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 141 - OG3 - Divisiono 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01330 | 877 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 142 - OG3 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 878 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 879 | Demolition/Temp Light & Power | 54750 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 5475 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 880 | Layout | 5401 | 5401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 881 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 882 | Framing & Drywall - Materials | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01325 | 883 | Framing- Labor | 13629 | 13629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01330 | 884 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01330 | 885 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01855 | 886 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01340 | 887 | Resilient Flooring and base - OG-3 | 15640 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01860 | 888 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-3 | 57648 | 28824 | 9608 | 9608 | 9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01860 | 889 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-3 | 63427 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-02120 | 890 | Firestopping | 5250 | 0 | 4593.75 | 0 | 0 | 0 | 0 | 0 | 164.0625 | 164.0625 | 164.0625 | 164.0625 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01865 | 891 | Temporary Egress Stair Storage Sign | 2640 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01865 | 892 | Address Signs | 4675 | 0 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 144 - OG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01380 | 893 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 894 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 895 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 896 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 897 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 898 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 899 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 900 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02030 | 901 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 902 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 903 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 904 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 905 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 906 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 907 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 908 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 909 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 910 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 911 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02115 | 912 | Lighting Controls | 26250 | 13125 | 3750 | 0 | 0 | 0 | 0 | 0 | 2343.75 | 2343.75 | 2343.75 | 2343.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 913 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01380 | 914 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 145 - OG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 915 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 | 0 | 5443.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 916 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 786 | 550.2 | 0 | 235.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 917 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 330 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 918 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2637 | 1582.2 | 0 | 1054.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 919 | HANGERS AND SUPPORTS | 11526 | 9797.1 | 0 | 1728.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 920 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 921 | DOMESTIC WATER PIPING | 128777 | 109460.45 | 0 | 19316.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 922 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 18223.85 | 0 | 959.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 923 | Lighting Remove & Re-install | 27972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6993 | 6993 | 6993 | 6993 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 924 | SANITARY WASTE PIPING | 147017 | 117613.6 | 0 | 0 | 14701.7 | 14701.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 925 | SANITARY WASTE PIPING SPECIALTIES | 33792 | 30412.8 | 0 | 3379.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 926 | STORM DRAINAGE PIPING SPECIALTIES | 33792 | 16896 | 0 | 16896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03030 | 927 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 264000 | 224400 | 0 | 0 | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 928 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9317 | 9317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03005 | 929 | Plumbing Pipe Insulation | 35464 | 8866 | 0 | 13299 | 13299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02030 | 930 | Heat Trace | 5475 | 0 | 4380 | 0 | 0 | 0 | 365 | 365 | 365 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-M-01005 | 931 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 932 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03112 | 933 | Exhaust Fans: Install | 14960 | 7480 | 326.781 | 7153.219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 934 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 935 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03032 | 936 | Steam Unit Heaters: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 937 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03032 | 938 | Condensate Return Unit: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03112 | 939 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03112 | 940 | Heating and Ventilation Unit: Install | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03015 | 941 | Steam Traps: Furnish | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03015 | 942 | Steam Traps: Install | 25025 | 25025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 943 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03032 | 944 | Vacuum Pump Unit: Install | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02040 | 945 | Mechanical Terminations(Dampers, Heaters, Motors) | 39420 | 0 | 0 | 33788.5714 | 0 | 0 | 0 | 0 | 1407.8571 | 1407.8571 | 1407.8571 | 1407.8571 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03007 | 946 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 331045 | 331045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03007 | 947 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 421300 | 421300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 948 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 143000 | 143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03025 | 949 | Mechanical Pipe: Hydrostatic Testing | 4455 | 4455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03107 | 950 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 951 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 66000 | 62700 | 0 | 2129.0323 | 0 | 0 | 0 | 1170.9677 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03135 | 952 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 106.4516 | 0 | 0 | 0 | 3193.5484 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 953 | Controls: Furnish and Install: Devices | 77000 | 65450 | 0 | 10745.5224 | 0 | 804.4776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 954 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 955 | Controls: Furnish and Install: Controls Wiring | 11000 | 8580 | 0 | 1535.0746 | 0 | 884.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-E-01030 | 956 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 957 | Controls: Connect to Final Termination Points | 8800 | 4400 | 0 | 1228.0597 | 0 | 3171.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-03025 | 958 | Controls: Controls Testing | 6600 | 0 | 0 | 921.0448 | 0 | 5678.9552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 959 | Insulation: Furnish and Install: Ductwork Insulation | 19800 | 0 | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 960 | Insulation: Furnish and Install: Piping Insulation | 39600 | 27720 | 11880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 961 | Insulation: Furnish and Install: Equipment Insulation | 19800 | 13860 | 5940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 962 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 963 | ATS Installation | 153300 | 137970 | 0 | 0 | 0 | 0 | 5110 | 5110 | 5110 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 964 | ATS Terminations | 10950 | 2737.5 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02210 | 965 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02010 | 966 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02105 | 967 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 2737.5 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02025 | 968 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 0 | 42857.1429 | 0 | 0 | 0 | 35714.2857 | 35714.2857 | 35714.2857 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02260 | 969 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 295650 | 56314.2857 | 42235.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02020 | 970 | Conduit - Branch Circuits (1 1/2" & Smaller) | 219000 | 175200 | 0 | 0 | 0 | 0 | 14600 | 14600 | 14600 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02130 | 971 | Conduit - Risers (2" & Larger) | 394200 | 374490 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02015 | 972 | Demolition/Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02150 | 973 | Firestopping | 5250 | 2625 | 0 | 0 | 0 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02035 | 974 | Foundation Coring | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02240 | 975 | Lighting Controls | 33600 | 16800 | 0 | 0 | 0 | 0 | 5600 | 5600 | 5600 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02015 | 976 | Lighting Remove & Re-install | 39420 | 0 | 0 | 0 | 0 | 0 | 13140 | 13140 | 13140 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02015 | 977 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02655 | 978 | Switchgear & Panelboard Energization | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02070 | 979 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 15877.5 | 41678.4375 | 0 | 0 | 0 | 1984.6875 | 1984.6875 | 1984.6875 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGW-E-01015 | 980 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02245 | 981 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02515 | 982 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02265 | 983 | Switchgear & Panelboard Installation | 361350 | 343282.5 | 18067.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02265 | 984 | Switchgear & Panelboard Terminations | 30525 | 7631.25 | 26709.375 | 0 | 0 | 0 | -1271.875 | -1271.875 | -1271.875 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02510 | 985 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02020 | 986 | Fire Alarm Conduit | 21900 | 5475 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02115 | 987 | Fire Alarm Wiring | 16425 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02115 | 988 | Fire Alarm Devices | 20805 | 10402.5 | 0 | 0 | 0 | 0 | 3467.5 | 3467.5 | 3467.5 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02330 | 989 | Switchgear & Panelboard Installation | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 16425 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02115 | 990 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-02535 | 991 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG3-01405 | 992 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 150 - OG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01780 | 993 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-3 | 3981 | 3582.9 | 0 | 398.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 150 - OG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01780 | 994 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-3 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 150 - OG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01005 | 995 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 7500 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01010 | 996 | Wire Insulation | 37500 | 35625 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01015 | 997 | Assumed Flooring Material (Slab Penetrations) | 75600 | 75600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 998 | Pipe Insulation | 126000 | 120000 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 999 | Tank Insulation | 9750 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG7-02330 | 1000 | Switchgear & Panelboard Terminations | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01015 | 1001 | Fireproofing | 32550 | 32550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01015 | 1002 | Fibrous Slate | 9180 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 1003 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01020 | 1004 | Underground Utility Materials | 11388 | 11388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1005 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01220 | 1006 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1007 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1008 | Remove existing door, frame and hardware | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01115 | 1009 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01115 | 1010 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG7-02650 | 1011 | Switchgear & Panelboard Testing | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01115 | 1012 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1013 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01210 | 1014 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01105 | 1015 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1016 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1017 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01210 | 1018 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1019 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1020 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1021 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG1-01405 | 1022 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 20834 | 20834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 014 - SG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01210 | 1023 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1024 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01210 | 1025 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01105 | 1026 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1027 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01105 | 1028 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01210 | 1029 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01410 | 1030 | FORM FLOOD BARRIER FOUNDATIONS - OG-4 | 30704 | 30704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01450 | 1031 | DRILL & GROUT DOWELS - OG-4 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG3-01450 | 1032 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-4 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01480 | 1033 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-1 | 7542 | 1131.3 | 6464.5714 | 0 | 0 | 0 | -17.9571 | -17.9571 | -17.9571 | 0 | 0 | 0 | 0 | SG1 | 014 - SG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01570 | 1034 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-4 | 18763 | 18763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01440 | 1035 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-4 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01440 | 1036 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-4 | 3232 | 0 | 0 | 1616 | 1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01320 | 1037 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-4 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01415 | 1038 | Footing/Pier | 9009 | 6756.75 | 2252.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01435 | 1039 | Retaining Walls | 1428 | 714 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01615 | 1040 | Entrance Slab | 12342 | 0 | 12342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01810 | 1041 | Concrete Shelf | 6528 | 6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01350 | 1042 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01830 | 1043 | GFRP Sikawrap 100 G | 41184 | 0 | 0 | 0 | 13728 | 13728 | 13728 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 152 - OG4 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG1-01480 | 1044 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-1 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 014 - SG1 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01440 | 1045 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-4 | 396 | 0 | 0 | 198 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01015 | 1046 | Overhead protection for Masonry | 5088 | 3816 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01820 | 1047 | 6" vertically reinforced CMU | 44875 | 42631.25 | 0 | 2243.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01830 | 1048 | 2" Face brick | 198275 | 198275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01830 | 1049 | 2" rigid Insulation | 7662 | 5363.4 | 0 | 2298.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01820 | 1050 | Coping stone C1/A-300 | 28328 | 28328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05140 | 1051 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01315 | 1052 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01860 | 1053 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-02145 | 1054 | PENETRATION FIRESTOPPING EXTG BLDG - OG 4 | 11505 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01005 | 1055 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01320 | 1056 | JOINT SEALANTS EXTG BLDGS - OG-4 | 11505 | 0 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01830 | 1057 | Bituthene 4000 waterproofing membrane | 7491 | 7116.45 | 0 | 374.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01830 | 1058 | GE Elemax 2600 Silicone air and vapor barrier | 22176 | 21067.2 | 0 | 1108.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01370 | 1059 | Crystalline Waterproofing at perimeter walls | 30360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01825 | 1060 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 155 - OG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01330 | 1061 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 156 - OG4 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 1062 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01325 | 1063 | Layout | 5401 | 5401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01325 | 1064 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01325 | 1065 | Framing & Drywall - Materials | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01010 | 1066 | Wire Insulation | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01325 | 1067 | Framing- Labor | 13372 | 13372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01330 | 1068 | Drywall - Labor | 15687 | 15687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01330 | 1069 | Tape/ Spackle finishes | 12344 | 12344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01855 | 1070 | Stucco | 10183 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01340 | 1071 | Resilient Flooring and base - OG-4 | 15640 | 0 | 0 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01860 | 1072 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-4 | 57648 | 57648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01860 | 1073 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-4 | 63427 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01865 | 1074 | Temporary Egress Stair Storage Sign | 2640 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01865 | 1075 | Address Signs | 4950 | 0 | 1650 | 1650 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 158 - OG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01380 | 1076 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1077 | Assumed Flooring Material (Slab Penetrations) | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01380 | 1078 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1079 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1080 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1081 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1082 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1083 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1084 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1085 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1086 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1087 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1088 | Pipe Insulation | 113400 | 97776 | 0 | 0 | 15624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01380 | 1089 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1090 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1091 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1092 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1093 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1094 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1095 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1096 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01380 | 1097 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 159 - OG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1098 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 6804.5 | 1701.125 | 1701.125 | 1701.125 | 1701.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1099 | Tank Insulation | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03005 | 1100 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 786 | 471.6 | 78.6 | 78.6 | 78.6 | 78.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1101 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 440 | 165 | 165 | 165 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1102 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3282 | 656.4 | 656.4 | 656.4 | 656.4 | 656.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1103 | HANGERS AND SUPPORTS | 11539 | 8077.3 | 865.425 | 865.425 | 865.425 | 865.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1104 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 548.75 | 548.75 | 548.75 | 548.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1105 | DOMESTIC WATER PIPING | 125548 | 87883.6 | 9416.1 | 9416.1 | 9416.1 | 9416.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1106 | DOMESTIC WATER PIPING SPECIALTIES | 19183 | 15346.4 | 959.15 | 959.15 | 959.15 | 959.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1107 | SANITARY WASTE PIPING | 106914 | 96222.6 | 2672.85 | 2672.85 | 2672.85 | 2672.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1108 | SANITARY WASTE PIPING SPECIALTIES | 30067 | 27060.3 | 751.675 | 751.675 | 751.675 | 751.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1109 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 | 4125 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01005 | 1110 | Duct Seal | 18000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03030 | 1111 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 187000 | 149600 | 18700 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1112 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9306 | 9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03005 | 1113 | Plumbing Pipe Insulation | 35464 | 21278.4 | 7092.8 | 7092.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02045 | 1114 | Heat Trace | 5475 | 0 | 0 | 4692.8571 | 0 | 0 | 260.7143 | 260.7143 | 260.7143 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-M-01005 | 1115 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 1116 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03112 | 1117 | Exhaust Fans: Install | 13860 | 0 | 1663.7592 | 12196.2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1118 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03032 | 1119 | Steam Unit Heaters: Install | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1120 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1121 | Vinyl Membrane and Mastic | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03032 | 1122 | Condensate Return Unit: Install | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03112 | 1123 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03112 | 1124 | Heating and Ventilation Unit: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03015 | 1125 | Steam Traps: Furnish | 1980 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03015 | 1126 | Steam Traps: Install | 23100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1127 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03032 | 1128 | Vacuum Pump Unit: Install | 25300 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1129 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 270930 | 270930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1130 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 352000 | 352000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1131 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 132000 | 132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1132 | Caulk | 112500 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-03025 | 1133 | Mechanical Pipe: Hydrostatic Testing | 4070 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 1134 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 27500 | 26125 | 0 | 793.2692 | 0 | 193.9103 | 193.9103 | 193.9103 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 1135 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 55000 | 54450 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03032 | 1136 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 95.1923 | 0 | 0 | 0 | 3204.8077 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1137 | Controls: Furnish and Install: Devices | 77000 | 69300 | 0 | 5688.806 | 0 | 2011.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1138 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1139 | Controls: Furnish and Install: Controls Wiring | 11000 | 10450 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1140 | Controls: Connect to Final Termination Points | 8800 | 8360 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-03025 | 1141 | Controls: Controls Testing | 6600 | 0 | 0 | 487.6119 | 0 | 6112.3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1142 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 9075 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01015 | 1143 | Fibrous Slate | 14025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG1-03040 | 1144 | Insulation: Furnish and Install: Piping Insulation | 37950 | 22770 | 12228.3333 | 2951.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1145 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 10890 | 5848.3333 | 1411.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1146 | ATS Energization | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1147 | ATS Installation | 191625 | 172462.5 | 0 | 0 | 0 | 0 | 6387.5 | 6387.5 | 6387.5 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1148 | ATS Terminations | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02210 | 1149 | ATS Testing | 13688 | 0 | 0 | 0 | 0 | 0 | 4562.6667 | 4562.6667 | 4562.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02015 | 1150 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 6843.75 | 0 | 0 | 0 | 0 | 6843.75 | 6843.75 | 6843.75 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02040 | 1151 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGP1-02010 | 1152 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 295650 | 147825 | 147825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02020 | 1153 | Conduit - Branch Circuits (1 1/2" & Smaller) | 260063 | 208050.4 | 0 | 0 | 0 | 0 | 17337.5333 | 17337.5333 | 17337.5333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1154 | Waterproofing | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-02130 | 1155 | Conduit - Risers (2" & Larger) | 492750 | 468112.5 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02025 | 1156 | Demolition/Temp Light & Power | 54750 | 52012.5 | 1368.75 | 1368.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02145 | 1157 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 0 | 1750 | 1750 | 1750 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02030 | 1158 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02240 | 1159 | Lighting Controls | 26250 | 13125 | 0 | 11250 | 0 | 0 | 625 | 625 | 625 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02025 | 1160 | Lighting Remove & Re-install | 39420 | 0 | 0 | 0 | 0 | 0 | 13140 | 13140 | 13140 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02025 | 1161 | Lighting System Program & Energize | 5550 | 0 | 0 | 0 | 0 | 0 | 1850 | 1850 | 1850 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02050 | 1162 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 15877.5 | 0 | 0 | 0 | 0 | 15877.5 | 15877.5 | 15877.5 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-E-01010 | 1163 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02245 | 1164 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01020 | 1165 | Underground Utility Materials | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-02515 | 1166 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 0 | 24090.4 | 2007.5333 | 2007.5333 | 2007.5333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02260 | 1167 | Switchgear & Panelboard Installation | 361350 | 325215 | 18067.5 | 18067.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02260 | 1168 | Switchgear & Panelboard Terminations | 30525 | 7631.25 | 0 | 0 | 0 | 0 | 7631.25 | 7631.25 | 7631.25 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02510 | 1169 | Switchgear & Panelboard Testing | 30113 | 0 | 0 | 0 | 0 | 15056.5 | 5018.8333 | 5018.8333 | 5018.8333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02020 | 1170 | Fire Alarm Conduit | 27375 | 19162.5 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02115 | 1171 | Fire Alarm Wiring | 19710 | 0 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02115 | 1172 | Fire Alarm Devices | 21900 | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02115 | 1173 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-02535 | 1174 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG4-01405 | 1175 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 164 - OG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01105 | 1176 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG4-01580 | 1177 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-4 | 3981 | 3582.9 | 398.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 164 - OG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG4-01580 | 1178 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-4 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 164 - OG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01005 | 1179 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01010 | 1180 | Wire Insulation | 37500 | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01015 | 1181 | Assumed Flooring Material (Slab Penetrations) | 57600 | 57600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1182 | Pipe Insulation | 113400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1183 | Tank Insulation | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01015 | 1184 | Fireproofing | 127875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01015 | 1185 | Fibrous Slate | 9180 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1186 | Waterproofing | 4971 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01220 | 1187 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01020 | 1188 | Underground Utility Materials | 11388 | 9110.4 | 0 | 2277.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1189 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01220 | 1190 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1191 | Remove existing vent / window and frame | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1192 | Remove existing door, frame and hardware | 20000 | 0 | 0 | 0 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01115 | 1193 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01115 | 1194 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01115 | 1195 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1196 | Prepare existing wall surface for paint - 1st floor | 6000 | 0 | 0 | 0 | 3000 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01210 | 1197 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01105 | 1198 | Remove existing vent / window and frame - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1199 | Remove existing AC units and sleeves - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1200 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1201 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01210 | 1202 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1203 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1204 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1205 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1206 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1207 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01210 | 1208 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01105 | 1209 | Remove existing door, frame and hardware - cellar | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1210 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1211 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01105 | 1212 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01210 | 1213 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01410 | 1214 | FORM FLOOD BARRIER FOUNDATIONS - OG-5 | 30704 | 30704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01450 | 1215 | DRILL & GROUT DOWELS - OG-5 | 3745 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG2-01450 | 1216 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-5 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01570 | 1217 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-5 | 18763 | 18763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01440 | 1218 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-5 | 15427 | 15427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01440 | 1219 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-5 | 3113 | 0 | 0 | 0 | 1556.5 | 778.25 | 778.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01115 | 1220 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01320 | 1221 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-5 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01415 | 1222 | Footing/Pier | 14820 | 14820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01435 | 1223 | Retaining Walls | 1428 | 714 | 0 | 357 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01565 | 1224 | Entrance Slab | 12342 | 0 | 0 | 6171 | 6171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01810 | 1225 | Concrete Shelf | 6576 | 5918.4 | 0 | 328.8 | 328.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01350 | 1226 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01830 | 1227 | GFRP Sikawrap 100 G | 41184 | 41184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 166 - OG5 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01440 | 1228 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - OG-5 | 396 | 0 | 0 | 0 | 198 | 99 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01015 | 1229 | Overhead protection for Masonry | 5088 | 3816 | 0 | 0 | 636 | 318 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01820 | 1230 | 6" vertically reinforced CMU | 44875 | 44875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01115 | 1231 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01830 | 1232 | 2" Face brick | 198275 | 198275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01830 | 1233 | 2" rigid Insulation | 7662 | 7662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01820 | 1234 | Coping stone C1/A-300 | 28002 | 28002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05260 | 1235 | MATERIAL AND FABRICATION | 16765 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01315 | 1236 | INSTALLATION | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01860 | 1237 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02145 | 1238 | PENETRATION FIRESTOPPING EXTG BLDG - OG 5 | 11505 | 0 | 0 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01320 | 1239 | JOINT SEALANTS EXTG BLDGS - OG-5 | 11505 | 0 | 0 | 0 | 5752.5 | 2876.25 | 2876.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01830 | 1240 | Bituthene 4000 waterproofing membrane | 7491 | 7491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01830 | 1241 | GE Elemax 2600 Silicone air and vapor barrier | 22176 | 22176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01115 | 1242 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01370 | 1243 | Crystalline Waterproofing at perimeter walls | 29440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01825 | 1244 | Waterproofing at foundation walls | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 169 - OG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01330 | 1245 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 170 - OG5 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 1246 | Furnish Doors | 6272 | 6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1247 | Layout | 3858 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1248 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1249 | Framing & Drywall - Materials | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01325 | 1250 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01330 | 1251 | Drywall - Labor | 16715 | 16715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01330 | 1252 | Tape/ Spackle finishes | 12087 | 12087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01210 | 1253 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01855 | 1254 | Stucco | 10183 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01340 | 1255 | Resilient Flooring and base - OG-5 | 15640 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01860 | 1256 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-5 | 57648 | 57648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01860 | 1257 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-5 | 63427 | 0 | 0 | 0 | 21142.3333 | 21142.3333 | 21142.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01865 | 1258 | Temporary Egress Stair Storage Sign | 2640 | 0 | 0 | 0 | 880 | 880 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01865 | 1259 | Address Signs | 4950 | 0 | 0 | 0 | 1650 | 1650 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 172 - OG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01380 | 1260 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1261 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1262 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1263 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01105 | 1264 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01380 | 1265 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1266 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1267 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1268 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1269 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1270 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1271 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1272 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1273 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1274 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01205 | 1275 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-01380 | 1276 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1277 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1278 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1279 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1280 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01380 | 1281 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 173 - OG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1282 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 0 | 3402.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1283 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 550 | 440 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1284 | ESCUTCHEONS FOR PLUMBING PIPING | 1100 | 825 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1285 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2860 | 1430 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01205 | 1286 | Existing Ramp railing to be be removed - 1st fllor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG5-03005 | 1287 | HANGERS AND SUPPORTS | 11541 | 11541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1288 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1289 | DOMESTIC WATER PIPING | 120919 | 120919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1290 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 | 0 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1291 | SANITARY WASTE PIPING | 111989 | 100790.1 | 0 | 11198.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1292 | SANITARY WASTE PIPING SPECIALTIES | 30069 | 27062.1 | 0 | 3006.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1293 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 16500 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03030 | 1294 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 186998 | 149598.4 | 0 | 0 | 18699.8 | 18699.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1295 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 1296 | Plumbing Pipe Insulation | 35464 | 31917.6 | 0 | 1773.2 | 1773.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01410 | 1297 | FORM FLOOD BARRIER FOUNDATIONS - SG-2 | 33187 | 16593.5 | 0 | 16593.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02045 | 1298 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-M-01005 | 1299 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 1300 | Exhaust Fans: Furnish | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03112 | 1301 | Exhaust Fans: Install | 17160 | 0 | 5720 | 5720 | 5720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1302 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03032 | 1303 | Steam Unit Heaters: Install | 18700 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1304 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03032 | 1305 | Condensate Return Unit: Install | 25300 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03112 | 1306 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03112 | 1307 | Heating and Ventilation Unit: Install | 26400 | 0 | 8800 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01450 | 1308 | DRILL & GROUT DOWELS - SG-2 | 3359 | 3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-03015 | 1309 | Steam Traps: Furnish | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03015 | 1310 | Steam Traps: Install | 25300 | 12650 | 1753.7673 | 1555.5154 | 9340.7173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1311 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03032 | 1312 | Vacuum Pump Unit: Install | 28600 | 28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03107 | 1313 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 350570 | 262927.5 | 52287.1026 | 35355.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03007 | 1314 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 451000 | 225500 | 112750 | 112750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1315 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 220000 | 110000 | 32812.7409 | 77187.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03025 | 1316 | Mechanical Pipe: Hydrostatic Testing | 5830 | 0 | 2915 | 2915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1317 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 38500 | 37730 | 0 | 0 | 741.7431 | 0 | 0 | 28.2569 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1318 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 75460 | 0 | 0 | 1483.4862 | 0 | 0 | 56.5138 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01450 | 1319 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-2 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-03310 | 1320 | HVAC Ductwork: Testing & Balancing | 4400 | 0 | 0 | 0 | 84.7706 | 0 | 0 | 4315.2294 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1321 | Controls: Furnish and Install: Devices | 77000 | 55440 | 0 | 20456.7164 | 0 | 1103.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1322 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1323 | Controls: Furnish and Install: Controls Wiring | 11000 | 4400 | 0 | 2922.3881 | 0 | 3677.6119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1324 | Controls: Connect to Final Termination Points | 8800 | 0 | 0 | 2337.9104 | 0 | 6462.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03025 | 1325 | Controls: Controls Testing | 6600 | 0 | 0 | 1753.4328 | 0 | 4846.5672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1326 | Insulation: Furnish and Install: Ductwork Insulation | 22000 | 0 | 0 | 0 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1327 | Insulation: Furnish and Install: Piping Insulation | 44000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1328 | Insulation: Furnish and Install: Equipment Insulation | 22000 | 0 | 0 | 0 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02210 | 1329 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01470 | 1330 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-2 | 25018 | 12509 | 10424.1667 | 0 | 0 | 1042.4167 | 1042.4167 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02210 | 1331 | ATS Installation | 153300 | 137970 | 0 | 0 | 0 | 0 | 5110 | 5110 | 5110 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02210 | 1332 | ATS Terminations | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02210 | 1333 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02010 | 1334 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02040 | 1335 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGP1-02025 | 1336 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 246375 | 82125 | 82125 | 82125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02015 | 1337 | Conduit - Branch Circuits (1 1/2" & Smaller) | 232688 | 197784.8 | 0 | 0 | 0 | 0 | 11634.4 | 11634.4 | 11634.4 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02125 | 1338 | Conduit - Risers (2" & Larger) | 492750 | 468112.5 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02025 | 1339 | Demolition/Temp Light & Power | 54750 | 43800 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02145 | 1340 | Firestopping | 5250 | 2625 | 0 | 0 | 0 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01440 | 1341 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-2 | 24855 | 24855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02030 | 1342 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02240 | 1343 | Lighting Controls | 32550 | 16275 | 0 | 13950 | 0 | 0 | 775 | 775 | 775 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02025 | 1344 | Lighting Remove & Re-install | 39420 | 0 | 0 | 0 | 0 | 0 | 13140 | 13140 | 13140 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02025 | 1345 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02050 | 1346 | Mechanical Terminations(Dampers, Heaters, Motors) | 65700 | 16425 | 43115.625 | 0 | 0 | 0 | 2053.125 | 2053.125 | 2053.125 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGP1-E-01010 | 1347 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02250 | 1348 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02515 | 1349 | Switchgear & Panelboard Energization | 30113 | 0 | 0 | 0 | 25811.1429 | 0 | 1433.9524 | 1433.9524 | 1433.9524 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02265 | 1350 | Switchgear & Panelboard Installation | 366300 | 329670 | 18315 | 18315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02265 | 1351 | Switchgear & Panelboard Terminations | 30113 | 7528.25 | 0 | 0 | 0 | 0 | 7528.25 | 7528.25 | 7528.25 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01415 | 1352 | Footing/Pier | 11409 | 5704.5 | 3803 | 1901.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-02510 | 1353 | Switchgear & Panelboard Testing | 30113 | 0 | 4301.8571 | 4301.8571 | 4301.8571 | 5735.8095 | 5735.8095 | 5735.8095 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02015 | 1354 | Fire Alarm Conduit | 21900 | 16425 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02115 | 1355 | Fire Alarm Wiring | 19710 | 0 | 0 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02115 | 1356 | Fire Alarm Devices | 20805 | 10402.5 | 0 | 0 | 0 | 0 | 3467.5 | 3467.5 | 3467.5 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02115 | 1357 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-02535 | 1358 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-01405 | 1359 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 11300 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 178 - OG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01580 | 1360 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-5 | 3981 | 3981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 178 - OG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG5-01580 | 1361 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-5 | 1181 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 178 - OG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01005 | 1362 | Gaskets | 58500 | 43875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14625 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01435 | 1363 | Retaining Walls | 3047 | 3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01010 | 1364 | Wire Insulation | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01015 | 1365 | Assumed Flooring Material (Slab Penetrations) | 64800 | 64800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01020 | 1366 | Pipe Insulation | 90720 | 90720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01005 | 1367 | Duct Seal | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01015 | 1368 | Asbestos Panels | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01015 | 1369 | Fibrous Slate | 14280 | 14280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01020 | 1370 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01020 | 1371 | Underground Utility Materials | 11388 | 11388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1372 | Remove existing paint and plaster - cellar and basement | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01220 | 1373 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01535 | 1374 | Entrance Slab | 17178 | 4294.5 | 4294.5 | 4294.5 | 4294.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01105 | 1375 | Remove existing vent / window and frame- cellar and basement | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1376 | Remove existing door, frame and hardware - basement | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01115 | 1377 | Remove Areaway slab and drain - basement | 60000 | 51000 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 1800 | 1800 | 1800 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01115 | 1378 | Remove Areaway grate - cellar and basement | 20000 | 15000 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01115 | 1379 | Sawcut and remove portion of areaway wall - basement | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1380 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01105 | 1381 | Remove existing AC units and sleeves - 1st floor | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1382 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1383 | Sawcut slab opening for mechanical - 1st floor | 40000 | 20000 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01210 | 1384 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01810 | 1385 | Concrete Shelf | 5241 | 5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01210 | 1386 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1387 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1388 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1389 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1390 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01210 | 1391 | Cut openings in slab - 2nd floor | 40000 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01105 | 1392 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1393 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01105 | 1394 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG6-01210 | 1395 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-01350 | 1396 | New Concrete Curb Next to Existing Wall | 297 | 0 | 148.5 | 148.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01410 | 1397 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - OG-6 | 196219 | 117731.4 | 39243.8 | 39243.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01450 | 1398 | DRILL & GROUT DOWELS - OG-6 | 42646 | 42646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01450 | 1399 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - OG-6 | 57788 | 15894 | 0 | 35909.1429 | 2992.4286 | 1496.2143 | 1496.2143 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01770 | 1400 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - OG-6 | 56948 | 28474 | 0 | 0 | 9491.3333 | 9491.3333 | 9491.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01440 | 1401 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - OG-6 | 11142 | 8356.5 | 0 | 2785.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01440 | 1402 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - OG-6 | 3927 | 0 | 0 | 3272.5 | 327.25 | 163.625 | 163.625 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01320 | 1403 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - OG-6 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01415 | 1404 | Footing/Pier | 13845 | 0 | 0 | 0 | 6922.5 | 6922.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01435 | 1405 | Retaining Walls | 1275 | 637.5 | 637.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01765 | 1406 | Entrance Slab | 23358 | 0 | 0 | 0 | 11679 | 11679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01830 | 1407 | GFRP Sikawrap 100 G | 44616 | 0 | 0 | 0 | 14872 | 14872 | 14872 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 016 - SG2 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01810 | 1408 | Concrete Shelf | 5472 | 0 | 0 | 0 | 2736 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01350 | 1409 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01765 | 1410 | Boiler Room Walls | 18288 | 18288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1411 | GFRP Sikawrap 100 G | 32604 | 0 | 10868 | 10868 | 10868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 180 - OG6 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OGE-01015 | 1412 | Overhead protection for Masonry | 15262 | 0 | 0 | 0 | 7631 | 3815.5 | 3815.5 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01820 | 1413 | 6" vertically reinforced CMU | 34760 | 26070 | 0 | 0 | 8690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1414 | 2" Face brick | 161546 | 0 | 80773 | 80773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1415 | 2" rigid Insulation | 6083 | 0 | 2027.6667 | 2027.6667 | 2027.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01820 | 1416 | Coping stone C1/A-300 | 12375 | 0 | 0 | 0 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05290 | 1417 | MATERIAL AND FABRICATION | 16765 | 0 | 16765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01440 | 1418 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-2 | 324 | 0 | 162 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01315 | 1419 | INSTALLATION | 19800 | 0 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01860 | 1420 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-02145 | 1421 | PENETRATION FIRESTOPPING EXTG BLDG - OG-6 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11505 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01320 | 1422 | JOINT SEALANTS EXTG BLDGS - OG 6 | 33516 | 0 | 0 | 0 | 11172 | 11172 | 11172 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01830 | 1423 | Bituthene 4000 waterproofing membrane | 9485 | 0 | 3161.6667 | 3161.6667 | 3161.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01830 | 1424 | GE Elemax 2600 Silicone air and vapor barrier | 18810 | 0 | 6270 | 6270 | 6270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01370 | 1425 | Crystalline Waterproofing at perimeter walls | 54338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01825 | 1426 | Waterproofing at foundation walls | 22080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 183 - OG6 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
08140 | 1427 | ALUMINUM WINDOWS | 19222 | 0 | 0 | 0 | 9611 | 4805.5 | 4805.5 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 184 - OG6 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01330 | 1428 | Doors, Frames & Hardware - Labor | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 184 - OG6 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01015 | 1429 | Overhead protection for Masonry | 5088 | 2544 | 0 | 0 | 0 | 1272 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
08020 | 1430 | Furnish Doors | 14634 | 4829.22 | 0 | 0 | 4902.39 | 2451.195 | 2451.195 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1431 | Layout | 3858 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1432 | Loading | 6686 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1433 | Framing & Drywall - Materials | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01325 | 1434 | Framing- Labor | 12601 | 12601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01330 | 1435 | Drywall - Labor | 18260 | 18260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01330 | 1436 | Tape/ Spackle finishes | 11829 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01855 | 1437 | Stucco | 10183 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01340 | 1438 | Resilient Flooring and base - OG-6 | 15640 | 0 | 0 | 0 | 0 | 0 | 11730 | 3910 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01860 | 1439 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - OG-6 | 111178 | 55589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55589 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01820 | 1440 | 6" vertically reinforced CMU | 125840 | 119548 | 0 | 0 | 6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01860 | 1441 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - OG-6 | 63427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63427 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01865 | 1442 | Temporary Egress Stair Storage Sign | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2640 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01865 | 1443 | Address Signs | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | OG6 | 186 - OG6 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01380 | 1444 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1445 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1446 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1447 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1448 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1449 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1450 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01830 | 1451 | 2" Face brick | 357280 | 285824 | 0 | 0 | 71456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01380 | 1452 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1453 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1454 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1455 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1456 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1457 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1458 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1459 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1460 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1461 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01830 | 1462 | 2" rigid Insulation | 18876 | 9438 | 0 | 0 | 3146 | 3146 | 3146 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01380 | 1463 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1464 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01380 | 1465 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 187 - OG6 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1466 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 8165.4 | 1814.5333 | 1814.5333 | 1814.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1467 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 2634 | 2107.2 | 175.6 | 175.6 | 175.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1468 | ESCUTCHEONS FOR PLUMBING PIPING | 1650 | 1320 | 110 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1469 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4171 | 2502.6 | 556.1333 | 556.1333 | 556.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1470 | HANGERS AND SUPPORTS | 11526 | 8644.5 | 960.5 | 960.5 | 960.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1471 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1472 | DOMESTIC WATER PIPING | 195822 | 176239.8 | 6527.4 | 6527.4 | 6527.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01820 | 1473 | Coping Stone C1/A-300 | 30958 | 30958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-03005 | 1474 | DOMESTIC WATER PIPING SPECIALTIES | 16279 | 13837.15 | 813.95 | 813.95 | 813.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1475 | SANITARY WASTE PIPING | 37529 | 35652.55 | 625.4833 | 625.4833 | 625.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1476 | SANITARY WASTE PIPING SPECIALTIES | 162217 | 145995.3 | 5407.2333 | 5407.2333 | 5407.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1477 | STORM DRAINAGE PIPING SPECIALTIES | 53592 | 34834.8 | 6252.4 | 6252.4 | 6252.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03030 | 1478 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 231000 | 127050 | 34650 | 34650 | 34650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1479 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13277 | 13277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03005 | 1480 | Plumbing Pipe Insulation | 35464 | 26598 | 0 | 4433 | 4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02045 | 1481 | Heat Trace | 5475 | 0 | 0 | 4692.8571 | 0 | 0 | 260.7143 | 260.7143 | 260.7143 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-M-01005 | 1482 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 1483 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
05470 | 1484 | MATERIAL AND FABRICATION | 5824 | 0 | 5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03112 | 1485 | Exhaust Fans: Install | 12595 | 6297.5 | 0 | 2226.936 | 4070.564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1486 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03032 | 1487 | Steam Unit Heaters: Install | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1488 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03032 | 1489 | Condensate Return Unit: Install | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03112 | 1490 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03112 | 1491 | Heating and Ventilation Unit: Install | 23100 | 0 | 0 | 4084.3368 | 19015.6632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03015 | 1492 | Steam Traps: Furnish | 2860 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03015 | 1493 | Steam Traps: Install | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1494 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01315 | 1495 | INSTALLATION | 6600 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03032 | 1496 | Vacuum Pump Unit: Install | 25300 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03107 | 1497 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 263780 | 255866.6 | 3956.7 | 3956.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03007 | 1498 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 341000 | 330770 | 5115 | 5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1499 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 165000 | 160050 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03025 | 1500 | Mechanical Pipe: Hydrostatic Testing | 5720 | 0 | 2860 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 1501 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 27500 | 26950 | 0 | 0 | 528.8462 | 0 | 0 | 0 | 21.1538 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 1502 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 55000 | 53900 | 0 | 0 | 1057.6923 | 0 | 0 | 0 | 42.3077 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03135 | 1503 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 0 | 63.4615 | 0 | 0 | 0 | 3236.5385 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1504 | Controls: Furnish and Install: Devices | 71500 | 57200 | 0 | 0 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1505 | Controls: Furnish and Install: Controls Conduit | 38500 | 36575 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01860 | 1506 | Temporary Aluminum Over Pass Stairs | 28598 | 0 | 0 | 0 | 0 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 1507 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 3420.7317 | 7579.2683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 1508 | Controls: Connect to Final Termination Points | 7700 | 0 | 0 | 0 | 2394.5122 | 5305.4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-03025 | 1509 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 2052.439 | 4547.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1510 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 0 | 0 | 9075 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1511 | Insulation: Furnish and Install: Piping Insulation | 33000 | 0 | 0 | 0 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1512 | Insulation: Furnish and Install: Equipment Insulation | 18150 | 0 | 0 | 0 | 9075 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1513 | ATS Energization | 13688 | 0 | 5475.2 | 5475.2 | 0 | 0 | 912.5333 | 912.5333 | 912.5333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1514 | ATS Installation | 191625 | 153300 | 38325 | 38325 | 0 | 0 | -12775 | -12775 | -12775 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1515 | ATS Terminations | 13688 | 0 | 5475.2 | 5475.2 | 0 | 0 | 912.5333 | 912.5333 | 912.5333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02210 | 1516 | ATS Testing | 13688 | 0 | 5475.2 | 5475.2 | 0 | 0 | 912.5333 | 912.5333 | 912.5333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02125 | 1517 | PENETRATION FIRESTOPPING EXTG BLDG - SG-2 | 11505 | 0 | 10226.6667 | 0 | 0 | 639.1667 | 639.1667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02015 | 1518 | Bypass Connections (Misc Panels, Re-routes, etc) | 27750 | 15262.5 | 0 | 0 | 0 | 0 | 4162.5 | 4162.5 | 4162.5 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02040 | 1519 | Cabling - Interior Branch (1/0 & Smaller) | 136875 | 0 | 109500 | 13687.5 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-02115 | 1520 | Cabling - Risers & Feeders (2/0 & Larger) | 591300 | 0 | 0 | 0 | 147825 | 147825 | 147825 | 147825 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02020 | 1521 | Conduit - Branch Circuits (1 1/2" & Smaller) | 273750 | 0 | 39107.1429 | 39107.1429 | 39107.1429 | 52142.8571 | 52142.8571 | 52142.8571 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02115 | 1522 | Conduit - Risers (2" & Larger) | 689850 | 137970 | 75366.8722 | 0 | 0 | 0 | 158837.7093 | 158837.7093 | 158837.7093 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02025 | 1523 | Demolition/Temp Light & Power | 55500 | 36075 | 3171.4286 | 3171.4286 | 3171.4286 | 3303.5714 | 3303.5714 | 3303.5714 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02145 | 1524 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 4500 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02030 | 1525 | Foundation Coring | 21000 | 13650 | 567.9545 | 0 | 0 | 0 | 2260.6818 | 2260.6818 | 2260.6818 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02240 | 1526 | Lighting Controls | 49350 | 24675 | 0 | 0 | 0 | 10575 | 4700 | 4700 | 4700 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02025 | 1527 | Lighting Remove & Re-install | 40406 | 0 | 11544.5714 | 0 | 0 | 0 | 9620.4762 | 9620.4762 | 9620.4762 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01320 | 1528 | JOINT SEALANTS EXTG BLDGS - SG-2 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02025 | 1529 | Lighting System Program & Energize | 5550 | 0 | 1585.7143 | 0 | 0 | 0 | 1321.4286 | 1321.4286 | 1321.4286 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02050 | 1530 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 0 | 0 | 54437.1429 | 0 | 0 | 3024.2857 | 3024.2857 | 3024.2857 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-OGE-01020 | 1531 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02245 | 1532 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 9385.7143 | 521.4286 | 521.4286 | 521.4286 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02515 | 1533 | Switchgear & Panelboard Energization | 32850 | 0 | 0 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02260 | 1534 | Switchgear & Panelboard Installation | 492750 | 394200 | 0 | 0 | 0 | 211178.5714 | -37542.8571 | -37542.8571 | -37542.8571 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02260 | 1535 | Switchgear & Panelboard Terminations | 32850 | 0 | 0 | 0 | 0 | 28157.1429 | 1564.2857 | 1564.2857 | 1564.2857 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02510 | 1536 | Switchgear & Panelboard Testing | 32850 | 0 | 0 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02020 | 1537 | Fire Alarm Conduit | 27375 | 0 | 3910.7143 | 3910.7143 | 3910.7143 | 5214.2857 | 5214.2857 | 5214.2857 | 0 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02120 | 1538 | Fire Alarm Wiring | 24638 | 0 | 0 | 0 | 12319 | 0 | 4106.3333 | 4106.3333 | 4106.3333 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01830 | 1539 | Bituthene 4000 waterproofing membrane | 16940 | 8470 | 0 | 0 | 2823.3333 | 2823.3333 | 2823.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-02120 | 1540 | Fire Alarm Devices | 24090 | 12045 | 0 | 0 | 6022.5 | 0 | 2007.5 | 2007.5 | 2007.5 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02120 | 1541 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 1369 | 0 | 456.3333 | 456.3333 | 456.3333 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-02535 | 1542 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG6-01405 | 1543 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 19775 | 14831.25 | 0 | 0 | 1647.9167 | 1647.9167 | 1647.9167 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 192 - OG6 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01780 | 1544 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - OG-6 | 6285 | 4085.25 | 0 | 0 | 1099.875 | 1099.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 192 - OG6 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG6-01780 | 1545 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - OG-6 | 1181 | 590.5 | 0 | 0 | 295.25 | 295.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 192 - OG6 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG10-01013 | 1546 | Caulk | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG10-01013 | 1547 | Fibrous Slate | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
OG10-01015 | 1548 | Demo Existing Building/Temp Light & Power | 35150 | 35150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 194 - OG7 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01070 | 1549 | FORMWORK NEW BUILDING - OG-8 | 751900 | 751900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01830 | 1550 | GE Elemax 2600 Silicone air and vapor barrier | 18876 | 0 | 0 | 0 | 6292 | 6292 | 6292 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01175 | 1551 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-8 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01040 | 1552 | POUR CONCRETE NEW BUILDINGS - OG-8 | 402192 | 402192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01135 | 1553 | FINISH SLABS - OG-8 | 34800 | 34800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01075 | 1554 | Footing/Pier | 80925 | 80925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01075 | 1555 | Grade Beams | 15788 | 15788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01170 | 1556 | Floor Slabs | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01130 | 1557 | Equipment Pads | 3855 | 3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01155 | 1558 | Foundation Walls | 8538 | 8538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01170 | 1559 | Concrete Stairs | 1122 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01205 | 1560 | WWM-Slabs | 13163 | 13163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 195 - OG8 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01370 | 1561 | Crystalline Waterproofing at perimeter walls | 32200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01230 | 1562 | 8" CMU (3 hour rated) | 434720 | 434720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01275 | 1563 | 4" CMU | 151404 | 151404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01230 | 1564 | 6" CMU (2 hour rated) | 8910 | 8910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01275 | 1565 | Face Brick 3-5/8" | 373450 | 373450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01275 | 1566 | 3-1/8" Rigid insulation | 32010 | 32010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01250 | 1567 | Cast Stone with SS letters | 8650 | 0 | 8650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01230 | 1568 | Steel Channel | 23642 | 23642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01230 | 1569 | Cont. Shelf angle | 12690 | 12690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1570 | STEEL (MATERIAL ONLY) | 245175 | 245175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1571 | FABRICATION COSTS | 338575 | 338575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01825 | 1572 | Waterproofing at foundation walls | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 019 - SG2 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01105 | 1573 | METAL DECK (BUY-OUT) | 24518 | 24518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1574 | ANCHORS & EMBEDS | 11676 | 11676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1575 | SURVEYING | 17514 | 17514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1576 | STEEL & DECK ERECTION | 817248 | 817248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1577 | BOLTS AND HARDWARE | 23351 | 23351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01105 | 1578 | TRUCKING | 11676 | 11676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01270 | 1579 | Dunnage Grating Galvanized | 72626 | 18156.5 | 54469.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01270 | 1580 | Dunnage Guard Rail | 32588 | 32588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01270 | 1581 | Dunnage Stair and Railing (1) | 13242 | 11917.8 | 0 | 1324.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01290 | 1582 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 172065 | 172065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01860 | 1583 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-2 | 1200 | 0 | 300 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 020 - SG2 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-01290 | 1584 | Stair B: Stair, Landing and Hand & Guard Rail | 81523 | 81523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01295 | 1585 | 1st to 2nd Floor Ship Ladder with Cage and Platform Landing | 27106 | 23040.1 | 0 | 4065.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01290 | 1586 | Egress Stair: Stair & Landing with Hand & Guard Rail | 47590 | 11897.5 | 0 | 0 | 35692.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1587 | Layout | 9195 | 9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1588 | Loading | 26857 | 26857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1589 | Exterior Framing, Insulation & Drywall - Materials | 116188 | 116188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1590 | Exterior Framing- Labor | 64809 | 64809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01125 | 1591 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-8 | 24599 | 24599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-02495 | 1592 | PENETRATION FIRESTOPPING NEW BLDG - OG-8 | 11505 | 0 | 0 | 0 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG3-01320 | 1593 | JOINT SEALANTS NEW BLDGS - OG-8 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01330 | 1594 | Doors, Frames & Hardware - Labor | 7784 | 7784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 020 - SG2 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01230 | 1595 | Air Film | 32010 | 32010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01305 | 1596 | Insulation- Labor | 10399 | 7799.25 | 2599.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01025 | 1597 | Crystalline Waterproofing at plumbing shaft | 10350 | 10350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01072 | 1598 | Waterproofing at foundation | 123540 | 123540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1599 | Layout | 138040 | 0 | 0 | 46013.3333 | 46013.3333 | 46013.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1600 | Framing | 328661 | 328661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1601 | Insulation | 58865 | 58865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01255 | 1602 | Cladding Install | 412052 | 20602.6 | 0 | 130483.1333 | 130483.1333 | 130483.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01225 | 1603 | Fireproofing | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01265 | 1604 | P&I Cold Applied Roof Membrane | 151996 | 106397.2 | 0 | 0 | 45598.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1605 | Furnish Doors | 2091 | 0 | 522.75 | 522.75 | 522.75 | 261.375 | 261.375 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01265 | 1606 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 160693 | 70346.5 | 0 | 0 | 90346.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01265 | 1607 | P&I Aluminum Coping | 9240 | 0 | 0 | 0 | 9240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01260 | 1608 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-8 | 14378 | 1437.8 | 0 | 0 | 0 | 6470.1 | 6470.1 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01245 | 1609 | Doors, Frames & Hardware - Labor | 35030 | 12000 | 5353.33 | 10000 | 7676.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01317 | 1610 | Louvers Install | 102778 | 0 | 0 | 34259.3333 | 34259.3333 | 34259.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08080 | 1611 | Overhead Door | 16000 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | Loading Dock | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1612 | Furnish Doors | 37629 | 0 | 9407.25 | 9407.25 | 9407.25 | 4703.625 | 4703.625 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01305 | 1613 | Sheathing & Drywall - Labor | 87184 | 0 | 0 | 30000 | 30000 | 27184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01245 | 1614 | Tape/ Spackle finishes | 41405 | 0 | 15000 | 15000 | 11405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01315 | 1615 | ACT ceilings - Materials | 1286 | 0 | 0 | 964.5 | 321.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01325 | 1616 | Layout | 2315 | 0 | 771.6667 | 771.6667 | 771.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01315 | 1617 | ACT ceilings - Labor | 3086 | 0 | 0 | 3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01280 | 1618 | Direct Applied Stucco | 26335 | 0 | 13167.5 | 13167.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01325 | 1619 | Painting OG-8 | 110000 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01310 | 1620 | Cermic Tile and Base - OG-8 | 5124 | 0 | 0 | 2562 | 2562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01260 | 1621 | FIRE EXTINGUISHERS NEW BLDGS - S8 | 1466 | 0 | 366.5 | 366.5 | 366.5 | 183.25 | 183.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01260 | 1622 | TOILET ACCESSORIES NEW BLDGS - OG-8 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1623 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1624 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1625 | Room Sign | 4400 | 0 | 0 | 0 | 0 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1626 | Exit Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01325 | 1627 | Loading | 3601 | 0 | 1200.3333 | 1200.3333 | 1200.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-01330 | 1628 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01330 | 1629 | Stairway Flood Access Door | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 202 - OG8 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1630 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 4140.8 | 323.5 | 323.5 | 0 | 129.4 | 129.4 | 129.4 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1631 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5016 | 132 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1632 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 2090 | 0 | 0 | 0 | 36.6667 | 36.6667 | 36.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1633 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 15180 | 14421 | 379.5 | 379.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1634 | HANGERS AND SUPPORTS | 21784 | 20694.8 | 544.6 | 544.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1635 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 | 913 | 913 | 913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1636 | DOMESTIC WATER PIPING | 207347 | 196979.65 | 6738.7775 | 0 | 0 | 1209.5242 | 1209.5242 | 1209.5242 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1637 | DOMESTIC WATER PIPING SPECIALTIES | 14344 | 13913.68 | 215.16 | 215.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01325 | 1638 | Framing & Drywall - Materials | 3858 | 0 | 1286 | 1286 | 1286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03105 | 1639 | SANITARY WASTE PIPING | 146824 | 142419.28 | 2202.36 | 2202.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1640 | SANITARY WASTE PIPING SPECIALTIES | 29738 | 28251.1 | 495.6333 | 495.6333 | 495.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1641 | STORM DRAINAGE PIPING SPECIALTIES | 73736 | 73736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1642 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 4910.4 | 3819.2 | 3819.2 | 3819.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1643 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 4012.8 | 4012.8 | 4012.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1644 | GAS SERVICE AND PIPING | 398429 | 358586.1 | 14941.0875 | 0 | 0 | 8300.6042 | 8300.6042 | 8300.6042 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1645 | PLUMBING FIXTURES | 18392 | 0 | 6130.6667 | 6130.6667 | 6130.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03140 | 1646 | EMERGENCY PLUMBING FIXTURES | 5104 | 0 | 1701.3333 | 1701.3333 | 1701.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1647 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 15101 | 15101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03105 | 1648 | Plumbing Pipe Insulation | 8895 | 0 | 0 | 0 | 4447.5 | 4447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01325 | 1649 | Framing- Labor | 5658 | 0 | 1886 | 1886 | 1886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-02150 | 1650 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGP1-M-01005 | 1651 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 1652 | Exhaust Fans: Furnish | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1653 | Exhaust Fans: Install | 40040 | 40040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1654 | Steam Unit Heaters: Furnish | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1655 | Steam Unit Heaters: Install | 85250 | 42625 | 42625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1656 | Electric Heaters: Furnish | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1657 | Condensate Return Unit: Furnish | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1658 | Condensate Return Unit: Install | 58850 | 58850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1659 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01330 | 1660 | Drywall - Labor | 5401 | 0 | 1800.3333 | 1800.3333 | 1800.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03142 | 1661 | Heating and Ventilation Unit: Install | 46750 | 0 | 23375 | 23375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1662 | Steam Traps: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1663 | Steam Traps: Install | 50600 | 50600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1664 | Steam Separator: Furnish | 52800 | 52800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1665 | Steam Separator: Install | 384450 | 384450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03210 | 1666 | Low Pressure Steam Boilers: Install | 208450 | 208450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1667 | Boiler Feed Unit: Furnish | 82500 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 1668 | Boiler Feed Unit: Install | 54450 | 54450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1669 | Fuel Oil Pump: Furnish | 77000 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 1670 | Fuel Oil Pump: Install | 54450 | 54450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01330 | 1671 | Tape/ Spackle finishes | 4629 | 0 | 1543 | 1543 | 1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03142 | 1672 | Fuel Oil Storage Tank: Furnish | 71500 | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03110 | 1673 | Fuel Oil Storage Tank: Install | 65450 | 65450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03110 | 1674 | Rigging | 285450 | 285450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03107 | 1675 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 719400 | 719400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1676 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 949300 | 949300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1677 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 379500 | 371910 | 7590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 1678 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 385000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03135 | 1679 | Mechanical Pipe: Hydrostatic Testing | 12100 | 10285 | 1815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1680 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 99000 | 89100 | 2475 | 2475 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 1681 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 192500 | 173250 | 4812.5 | 4812.5 | 4812.5 | 4812.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01855 | 1682 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG8-03245 | 1683 | HVAC Ductwork: Testing & Balancing | 11000 | 0 | 530 | 0 | 0 | 3490 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1684 | Controls: Furnish and Install: Devices | 275000 | 137500 | 45833.3333 | 45833.3333 | 45833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1685 | Controls: Furnish and Install: Controls Conduit | 121000 | 90750 | 15125 | 15125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1686 | Controls: Furnish and Install: Controls Wiring | 33000 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1687 | Controls: Connect to Final Termination Points | 22000 | 0 | 7333.3333 | 7333.3333 | 7333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03135 | 1688 | Controls: Controls Testing | 19030 | 0 | 6343.3333 | 6343.3333 | 6343.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1689 | Insulation: Furnish and Install: Ductwork Insulation | 60500 | 0 | 30250 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1690 | Insulation: Furnish and Install: Piping Insulation | 126500 | 25300 | 37668.8889 | 63531.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1691 | Insulation: Furnish and Install: Equipment Insulation | 60500 | 0 | 30250 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 1692 | Furnish and Install: Chemical Feed Equipment | 10230 | 5115 | 1705 | 1705 | 1705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01860 | 1693 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-2 | 43236 | 21618 | 5404.5 | 0 | 5404.5 | 5404.5 | 5404.5 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-03242 | 1694 | Chemical Cleaning | 8250 | 0 | 2750 | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1695 | ATS Energization | 16425 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1696 | ATS Installation | 229950 | 206955 | 0 | 0 | 0 | 7665 | 7665 | 7665 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1697 | ATS Terminations | 16425 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02255 | 1698 | ATS Testing | 16425 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02130 | 1699 | Cabling - Interior Branch (1/0 & Smaller) | 219000 | 109500 | 0 | 0 | 0 | 36500 | 36500 | 36500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02490 | 1700 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 0 | 0 | 470352.2727 | 22397.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02115 | 1701 | Conduit - Branch Circuits (1 1/2" & Smaller) | 164250 | 139612.5 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02205 | 1702 | Conduit - In-Slab | 216810 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02010 | 1703 | Conduit - Risers (2" & Larger) | 443475 | 421301.25 | 0 | 0 | 0 | 7391.25 | 7391.25 | 7391.25 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01860 | 1704 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) - SG-2 | 31714 | 0 | 7928.5 | 0 | 7928.5 | 7928.5 | 7928.5 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-02495 | 1705 | Firestopping | 5250 | 3150 | 0 | 1050 | 525 | 175 | 175 | 175 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG8-01170 | 1706 | Generator Delivery | 78750 | 0 | 39375 | 0 | 0 | 13125 | 13125 | 13125 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG8-01010 | 1707 | Generator Release | 472500 | 472500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02420 | 1708 | Generator Terminations | 78750 | 0 | 0 | 0 | 73125 | 1875 | 1875 | 1875 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02730 | 1709 | Generator Test | 78750 | 39375 | 0 | 0 | 0 | 13125 | 13125 | 13125 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02120 | 1710 | Lighting Controls | 14700 | 7350 | 0 | 0 | 0 | 2450 | 2450 | 2450 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02140 | 1711 | Lighting Install | 144900 | 130410 | 7308.5526 | 0 | 0 | 2393.8158 | 2393.8158 | 2393.8158 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02140 | 1712 | Lighting Rough | 151110 | 143554.5 | 3048.7105 | 0 | 0 | 1502.2632 | 1502.2632 | 1502.2632 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02140 | 1713 | Lighting System Program & Energize | 5475 | 0 | 1104.6053 | 0 | 0 | 1456.7982 | 1456.7982 | 1456.7982 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02425 | 1714 | Lightning Protection | 21900 | 10950 | 0 | 0 | 9385.7143 | 521.4286 | 521.4286 | 521.4286 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01860 | 1715 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-2 | 80599 | 0 | 20149.75 | 0 | 20149.75 | 20149.75 | 20149.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-02145 | 1716 | Mechanical Terminations(Dampers, Heaters, Motors) | 164250 | 0 | 0 | 0 | 0 | 54750 | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGP1-E-01010 | 1717 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02160 | 1718 | Switches and Receptacles | 21900 | 5475 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02725 | 1719 | Switchgear & Panelboard Energization | 24638 | 0 | 0 | 0 | 0 | 8212.6667 | 8212.6667 | 8212.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02275 | 1720 | Switchgear & Panelboard Installation | 295650 | 221737.5 | 10558.9286 | 10558.9286 | 10558.9286 | 14078.5714 | 14078.5714 | 14078.5714 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02275 | 1721 | Switchgear & Panelboard Terminations | 24638 | 0 | 12319 | 0 | 0 | 4106.3333 | 4106.3333 | 4106.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02720 | 1722 | Switchgear & Panelboard Testing | 24638 | 0 | 0 | 0 | 0 | 8212.6667 | 8212.6667 | 8212.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02005 | 1723 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02115 | 1724 | Fire Alarm Conduit | 68438 | 58172.3 | 0 | 0 | 0 | 3421.9 | 3421.9 | 3421.9 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02480 | 1725 | Fire Alarm Wiring | 65700 | 32850 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01865 | 1726 | Temporary Egress Stair Storage Sign | 1320 | 0 | 880 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG8-02480 | 1727 | Fire Alarm Devices | 140160 | 119136 | 0 | 0 | 0 | 7008 | 7008 | 7008 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02480 | 1728 | Fire Alarm Programming & Pretest | 2750 | 0 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02740 | 1729 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-01005 | 1730 | EXCAVATION NEW BLDGS - OG-8 | 86240 | 86240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01055 | 1731 | BACKFILL NEW BLDGS - OG-8 | 36868 | 36868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1732 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-8 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1733 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-8 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1734 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-8 | 68282 | 68282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01005 | 1735 | STONE FOR FOUNDATION - OG-8 | 7221 | 7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 207 - OG8 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01070 | 1736 | FORMWORK NEW BUILDING - OG-9 | 215221 | 215221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01865 | 1737 | Address Signs | 4950 | 0 | 3300 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 022 - SG2 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG9-01175 | 1738 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-9 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01040 | 1739 | POUR CONCRETE NEW BUILDINGS - OG-9 | 102272 | 102272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01135 | 1740 | FINISH SLABS - OG-9 | 10493 | 10493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01075 | 1741 | Footing/Pier | 38922 | 38922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01075 | 1742 | Grade Beams | 11369 | 11369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01170 | 1743 | Floor Slabs | 15984 | 15984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01130 | 1744 | Equipment Pads | 106 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01035 | 1745 | Second Floor Plumbing Shaft Slab | 528 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01035 | 1746 | Plumbing Shafts | 23767 | 23767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01205 | 1747 | WWM-Slabs | 5262 | 5262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 208 - OG9 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1748 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01230 | 1749 | 8" CMU (3 hour rated) | 101420 | 101420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01275 | 1750 | 4" CMU | 13860 | 13860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01230 | 1751 | 6" CMU (2 hour rated) | 51414 | 51414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01275 | 1752 | Face Brick 3-5/8" | 99578 | 99578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01275 | 1753 | 3-1/8" Rigid insulation | 8415 | 8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01250 | 1754 | Cast Stone with SS letters | 142454 | 110000 | 27817.7143 | 4636.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01230 | 1755 | Steel Channel | 24020 | 24020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01230 | 1756 | Cont. Shelf angle | 11330 | 11330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1757 | STEEL (MATERIAL ONLY) | 101945 | 101945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1758 | FABRICATION COSTS | 173771 | 173771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1759 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01105 | 1760 | METAL DECK (BUY-OUT) | 7531 | 7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1761 | ANCHORS & EMBEDS | 6951 | 6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1762 | SURVEYING | 9848 | 9848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1763 | STEEL & DECK ERECTION | 347540 | 347540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1764 | BOLTS AND HARDWARE | 6951 | 6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01105 | 1765 | TRUCKING | 5793 | 5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01270 | 1766 | Dunnage Grating | 23588 | 23588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01290 | 1767 | Railing | 11768 | 11768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01270 | 1768 | Dunnage Stair and Railing | 17380 | 17380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01290 | 1769 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 141827 | 141827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1770 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01295 | 1771 | 1st to 2nd Floor Ship Ladder with Safety Cage and Landing Platform with Rail | 25036 | 25036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01295 | 1772 | Ship Ladder Bulkhead Roof | 7035 | 7035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1773 | Layout | 3065 | 3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1774 | Loading | 10218 | 10218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1775 | Exterior Framing, Insulation & Drywall - Materials | 37221 | 37221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01305 | 1776 | Exterior Framing- Labor | 56196 | 56196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01125 | 1777 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-9 | 10055 | 10055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-02400 | 1778 | PENETRATION FIRESTOPPING NEW BLDG - OG-9 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG4-01320 | 1779 | JOINT SEALANTS NEW BLDGS - OG-9 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01230 | 1780 | Air Film | 8415 | 8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1781 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01305 | 1782 | Insulation- Labor | 2906 | 2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01025 | 1783 | Crystalline Waterproofing at plumbing shaft | 3738 | 3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01072 | 1784 | Waterproofing at foundation | 43413 | 43413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1785 | Layout | 55016 | 55016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1786 | Framing | 114716 | 114716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1787 | Insulation | 20546 | 20546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01255 | 1788 | Cladding Install | 143823 | 107867.25 | 0 | 8988.9375 | 8988.9375 | 8988.9375 | 8988.9375 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01225 | 1789 | Fireproofing | 29700 | 29700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01265 | 1790 | P&I Cold Applied Roof Membrane | 54257 | 54257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01265 | 1791 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 69054 | 69054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1792 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01265 | 1793 | P&I Aluminum Coping | 6592 | 0 | 0 | 6592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01260 | 1794 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-9 | 12324 | 12324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01245 | 1795 | Doors, Frames & Hardware - Labor | 17514 | 15514 | 1333.3333 | 666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01317 | 1796 | Louvers Install | 35874 | 0 | 0 | 8968.5 | 8968.5 | 8968.5 | 8968.5 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1797 | Furnish Doors | 22996 | 11000 | 0 | 0 | 0 | 5998 | 5998 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01305 | 1798 | Sheathing & Drywall - Labor | 18774 | 15774 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01245 | 1799 | Tape/ Spackle finishes | 9258 | 8332.2 | 925.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01315 | 1800 | ACT ceilings - Materials | 2058 | 0 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01315 | 1801 | ACT ceilings - Labor | 4372 | 0 | 0 | 4372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01280 | 1802 | Direct Applied Stucco | 13167 | 0 | 0 | 13167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1803 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-01325 | 1804 | Painting OG-9 | 110000 | 0 | 0 | 0 | 47142.8571 | 62857.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01310 | 1805 | Cermic Tile and Base - OG-9 | 7198 | 0 | 0 | 3599 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01260 | 1806 | TOILET ACCESSORIES NEW BLDGS - OG-9 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1807 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1808 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1809 | Room Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1810 | Exit Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01330 | 1811 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 215 - OG9 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1812 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 4917.2 | 129.4 | 129.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1813 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5121.6 | 52.8 | 52.8 | 52.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1814 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-03105 | 1815 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1816 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 14740 | 14297.8 | 147.4 | 147.4 | 147.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1817 | HANGERS AND SUPPORTS | 21930 | 21272.1 | 219.3 | 219.3 | 219.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1818 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 0 | 913 | 913 | 913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1819 | DOMESTIC WATER PIPING | 169254 | 160791.3 | 2820.9 | 2820.9 | 2820.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1820 | DOMESTIC WATER PIPING SPECIALTIES | 3432 | 3329.04 | 34.32 | 34.32 | 34.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1821 | SANITARY WASTE PIPING | 128128 | 124284.16 | 1601.6 | 1601.6 | 640.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1822 | SANITARY WASTE PIPING SPECIALTIES | 19050 | 19050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1823 | STORM DRAINAGE PIPING SPECIALTIES | 41052 | 41052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03140 | 1824 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 10120 | 5060 | 2530 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1825 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-03140 | 1826 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 4012.8 | 4012.8 | 4012.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1827 | GAS SERVICE AND PIPING | 224774 | 213535.3 | 3746.2333 | 3746.2333 | 3746.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03140 | 1828 | PLUMBING FIXTURES | 14167 | 1416.7 | 4250.1 | 4250.1 | 4250.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1829 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03105 | 1830 | Plumbing Pipe Insulation | 3175 | 0 | 0 | 0 | 1587.5 | 1587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02130 | 1831 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGW-M-01005 | 1832 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 1833 | Exhaust Fans: Furnish | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1834 | Exhaust Fans: Install | 21725 | 21725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1835 | Electric Unit Heaters: Furnish | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1836 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 1837 | Steam Unit Heater: Furnish | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1838 | Steam Unit Heater: Install | 48400 | 48400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1839 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1840 | Condensate Return Unit: Install | 28600 | 28600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1841 | Steam Traps: Furnish | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03142 | 1842 | Steam Traps: Install | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03107 | 1843 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 181775 | 181775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03107 | 1844 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 212850 | 212850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 1845 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 100650 | 100650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03135 | 1846 | Mechanical Pipe: Hydrostatic Testing | 3025 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1847 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-03107 | 1848 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 18975 | 18975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 1849 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03145 | 1850 | HVAC Ductwork: Testing & Balancing | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1851 | Controls: Furnish and Install: Devices | 99000 | 31680 | 0 | 0 | 49767.5676 | 14247.973 | 3304.4595 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1852 | Controls: Furnish and Install: Controls Conduit | 38500 | 19250 | 0 | 0 | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1853 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 5529.7297 | 1583.1081 | 3887.1622 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 1854 | Controls: Connect to Final Termination Points | 7700 | 0 | 0 | 0 | 3870.8108 | 1108.1757 | 2721.0135 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-03135 | 1855 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 3317.8378 | 949.8649 | 2332.2973 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1856 | Insulation: Furnish and Install: Ductwork Insulation | 12100 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 1857 | Insulation: Furnish and Install: Piping Insulation | 25300 | 0 | 0 | 0 | 12650 | 12650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1858 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 1859 | Insulation: Furnish and Install: Equipment Insulation | 12100 | 0 | 0 | 0 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1860 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1861 | ATS Installation | 153300 | 145635 | 0 | 0 | 0 | 7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1862 | ATS Terminations | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02275 | 1863 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02125 | 1864 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 30000 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02255 | 1865 | Cabling - Risers & Feeders (2/0 & Larger) | 354780 | 0 | 50682.8571 | 50682.8571 | 50682.8571 | 67577.1429 | 67577.1429 | 67577.1429 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02115 | 1866 | Conduit - Branch Circuits (1 1/2" & Smaller) | 83250 | 70762.5 | 0 | 0 | 0 | 4162.5 | 4162.5 | 4162.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02105 | 1867 | Conduit - In-Slab | 126473 | 126473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02010 | 1868 | Conduit - Risers (2" & Larger) | 299700 | 284715 | 0 | 0 | 0 | 4995 | 4995 | 4995 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1869 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-02400 | 1870 | Firestopping | 5250 | 2625 | 0 | 0 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG9-01046 | 1871 | Generator Delivery | 52500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG9-01010 | 1872 | Generator Release | 315000 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02335 | 1873 | Generator Terminations | 52500 | 0 | 0 | 0 | 0 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02530 | 1874 | Generator Test | 52500 | 26250 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02160 | 1875 | Lighting Controls | 8400 | 5040 | 0 | 0 | 0 | 1120 | 1120 | 1120 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02140 | 1876 | Lighting Install | 71820 | 57456 | 0 | 0 | 0 | 4788 | 4788 | 4788 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02140 | 1877 | Lighting Rough | 74898 | 71153.1 | 1872.45 | 1872.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02140 | 1878 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG8-02310 | 1879 | Lightning Protection | 21900 | 10950 | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1880 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-02145 | 1881 | Mechanical Terminations(Dampers, Heaters, Motors) | 66600 | 19980 | 0 | 0 | 0 | 15540 | 15540 | 15540 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGW-E-01015 | 1882 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02155 | 1883 | Switches and Receptacles | 10950 | 1642.5 | 0 | 0 | 0 | 3102.5 | 3102.5 | 3102.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02515 | 1884 | Switchgear & Panelboard Energization | 19163 | 0 | 0 | 0 | 0 | 6387.6667 | 6387.6667 | 6387.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02260 | 1885 | Switchgear & Panelboard Installation | 229950 | 218452.5 | 9855 | 1642.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02260 | 1886 | Switchgear & Panelboard Terminations | 19163 | 0 | 16425.4286 | 0 | 0 | 912.5238 | 912.5238 | 912.5238 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02510 | 1887 | Switchgear & Panelboard Testing | 19425 | 0 | 0 | 0 | 0 | 6475 | 6475 | 6475 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02005 | 1888 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02115 | 1889 | Fire Alarm Conduit | 27375 | 24637.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02365 | 1890 | Fire Alarm Wiring | 24638 | 2463.8 | 0 | 0 | 0 | 7391.4 | 7391.4 | 7391.4 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-01380 | 1891 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG9-02365 | 1892 | Fire Alarm Devices | 36135 | 18067.5 | 0 | 0 | 0 | 6022.5 | 6022.5 | 6022.5 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02365 | 1893 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-02535 | 1894 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG9-01005 | 1895 | EXCAVATION NEW BLDGS - OG-9 | 70840 | 70840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01055 | 1896 | BACKFILL NEW BLDGS - OG-9 | 37706 | 37706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01005 | 1897 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-9 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01005 | 1898 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-9 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG9-01005 | 1899 | STONE FOR FOUNDATION - OG-9 | 7221 | 7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 220 - OG9 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01070 | 1900 | FORMWORK NEW BUILDING - OG-10 | 202716 | 202716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01175 | 1901 | SET ANCHOR BOLTS FOR STEEL COLUMNS - OG-10 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1902 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01040 | 1903 | POUR CONCRETE NEW BUILDINGS - OG-10 | 123339 | 123339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01135 | 1904 | FINISH SLABS - OG-10 | 13020 | 13020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01075 | 1905 | Footing/Pier | 49491 | 49491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01075 | 1906 | Grade Beams | 10811 | 10811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01170 | 1907 | Floor Slabs | 22032 | 22032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01130 | 1908 | First Floor Plumbing Shaft Slab | 1848 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01130 | 1909 | Second Floor Plumbing Shaft Slab | 792 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01035 | 1910 | Plumbing Shafts | 25269 | 25269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01205 | 1911 | WWM-Slabs | 4869 | 4869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 221 - OG10 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1912 | 8" CMU (3 hour rated) | 112024 | 112024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1913 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01230 | 1914 | 6" CMU (2 hour rated) | 140624 | 140624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01275 | 1915 | 4" CMU | 39688 | 39688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01275 | 1916 | Face Brick 3-5/8" | 93486 | 93486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1917 | 3-1/8" Rigid insulation | 7901 | 7901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01250 | 1918 | Cast Stone with SS letters | 6487 | 3243.5 | 0 | 1081.1667 | 1081.1667 | 1081.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1919 | Steel Channel | 24097 | 24097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01230 | 1920 | Cont. Shelf angle | 12731 | 12731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1921 | STEEL (MATERIAL ONLY) | 102320 | 102320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1922 | FABRICATION COSTS | 226149 | 226149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1923 | METAL DECK (BUY-OUT) | 11629 | 11629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1924 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01105 | 1925 | ANCHORS & EMBEDS | 6978 | 6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1926 | SURVEYING | 9884 | 9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1927 | STEEL & DECK ERECTION | 348817 | 348817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1928 | BOLTS AND HARDWARE | 6978 | 6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01105 | 1929 | TRUCKING | 6978 | 6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01270 | 1930 | Dunnage Grating Galvanized | 19967 | 19967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01270 | 1931 | Dunnage Stair with Guard Railing | 21932 | 21932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01290 | 1932 | Stair B: First Floor to Roof Stair and Landing with Hand & Guard Rail | 123974 | 123974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01295 | 1933 | Ship Ladder First Floor to Second Floor with Cage and Upper Platform | 16760 | 16760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01295 | 1934 | Ship Ladder Bulkhead | 7035 | 7035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1935 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01305 | 1936 | Layout | 6292 | 6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1937 | Loading | 17370 | 17370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1938 | Exterior Framing, Insulation & Drywall - Materials | 57656 | 57656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1939 | Exterior Framing- Labor | 84514 | 84514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01125 | 1940 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - OG-10 | 12749 | 12749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-02400 | 1941 | PENETRATION FIRESTOPPING NEW BLDG - OG-10 | 11505 | 0 | 0 | 0 | 8628.75 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG6-01320 | 1942 | JOINT SEALANTS NEW BLDGS - OG-10 | 11505 | 0 | 0 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01230 | 1943 | Air Film | 6584 | 6584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01305 | 1944 | Insulation- Labor | 4740 | 4740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01027 | 1945 | Crystalline Waterproofing at plumbing shaft | 4888 | 4888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1946 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01072 | 1947 | Waterproofing at foundation walls | 49565 | 49565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1948 | Layout | 89238 | 89238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1949 | Framing | 202902 | 202902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1950 | Insulation | 36341 | 36341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01255 | 1951 | Cladding Install | 254386 | 241666.7 | 4239.7667 | 4239.7667 | 4239.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01225 | 1952 | Fireproofing | 37400 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01265 | 1953 | P&I Cold Applied Roof Membrane | 48805 | 48805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01265 | 1954 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 59708 | 59708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01265 | 1955 | P&I Aluminum Coping | 6138 | 0 | 0 | 6138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01260 | 1956 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - OG-10 | 8216 | 2875.6 | 0 | 0 | 0 | 2670.2 | 2670.2 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-01380 | 1957 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 023 - SG2 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01245 | 1958 | Doors, Frames & Hardware - Labor | 18906 | 16906 | 1333.3333 | 0 | 666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01317 | 1959 | Louvers Install | 63452 | 0 | 31726 | 31726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 1960 | Furnish Doors | 25086 | 2508.6 | 0 | 0 | 0 | 11288.7 | 11288.7 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01305 | 1961 | Sheathing & Drywall - Labor | 36519 | 36519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01245 | 1962 | Tape/ Spackle finishes | 14144 | 14144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01315 | 1963 | ACT ceilings - Materials | 3086 | 0 | 0 | 0 | 3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01315 | 1964 | ACT ceilings - Labor | 14915 | 0 | 0 | 14915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01280 | 1965 | Direct Applied Stucco | 41559 | 0 | 21559 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01325 | 1966 | Painting OG-10 | 110000 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01310 | 1967 | Cermic Tile and Base - OG-10 | 4636 | 0 | 0 | 4636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 1968 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 0 | 0 | 1134.0833 | 1134.0833 | 1134.0833 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-01260 | 1969 | TOILET ACCESSORIES NEW BLDGS - OG-10 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1970 | Stair Identification Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1971 | Stairway Floor number and ID Sign | 1650 | 0 | 0 | 0 | 0 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1972 | Room Sign | 2750 | 0 | 0 | 0 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01330 | 1973 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 228 - OG10 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1974 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 4658.4 | 258.8 | 258.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1975 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5016 | 88 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1976 | ESCUTCHEONS FOR PLUMBING PIPING | 2200 | 2134 | 27.5 | 27.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1977 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 18920 | 17974 | 236.5 | 236.5 | 236.5 | 236.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1978 | HANGERS AND SUPPORTS | 21930 | 21272.1 | 657.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 1979 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1100 | 770 | 0 | 0 | 110 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-03105 | 1980 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2739 | 2465.1 | 0 | 0 | 0 | 0 | 182.6 | 91.3 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1981 | DOMESTIC WATER PIPING | 219912 | 208916.4 | 10995.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1982 | DOMESTIC WATER PIPING SPECIALTIES | 30184 | 28674.8 | 1509.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1983 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 78375 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1984 | SANITARY WASTE PIPING | 131989 | 129349.22 | 879.9267 | 879.9267 | 879.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1985 | SANITARY WASTE PIPING SPECIALTIES | 20064 | 20064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1986 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03140 | 1987 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 5401.44 | 4092 | 4092 | 2782.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03140 | 1988 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 4012.8 | 4012.8 | 4012.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1989 | GAS SERVICE AND PIPING | 244728 | 232491.6 | 6118.2 | 6118.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 1990 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 548 | 0 | 0 | 182.6667 | 182.6667 | 182.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-03140 | 1991 | PLUMBING FIXTURES | 18392 | 1839.2 | 5517.6 | 5517.6 | 5517.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1992 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 31900 | 31900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03105 | 1993 | Plumbing Pipe Insulation | 2317 | 0 | 0 | 0 | 1158.5 | 1158.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02145 | 1994 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGE-M-01005 | 1995 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 1996 | Exhaust Fans: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03410 | 1997 | Exhaust Fans: Install | 17325 | 17325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1998 | Electric Unit Heaters: Furnish | 3850 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 1999 | Steam Unit Heater: Furnish | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2000 | Steam Unit Heater: Install | 37400 | 28050 | 9350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2001 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2860 | 1430 | 0 | 0 | 476.6667 | 476.6667 | 476.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2002 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2003 | Condensate Return Unit: Install | 24200 | 12100 | 6050 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2004 | Steam Traps: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03142 | 2005 | Steam Traps: Install | 11550 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03107 | 2006 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 135795 | 135795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03107 | 2007 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 154000 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03007 | 2008 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 82500 | 74250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03135 | 2009 | Mechanical Pipe: Hydrostatic Testing | 1705 | 0 | 852.5 | 852.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03107 | 2010 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 2011 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2012 | HANGERS AND SUPPORTS | 11509 | 9782.65 | 0 | 0 | 575.45 | 575.45 | 575.45 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-03145 | 2013 | HVAC Ductwork: Testing & Balancing | 1650 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2014 | Controls: Furnish and Install: Devices | 99000 | 49500 | 0 | 0 | 16500 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2015 | Controls: Furnish and Install: Controls Conduit | 38500 | 23100 | 0 | 0 | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2016 | Controls: Furnish and Install: Controls Wiring | 11000 | 0 | 0 | 0 | 3218.2432 | 3693.9189 | 4087.8378 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 2017 | Controls: Connect to Final Termination Points | 7700 | 0 | 0 | 0 | 2252.7703 | 2585.7432 | 2861.4865 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-03135 | 2018 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 1930.9459 | 2216.3514 | 2452.7027 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 2019 | Insulation: Furnish and Install: Ductwork Insulation | 12100 | 0 | 0 | 0 | 2420 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 2020 | Insulation: Furnish and Install: Piping Insulation | 24200 | 0 | 0 | 0 | 4840 | 19360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 2021 | Insulation: Furnish and Install: Equipment Insulation | 12100 | 0 | 0 | 0 | 2420 | 9680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02335 | 2022 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2023 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02335 | 2024 | ATS Installation | 153300 | 145635 | 0 | 0 | 0 | 7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02335 | 2025 | ATS Terminations | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02335 | 2026 | ATS Testing | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02125 | 2027 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 37500 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02395 | 2028 | Cabling - Risers & Feeders (2/0 & Larger) | 295650 | 0 | 0 | 0 | 73912.5 | 73912.5 | 73912.5 | 73912.5 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02115 | 2029 | Conduit - Branch Circuits (1 1/2" & Smaller) | 82125 | 73912.5 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02105 | 2030 | Conduit - In-Slab | 126473 | 126473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02110 | 2031 | Conduit - Risers (2" & Larger) | 315360 | 299592 | 0 | 0 | 0 | 5256 | 5256 | 5256 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02400 | 2032 | Firestopping | 5250 | 3937.5 | 0 | 0 | 984.375 | 109.375 | 109.375 | 109.375 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-OG10-01145 | 2033 | Generator Delivery | 52500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2034 | DOMESTIC WATER PIPING | 115682 | 98329.7 | 0 | 0 | 5784.1 | 5784.1 | 5784.1 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
P-OG10-01010 | 2035 | Generator Release | 315000 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02315 | 2036 | Generator Terminations | 52500 | 0 | 0 | 0 | 0 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02535 | 2037 | Generator Test | 52500 | 26250 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02160 | 2038 | Lighting Controls | 21000 | 10500 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02135 | 2039 | Lighting Install | 56700 | 42525 | 0 | 0 | 0 | 4725 | 4725 | 4725 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02240 | 2040 | Lighting Rough | 59940 | 53946 | 2997 | 2997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02160 | 2041 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02325 | 2042 | Lightning Protection | 21900 | 10950 | 4106.25 | 0 | 0 | 2281.25 | 2281.25 | 2281.25 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02140 | 2043 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 19053 | 0 | 0 | 0 | 14819 | 14819 | 14819 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-OGE-01020 | 2044 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2045 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 13838 | 0 | 0 | 814 | 814 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02155 | 2046 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02525 | 2047 | Switchgear & Panelboard Energization | 19163 | 0 | 0 | 0 | 0 | 6387.6667 | 6387.6667 | 6387.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02405 | 2048 | Switchgear & Panelboard Installation | 229950 | 218451.5 | 0 | 0 | 6570.5714 | 4927.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02405 | 2049 | Switchgear & Panelboard Terminations | 19163 | 0 | 0 | 0 | 10950.2857 | 2737.5714 | 2737.5714 | 2737.5714 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02520 | 2050 | Switchgear & Panelboard Testing | 19163 | 0 | 0 | 0 | 0 | 6387.6667 | 6387.6667 | 6387.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02005 | 2051 | Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02115 | 2052 | Fire Alarm Conduit | 32850 | 26280 | 0 | 0 | 0 | 2190 | 2190 | 2190 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02385 | 2053 | Fire Alarm Wiring | 32850 | 0 | 0 | 0 | 0 | 10950 | 10950 | 10950 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02385 | 2054 | Fire Alarm Devices | 50370 | 25185 | 0 | 0 | 0 | 8395 | 8395 | 8395 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-02385 | 2055 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG2-03005 | 2056 | SANITARY WASTE PIPING | 135432 | 121888.8 | 0 | 0 | 4514.4 | 4514.4 | 4514.4 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG10-02540 | 2057 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
OG10-01020 | 2058 | EXCAVATION NEW BLDGS - OG-10 | 80696 | 80696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01055 | 2059 | BACKFILL NEW BLDGS - OG-10 | 39801 | 39801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2060 | DEWATERING COVERAGE FOR NEW BUILDINGS - OG-10 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2061 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - OG-10 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2062 | DRIVE PILES AND INSTALL LAGGING FOR SOE - OG-10 | 34172 | 34172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OG10-01020 | 2063 | STONE FOR FOUNDATION - OG-10 | 7221 | 7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 233 - OG10 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
OGE-01035 | 2064 | EROSION CONTROL FABRIC - OGE | 184400 | 184400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01035 | 2065 | INLET PROTECTION - OGE | 38875 | 38875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01035 | 2066 | SILT FENCE - OGE | 19290 | 19290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2067 | SANITARY WASTE PIPING SPECIALTIES | 19388 | 18418.6 | 0 | 0 | 323.1333 | 323.1333 | 323.1333 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01035 | 2068 | STABILIZED CONSTRUCTION ENTRANCE - OGE | 47400 | 47400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01035 | 2069 | MANTAIN EROSION CONTROL - OGE | 42735 | 42735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01770 | 2070 | REMOVE EROSION CONTROL - OGE | 29979 | 4496.85 | 0 | 0 | 0 | 8494.05 | 8494.05 | 8494.05 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2071 | REMOVE FENCE - OGE | 23930 | 23930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2072 | REMOVE FULL DEPTH ASPHALT PVMT - OGE | 141750 | 141750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01060 | 2073 | REMOVE SITE FURNISHING - OGE | 98825 | 98825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2074 | REMOVE CONCRETE CURB & STEPS - OGE | 69775 | 69775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01000 | 2075 | REMOVE PVMTS - OGE | 202600 | 202600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 234 - OGE - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01610 | 2076 | FORMWORK SITE CONCRETE - OGE | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2077 | CONCRETE FOOTING FOR SITE FURNISHING - OGE | 3304 | 0 | 0 | 0 | 1101.3333 | 1101.3333 | 1101.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2078 | STORM DRAINAGE PIPING SPECIALTIES | 33000 | 13200 | 0 | 0 | 6600 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
260543-01025 | 2079 | CONCRETE DUCTBANKS - OGE | 56347 | 56347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01520 | 2080 | CONCRETE SITE RETAINING WALL AND FOOTINGS - OGE | 33106 | 33106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 235 - OGE - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-02010 | 2081 | Manhole Work | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02215 | 2082 | Site Lighting - Cable | 68438 | 0 | 0 | 0 | 0 | 0 | 22812.6667 | 22812.6667 | 22812.6667 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02210 | 2083 | Site Lighting - Conduit | 87600 | 65700 | 3128.5714 | 3128.5714 | 3128.5714 | 4171.4286 | 4171.4286 | 4171.4286 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02220 | 2084 | Site Lighting - Fixtures | 108296 | 0 | 0 | 0 | 0 | 0 | 36098.6667 | 36098.6667 | 36098.6667 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-OGE-01020 | 2085 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-02115 | 2086 | Underground Electric Service - Cable | 1040250 | 676162.5 | 0 | 0 | 121362.5 | 121362.5 | 121362.5 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGE-01155 | 2087 | Underground Electric Service - Conduit | 821250 | 821250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGP1-01020 | 2088 | TREE PROTECTION - OGE | 14532 | 14532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03030 | 2089 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 186998 | 158948.3 | 0 | 0 | 9349.9 | 9349.9 | 9349.9 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGP1-01020 | 2090 | HAND EXCAVATION AS NEEDED - OGE | 36868 | 36868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2091 | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGE | 4025 | 0 | 0 | 0 | 1341.6667 | 1341.6667 | 1341.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01395 | 2092 | BACKFILL - OGE | 222505 | 222505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01709 | 2093 | EXCAVATE FOR ASPHALT PAVEMENTS - OGE | 21187 | 0 | 0 | 0 | 7062.3333 | 7062.3333 | 7062.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2094 | BACKFILL FOR ASPHALT PAVEMENTS - OGE | 9846 | 0 | 0 | 0 | 3282 | 3282 | 3282 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2095 | SITE FURNISHINGS - OGE | 46594 | 0 | 0 | 0 | 15531.3333 | 15531.3333 | 15531.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGP1-01750 | 2096 | DRINKING FOUNTAIN - OGE | 8030 | 0 | 0 | 0 | 2676.6667 | 2676.6667 | 2676.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01090 | 2097 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01090 | 2098 | Furnish and Install Deep Wells | 157500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01090 | 2099 | Furnish and Install Pumps and Piping | 128400 | 128400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2100 | GAS SERVICE AND PIPING | 2112 | 0 | 0 | 0 | 704 | 704 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01090 | 2101 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01090 | 2102 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01090 | 2103 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 237 - OGE - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01740 | 2104 | 4' Chain Link Fence | 23650 | 0 | 0 | 0 | 0 | 0 | 22073.3333 | 1576.6667 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01745 | 2105 | 10' Chain Link Fence | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 24750 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01005 | 2106 | 8' High Temporary Fence | 242250 | 242250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01745 | 2107 | Ametco Fence | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68475 | 68475 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGE-01710 | 2108 | 4" CONCRETE | 49500 | 24750 | 0 | 0 | 0 | 22982.1429 | 1767.8571 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01710 | 2109 | 5"POROUS CONCRETE | 551320 | 220528 | 0 | 0 | 110264 | 110264 | 110264 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01730 | 2110 | 5" COLOR CONCRETE | 38500 | 36575 | 0 | 641.6667 | 641.6667 | 641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2111 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01705 | 2112 | CONCRETE CURB | 38500 | 23100 | 0 | 0 | 14666.6667 | 733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01705 | 2113 | SFC -STELL FACING CURB | 4400 | 0 | 0 | 0 | 4190.4762 | 209.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01710 | 2114 | CONCRETE STEPS | 36960 | 27720 | 0 | 0 | 0 | 8580 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2115 | Asphalt Parking | 291050 | 0 | 0 | 0 | 0 | 270260.7143 | 20789.2857 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2116 | Pavement Marking for Parking | 4641 | 0 | 0 | 0 | 0 | 4309.5 | 331.5 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2117 | Pavement Marking for Basketball Court | 6195 | 0 | 0 | 0 | 0 | 5752.5 | 442.5 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01760 | 2118 | Deciduous Trees | 14175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7087.5 | 7087.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01760 | 2119 | Evergreen Trees | 2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417.5 | 1417.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01760 | 2120 | Deciduous Shrubs | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.5 | 220.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01025 | 2121 | Tree Removal | 34914 | 34914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG2-03005 | 2122 | Plumbing Pipe Insulation | 35464 | 31917.6 | 0 | 1773.2 | 1773.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01755 | 2123 | Lawn Seeding (not including topsoil) | 9671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4835.5 | 4835.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01025 | 2124 | Soil Erosion Mat | 6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353.5 | 3353.5 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01755 | 2125 | Topsoil Stockpile/Spread | 67996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33998 | 33998 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01755 | 2126 | Maintenance | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGE-01395 | 2127 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGE | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01380 | 2128 | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGE | 8796 | 8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01380 | 2129 | INSTALL HW, CW PIPE - OGE | 231845 | 231845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
OGP1-01115 | 2130 | TEST HW, CW - OGE | 8794 | 8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01280 | 2131 | INSTALL CONDENSATE AND STEAM PIPE - OGE | 427171 | 427171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
OGE-01285 | 2132 | TEST CONDENSATE, STEAM - OGE | 19421 | 19421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG2-02040 | 2133 | Heat Trace | 5475 | 0 | 0 | 0 | 4380 | 0 | 0 | 0 | 273.75 | 273.75 | 273.75 | 273.75 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGE-01095 | 2134 | DEWATERING COVERAGE FOR UTILITY WORK - OGE | 56118 | 56118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01565 | 2135 | SEWER / DRAINAGE PIPE - OGE | 221493 | 159475.26 | 0 | 0 | 0 | 20672.58 | 20672.58 | 20672.58 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2136 | CATCH BASIN DRAINS AND CONNECTIONS - OGE | 157243 | 113214.96 | 0 | 0 | 0 | 14676.0133 | 14676.0133 | 14676.0133 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2137 | DRAINAGE MANHOLES - OGE | 33988 | 21072.56 | 0 | 0 | 0 | 4305.1467 | 4305.1467 | 4305.1467 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2138 | REMOVE AREA DRAINS - OGE | 58300 | 36146 | 0 | 0 | 0 | 7384.6667 | 7384.6667 | 7384.6667 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01560 | 2139 | ELECTRICAL MANHOLES - OGE | 12725 | 12725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01205 | 2140 | ELECTRICAL CONDUIT TRENCHES - OGE | 91065 | 91065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 2141 | Equipment SUPPORT FOR SITE - OGE | 167754 | 167754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01035 | 2142 | EROSION CONTROL FABRIC - OGW | 12350 | 12350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01035 | 2143 | INLET PROTECTION - OGW | 34210 | 34210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SURV-SGS-M-01005 | 2144 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01035 | 2145 | SILT FENCE - OGW | 26085 | 26085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01035 | 2146 | STABILIZED CONSTRUCTION ENTRANCE - OGW | 48150 | 48150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01035 | 2147 | MANTAIN EROSION CONTROL - OGW | 42735 | 25641 | 0 | 0 | 0 | 0 | 5698 | 5698 | 5698 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGE-01770 | 2148 | REMOVE EROSION CONTROL - OGW | 29979 | 4496.85 | 0 | 0 | 0 | 0 | 8494.05 | 8494.05 | 8494.05 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2149 | REMOVE FENCE - OGW | 6800 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2150 | REMOVE FULL DEPTH ASPHALT PVMT - OGW | 157695 | 157695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01060 | 2151 | REMOVE SITE FURNISHING - OGW | 116200 | 116200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2152 | REMOVE CONCRETE CURB & STEPS - OGW | 98525 | 98525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01000 | 2153 | REMOVE PVMTS - OGW | 209575 | 209575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 240 - OGW - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01610 | 2154 | FORMWORK SITE CONCRETE - OGW | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OG1-03112 | 2155 | Exhaust Fans: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01750 | 2156 | CONCRETE FOOTING FOR SITE FURNISHING - OGW | 5286 | 0 | 0 | 0 | 0 | 0 | 0 | 2643 | 2643 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 2157 | CONCRETE DUCTBANKS - OGW | 61956 | 61956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01610 | 2158 | CONCRETE SITE RETAINING WALL AND FOOTINGS OGW | 31529 | 31529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 241 - OGW - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2159 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - OGW | 24647 | 0 | 0 | 0 | 0 | 0 | 0 | 12323.5 | 12323.5 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2160 | Jet Spray | 88000 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2161 | Crackle Corn | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2162 | 2-5 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2163 | 5-12 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2164 | Aquavator | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01735 | 2165 | Install Water Play Equipment and Piping | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 27500 | 0 | 0 | 0 | 0 | OGW | 242 - OGW - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03112 | 2166 | Exhaust Fans: Install | 4565 | 0 | 0 | 4565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-02010 | 2167 | Manhole Installation | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-02215 | 2168 | Site Lighting - Cable | 82125 | 0 | 0 | 0 | 0 | 0 | 27375 | 27375 | 27375 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-02210 | 2169 | Site Lighting - Conduit | 76650 | 68985 | 1642.5 | 1642.5 | 1642.5 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OG5-02250 | 2170 | Site Lighting - Fixtures | 85629 | 0 | 0 | 0 | 0 | 0 | 28543 | 28543 | 28543 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
SURV-OGW-E-01015 | 2171 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-02115 | 2172 | Underground Electric Service - Cable | 1095000 | 821250 | 156428.5714 | 117321.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-01155 | 2173 | Underground Electric Service - Conduit | 903375 | 903375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | SITE | Utilities | Site Utilities | 0
OGW-01020 | 2174 | TREE PROTECTION - OGW | 24912 | 24912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01020 | 2175 | HAND EXCAVATION AS NEEDED - OGW | 86903 | 81903 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2176 | EXCAVATION FOR SITE FURNISHING FOOTINGS - OGW | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 2012.5 | 2012.5 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OG1-03032 | 2177 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01315 | 2178 | BACKFILL - OGW | 196176 | 176558.4 | 0 | 0 | 0 | 6539.2 | 6539.2 | 6539.2 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01709 | 2179 | EXCAVATE FOR ASPHALT PAVEMENTS - OGW | 21187 | 0 | 0 | 0 | 7062.3333 | 7062.3333 | 7062.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01709 | 2180 | BACKFILL FOR ASPHALT PAVEMENTS - OGW | 4190 | 0 | 0 | 0 | 1396.6667 | 1396.6667 | 1396.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2181 | SITE FURNISHINGS - OGW | 31684 | 3168.4 | 0 | 0 | 0 | 9505.2 | 9505.2 | 9505.2 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2182 | DRINKING FOUNTAIN - OGW | 8030 | 0 | 0 | 0 | 0 | 0 | 0 | 4015 | 4015 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01750 | 2183 | LANDSCAPE BOULDERS - OGW | 277962 | 222369.6 | 0 | 0 | 0 | 18530.8 | 18530.8 | 18530.8 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01090 | 2184 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01090 | 2185 | Furnish and Install Deep Wells | 123750 | 123750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01090 | 2186 | Furnish and Install Pumps and Piping | 24600 | 24600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
OGW-01090 | 2187 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG2-03032 | 2188 | Steam Unit Heaters: Install | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01090 | 2189 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01090 | 2190 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 244 - OGW - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01740 | 2191 | 4' Chain Link Fence | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01745 | 2192 | 10' Chain Link Fence | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19250 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01005 | 2193 | 8' High Temporary Fence | 316350 | 316350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01745 | 2194 | Ametco Fence | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68475 | 68475 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2195 | 4" CONCRETE | 143000 | 21450 | 0 | 40516.6667 | 40516.6667 | 40516.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2196 | 7" CONCRETE RAMP | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2197 | 5" POROUS CONCRETE | 459030 | 0 | 153010 | 153010 | 153010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01730 | 2198 | 5" COLOR CONCRETE | 39600 | 17820 | 0 | 7260 | 7260 | 7260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OG2-03032 | 2199 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01705 | 2200 | CONCRETE CURB | 39600 | 15840 | 0 | 7920 | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01705 | 2201 | SFC -STELL FACING CURB | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13750 | 13750 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01710 | 2202 | CONCRETE STEPS | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
OGW-01709 | 2203 | Asphalt Parking | 129675 | 0 | 0 | 0 | 0 | 0 | 129675 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGE-01709 | 2204 | Pavement Marking for Parking | 2730 | 0 | 0 | 0 | 0 | 2535 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2205 | Deciduous Trees | 9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4607 | 4607 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2206 | Deciduous Shrubs | 2793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396.5 | 1396.5 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2207 | Evergreen Shrubs | 3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843 | 1843 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01760 | 2208 | Perennials | 8180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4090 | 4090 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2209 | Grasses | 16160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8080 | 8080 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
SG2-03032 | 2210 | Condensate Return Unit: Install | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OGW-01025 | 2211 | Tree Removal | 39351 | 39351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2212 | Lawn Seeding (not including topsoil) | 9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4796.5 | 4796.5 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01025 | 2213 | Soil Erosion Mat | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504 | 504 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2214 | Topsoil Stockpile/Spread | 67725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33862.5 | 33862.5 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01755 | 2215 | Maintenance | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OGW-01315 | 2216 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - OGW | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01355 | 2217 | TERMINATE AND DEMOLISH EXISTING UTILITIES - OGW | 20278 | 17236.3 | 0 | 0 | 0 | 0 | 1013.9 | 1013.9 | 1013.9 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGS-01355 | 2218 | INSTALL HW, CW PIPE - OGW | 452669 | 452669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
OGW-01115 | 2219 | TEST HW, CW - OGW | 21983 | 21983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01280 | 2220 | INSTALL CONDENSATE AND STEAM PIPE - OGW | 622421 | 609972.58 | 0 | 0 | 12448.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SG2-03112 | 2221 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01305 | 2222 | TEST CONDENSATE, STEAM - OGW | 32367 | 32367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGW-01095 | 2223 | DEWATERING COVERAGE FOR UTILITY WORK - OGW | 56118 | 56118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01565 | 2224 | SEWER / DRAINAGE PIPE - OGW | 187235 | 140426.25 | 46808.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01560 | 2225 | CATCH BASIN DRAINS AND CONNECTIONS - OGW | 131036 | 98277 | 0 | 0 | 0 | 10919.6667 | 10919.6667 | 10919.6667 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGP1-01560 | 2226 | REMOVE AREA DRAINS - OGW | 46640 | 46640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01205 | 2227 | ELECTRICAL CONDUIT TRENCHES - OGW | 77232 | 77232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 2228 | Equipment SUPPORT FOR SITE - OGW | 167754 | 167754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01035 | 2229 | INLET PROTECTION - S8 | 21770 | 21770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01035 | 2230 | SILT FENCE - S8 | 14520 | 14520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01035 | 2231 | STABILIZED CONSTRUCTION ENTRANCE - S8 | 45660 | 45660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03112 | 2232 | Heating and Ventilation Unit: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01035 | 2233 | EROSION CONTROL FABRIC - S8 | 31260 | 31260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01035 | 2234 | MANTAIN EROSION CONTROL - S8 | 42735 | 29914.5 | 0 | 0 | 4273.5 | 4273.5 | 4273.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01770 | 2235 | REMOVE EROSION CONTROL - S8 | 29979 | 2997.9 | 0 | 0 | 8993.7 | 8993.7 | 8993.7 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2236 | REMOVE FENCE - S8 | 10510 | 10510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2237 | REMOVE FULL DEPTH ASPHALT PVMT - S8 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01060 | 2238 | REMOVE SITE FURNISHING -S8 | 120545 | 120545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2239 | REMOVE CONCRETE CURB & STEPS - S8 | 15600 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01000 | 2240 | REMOVE PVMTS - S8 | 115615 | 115615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01005 | 2241 | Gaskets | 101250 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 20250 | 20250 | 20250 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01010 | 2242 | Wire Insulation | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG2-03015 | 2243 | Steam Traps: Furnish | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01015 | 2244 | Assumed Flooring Material (Slab Penetrations) | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 2160 | 2160 | 2160 | 2160 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01015 | 2245 | Vinyl Membrane and Mastic | 72114 | 0 | 0 | 0 | 0 | 0 | 0 | 14422.8 | 14422.8 | 14422.8 | 14422.8 | 14422.8 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01015 | 2246 | Caulk | 184500 | 51750 | 0 | 0 | 0 | 0 | 0 | 26550 | 26550 | 26550 | 26550 | 26550 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01015 | 2247 | Fibrous Slate | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 5100 | 5100 | 5100 | 5100 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01020 | 2248 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 1988.4 | 1988.4 | 1988.4 | 1988.4 | 1988.4 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01020 | 2249 | Underground Utility Materials | 4680 | 0 | 0 | 0 | 0 | 0 | 0 | 936 | 936 | 936 | 936 | 936 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
S8E-01105 | 2250 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01220 | 2251 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2252 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 0 | 5000 | 5000 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2253 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 | 5000 | 5000 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03015 | 2254 | Steam Traps: Install | 12100 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01115 | 2255 | Remove Areaway slab and drain - cellar | 60000 | 21000 | 0 | 0 | 13000 | 13000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01115 | 2256 | Remove Areaway grate - cellar | 20000 | 10000 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01115 | 2257 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2258 | Remove existing portion wall - 1st floor | 60000 | 0 | 15000 | 15000 | 15000 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01210 | 2259 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 0 | 10000 | 10000 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01105 | 2260 | Remove window sill - 1st floor | 10000 | 0 | 2500 | 2500 | 2500 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 247 - S8 - Division 2 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SGS-01610 | 2261 | FORMWORK SITE CONCRETE - S8 | 55661 | 55661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 248 - S8 - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2262 | CONCRETE FOOTING FOR SITE FURNISHING - S8 | 5947 | 0 | 1486.75 | 1486.75 | 1486.75 | 743.375 | 743.375 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 248 - S8 - Division 3 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
260543-01025 | 2263 | CONCRETE DUCTBANKS - S8 | 38245 | 38245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 248 - S8 - Division 3 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8A-01250 | 2264 | Cast Stone with SS letters | 6870 | 0 | 6870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 249 - S8 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
OG1-03032 | 2265 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01270 | 2266 | Dunnage Grating Galvanized | 20173 | 20173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01270 | 2267 | Dunnage Stair and Guard Rail at 1 Location | 13035 | 0 | 0 | 0 | 13035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01290 | 2268 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 124892 | 112402.8 | 12489.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01295 | 2269 | Ship Ladder with Cage and Platform | 25450 | 0 | 12725 | 12725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01295 | 2270 | Bulkhead Roof Access Ship Ladder at 2 Locations | 15311 | 0 | 7655.5 | 7655.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
S8E-01860 | 2271 | Temporary Aluminum Over Pass Stair | 114392 | 0 | 0 | 0 | 0 | 0 | 114392 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 250 - S8 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
08080 | 2272 | Overhead Door | 16000 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 251 - S8 - Division 8 | 0% | Loading Dock | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01325 | 2273 | Painting S8-2 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 35000 | 0 | 0 | 0 | 0 | S82 | 252 - S8 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
S8E-01865 | 2274 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2275 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03032 | 2276 | Vacuum Pump Unit: Install | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01865 | 2277 | Room Sign | 2200 | 0 | 0 | 0 | 0 | 0 | 733.3333 | 733.3333 | 733.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2278 | Exit Sign | 550 | 0 | 0 | 0 | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2279 | Stairway Flood Access Door | 550 | 0 | 0 | 0 | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2280 | Temporary Egress Stair Storage Sign | 1320 | 0 | 0 | 0 | 0 | 0 | 440 | 440 | 440 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01865 | 2281 | Address Signs | 3850 | 0 | 0 | 0 | 0 | 0 | 1283.3333 | 1283.3333 | 1283.3333 | 0 | 0 | 0 | 0 | S8 | 253 - S8 - Division 10 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2282 | EXCAVATE & POUR CONCRETE FOOTINGS FOR PLAY EQUIPMENT - S8 | 36970 | 0 | 9242.5 | 9242.5 | 9242.5 | 4621.25 | 4621.25 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2283 | Arch Jet | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2284 | Mist Spray | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2285 | 2-5 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2286 | 5-12 year play equipment | 88000 | 44000 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03107 | 2287 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 91850 | 91850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01735 | 2288 | Aquavator | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2289 | Splash Pad | 22000 | 11000 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01735 | 2290 | Install Water Play Equipment and Piping | 55000 | 27500 | 0 | 0 | 0 | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 254 - S8 - Division 11 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8E-01380 | 2291 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2292 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2293 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2294 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2295 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2296 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2297 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-03007 | 2298 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 122100 | 122100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2299 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2300 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2301 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2302 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2303 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2304 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2305 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2306 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2307 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2308 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-03007 | 2309 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 45100 | 45100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2310 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2311 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01380 | 2312 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 255 - S8 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2313 | Plumbing Pipe Insulation | 53797 | 0 | 0 | 0 | 26898.5 | 26898.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 256 - S8 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01020 | 2314 | TREE PROTECTION - S8 | 4844 | 4117.4 | 0 | 0 | 0 | 363.3 | 363.3 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01020 | 2315 | HAND EXCAVATION AS NEEDED - S8 | 52668 | 44767.8 | 0 | 0 | 0 | 3950.1 | 3950.1 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2316 | EXCAVATION FOR SITE FURNISHING FOOTINGS - S8 | 4025 | 0 | 1006.25 | 1006.25 | 1006.25 | 503.125 | 503.125 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01675 | 2317 | BACKFILL - S8 | 141886 | 70943 | 0 | 70943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01709 | 2318 | EXCAVATE FOR ASPHALT PAVEMENTS - S8 | 7063 | 0 | 0 | 0 | 0 | 3531.5 | 3531.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01709 | 2319 | BACKFILL FOR ASPHALT PAVEMENTS - S8 | 4190 | 0 | 0 | 0 | 0 | 2095 | 2095 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
SG2-03025 | 2320 | Mechanical Pipe: Hydrostatic Testing | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01750 | 2321 | SITE FURNISHINGS - S8 | 27956 | 0 | 6989 | 6989 | 6989 | 3494.5 | 3494.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01750 | 2322 | DRINKING FOUNTAIN - S8 | 8030 | 0 | 2007.5 | 2007.5 | 2007.5 | 1003.75 | 1003.75 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01090 | 2323 | Dewatering Permits | 15178 | 15178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01090 | 2324 | Furnish and Install Deep Wells | 67500 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01090 | 2325 | Furnish and Install Pumps and Piping | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Restoration | Site Restoration | 0
S8-01090 | 2326 | Power for Dewatering | 109091 | 109091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01090 | 2327 | Installation Support | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01090 | 2328 | Dewatering expenses | 218182 | 218182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 257 - S8 - Division 31 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01740 | 2329 | 4' High Steel Bar Fence | 87450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87450 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
S8-01005 | 2330 | 8' High Temporary Fence | 138225 | 138225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ATLAS | SITE | Restoration | Site Restoration | 0
OG1-03007 | 2331 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9900 | 9702 | 0 | 0 | 190.3846 | 0 | 0 | 7.6154 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01710 | 2332 | 4" CONCRETE | 38500 | 0 | 0 | 0 | 0 | 0 | 19250 | 19250 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01710 | 2333 | 5"POROUS CONCRETE | 148940 | 0 | 0 | 0 | 0 | 0 | 74470 | 74470 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01730 | 2334 | 5" COLOR CONCRETE | 121000 | 0 | 0 | 0 | 0 | 0 | 60500 | 60500 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01705 | 2335 | CONCRETE CURB | 38500 | 0 | 0 | 0 | 0 | 0 | 19250 | 19250 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01705 | 2336 | SFC -STELL FACING CURB | 8800 | 0 | 0 | 0 | 0 | 0 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01710 | 2337 | CONCRETE STEPS | 9240 | 0 | 0 | 0 | 0 | 0 | 4620 | 4620 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | SITE | Restoration | Site Restoration | 0
S8-01709 | 2338 | Asphalt Parking | 43544 | 0 | 0 | 0 | 0 | 0 | 43544 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | CITYWIDE | SITE | Restoration | Site Restoration | 0
S8-01760 | 2339 | Deciduous Trees | 11340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5670 | 5670 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01760 | 2340 | Evergreen Trees | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063.5 | 1063.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01760 | 2341 | Deciduous Shrubs | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441 | 441 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
OG1-03110 | 2342 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 17248 | 0 | 0 | 338.4615 | 0 | 0 | 13.5385 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01760 | 2343 | Evergreen Shrubs | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709 | 709 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01760 | 2344 | Perennials | 3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 1676 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2345 | Grasses | 6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112.5 | 3112.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01025 | 2346 | Tree Removal | 32700 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16350 | 11350 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2347 | Lawn Seeding (not including topsoil) | 2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310.5 | 1310.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2348 | Topsoil Stockpile/Spread | 18963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9481.5 | 9481.5 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01755 | 2349 | Maintenance | 2659.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329.67 | 1329.67 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | SITE | Restoration | Site Restoration | 0
S8-01675 | 2350 | MAINTAINING AND PROTECTING EXISTING PRIVATELY OWNED UTILITIES - S8 | 16286 | 16286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01135 | 2351 | TERMINATE AND DEMOLISH EXISTING UTILITIES - S8 | 6926 | 5887.1 | 0 | 0 | 346.3 | 346.3 | 346.3 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SGN-01135 | 2352 | INSTALL CONDENSATE AND STEAM PIPE - S8 | 55999 | 0 | 0 | 0 | 25845.6943 | 30153.3057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | WELKIN | SITE | Utilities | Site Utilities | 0
SG2-03135 | 2353 | HVAC Ductwork: Testing & Balancing | 1100 | 0 | 0 | 0 | 21.1538 | 0 | 0 | 1078.8462 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01305 | 2354 | TEST CONDENSATE, STEAM - S8 | 6474 | 0 | 1618.5 | 1618.5 | 1618.5 | 809.25 | 809.25 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01095 | 2355 | DEWATERING COVERAGE FOR UTILITY WORK - S8 | 56118 | 53312.1 | 0 | 0 | 935.3 | 935.3 | 935.3 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01655 | 2356 | SEWER / DRAINAGE PIPE - S8 | 126691 | 44341.85 | 41174.575 | 41174.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01560 | 2357 | CATCH BASIN DRAINS AND CONNECTIONS - S8 | 69886 | 34943 | 33354.6818 | 0 | 0 | 794.1591 | 794.1591 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01560 | 2358 | REMOVE AREA DRAINS - S8 | 58300 | 29150 | 27825 | 0 | 0 | 662.5 | 662.5 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01255 | 2359 | ELECTRICAL MANHOLES - S8 | 6363 | 6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8-01255 | 2360 | ELECTRICAL CONDUIT TRENCHES - S8 | 39193 | 39193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
OGE-01010 | 2361 | Equipment SUPPORT FOR SITE - S8 | 167754 | 75489.3 | 0 | 0 | 30754.9 | 30754.9 | 30754.9 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
S8E-01420 | 2362 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - S8 | 143660 | 50281 | 93379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01450 | 2363 | DRILL & GROUT DOWELS - S8 | 20861 | 0 | 0 | 0 | 18253.375 | 1303.8125 | 1303.8125 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 2364 | Controls: Furnish and Install: Devices | 71500 | 67925 | 0 | 0 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01450 | 2365 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - S8 | 60871 | 0 | 0 | 0 | 53262.125 | 3804.4375 | 3804.4375 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01570 | 2366 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - S8 | 117673 | 88254.75 | 0 | 0 | 9806.0833 | 9806.0833 | 9806.0833 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01540 | 2367 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - S8 | 10239 | 2559.75 | 0 | 7679.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01415 | 2368 | Footing/Pier | 38805 | 0 | 12935 | 12935 | 12935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01435 | 2369 | Retaining Walls | 8668 | 0 | 0 | 8001.2308 | 666.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01565 | 2370 | Entrance Slab | 90825 | 0 | 0 | 0 | 0 | 50000 | 40825 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01810 | 2371 | Concrete Shelf | 5785 | 0 | 0 | 4958.5714 | 0 | 826.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01810 | 2372 | Brick Shelf | 29445 | 0 | 0 | 25238.5714 | 0 | 4206.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01350 | 2373 | Boiler Room Concrete Curb | 6508 | 0 | 0 | 0 | 0 | 6508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2374 | GFRP Sikawrap 100 G | 23232 | 0 | 0 | 0 | 7744 | 7744 | 7744 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 260 - S81 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 2375 | Controls: Furnish and Install: Controls Conduit | 33000 | 31350 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-01015 | 2376 | Overhead protection for Masonry | 94478 | 0 | 23619.5 | 23619.5 | 23619.5 | 11809.75 | 11809.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2377 | Face Brick 3-5/8" | 166796 | 0 | 83398 | 83398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2378 | 2" Face Brick | 346786 | 0 | 173393 | 173393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2379 | 8" CMU | 146034 | 29206.8 | 0 | 20000 | 32275.7333 | 32275.7333 | 32275.7333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2380 | 6" CMU (2 hour rated) | 249945 | 0 | 0 | 50000 | 66648.3333 | 66648.3333 | 66648.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2381 | 4" CMU | 109956 | 0 | 54978 | 54978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2382 | 3-1/8" Rigid insulation | 14969 | 0 | 0 | 0 | 4989.6667 | 4989.6667 | 4989.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2383 | 2" Rigid Insulation | 17391 | 0 | 0 | 0 | 5797 | 5797 | 5797 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2384 | Coping stone C1/A-260 | 32747 | 0 | 0 | 0 | 10915.6667 | 10915.6667 | 10915.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2385 | Steel Channel on top | 9460 | 0 | 0 | 0 | 3153.3333 | 3153.3333 | 3153.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
OG1-03120 | 2386 | Controls: Furnish and Install: Controls Wiring | 9900 | 9405 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01230 | 2387 | Cont. Shelf angle | 9680 | 0 | 0 | 0 | 3226.6667 | 3226.6667 | 3226.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01230 | 2388 | Steel Channel on top | 9680 | 0 | 0 | 0 | 3226.6667 | 3226.6667 | 3226.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01105 | 2389 | STEEL (MATERIAL ONLY) | 117614 | 117614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2390 | FABRICATION COSTS | 226674 | 226674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2391 | METAL DECK (BUY-OUT) | 10693 | 10693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2392 | ANCHORS & EMBEDS | 8554 | 8554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2393 | SURVEYING | 6416 | 6416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2394 | STEEL & DECK ERECTION | 433032 | 433032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2395 | BOLTS AND HARDWARE | 9623 | 9623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01105 | 2396 | TRUCKING | 10693 | 10693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2397 | Controls: Connect to Final Termination Points | 6600 | 6270 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02130 | 2398 | PENETRATION FIRESTOPPING EXTG BLDG - S8 | 9611 | 0 | 0 | 0 | 7688.8 | 961.1 | 961.1 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01320 | 2399 | JOINT SEALANTS EXTG BLDGS - S8 | 9611 | 0 | 2402.75 | 2402.75 | 2402.75 | 1201.375 | 1201.375 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01230 | 2400 | Air Film | 17108 | 0 | 0 | 0 | 5702.6667 | 5702.6667 | 5702.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2401 | Bituthene 4000 waterproofing membrane | 27967 | 0 | 0 | 0 | 9322.3333 | 9322.3333 | 9322.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01275 | 2402 | GE Elemax 2600 Silicone air and vapor barrier | 16896 | 0 | 0 | 0 | 5632 | 5632 | 5632 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01370 | 2403 | Crystalline Waterproofing at perimeter walls | 48933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01825 | 2404 | Waterproofing at foundation walls | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 263 - S81 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01255 | 2405 | Layout | 55794 | 0 | 0 | 0 | 0 | 27897 | 27897 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01255 | 2406 | Framing | 116720 | 116720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01255 | 2407 | Insulation | 20905 | 20905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG2-03135 | 2408 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01255 | 2409 | Cladding Install | 146335 | 0 | 0 | 0 | 0 | 73167.5 | 73167.5 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01317 | 2410 | Louvers Install | 36500 | 0 | 0 | 0 | 0 | 18250 | 18250 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 264 - S81 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 2411 | Furnish Doors | 6272 | 0 | 1568 | 1568 | 1568 | 784 | 784 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 265 - S81 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01860 | 2412 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - S8 | 306768 | 153379 | 0 | 0 | 0 | 76694.5 | 76694.5 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 266 - S81 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01860 | 2413 | WINDOW FLOODGATES (8.06 AND 8.14) - S8 | 49836 | 0 | 0 | 0 | 0 | 24918 | 24918 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 266 - S81 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-03005 | 2414 | COMMON WORK RESULTS FOR PLUMBING | 15371 | 8454.05 | 0 | 0 | 2305.65 | 2305.65 | 2305.65 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2415 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 6000 | 4500 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2416 | ESCUTCHEONS FOR PLUMBING PIPING | 2500 | 750 | 0 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2417 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 12200 | 1220 | 0 | 0 | 3660 | 3660 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2418 | HANGERS AND SUPPORTS | 21800 | 10900 | 0 | 0 | 3633.3333 | 3633.3333 | 3633.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2419 | Insulation: Furnish and Install: Ductwork Insulation | 7700 | 0 | 0 | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2420 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2975 | 0 | 0 | 0 | 991.6667 | 991.6667 | 991.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2421 | DOMESTIC WATER PIPING | 284883 | 99709.05 | 0 | 0 | 0 | 61724.65 | 61724.65 | 61724.65 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2422 | DOMESTIC WATER PIPING SPECIALTIES | 38000 | 0 | 0 | 0 | 12666.6667 | 12666.6667 | 12666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2423 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 18750 | 0 | 0 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2424 | SANITARY WASTE PIPING | 170771 | 145155.35 | 0 | 0 | 8538.55 | 8538.55 | 8538.55 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2425 | SANITARY WASTE PIPING SPECIALTIES | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2426 | STORM DRAINAGE PIPING SPECIALTIES | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03030 | 2427 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 359996 | 269997 | 0 | 0 | 29999.6667 | 29999.6667 | 29999.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03030 | 2428 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 145920 | 58368 | 0 | 0 | 29184 | 29184 | 29184 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2429 | GAS SERVICE AND PIPING | 262955 | 65738.75 | 0 | 0 | 0 | 65738.75 | 65738.75 | 65738.75 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2430 | Insulation: Furnish and Install: Piping Insulation | 18150 | 0 | 0 | 9075 | 0 | 0 | 9075 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03030 | 2431 | PLUMBING FIXTURES | 5200 | 0 | 0 | 0 | 1733.3333 | 1733.3333 | 1733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-03005 | 2432 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 63171 | 31585.5 | 0 | 0 | 10528.5 | 10528.5 | 10528.5 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02055 | 2433 | Heat Trace | 5000 | 0 | 0 | 4285.7143 | 0 | 0 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-S8-M-01005 | 2434 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 2435 | Exhaust Fans: Furnish | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2436 | Exhaust Fans: Install | 19050 | 0 | 2625.354 | 1539.2486 | 13596.0968 | 1289.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2437 | Electric Unit Heaters: Furnish | 3500 | 0 | 482.3485 | 282.8016 | 2497.9705 | 236.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2438 | Steam Unit Heater: Install | 20000 | 0 | 2756.2771 | 1616.0091 | 14274.1174 | 1353.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2439 | Steam Unit Heater: Furnish | 54000 | 0 | 7441.9483 | 4363.2245 | 38540.117 | 3654.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2440 | Condensate Return Unit: Furnish | 14000 | 0 | 1929.394 | 1131.2063 | 9991.8822 | 947.5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2441 | Insulation: Furnish and Install: Equipment Insulation | 7700 | 0 | 0 | 3850 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2442 | Condensate Return Unit: Install | 35000 | 0 | 4823.485 | 2828.0159 | 24979.7055 | 2368.7937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2443 | Steam Traps: Furnish | 4400 | 0 | 606.381 | 355.522 | 3140.3058 | 297.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2444 | Steam Traps: Install | 34000 | 0 | 4685.6711 | 2747.2154 | 24265.9996 | 2301.1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2445 | Heating and Ventilation Unit: Furnish | 6500 | 0 | 895.7901 | 525.2029 | 4639.0882 | 439.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2446 | Heating and Ventilation Unit: Install | 24000 | 0 | 3307.5326 | 1939.2109 | 17128.9409 | 1624.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2447 | Vacuum Pump Unit: Furnish | 16000 | 0 | 2205.0217 | 1292.8072 | 11419.2939 | 1082.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03142 | 2448 | Vacuum Pump Unit : Install | 26000 | 0 | 3583.1603 | 2100.8118 | 18556.3527 | 1759.6753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2449 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 250500 | 25050 | 41140.3551 | 62304.7585 | 61230.1705 | 49843.8068 | 10930.9091 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2450 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 511500 | 10230 | 84005.1562 | 127221.0938 | 125026.875 | 101776.875 | 63240 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2451 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 0 | 26277.2727 | 39795.4545 | 39109.0909 | 31836.3636 | 22981.8182 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02010 | 2452 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 5475 | 5475 | 5475 | 5475 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03135 | 2453 | Mechanical Pipe: Hydrostatic Testing | 4950 | 0 | 812.9531 | 1231.1719 | 1209.9375 | 984.9375 | 711 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2454 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 17500 | 0 | 8467.7419 | 8467.7419 | 8467.7419 | -2634.4086 | -2634.4086 | -2634.4086 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 2455 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 77000 | 38500 | 0 | 18629.0323 | 18629.0323 | 18629.0323 | -5795.6989 | -5795.6989 | -5795.6989 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03145 | 2456 | HVAC Ductwork: Testing & Balancing | 3500 | 0 | 0 | 846.7742 | 846.7742 | 846.7742 | 846.7742 | 0 | 112.9032 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2457 | Controls: Furnish and Install: Devices | 115000 | 42550 | 0 | 0 | 0 | 0 | 22406.3625 | 50043.6375 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2458 | Controls: Furnish and Install: Controls Conduit | 60000 | 18000 | 0 | 0 | 0 | 0 | 11690.2761 | 29135.6543 | 1174.0696 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2459 | Controls: Furnish and Install: Controls Wiring | 17250 | 0 | 0 | 0 | 0 | 0 | 3360.9544 | 8376.5006 | 5512.545 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2460 | Controls: Connect to Final Termination Points | 10000 | 0 | 0 | 0 | 0 | 0 | 1948.3794 | 4855.9424 | 3195.6783 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-03135 | 2461 | Controls: Controls Testing | 6000 | 0 | 0 | 0 | 0 | 0 | 1169.0276 | 2913.5654 | 1917.407 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2462 | Insulation: Furnish and Install: Ductwork Insulation | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 9075 | 5445 | 3630 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02035 | 2463 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 8750 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2464 | Insulation: Furnish and Install: Piping Insulation | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 15125 | 9075 | 6050 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2465 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 4950 | 3300 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2466 | ATS Energization | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2467 | ATS Installation | 210000 | 168000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2468 | ATS Terminations | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02345 | 2469 | ATS Testing | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02010 | 2470 | Bypass Connections (Misc Panels, Re-routes, etc) | 5000 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02040 | 2471 | Cabling - Interior Branch (1/0 & Smaller) | 225000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02115 | 2472 | Cabling - Risers & Feeders (2/0 & Larger) | 886950 | 0 | 0 | 0 | 221737.5 | 221737.5 | 221737.5 | 221737.5 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02030 | 2473 | Conduit - Branch Circuits (1 1/2" & Smaller) | 136875 | 13687.5 | 17598.2143 | 17598.2143 | 17598.2143 | 23464.2857 | 23464.2857 | 23464.2857 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02135 | 2474 | Cabling - Risers & Feeders (2/0 & Larger) | 689850 | 0 | 30000 | 98550 | 98550 | 20000 | 20000 | 20000 | 100687.5 | 100687.5 | 100687.5 | 100687.5 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02155 | 2475 | Conduit - In-Slab | 216810 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02105 | 2476 | Conduit - Risers (2" & Larger) | 985500 | 689850 | 0 | 295650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02010 | 2477 | Demolition | 20000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 5666.6667 | 5666.6667 | 5666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02130 | 2478 | Firestopping | 5000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02025 | 2479 | Foundation Coring | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
P-S8A-01100 | 2480 | Generator Delivery | 50000 | 0 | 0 | 0 | 0 | 28571.4286 | 14285.7143 | 0 | 2380.9524 | 2380.9524 | 2380.9524 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
P-S8A-01030 | 2481 | Generator Release | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02310 | 2482 | Generator Terminations | 50000 | 0 | 0 | 0 | 0 | 0 | 46428.5714 | 0 | 1190.4762 | 1190.4762 | 1190.4762 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02510 | 2483 | Generator Test | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02160 | 2484 | Lighting Controls | 50000 | 25000 | 0 | 0 | 12500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02020 | 2485 | Conduit - Branch Circuits (1 1/2" & Smaller) | 191625 | 19162.5 | 0 | 0 | 7839.2045 | 0 | 0 | 0 | 41155.8239 | 41155.8239 | 41155.8239 | 41155.8239 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02110 | 2486 | Lighting Install | 67800 | 33900 | 0 | 0 | 27120 | 0 | 0 | 0 | 2260 | 2260 | 2260 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02365 | 2487 | Lighting Rough | 67800 | 0 | 0 | 0 | 0 | 54240 | 0 | 0 | 4520 | 4520 | 4520 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG1-02025 | 2488 | Lighting System Program & Energize | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02370 | 2489 | Lightning Protection | 20000 | 10000 | 0 | 0 | 0 | 0 | 8333.3333 | 0 | 555.5556 | 555.5556 | 555.5556 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-02010 | 2490 | Manhole Work | 25000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8E-02045 | 2491 | Mechanical Terminations(Dampers, Heaters, Motors) | 100000 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8-02215 | 2492 | Site Lighting - Cable | 24638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.6667 | 8212.6667 | 8212.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8-02210 | 2493 | Site Lighting - Conduit | 32850 | 3285 | 0 | 0 | 0 | 0 | 0 | 0 | 9855 | 9855 | 9855 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8-02220 | 2494 | Site Lighting - Fixtures | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 11500 | 11500 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
SURV-S8-E-01015 | 2495 | Site Survey | 64000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
SG2-02050 | 2496 | Conduit - Risers (2" & Larger) | 788400 | 78840 | 0 | 0 | 0 | 0 | 0 | 0 | 177390 | 177390 | 177390 | 177390 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-S8-E-01015 | 2497 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02125 | 2498 | Switches and Receptacles | 10000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02520 | 2499 | Switchgear & Panelboard Energization | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02520 | 2500 | Switchgear & Panelboard Installation | 360000 | 270000 | 0 | 0 | 0 | 0 | 0 | 25714.2857 | 64285.7143 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02520 | 2501 | Switchgear & Panelboard Terminations | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02525 | 2502 | Switchgear & Panelboard Testing | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-02020 | 2503 | Temp Light & Power | 50000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 6989.5288 | 6989.5288 | 6020.9424 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02415 | 2504 | Underground Electric Service - Cable | 410625 | 0 | 58660.7143 | 58660.7143 | 58660.7143 | 78214.2857 | 78214.2857 | 78214.2857 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8-01155 | 2505 | Underground Electric Service - Conduit | 328500 | 328500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Site Utilities | 0
S8E-02030 | 2506 | Fire Alarm Conduit | 32850 | 0 | 4692.8571 | 4692.8571 | 4692.8571 | 6257.1429 | 6257.1429 | 6257.1429 | 0 | 0 | 0 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02015 | 2507 | Demolition/Temp Light & Power | 54750 | 30112.5 | 0 | 0 | 0 | 0 | 0 | 0 | 6159.375 | 6159.375 | 6159.375 | 6159.375 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02380 | 2508 | Fire Alarm Wiring | 31500 | 0 | 0 | 0 | 0 | 15750 | 0 | 0 | 5250 | 5250 | 5250 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02380 | 2509 | Fire Alarm Devices | 57000 | 28500 | 0 | 0 | 0 | 14250 | 0 | 0 | 4750 | 4750 | 4750 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02380 | 2510 | Fire Alarm Programming & Pretest | 2500 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-02505 | 2511 | Fire Alarm FDNY Approval | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8E-01705 | 2512 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 74861 | 7486.1 | 18715.25 | 18715.25 | 9981.4667 | 9981.4667 | 9981.4667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 271 - S81 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01580 | 2513 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - S8 | 28908 | 4336.2 | 0 | 0 | 8190.6 | 8190.6 | 8190.6 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 271 - S81 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8E-01580 | 2514 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - S8 | 417 | 0 | 0 | 0 | 0 | 208.5 | 208.5 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 271 - S81 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
S8A-01070 | 2515 | FORMWORK NEW BUILDING - S8 | 317228 | 317228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01175 | 2516 | SET ANCHOR BOLTS FOR STEEL COLUMNS - S8 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01040 | 2517 | POUR CONCRETE NEW BUILDINGS - S8 | 147088 | 147088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02125 | 2518 | Firestopping | 5250 | 0 | 4666.6667 | 0 | 0 | 0 | 0 | 0 | 145.8333 | 145.8333 | 145.8333 | 145.8333 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01135 | 2519 | FINISH SLABS - S8 | 15940 | 15940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01075 | 2520 | Footing/Pier | 43103 | 43103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01075 | 2521 | Grade Beams | 2298 | 2298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01130 | 2522 | Floor Slabs | 23287 | 23287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01130 | 2523 | Equipment Pads | 109 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01130 | 2524 | First Floor Plumbing Shaft Slab | 1034 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01035 | 2525 | Plumbing Shafts | 28192 | 28192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01170 | 2526 | Concrete Bench | 890 | 0 | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01205 | 2527 | WWM-Slabs | 4933 | 4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 272 - S82 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01305 | 2528 | Layout | 5109 | 0 | 0 | 0 | 0 | 4014.2143 | 729.8571 | 364.9286 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02050 | 2529 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01305 | 2530 | Loading | 13137 | 0 | 0 | 0 | 0 | 2000 | 7424.6667 | 3712.3333 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01305 | 2531 | Exterior Framing, Insulation & Drywall - Materials | 46709 | 0 | 0 | 0 | 0 | 15000 | 21139.3333 | 10569.6667 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01305 | 2532 | Exterior Framing- Labor | 54445 | 0 | 0 | 0 | 0 | 20000 | 22963.3333 | 11481.6667 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
OG8-01125 | 2533 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - S8 | 12569 | 12569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-02395 | 2534 | PENETRATION FIRESTOPPING NEW BLDG - S8 | 11505 | 0 | 9587.5 | 0 | 0 | 0 | 639.1667 | 639.1667 | 639.1667 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
S8E-01320 | 2535 | JOINT SEALANTS NEW BLDGS - S8 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
S8A-01305 | 2536 | Insulation- Labor | 4740 | 0 | 0 | 0 | 0 | 3724.2857 | 677.1429 | 338.5714 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01025 | 2537 | Crystalline Waterproofing at plumbing shaft | 3514 | 3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01072 | 2538 | Waterproofing at foundation | 66700 | 66700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01225 | 2539 | Fireproofing | 46200 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02065 | 2540 | Lighting Controls | 24150 | 12075 | 0 | 0 | 9660 | 0 | 0 | 0 | 603.75 | 603.75 | 603.75 | 603.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01265 | 2541 | P&I Cold Applied Roof Membrane | 68145 | 0 | 0 | 68145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01265 | 2542 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 70092 | 0 | 0 | 70092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01265 | 2543 | P&I Aluminum Coping | 3102 | 0 | 0 | 3102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01260 | 2544 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S8 | 14378 | 1437.8 | 0 | 0 | 0 | 6470.1 | 6470.1 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 275 - S82 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01245 | 2545 | Doors, Frames & Hardware - Labor | 26968 | 0 | 26968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 275 - S82 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 2546 | Furnish Doors | 22996 | 0 | 5749 | 5749 | 5749 | 2874.5 | 2874.5 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
S8A-01305 | 2547 | Sheathing & Drywall - Labor | 33946 | 0 | 0 | 0 | 0 | 10000 | 15964 | 7982 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01245 | 2548 | Tape/ Spackle finishes | 13372 | 0 | 13372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01280 | 2549 | Direct Applied Stucco | 31684 | 0 | 15842 | 15842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2550 | EXCAVATION NEW BLDGS - S8-2 | 70840 | 70840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG2-02015 | 2551 | Lighting Remove & Re-install | 22667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5666.75 | 5666.75 | 5666.75 | 5666.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
S8A-01055 | 2552 | BACKFILL NEW BLDGS - S8 | 35192 | 35192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2553 | DEWATERING COVERAGE FOR NEW BUILDINGS - S8 | 42088 | 42088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2554 | DENSE GRADED STONE BASE FOR FOUNDATION SLAB - S8 | 27148 | 27148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
S8A-01005 | 2555 | DRIVE PILES AND INSTALL LAGGING FOR SOE - S8 | 68282 | 68282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 277 - S82 - Division 31 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
| 2556 | CON EDISON ELECTRICAL UTILITY SERVICE FEE | 51926.66 | 2449.46 | 24738.6 | 24738.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALLOWANCE | 278 - Allowance - Division 1 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
| 2557 | NATIONAL GRID GAS UTILITY -CIAC | 141408 | 0 | 70704 | 70704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ALLOWANCE | 278 - Allowance - Division 1 | 0% | MLJ | SITE | Utilities | Site Utilities | 0
SG2-02015 | 2558 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02025 | 2559 | Mechanical Terminations(Dampers, Heaters, Motors) | 43800 | 0 | 0 | 0 | 35040 | 0 | 0 | 0 | 2190 | 2190 | 2190 | 2190 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-E-01030 | 2560 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-02110 | 2561 | Switches and Receptacles | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2737.5 | 2737.5 | 2737.5 | 2737.5 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02675 | 2562 | Switchgear & Panelboard Energization | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02375 | 2563 | Switchgear & Panelboard Installation | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16425 | 16425 | 16425 | 16425 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02375 | 2564 | Switchgear & Panelboard Terminations | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG7-02680 | 2565 | Switchgear & Panelboard Testing | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG2-01405 | 2566 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 12713 | 12713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 027 - SG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01480 | 2567 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-2 | 5028 | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 027 - SG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG2-01480 | 2568 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-2 | 486 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 027 - SG2 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01005 | 2569 | Gaskets | 36000 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01010 | 2570 | Wire Insulation | 37500 | 0 | 0 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2571 | Assumed Flooring Material (Slab Penetrations) | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2572 | Vinyl Membrane and Mastic | 53652 | 0 | 0 | 26826 | 26826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2573 | Caulk | 103500 | 103500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01015 | 2574 | Fibrous Slate | 14025 | 0 | 0 | 7012.5 | 7012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01020 | 2575 | Waterproofing | 9942 | 0 | 0 | 4971 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01020 | 2576 | Underground Utility Materials | 46800 | 0 | 0 | 23400 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2577 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01220 | 2578 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2579 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2580 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01115 | 2581 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01115 | 2582 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01115 | 2583 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2584 | Saw cut openings through slab for cellar ventilation / exhaust ducts | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01105 | 2585 | Remove window sill - 1st floor | 10000 | 5000 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01205 | 2586 | Remove Existing Ramp - 1st floor | 80000 | 40000 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 8000 | 8000 | 8000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01205 | 2587 | Existing Ramp railing to be be removed - 1st floor | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2588 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01210 | 2589 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2590 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2591 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2592 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2593 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2594 | Patch floor and make smooth - 2nd floor | 20000 | 0 | 5000 | 5000 | 5000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01210 | 2595 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01105 | 2596 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2597 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01105 | 2598 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01210 | 2599 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG3-01410 | 2600 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-3 | 52908 | 16072.4 | 0 | 0 | 0 | 18417.8 | 18417.8 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01450 | 2601 | DRILL & GROUT DOWELS - SG-3 | 7874 | 7874 | -2.8422e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01450 | 2602 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-3 | 42713 | 42713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01470 | 2603 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-3 | 30285 | 7571.25 | 0 | 18928.125 | 0 | 1892.8125 | 1892.8125 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01440 | 2604 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-3 | 30854 | 27748.6 | 0 | 0 | 1035.1333 | 1035.1333 | 1035.1333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01440 | 2605 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-3 | 4329 | 0 | 1082.25 | 1082.25 | 1082.25 | 541.125 | 541.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01320 | 2606 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-3 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01415 | 2607 | Footing/Pier | 17233 | 0 | 8616.5 | 8616.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01435 | 2608 | Retaining Walls | 2856 | 2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01535 | 2609 | Entrance Slab | 13291 | 0 | 11629.625 | 1661.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01810 | 2610 | Concrete Shelf | 6304 | 6304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01350 | 2611 | New Concrete Curb Next to Existing Wall | 242 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01350 | 2612 | Boiler Room Concrete Curb | 4178 | 0 | 0 | 4178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2613 | GFRP Sikawrap 100 G | 60346 | 0 | 10222.5464 | 9233.2678 | 13630.0619 | 13630.0619 | 13630.0619 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 029 - SG3 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01440 | 2614 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-3 | 378 | 0 | 94.5 | 94.5 | 94.5 | 47.25 | 47.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-01015 | 2615 | Overhead protection for Masonry | 24710 | 2471 | 0 | 0 | 0 | 11119.5 | 11119.5 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01820 | 2616 | 6" vertically reinforced CMU | 132685 | 112782.25 | 0 | 0 | 6634.25 | 6634.25 | 6634.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2617 | 2" Face brick | 410182 | 41018.2 | 69484.3825 | 62760.0874 | 78973.11 | 78973.11 | 78973.11 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2618 | 2" rigid Insulation | 19418 | 0 | 3289.388 | 2971.0601 | 4385.8506 | 4385.8506 | 4385.8506 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01820 | 2619 | Coping Stone C1/A-300 | 22968 | 2296.8 | 0 | 0 | 6890.4 | 6890.4 | 6890.4 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05530 | 2620 | MATERIAL AND FABRICATION | 21224 | 21224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01315 | 2621 | INSTALLATION | 37400 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01860 | 2622 | Temporary Aluminum Over Pass Stairs | 57196 | 0 | 0 | 0 | 0 | 0 | 0 | 14299 | 42897 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-02145 | 2623 | PENETRATION FIRESTOPPING EXTG BLDG - SG-3 | 11505 | 0 | 0 | 0 | 0 | 0 | 3835 | 3835 | 3835 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01320 | 2624 | JOINT SEALANTS EXTG BLDGS - SG-3 | 11505 | 0 | 2876.25 | 2876.25 | 2876.25 | 1438.125 | 1438.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01830 | 2625 | Bituthene 4000 waterproofing membrane | 17281 | 0 | 2927.3825 | 2644.0874 | 3903.1767 | 3903.1767 | 3903.1767 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01830 | 2626 | GE Elemax 2600 Silicone air and vapor barrier | 25531 | 0 | 4324.9235 | 3906.3825 | 5766.5647 | 5766.5647 | 5766.5647 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01370 | 2627 | Crystalline Waterproofing at perimeter walls | 50313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01825 | 2628 | Waterproofing at foundation walls | 17020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 032 - SG3 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01330 | 2629 | Doors, Frames & Hardware - Labor | 5838 | 5838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 033 - SG3 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 2630 | Furnish Doors | 8362 | 8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2631 | Layout | 5658 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2632 | Loading | 8744 | 8744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2633 | Framing & Drywall - Materials | 13115 | 13115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01325 | 2634 | Framing- Labor | 20060 | 20060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01330 | 2635 | Drywall - Labor | 23660 | 23660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01330 | 2636 | Tape/ Spackle finishes | 18517 | 18517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01855 | 2637 | Stucco | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01340 | 2638 | Resilient Flooring and base - SG-3 | 15640 | 0 | 7820 | 7820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01860 | 2639 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-3 | 45295 | 22647.5 | 0 | 0 | 0 | 0 | 7549.1667 | 7549.1667 | 7549.1667 | 0 | 0 | 0 | 0 | SG3 | 035 - SG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01820 | 2640 | Wiper wall panel | 4851 | 0 | 0 | 0 | 1617 | 1617 | 1617 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 035 - SG3 - Division 10 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01865 | 2641 | Address Signs | 4950 | 0 | 0 | 0 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 035 - SG3 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01380 | 2642 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2643 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2644 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2645 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2646 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2647 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2648 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2649 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2650 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2651 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2652 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2653 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2654 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2655 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2656 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2657 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2658 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2659 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2660 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01380 | 2661 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 036 - SG3 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2662 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10206.75 | 0 | 0 | 1134.0833 | 1134.0833 | 1134.0833 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2663 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1056 | 105.6 | 0 | 0 | 316.8 | 316.8 | 316.8 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2664 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 0 | 0 | 0 | 365.3333 | 365.3333 | 365.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2665 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 5940 | 4158 | 0 | 0 | 594 | 594 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2666 | HANGERS AND SUPPORTS | 11512 | 9209.6 | 0 | 0 | 767.4667 | 767.4667 | 767.4667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2667 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 0 | 731.6667 | 731.6667 | 731.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2668 | DOMESTIC WATER PIPING | 137444 | 109955.2 | 0 | 0 | 9162.9333 | 9162.9333 | 9162.9333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2669 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 13838 | 0 | 0 | 814 | 814 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2670 | SANITARY WASTE PIPING | 135254 | 108203.2 | 0 | 0 | 9016.9333 | 9016.9333 | 9016.9333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2671 | SANITARY WASTE PIPING SPECIALTIES | 47078 | 42370.2 | 0 | 0 | 1569.2667 | 1569.2667 | 1569.2667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2672 | STORM DRAINAGE PIPING SPECIALTIES | 47078 | 18831.2 | 0 | 0 | 9415.6 | 9415.6 | 9415.6 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03030 | 2673 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 417998 | 376198.2 | 0 | 0 | 13933.2667 | 13933.2667 | 13933.2667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2674 | GAS SERVICE AND PIPING | 2261 | 0 | 0 | 0 | 753.6667 | 753.6667 | 753.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2675 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13266 | 13266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03005 | 2676 | Plumbing Pipe Insulation | 35750 | 0 | 0 | 17875 | 17875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02040 | 2677 | Heat Trace | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-M-01005 | 2678 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 2679 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2680 | Exhaust Fans: Install | 14795 | 7397.5 | 2465.8333 | 2465.8333 | 2465.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2681 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2682 | Steam Unit Heaters: Install | 17600 | 0 | 5866.6667 | 5866.6667 | 5866.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2683 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2684 | Condensate Return Unit: Install | 24200 | 0 | 8066.6667 | 8066.6667 | 8066.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2685 | Heating and Ventilation Unit: Furnish | 7150 | 0 | 2383.3333 | 2383.3333 | 2383.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2686 | Heating and Ventilation Unit: Install | 25300 | 0 | 8433.3333 | 8433.3333 | 8433.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2687 | Steam Traps: Furnish | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03112 | 2688 | Steam Traps: Install | 25850 | 0 | 8616.6667 | 8616.6667 | 8616.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2689 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2690 | Vacuum Pump Unit: Install | 27500 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2691 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 290565 | 232452 | 14528.25 | 14528.25 | 14528.25 | 14528.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2692 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 445500 | 378675 | 16706.25 | 16706.25 | 16706.25 | 16706.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2693 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 176000 | 0 | 58666.6667 | 58666.6667 | 58666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03015 | 2694 | Mechanical Pipe: Hydrostatic Testing | 6435 | 0 | 2145 | 2145 | 2145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03007 | 2695 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 33000 | 30360 | 0 | 0 | 2572.8814 | 0 | 0 | 0 | 67.1186 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 2696 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 93500 | 86020 | 0 | 0 | 7289.8305 | 0 | 0 | 0 | 190.1695 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03235 | 2697 | HVAC Ductwork: Testing & Balancing | 3300 | 0 | 0 | 0 | 257.2881 | 0 | 0 | 0 | 3042.7119 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2698 | Controls: Furnish and Install: Devices | 82500 | 78375 | 0 | 0 | 3946.9424 | 0 | 0 | 178.0576 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2699 | Controls: Furnish and Install: Controls Conduit | 44000 | 41800 | 0 | 0 | 2105.036 | 0 | 0 | 94.964 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2700 | Controls: Furnish and Install: Controls Wiring | 11000 | 10450 | 0 | 0 | 526.259 | 0 | 0 | 23.741 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2701 | Controls: Connect to Final Termination Points | 8800 | 8360 | 0 | 0 | 421.0072 | 0 | 0 | 18.9928 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03310 | 2702 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 315.7554 | 0 | 0 | 6284.2446 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2703 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 0 | 0 | 0 | 0 | 4125 | 0 | 10725 | 1650 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2704 | Insulation: Furnish and Install: Piping Insulation | 33000 | 0 | 0 | 0 | 0 | 8250 | 0 | 21450 | 3300 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2705 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 0 | 0 | 0 | 0 | 4125 | 0 | 10725 | 1650 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2706 | ATS Energization | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 11406.6667 | 570.3333 | 570.3333 | 570.3333 | 570.3333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2707 | ATS Installation | 194250 | 97125 | 0 | 0 | 0 | 0 | 0 | 80937.5 | 4046.875 | 4046.875 | 4046.875 | 4046.875 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2708 | ATS Terminations | 13875 | 0 | 0 | 0 | 0 | 0 | 0 | 11562.5 | 578.125 | 578.125 | 578.125 | 578.125 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02210 | 2709 | ATS Testing | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 11406.6667 | 570.3333 | 570.3333 | 570.3333 | 570.3333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02010 | 2710 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 13687.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3421.875 | 3421.875 | 3421.875 | 3421.875 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02035 | 2711 | Cabling - Interior Branch (1/0 & Smaller) | 164250 | 0 | 23464.2857 | 23464.2857 | 23464.2857 | 31285.7143 | 31285.7143 | 31285.7143 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGS-02105 | 2712 | Cabling - Risers & Feeders (2/0 & Larger) | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98550 | 98550 | 98550 | 98550 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02015 | 2713 | Conduit - Branch Circuits (1 1/2" & Smaller) | 222000 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 27750 | 27750 | 27750 | 27750 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02115 | 2714 | Conduit - Risers (2" & Larger) | 399600 | 359640 | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | 9990 | 9990 | 9990 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02020 | 2715 | Demolition/Temp Light & Power | 54750 | 46537.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2053.125 | 2053.125 | 2053.125 | 2053.125 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02145 | 2716 | Firestopping | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02025 | 2717 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02125 | 2718 | Lighting Controls | 31500 | 15750 | 13500 | 0 | 0 | 0 | 0 | 0 | 562.5 | 562.5 | 562.5 | 562.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02020 | 2719 | Lighting Remove & Re-install | 54203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13550.75 | 13550.75 | 13550.75 | 13550.75 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02020 | 2720 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1368.75 | 1368.75 | 1368.75 | 1368.75 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02045 | 2721 | Mechanical Terminations(Dampers, Heaters, Motors) | 63510 | 19053 | 38106 | 0 | 0 | 0 | 0 | 0 | 1587.75 | 1587.75 | 1587.75 | 1587.75 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGS-E-01030 | 2722 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02515 | 2723 | Switchgear & Panelboard Energization | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02265 | 2724 | Switchgear & Panelboard Installation | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98550 | 98550 | 98550 | 98550 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02265 | 2725 | Switchgear & Panelboard Terminations | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02510 | 2726 | Switchgear & Panelboard Testing | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 8212.5 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02015 | 2727 | Fire Alarm Conduit | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6843.75 | 6843.75 | 6843.75 | 6843.75 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02120 | 2728 | Fire Alarm Wiring | 24638 | 0 | 18478.5 | 0 | 0 | 0 | 0 | 0 | 1539.875 | 1539.875 | 1539.875 | 1539.875 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02120 | 2729 | Fire Alarm Devices | 19710 | 9855 | 7391.25 | 0 | 0 | 0 | 0 | 0 | 615.9375 | 615.9375 | 615.9375 | 615.9375 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02120 | 2730 | Fire Alarm Programming & Pretest | 2738 | 0 | 2053.5 | 0 | 0 | 0 | 0 | 0 | 171.125 | 171.125 | 171.125 | 171.125 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-02535 | 2731 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684.5 | 684.5 | 684.5 | 684.5 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-01405 | 2732 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 15538 | 15538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 041 - SG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01480 | 2733 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-3 | 6285 | 942.75 | 0 | 5387.1429 | 0 | 0 | -14.9643 | -14.9643 | -14.9643 | 0 | 0 | 0 | 0 | SG3 | 041 - SG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG3-01480 | 2734 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-3 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 041 - SG3 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01005 | 2735 | Gaskets | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 9000 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01010 | 2736 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2737 | Assumed Flooring Material (Slab Penetrations) | 46800 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01020 | 2738 | Pipe Insulation | 15750 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2739 | Vinyl Membrane and Mastic | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2740 | Caulk | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01015 | 2741 | Fibrous Slate | 14535 | 14535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01020 | 2742 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01020 | 2743 | Underground Utility Materials | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2744 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01220 | 2745 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2746 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2747 | Remove existing door, frame and hardware - cellar and 1st floor | 20000 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01115 | 2748 | Remove Areaway slab and drain - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01115 | 2749 | Remove Areaway grate - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01115 | 2750 | Sawcut and remove portion of areaway wall - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2751 | Saw cut openings through slab for cellar ventilation / exhaust ducts | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01105 | 2752 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01205 | 2753 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01205 | 2754 | Existing Ramp railing to be be removed - 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2755 | Sawcut slab opening for mechanical - cellar and 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01210 | 2756 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2757 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2758 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2759 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2760 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2761 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01210 | 2762 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01105 | 2763 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2764 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01105 | 2765 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01210 | 2766 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG4-01410 | 2767 | FORM FLOOD BARRIER FOUNDATIONS & BOILER ROOM WALLS - SG-4 | 106025 | 106025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01450 | 2768 | DRILL & GROUT DOWELS - SG-4 | 25962 | 25962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01450 | 2769 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-4 | 25126 | 25126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01470 | 2770 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-4 | 49048 | 49048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01440 | 2771 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-4 | 23998 | 23998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01440 | 2772 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-4 | 4137 | 0 | 2068.5 | 2068.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01320 | 2773 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-4 | 50274 | 50274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01415 | 2774 | Footing/Pier | 20904 | 20904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01435 | 2775 | Retaining Walls | 4692 | 4692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01665 | 2776 | Entrance Slab | 20706 | 5176.5 | 15529.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01810 | 2777 | Concrete Shelf | 4320 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01350 | 2778 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01350 | 2779 | Boiler Room Concrete Curb | 3354 | 3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2780 | GFRP Sikawrap 100 G | 87230 | 87230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 043 - SG4 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01440 | 2781 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-4 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01015 | 2782 | Overhead protection for Masonry | 35611 | 33830.45 | 890.275 | 890.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01820 | 2783 | 6" vertically reinforced CMU | 126280 | 126280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2784 | 2" Face brick | 538422 | 484579.8 | 53842.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2785 | 2" rigid Insulation | 18480 | 18480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01820 | 2786 | Coping Stone C1/A-300 | 18586 | 18586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05350 | 2787 | MATERIAL AND FABRICATION | 21224 | 21224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01315 | 2788 | INSTALLATION | 37400 | 37400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01860 | 2789 | Temporary Aluminum Over Pass Stairs | 57196 | 0 | 28598 | 28598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-02345 | 2790 | PENETRATION FIRESTOPPING EXTG BLDG - SG-4 | 11505 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01320 | 2791 | JOINT SEALANTS EXTG BLDGS - SG-4 | 11505 | 0 | 5752.5 | 5752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01830 | 2792 | Bituthene 4000 waterproofing membrane | 21142 | 21142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01830 | 2793 | GE Elemax 2600 Silicone air and vapor barrier | 36905 | 36905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01370 | 2794 | Crystalline Waterproofing at perimeter walls | 42694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01825 | 2795 | Waterproofing at foundation walls | 17020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 046 - SG4 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01860 | 2796 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-4 | 1050 | 0 | 525 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 047 - SG4 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01330 | 2797 | Doors, Frames & Hardware - Labor | 13066 | 13066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 047 - SG4 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 2798 | Furnish Doors | 8362 | 2759.46 | 2801.27 | 2801.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2799 | Layout | 7715 | 7715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2800 | Loading | 9001 | 9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2801 | Framing & Drywall - Materials | 17638 | 17638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01325 | 2802 | Framing- Labor | 7458 | 7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01330 | 2803 | Drywall - Labor | 15944 | 15944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01330 | 2804 | Tape/ Spackle finishes | 23660 | 23660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01855 | 2805 | Stucco | 10183 | 0 | 5091.5 | 5091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01340 | 2806 | Resilient Flooring and base - SG-4 | 27600 | 0 | 13800 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01860 | 2807 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-4 | 51471 | 25735.5 | 12867.75 | 12867.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01860 | 2808 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-4 | 11690 | 0 | 5845 | 5845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01860 | 2809 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-4 | 140863 | 84517.8 | 28172.6 | 28172.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01820 | 2810 | Wiper wall panel | 3234 | 3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01865 | 2811 | Temporary Egress Stair Storage Sign | 2640 | 0 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01865 | 2812 | Address Signs | 4950 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 049 - SG4 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01380 | 2813 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2814 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2815 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2816 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2817 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2818 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2819 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2820 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2821 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2822 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2823 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2824 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2825 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2826 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2827 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2828 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2829 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2830 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2831 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01380 | 2832 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 050 - SG4 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2833 | COMMON WORK RESULTS FOR PLUMBING | 13609 | 10887.2 | 680.45 | 680.45 | 680.45 | 680.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2834 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1056 | 950.4 | 0 | 105.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2835 | ESCUTCHEONS FOR PLUMBING PIPING | 1096 | 986.4 | 0 | 109.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2836 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4620 | 2772 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2837 | HANGERS AND SUPPORTS | 11509 | 9207.2 | 0 | 2301.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2838 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2195 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2839 | DOMESTIC WATER PIPING | 140998 | 126898.2 | 0 | 14099.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 2840 | DOMESTIC WATER PIPING SPECIALTIES | 16280 | 12210 | 0 | 4070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2841 | SANITARY WASTE PIPING | 122074 | 122074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2842 | SANITARY WASTE PIPING SPECIALTIES | 45569 | 45569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2843 | STORM DRAINAGE PIPING SPECIALTIES | 45569 | 45569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03030 | 2844 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 324500 | 308275 | 0 | 16225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2845 | GAS SERVICE AND PIPING | 6369 | 5732.1 | 0 | 636.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2846 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 5357 | 5357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03005 | 2847 | Plumbing Pipe Insulation | 35464 | 24824.8 | 0 | 5319.6 | 5319.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02260 | 2848 | Heat Trace | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-M-01005 | 2849 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 2850 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03112 | 2851 | Exhaust Fans: Install | 11495 | 0 | 2873.75 | 2873.75 | 2873.75 | 2873.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2852 | Steam Unit Heaters: Furnish | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03032 | 2853 | Steam Unit Heaters: Install | 14300 | 14300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2854 | Condensate Return Unit: Furnish | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03032 | 2855 | Condensate Return Unit: Install | 20900 | 20900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03112 | 2856 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03112 | 2857 | Heating and Ventilation Unit: Install | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03310 | 2858 | Steam Traps: Furnish | 2420 | 2420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG3-03310 | 2859 | Steam Traps: Install | 18150 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 2860 | Vacuum Pump Unit: Furnish | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03032 | 2861 | Vacuum Pump Unit: Install | 24200 | 24200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03107 | 2862 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 189613 | 189613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03007 | 2863 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 312400 | 312400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03007 | 2864 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 96250 | 96250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03025 | 2865 | Mechanical Pipe: Hydrostatic Testing | 3163 | 3163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03107 | 2866 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 19250 | 13475 | 1854.3578 | 0 | 1306.8807 | 1306.8807 | 1306.8807 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 2867 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 38500 | 26950 | 3708.7156 | 0 | 2613.7615 | 2613.7615 | 2613.7615 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03140 | 2868 | HVAC Ductwork: Testing & Balancing | 2200 | 0 | 211.9266 | 0 | 662.6911 | 662.6911 | 662.6911 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2869 | Controls: Furnish and Install: Devices | 82500 | 79200 | 1809.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2870 | Controls: Furnish and Install: Controls Conduit | 44000 | 42240 | 965.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2871 | Controls: Furnish and Install: Controls Wiring | 11000 | 10560 | 241.2903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 2872 | Controls: Connect to Final Termination Points | 88000 | 74800 | 0 | 0 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-03310 | 2873 | Controls: Controls Testing | 6600 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2874 | Insulation: Furnish and Install: Ductwork Insulation | 12650 | 8855 | 1897.5 | 1897.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2875 | Insulation: Furnish and Install: Piping Insulation | 25300 | 24035 | 632.5 | 632.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 2876 | Insulation: Furnish and Install: Equipment Insulation | 12650 | 12017.5 | 632.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2877 | ATS Energization | 13688 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2878 | ATS Installation | 191625 | 191625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2879 | ATS Terminations | 13688 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02430 | 2880 | ATS Testing | 13688 | 13003.6 | 0 | 0 | 0 | 228.1333 | 228.1333 | 228.1333 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02225 | 2881 | Bypass Connections (Misc Panels, Re-routes, etc) | 27375 | 26006.25 | 0 | 0 | 0 | 456.25 | 456.25 | 456.25 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02245 | 2882 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-02125 | 2883 | Cabling - Risers & Feeders (2/0 & Larger) | 473040 | 449388 | 0 | 0 | 0 | 7884 | 7884 | 7884 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02230 | 2884 | Conduit - Branch Circuits (1 1/2" & Smaller) | 273750 | 260062.5 | 0 | 0 | 0 | 4562.5 | 4562.5 | 4562.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02305 | 2885 | Conduit - Risers (2" & up) | 542025 | 542025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02210 | 2886 | Demolition/Temp Light & Power | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02345 | 2887 | Firestopping | 5250 | 4987.5 | 0 | 0 | 0 | 87.5 | 87.5 | 87.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02215 | 2888 | Foundation Coring | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02250 | 2889 | Lighting Controls | 25200 | 23940 | 0 | 0 | 0 | 420 | 420 | 420 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02210 | 2890 | Lighting Remove & Re-install | 54945 | 52197.75 | 0 | 0 | 0 | 915.75 | 915.75 | 915.75 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02210 | 2891 | Lighting System Program & Energize | 5475 | 2737.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02270 | 2892 | Mechanical Terminations(Dampers, Heaters, Motors) | 56940 | 54093 | 0 | 0 | 0 | 949 | 949 | 949 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-E-01000 | 2893 | Survey | 65700 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02425 | 2894 | Switches and Receptacles | 10950 | 10402.5 | 0 | 0 | 0 | 182.5 | 182.5 | 182.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02515 | 2895 | Switchgear & Panelboard Energization | 30113 | 27101.7 | 0 | 0 | 0 | 1003.7667 | 1003.7667 | 1003.7667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02455 | 2896 | Switchgear & Panelboard Installation | 361350 | 361350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02455 | 2897 | Switchgear & Panelboard Terminations | 30113 | 28607.35 | 0 | 0 | 1505.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02520 | 2898 | Switchgear & Panelboard Testing | 30113 | 24090.4 | 860.3714 | 860.3714 | 860.3714 | 1147.1619 | 1147.1619 | 1147.1619 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02230 | 2899 | Fire Alarm Conduit | 16650 | 15817.5 | 0 | 0 | 0 | 277.5 | 277.5 | 277.5 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02325 | 2900 | Fire Alarm Wiring | 13140 | 12483 | 0 | 0 | 0 | 219 | 219 | 219 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02325 | 2901 | Fire Alarm Devices | 21900 | 20805 | 0 | 0 | 0 | 365 | 365 | 365 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02325 | 2902 | Fire Alarm Programming & Pretest | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-02505 | 2903 | Fire Alarm FDNY Approval | 2738 | 0 | 0 | 0 | 0 | 912.6667 | 912.6667 | 912.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG4-01405 | 2904 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 17656 | 17656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 055 - SG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01480 | 2905 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-4 | 7542 | 7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 055 - SG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG4-01480 | 2906 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-4 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 055 - SG4 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01005 | 2907 | Gaskets | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01010 | 2908 | Wire Insulation | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2909 | Assumed Flooring Material (Slab Penetrations) | 43200 | 43200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01020 | 2910 | Pipe Insulation | 151200 | 151200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2911 | Mudded Joint Packing | 25086 | 25086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2912 | Vinyl Membrane and Mastic | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2913 | Caulk | 108000 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01015 | 2914 | Fibrous Slate | 15810 | 15810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01020 | 2915 | Waterproofing | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01020 | 2916 | Underground Utility Materials | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2917 | Remove existing paint and plaster - cellar | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01220 | 2918 | Remove sump pump - cellar | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2919 | Remove existing vent / window and frame - cellar and 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2920 | Remove existing door, frame and hardware | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01115 | 2921 | Remove Areaway slab and drain | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01115 | 2922 | Remove Areaway grate | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01115 | 2923 | Sawcut and remove portion of areaway wall | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2924 | Prepare existing wall surface for paint | 6000 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01210 | 2925 | Saw cut openings through slab for cellar ventilation / exhaust ducts - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01105 | 2926 | Remove window sill - 1st floor | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01205 | 2927 | Remove Existing Ramp - 1st floor | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01205 | 2928 | Existing Ramp railing to be be removed - 1st floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2929 | Sawcut slab opening for mechanical - 1st floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01210 | 2930 | Remove floor finish - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2931 | Remove stove - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2932 | Remove CMU wall - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2933 | Remove sinks - 2nd floor | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2934 | Remove interior walls - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2935 | Patch floor and make smooth - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01210 | 2936 | Cut openings in slab - 2nd floor | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01105 | 2937 | Remove existing windows - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2938 | Remove appliances - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01105 | 2939 | Remove ceiling finishes - 2nd floor | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01210 | 2940 | Remove plumbing to fixtures - 2nd floor | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | MLJ | EXISTING BUILDINGS | Building Demo | Site Demo | 0
SG5-01410 | 2941 | FORM FLOOD BARRIER FOUNDATIONS - SG-5 | 86514 | 86514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01450 | 2942 | DRILL & GROUT DOWELS - SG-5 | 26772 | 26772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01450 | 2943 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE - SG-5 | 41980 | 41980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01470 | 2944 | POUR CONCRETE FLOOD BARRIER FOUNDATIONS - SG-5 | 45756 | 45756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01440 | 2945 | FORM AND POUR CONCRETE SHELF AND BOND BEAM EXTG BLDGS - SG-5 | 23998 | 23998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01440 | 2946 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL SMOOTH - SG-5 | 3591 | 3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01320 | 2947 | FURNISH AND INSTALL FRP REINFORCING ELECTRICAL ROOM - SG-5 | 168000 | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01435 | 2948 | Footing/Pier | 24258 | 19406.4 | 4851.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01465 | 2949 | Retaining Walls | 4692 | 4692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01665 | 2950 | Entrance Slab | 20400 | 16320 | 2040 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01810 | 2951 | Concrete Shelf | 4320 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01415 | 2952 | New Concrete Curb Next to Existing Wall | 234 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01415 | 2953 | Boiler Room Concrete Curb | 3354 | 3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | TONAGE | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2954 | GFRP Sikawrap 100 G | 83226 | 83226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 057 - SG5 - Division 3 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01440 | 2955 | CLEAN SURFACE OF CONCRETE FOUNDATION WALL. PATCH VOIDS WITH REPAIR MORTAR - SG-5 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SGN-01015 | 2956 | Overhead protection for Masonry | 34158 | 34158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01820 | 2957 | 6" vertically reinforced CMU | 123200 | 123200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2958 | 2" Face brick | 530612 | 477550.8 | 53061.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2959 | 2" rigid Insulation | 18480 | 18480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01820 | 2960 | Coping Stone C1/A-300 | 17319 | 17319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
05380 | 2961 | MATERIAL AND FABRICATION | 38589 | 38589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01315 | 2962 | INSTALLATION | 68000 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | WEIR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01860 | 2963 | Temporary Aluminum Over Pass Stairs | 103992 | 0 | 51996 | 51996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | E&Y | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-02345 | 2964 | PENETRATION FIRESTOPPING EXTG BLDG - SG-5 | 19222 | 0 | 9611 | 9611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01320 | 2965 | JOINT SEALANTS EXTG BLDGS - SG-5 | 19222 | 0 | 9611 | 9611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01830 | 2966 | Bituthene 4000 waterproofing membrane | 21362 | 21362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01830 | 2967 | GE Elemax 2600 Silicone air and vapor barrier | 35211 | 35211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01825 | 2968 | Crystalline Waterproofing at perimeter walls | 42694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01835 | 2969 | Waterproofing at foundation walls | 17020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 060 - SG5 - Division 7 | 0% | DSTAR | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01860 | 2970 | (2'9"X8"H) S.S FLOOD VENT W/ S.S SCREEN COVER NEW BLDGS (8.06) - SG-5 | 1200 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 061 - SG5 - Division 8 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01330 | 2971 | Doors, Frames & Hardware - Labor | 5004 | 5004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 061 - SG5 - Division 8 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
08020 | 2972 | Furnish Doors | 6780 | 3390 | 1695 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | MLJ | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2973 | Layout | 4170 | 4170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2974 | Loading | 6950 | 6950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2975 | Framing & Drywall - Materials | 14456 | 14456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01325 | 2976 | Framing- Labor | 16680 | 16680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01330 | 2977 | Drywall - Labor | 28914 | 28914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01330 | 2978 | Tape/ Spackle finishes | 13344 | 13344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01855 | 2979 | Stucco | 11008 | 0 | 5504 | 5504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01340 | 2980 | Resilient Flooring and base - SG-5 | 27600 | 0 | 13800 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | FLOORING | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01860 | 2981 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) - SG-5 | 49413 | 24706.5 | 12353.25 | 12353.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01860 | 2982 | WINDOW FLOODGATES (8.06 AND 8.14) - SG-5 | 27072 | 27072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01860 | 2983 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE (8.15) - SG-5 | 140863 | 84517.8 | 28172.6 | 28172.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01820 | 2984 | Wiper wall panel | 3333 | 3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | FAXA | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01865 | 2985 | Temporary Egress Stair Storage Sign | 2400 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01865 | 2986 | Address Signs | 9000 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 063 - SG5 - Division 10 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01370 | 2987 | Clean and refurbish landing device components in the pit | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2988 | Replace switches, wiring and junction boxes exposed to water in the pit to 5' above the 1st floor | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2989 | Clean and paint components subjected to water exposure per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2990 | Replace oil buffers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2991 | Replace compensation guidance system per dwgs | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01380 | 2992 | Wire brush all rust from rails and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2993 | Wire brush all rust from pit steel and paint with rust inhibiting enamel per dwgs | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2994 | Clad exposed entrances with textured stainless steel sheet metal (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2995 | Replace all closers, door gibs and other door compnents (at the first floor only) | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2996 | Replace door panels with new stainless steel door panels (at the first floor only) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01380 | 2997 | Wire brush sills and support (at the first floor only) | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01380 | 2998 | Wire brush, clean and paint all facia and toe guards below first floor level | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 2999 | Replace pit lights and outlets | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3000 | Replace all pit stop switches and light switches | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3001 | Repair/replace pit access doors and hardware | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3002 | Replace governor tension sheave and governor ropes per dwgs | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3003 | Clean and paint grating with rust inhibiting enamel | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3004 | Clean and paint buffer inspection ladders | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3005 | Clean out pit of all dirt and debris | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01370 | 3006 | Replace all limit switches and brackets in the pit and lower level | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 064 - SG5 - Division 14 | 0% | Dynasty Elevator | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3007 | COMMON WORK RESULTS FOR PLUMBING | 14846 | 11876.8 | 742.3 | 742.3 | 742.3 | 742.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3008 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 864 | 777.6 | 21.6 | 21.6 | 21.6 | 21.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3009 | ESCUTCHEONS FOR PLUMBING PIPING | 1196 | 837.2 | 89.7 | 89.7 | 89.7 | 89.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3010 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4080 | 0 | 1020 | 1020 | 1020 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3011 | HANGERS AND SUPPORTS | 12555 | 2511 | 2511 | 2511 | 2511 | 2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3012 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2394 | 0 | 598.5 | 598.5 | 598.5 | 598.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3013 | DOMESTIC WATER PIPING | 108372 | 86697.6 | 5418.6 | 5418.6 | 5418.6 | 5418.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3014 | DOMESTIC WATER PIPING SPECIALTIES | 17760 | 13320 | 1110 | 1110 | 1110 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3015 | SANITARY WASTE PIPING | 107844 | 86275.2 | 5392.2 | 5392.2 | 5392.2 | 5392.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3016 | SANITARY WASTE PIPING SPECIALTIES | 22562 | 20305.8 | 564.05 | 564.05 | 564.05 | 564.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3017 | STORM DRAINAGE PIPING SPECIALTIES | 46560 | 39576 | 1746 | 1746 | 1746 | 1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03030 | 3018 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 270000 | 256500 | 3375 | 3375 | 3375 | 3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3019 | GAS SERVICE AND PIPING | 2112 | 0 | 528 | 528 | 528 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03005 | 3020 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 10714 | 10714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG5-03005 | 3021 | Plumbing Pipe Insulation | 35464 | 35464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | TRISTAN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02240 | 3022 | Heat Trace | 6000 | 4800 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-M-01005 | 3023 | Survey | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03112 | 3024 | Exhaust Fans: Furnish | 4320 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03112 | 3025 | Exhaust Fans: Install | 8940 | 0 | 0 | 0 | 8940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 3026 | Steam Unit Heaters: Furnish | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03032 | 3027 | Steam Unit Heaters: Install | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 3028 | Condensate Return Unit: Furnish | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03032 | 3029 | Condensate Return Unit: Install | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03112 | 3030 | Heating and Ventilation Unit: Furnish | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03112 | 3031 | Heating and Ventilation Unit: Install | 20400 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03015 | 3032 | Steam Traps: Furnish | 1920 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03015 | 3033 | Steam Traps: Install | 15600 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03032 | 3034 | Vacuum Pump Unit: Furnish | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03032 | 3035 | Vacuum Pump Unit: Install | 22800 | 22800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03107 | 3036 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 104700 | 104700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03007 | 3037 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 167200 | 167200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03007 | 3038 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 50400 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03025 | 3039 | Mechanical Pipe: Hydrostatic Testing | 1925 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03107 | 3040 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 10800 | 10584 | 0 | 0 | 407.0769 | 0 | -191.0769 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03110 | 3041 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 17600 | 16720 | 0 | 0 | 663.3846 | 0 | 216.6154 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03035 | 3042 | HVAC Ductwork: Testing & Balancing | 1200 | 0 | 0 | 0 | 45.2308 | 0 | 1154.7692 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3043 | Controls: Furnish and Install: Devices | 90000 | 83500 | 0 | 0 | 3250 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3044 | Controls: Furnish and Install: Controls Conduit | 42000 | 40320 | 560 | 560 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3045 | Controls: Furnish and Install: Controls Wiring | 12000 | 11520 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03120 | 3046 | Controls: Connect to Final Termination Points | 9000 | 8550 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-03235 | 3047 | Controls: Controls Testing | 7200 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 3048 | Insulation: Furnish and Install: Ductwork Insulation | 12650 | 0 | 6325 | 6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 3049 | Insulation: Furnish and Install: Piping Insulation | 25300 | 24035 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
OG1-03040 | 3050 | Insulation: Furnish and Install: Equipment Insulation | 13800 | 0 | 6900 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3051 | ATS Energization | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3052 | ATS Installation | 168000 | 151200 | 0 | 0 | 0 | 5600 | 5600 | 5600 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3053 | ATS Terminations | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02420 | 3054 | ATS Testing | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02210 | 3055 | Bypass Connections (Misc Panels, Re-routes, etc) | 30000 | 15000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02235 | 3056 | Cabling - Interior Branch (1/0 & Smaller) | 160000 | 0 | 22857.1429 | 22857.1429 | 22857.1429 | 30476.1905 | 30476.1905 | 30476.1905 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02475 | 3057 | Cabling - Risers & Feeders (2/0 & Larger) | 354780 | 266085 | 50682.8571 | 38012.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02215 | 3058 | Conduit - Branch Circuits (1 1/2" & Smaller) | 219000 | 175200 | 0 | 0 | 0 | 14600 | 14600 | 14600 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02325 | 3059 | Conduit - Risers (2" & Larger) | 394200 | 374490 | 0 | 0 | 0 | 6570 | 6570 | 6570 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02220 | 3060 | Demolition/Temp Light & Power | 60000 | 51000 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02345 | 3061 | Firestopping | 6000 | 4500 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02225 | 3062 | Foundation Coring | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02265 | 3063 | Lighting Controls | 33600 | 0 | 0 | 0 | 0 | 11200 | 11200 | 11200 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02220 | 3064 | Lighting Remove & Re-install | 60480 | 0 | 0 | 0 | 0 | 20160 | 20160 | 20160 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02220 | 3065 | Lighting System Program & Energize | 6000 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02245 | 3066 | Mechanical Terminations(Dampers, Heaters, Motors) | 62400 | 28080 | 0 | 0 | 0 | 11440 | 11440 | 11440 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SURV-SGN-E-01000 | 3067 | Survey | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02460 | 3068 | Switches and Receptacles | 12000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02515 | 3069 | Switchgear & Panelboard Energization | 33000 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02405 | 3070 | Switchgear & Panelboard Installation | 396000 | 356400 | 11314.2857 | 11314.2857 | 11314.2857 | 1885.7143 | 1885.7143 | 1885.7143 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02405 | 3071 | Switchgear & Panelboard Terminations | 33000 | 0 | 20625 | 0 | 0 | 4125 | 4125 | 4125 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02530 | 3072 | Switchgear & Panelboard Testing | 33000 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02215 | 3073 | Fire Alarm Conduit | 16650 | 11655 | 0 | 0 | 0 | 1665 | 1665 | 1665 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02315 | 3074 | Fire Alarm Wiring | 13140 | 0 | 0 | 0 | 0 | 4380 | 4380 | 4380 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02315 | 3075 | Fire Alarm Devices | 24000 | 0 | 0 | 0 | 0 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02315 | 3076 | Fire Alarm Programming & Pretest | 3000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-02505 | 3077 | Fire Alarm FDNY Approval | 3000 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | EXISTING BUILDINGS | Interior | Existing Buildings | 0
SG5-01405 | 3078 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 17656 | 17656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 069 - SG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01480 | 3079 | BACKFILL FOR FLOOD BARRIER FOOTINGS AND FOR MASONRY FACADE - SG-5 | 7542 | 7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 069 - SG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG5-01480 | 3080 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - SG-5 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 069 - SG5 - Division 31 | 0% | MLJ | EXISTING BUILDINGS | Exterior | Existing Buildings | 0
SG6-01070 | 3081 | FORMWORK NEW BUILDING - SG-6 | 469701 | 469701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01175 | 3082 | SET ANCHOR BOLTS FOR STEEL COLUMNS - SG-6 | 5411 | 5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01040 | 3083 | POUR CONCRETE NEW BUILDINGS - SG-6 | 179646 | 179646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01135 | 3084 | FINISH SLABS - SG-6 | 10746 | 10746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01075 | 3085 | Footing/Pier | 69927 | 69927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01075 | 3086 | Grade Beams | 4634 | 4634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01130 | 3087 | First Floor Slab | 29856 | 29856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01130 | 3088 | Equipment Pads | 1690 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01035 | 3089 | First Floor Plumbing Shaft Slab | 1373 | 1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01035 | 3090 | Second Floor Plumbing Shaft Slab | 898 | 898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01035 | 3091 | Plumbing Shafts | 22737 | 22737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01155 | 3092 | Fuel Oil Tank Room | 11970 | 11970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01205 | 3093 | WWM-Slabs | 4173 | 4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 070 - SG6 - Division 3 | 0% | TONAGE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01230 | 3094 | 8" CMU (3 hour rated) | 349751 | 349751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01275 | 3095 | 4" CMU | 61023 | 61023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01275 | 3096 | Face Brick 3-5/8" | 158400 | 158400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01275 | 3097 | 3-1/8" Rigid insulation | 15840 | 15840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01250 | 3098 | Cast Stone with SS letters | 8521 | 6390.75 | 0 | 710.0833 | 710.0833 | 710.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | JMC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01230 | 3099 | Steel Channel | 18876 | 18876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01230 | 3100 | Cont. Shelf angle | 11616 | 11616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3101 | STEEL (MATERIAL ONLY) | 165824 | 165824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3102 | FABRICATION COSTS | 246972 | 246972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3103 | METAL DECK (BUY-OUT) | 14113 | 14113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3104 | ANCHORS & EMBEDS | 9410 | 9410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3105 | SURVEYING | 11762 | 11762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3106 | STEEL & DECK ERECTION | 576267 | 576267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3107 | BOLTS AND HARDWARE | 23522 | 23522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01105 | 3108 | TRUCKING | 11762 | 11762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01270 | 3109 | Dunnage Grating Galvanized | 60521 | 60521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01270 | 3110 | Dunnage Guard Rail | 28968 | 28968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01270 | 3111 | Dunnage Platform Stair with Guard Rail | 13035 | 13035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01290 | 3112 | Stair A: Ground to Roof Floor Stair and Landing with and Hand & Guard Rail | 136365 | 136365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01290 | 3113 | Stair B: Ground to 2nd Floor Stair and Landing with Hand & Guard Rail | 64143 | 64143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01295 | 3114 | 1st to 2nd Floor Ship Ladder with Cage and Platform | 27106 | 27106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01120 | 3115 | Egress Stair: Stair & Landing with Hand & Guard Rail | 64143 | 64143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3116 | Layout | 5109 | 5109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3117 | Loading | 18391 | 18391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3118 | Exterior Framing, Insulation & Drywall - Materials | 74880 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3119 | Exterior Framing- Labor | 87871 | 87871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01125 | 3120 | 3" RIGID INSULATION UNDER GRADE NEW BLDGS - SG-6 | 1444 | 1444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-02425 | 3121 | PENETRATION FIRESTOPPING NEW BLDG - SG-6 | 11505 | 11505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG5-01320 | 3122 | JOINT SEALANTS NEW BLDGS - S6 | 11505 | 5752.5 | 0 | 0 | 0 | 2876.25 | 2876.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01230 | 3123 | Air Film | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | FAXA | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01305 | 3124 | Insulation- Labor | 6422 | 6422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01025 | 3125 | Crystalline Waterproofing at plumbing shaft | 5486 | 5486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01072 | 3126 | Waterproofing at foundation | 10040 | 10040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | DSTAR | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3127 | Layout | 86622 | 86622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3128 | Framing | 196161 | 196161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3129 | Insulation | 35133 | 35133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01255 | 3130 | Cladding Install | 245934 | 221340.6 | 0 | 12296.7 | 12296.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01225 | 3131 | Fireproofing | 41800 | 41800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | SIG | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01265 | 3132 | P&I Cold Applied Roof Membrane | 102076 | 102076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01265 | 3133 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 123891 | 123891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01265 | 3134 | P&I Aluminum Coping | 8547 | 0 | 0 | 8547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01260 | 3135 | (1'4"WX8"H) S.S. FLOOD VENTS NEW BLDGS (153) - S6 | 12324 | 9859.2 | 0 | 0 | 0 | 1232.4 | 1232.4 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | MLJ | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01245 | 3136 | Doors, Frames & Hardware - Labor | 22798 | 22798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01317 | 3137 | Louvers Install | 61342 | 0 | 0 | 30671 | 30671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | NAVILLUS | NEW BUILDINGS | Structure | New Buildings | 0
08020 | 3138 | Furnish Doors | 33448 | 33448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01305 | 3139 | Sheathing & Drywall - Labor | 40634 | 40634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01245 | 3140 | Tape/ Spackle finishes | 13372 | 13372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01315 | 3141 | ACT ceilings - Materials | 1029 | 0 | 0 | 1029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01315 | 3142 | ACT ceilings - Labor | 4629 | 0 | 2314.5 | 2314.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01280 | 3143 | Direct Applied Stucco | 18722 | 0 | 9361 | 9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | NEW BUILDINGS | Structure | New Buildings | 0
SG6-01325 | 3144 | Painting SG-6 | 110000 | 55000 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | GG PAINT | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01310 | 3145 | Cermic Tile and Base - SG-6 | 7564 | 7564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | FLOORING | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01260 | 3146 | FIRE EXTINGUISHERS NEW BLDGS - SG-6 | 2931 | 0 | 732.75 | 732.75 | 732.75 | 366.375 | 366.375 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01260 | 3147 | TOILET ACCESSORIES NEW BLDGS - SG-6 | 2830 | 0 | 707.5 | 707.5 | 707.5 | 353.75 | 353.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3148 | Stair Identification Sign | 2750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3149 | Stairway Floor number and ID Sign | 2750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3150 | Room Sign | 2750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3151 | Exit Sign | 1100 | 0 | 0 | 0 | 366.6667 | 366.6667 | 366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3152 | Public Unisex Toilet Sign | 550 | 0 | 0 | 0 | 183.3333 | 183.3333 | 183.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-01330 | 3153 | Stairway Flood Access Door | 550 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 077 - SG6 - Division 10 | 0% | MLJ | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3154 | COMMON WORK RESULTS FOR PLUMBING | 5176 | 5176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3155 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3156 | ESCUTCHEONS FOR PLUMBING PIPING | 2178 | 2069.1 | 27.225 | 27.225 | 27.225 | 27.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3157 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 19800 | 18810 | 247.5 | 247.5 | 247.5 | 247.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3158 | HANGERS AND SUPPORTS | 21995 | 20895.25 | 274.9375 | 274.9375 | 274.9375 | 274.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3159 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2728 | 0 | 682 | 682 | 682 | 682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3160 | DOMESTIC WATER PIPING | 224153 | 212945.35 | 2801.9125 | 2801.9125 | 2801.9125 | 2801.9125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3161 | DOMESTIC WATER PIPING SPECIALTIES | 39863 | 37869.85 | 498.2875 | 498.2875 | 498.2875 | 498.2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3162 | DOMESTIC WATER PUMPING SYSTEMS | 82500 | 78375 | 1031.25 | 1031.25 | 1031.25 | 1031.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3163 | SANITARY WASTE PIPING | 118800 | 118800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3164 | SANITARY WASTE PIPING SPECIALTIES | 21998 | 21998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3165 | STORM DRAINAGE PIPING SPECIALTIES | 32997 | 32997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3166 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 16368 | 13094.4 | 818.4 | 818.4 | 818.4 | 818.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3167 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 240768 | 228729.6 | 3009.6 | 3009.6 | 3009.6 | 3009.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3168 | GAS SERVICE AND PIPING | 277970 | 266851.2 | 2779.7 | 2779.7 | 2779.7 | 2779.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3169 | PLUMBING FIXTURES | 14167 | 10625.25 | 885.4375 | 885.4375 | 885.4375 | 885.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03140 | 3170 | EMERGENCY PLUMBING FIXTURES | 5104 | 2552 | 638 | 638 | 638 | 638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3171 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 45430 | 45430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03105 | 3172 | Plumbing Pipe Insulation | 3032 | 3032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | TRISTAN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02140 | 3173 | Heat Trace | 5475 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGN-M-01005 | 3174 | Survey | 66000 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03112 | 3175 | Exhaust Fans: Furnish | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3176 | Exhaust Fans: Install | 23045 | 23045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 3177 | Steam Unit Heaters: Furnish | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3178 | Steam Unit Heaters: Install | 45650 | 45650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 3179 | Electric Unit Heaters: Furnish | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03032 | 3180 | Condensate Return Unit: Furnish | 15400 | 15400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3181 | Condensate Return Unit: Install | 45650 | 45650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3182 | Heating and Ventilation Unit: Furnish | 7150 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3183 | Heating and Ventilation Unit: Install | 33550 | 33550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3184 | Steam Traps: Furnish | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3185 | Steam Traps: Install | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3186 | Steam Separator: Furnish | 26400 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3187 | Steam Separator: Install | 195250 | 195250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3188 | Low Pressure Steam Boilers: Install | 107250 | 107250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 3189 | Boiler Feed Unit: Furnish | 38500 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 3190 | Boiler Feed Unit: Install | 52250 | 52250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 3191 | Fuel Oil Pump: Furnish | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03130 | 3192 | Fuel Oil Pump: Install | 52250 | 52250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03142 | 3193 | Fuel Oil Storage Tank: Furnish | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03130 | 3194 | Fuel Oil Storage Tank: Install | 52250 | 52250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03110 | 3195 | Rigging | 145750 | 145750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03107 | 3196 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 433895 | 433895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03107 | 3197 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 682000 | 682000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03207 | 3198 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 187000 | 187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03135 | 3199 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 181500 | 181500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03135 | 3200 | Mechanical Pipe: Hydrostatic Testing | 6105 | 6105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03207 | 3201 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 55000 | 53900 | 1064.5161 | 0 | 0 | 0 | 35.4839 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03110 | 3202 | HVAC Ductwork:Furnish and Install: Sheetmetal and RGDs | 110000 | 107800 | 2129.0323 | 0 | 0 | 0 | 70.9677 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03245 | 3203 | HVAC Ductwork:Testing & Balancing | 5500 | 0 | 106.4516 | 0 | 0 | 0 | 5393.5484 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3204 | Controls: Furnish and Install: Devices | 209000 | 198550 | 3483.3333 | 3483.3333 | 3483.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3205 | Controls: Furnish and Install: Controls Conduit | 93500 | 88825 | 1558.3333 | 1558.3333 | 1558.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3206 | Controls: Furnish and Install: Controls Wiring | 27500 | 26125 | 458.3333 | 458.3333 | 458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03120 | 3207 | Controls: Connect to Final Termination Points | 18700 | 12155 | 2181.6667 | 2181.6667 | 2181.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03510 | 3208 | Controls Testing | 14575 | 0 | 4858.3333 | 4858.3333 | 4858.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 3209 | Furnish and Install: Ductwork Insulation | 29700 | 0 | 11062.5688 | 0 | 18637.4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 3210 | Furnish and Install: Piping Insulation | 60500 | 48400 | 12100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG1-03040 | 3211 | Furnish and Install: Equipment Insulation | 29700 | 23760 | 5940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
OG8-03242 | 3212 | Furnish and Install: Chemical Feed Equipment | 10230 | 10230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-03142 | 3213 | Chemical Cleaning | 8250 | 0 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3214 | ATS Energization | 10950 | 0 | 0 | 0 | 0 | 3650 | 3650 | 3650 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3215 | ATS Installation | 153300 | 145635 | 0 | 0 | 0 | 7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3216 | ATS Terminations | 10950 | 10402.5 | 0 | 0 | 0 | 547.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02310 | 3217 | ATS Testing | 10950 | 5475 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02120 | 3218 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02410 | 3219 | Cabling - Risers & Feeders (2/0 & Larger) | 492750 | 468112.5 | 0 | 0 | 0 | 8212.5 | 8212.5 | 8212.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02110 | 3220 | Conduit - Branch Circuits (1 1/2" & Smaller) | 54750 | 52012.5 | 0 | 0 | 0 | 912.5 | 912.5 | 912.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02155 | 3221 | Conduit - In-Slab | 216810 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02210 | 3222 | Conduit - Risers (2" & Larger) | 295650 | 280867.5 | 0 | 0 | 0 | 4927.5 | 4927.5 | 4927.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02425 | 3223 | Firestopping | 5250 | 4987.5 | 0 | 0 | 0 | 87.5 | 87.5 | 87.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG6-01025 | 3224 | Generator Delivery | 52500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
P-SG6-01010 | 3225 | Generator Release | 315000 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02385 | 3226 | Generator Terminations | 52500 | 47250 | 0 | 0 | 0 | 1750 | 1750 | 1750 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02510 | 3227 | Generator Test | 52500 | 26250 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02160 | 3228 | Lighting Controls | 25200 | 22680 | 0 | 0 | 0 | 840 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02130 | 3229 | Lighting Install | 88830 | 84388.5 | 0 | 0 | 0 | 1480.5 | 1480.5 | 1480.5 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02130 | 3230 | Lighting Rough | 92637 | 92637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02130 | 3231 | Lighting System Program & Energize | 5475 | 0 | 0 | 0 | 0 | 1825 | 1825 | 1825 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02395 | 3232 | Lightning Protection | 21900 | 13140 | 0 | 0 | 0 | 2920 | 2920 | 2920 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SG6-02135 | 3233 | Mechanical Terminations(Dampers, Heaters, Motors) | 142350 | 128115 | 0 | 0 | 0 | 4745 | 4745 | 4745 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
SURV-SGN-E-01000 | 3234 | Survey | 54750 | 54750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | NEW BUILDINGS | Interior | New Buildings | 0
CO | CO-01 | Second floor Apartment Removals | 17585 | 17585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-02 | National Grid Additional Allowance | 199883 | 199883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-03 | SG6 Additional Strobe | 2486 | 2486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-04 | CO#2-GC - PCOCO 2 Site 8 Basement Deteriorated Slab Shoring | 39587 | 39587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-05 | First Floor Move | 61418 | 61418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-06 | Site 8 Electrical Hazards | 22438.52 | 22438.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-07 | PCO-4 Door Hardware Changes | 25825.5 | 25825.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-08 | PCO-7 Boiler Accessories Supply | 195313 | 195313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-09 | PCO-9 Irma Pagan Move | 2603 | 2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-10 | PCO-14 National Grid Gas Line Work | 21598 | 21598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-11 | PCO-15 Additional Windows | 7011 | 7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-12 | PCO 11 - Concrete Pads for Mechanical Equipment | 39740 | 39740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-13 | PCO 19 - Window Infill | 3598.42 | 3598.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-14 | PCO 64 - OG10 Additional 3-Way Switch | 2494.4 | 2494.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-15 | PCO-21 Site 8 Fire Stand Pipe | 81400.51 | 81400.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-16 | PCO 42 - Tank in OG8 | 22925.66 | 22925.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-17 | PCO 46 - Sanitary Venting | 74242.32 | 74242.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-18 | PCO 52 - Relocation of Playground OGE | 12810.32 | 12810.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-19 | PCO 53 - SG6 and OG8 Boiler Stack Support | 72889.74 | 72889.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-20 | PCO 54 - ACM Abatement Waterproofing | 377117 | 377117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-21 | PCO 66 - Electric Ductbank Conflict | 25899.61 | 25899.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-22 | PCO 85 - OG5 OG4 Tank Insulation | 133560 | 133560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-23 | PCO 62 - O'Dwyer Fence Install | 159967.11 | 159967.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-24 | PCO 76 - Additional Fire Extinguishers | 4609.81 | 4609.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-25 | PCO 77 - SGS Steam Pipe Abatement | 117169.94 | 117169.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-26 | PCO 63 Support for Concrete Encasement of Electrical Conduits | 194900.63 | 194900.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-27 | PCO 93 Roof Access and ATS Room Door Issue | 97988.19 | 97988.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-28 | PCO 100 Exterior Metal Panel Support OG8/OG9/OG10 | 158262.1 | 158262.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
CO | CO-29 | PCO 102 SGS Outage Temporary Lighting | 12743.73 | 12743.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Change Order |  | 0% | MLJ | Change Orders |  | Change Order | 0
|  |  | 188988067.51 | 133689925.23 | 6760911.375 | 7993164.5261 | 7381505.4665 | 8347308.2383 | 6805699.2392 | 4772404.6508 | 3617235.7104 | 2903196.7827 | 2466119.9313 | 1745487.0318 | 0 |  |  | 0% |  |  |  |  | 0

## Sub Cost Forecast
Schedule Act | Item # | Description | Cost | Current Commitment | Previous Total | January | February | March | April | May | June | July | August | September | October | Final Total | SOV Level 1 | SOV Level 2 | Percent Complete | Sub | Total>Commitment? | Category
SG1-01005 | 47 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01010 | 48 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 49 | Assumed Flooring Material (Slab Penetrations) | 3600 | 10800 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01020 | 50 | Pipe Insulation | 44100 | 132300 | 44100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01005 | 51 | Duct Seal | 14400 | 43200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 52 | Vinyl Membrane and Mastic | 12240 | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 53 | Caulk | 36750 | 110250 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01015 | 54 | Fibrous Slate | 4080 | 12240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01020 | 55 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01020 | 56 | Underground Utility Materials | 15600 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 002 - SG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-01820 | 82 | 6" vertically reinforced CMU | 179000 | 230912 | 170050 | 0 | 0 | 8950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG1-01830 | 83 | 2" Face brick | 195000 | 597520 | 58500 | 0 | 32634.8909 | 34621.703 | 34621.703 | 34621.703 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG1-01820 | 85 | Coping Stone C1/A-300 | 142000 | 13200 | 127800 | 0 | 0 | 4733.3333 | 4733.3333 | 4733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 004 - SG1 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05440 | 86 | MATERIAL AND FABRICATION | 5000 | 5824 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG1-01315 | 87 | INSTALLATION | 6000 | 6600 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG1-01860 | 88 | Temporary Aluminum Over Pass Stairs | 51996 | 57196 | 0 | 25998 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 005 - SG1 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG1-01330 | 96 | Doors, Frames & Hardware - Labor | 3000 | 6672 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 007 - SG1 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01325 | 98 | Layout | 3375 | 2829 | 3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01325 | 99 | Loading | 1875 | 3858 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01325 | 100 | Framing & Drywall - Materials | 4875 | 2829 | 0 | 1625 | 1625 | 1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01325 | 101 | Framing- Labor | 2250 | 4629 | 0 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01330 | 102 | Drywall - Labor | 2250 | 4629 | 0 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01330 | 103 | Tape/ Spackle finishes | 1500 | 3086 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-01855 | 104 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 008 - SG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG6-02150 | 110 | Switches and Receptacles | 10000 | 10950 | 9500 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02525 | 111 | Switchgear & Panelboard Energization | 17500 | 19163 | 8750 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02405 | 112 | Switchgear & Panelboard Installation | 210000 | 229950 | 199500 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02405 | 113 | Switchgear & Panelboard Terminations | 17500 | 19163 | 16625 | 0 | 0 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02530 | 114 | Switchgear & Panelboard Testing | 17500 | 19163 | 13125 | 0 | 0 | 0 | 1458.3333 | 1458.3333 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02025 | 115 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02110 | 116 | Fire Alarm Conduit | 62500 | 68438 | 59375 | 0 | 0 | 0 | 1041.6667 | 1041.6667 | 1041.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02365 | 117 | Fire Alarm Wiring | 60000 | 65700 | 57000 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02365 | 118 | Fire Alarm Devices | 85000 | 93075 | 80750 | 0 | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02365 | 119 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02505 | 121 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 081 - SG6 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-01230 | 140 | 8" CMU (3 hour rated) | 407500 | 171133 | 387125 | 20375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
SG7-01275 | 144 | Face Brick 3-5/8" | 225500 | 235521 | 180400 | 45100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
SG7-01250 | 146 | Cast Stone with SS letters | 6300.7 | 8521 | 2520.2726 | 0 | 1260.1425 | 1260.1425 | 1260.1425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 084 - SG7 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
SG7-01105 | 149 | STEEL (MATERIAL ONLY) | 152000 | 178532 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 150 | FABRICATION COSTS | 325000 | 303034 | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 151 | METAL DECK (BUY-OUT) | 13000 | 15270 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 152 | ANCHORS & EMBEDS | 8000 | 9398 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 154 | SURVEYING | 12000 | 14096 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 155 | STEEL & DECK ERECTION | 520000 | 610764 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 156 | BOLTS AND HARDWARE | 20000 | 23492 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01105 | 157 | TRUCKING | 12000 | 11746 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG7-01270 | 158 | Dunnage Grating Galvanized | 58687 | 64556 | 0 | 29343.5 | 29343.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01270 | 159 | Dunnage Guard Rail | 27650 | 30415 | 27650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01270 | 160 | Dunnage Stair and Guard Rail | 11850 | 13035 | 11850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01290 | 161 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 106861 | 128548 | 98548.0741 | 4156.463 | 4156.463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01295 | 162 | 1st to 2nd Floor Ship Ladder with Cages | 23409 | 25750 | 14045.4 | 7022.7 | 2340.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01295 | 163 | Bulkhead Ship Ladder to Roof at 2 Locations | 11257 | 12383 | 1125.7 | 5065.65 | 5065.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 085 - SG7 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG7-01305 | 165 | Layout | 8875 | 8028 | 0 | 0 | 0 | 1267.8571 | 7607.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01305 | 166 | Loading | 16125 | 15326 | 0 | 0 | 0 | 2104.2673 | 3156.4009 | 7242.8879 | 3621.444 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01305 | 167 | Exterior Framing, Insulation & Drywall - Materials | 61814 | 67511 | 61814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01305 | 168 | Exterior Framing- Labor | 58711 | 58049 | 0 | 0 | 0 | 8387.2857 | 10114.0416 | 26806.4485 | 13403.2242 | 0 | 0 | 0 | 0 | 0 | SG7 | 086 - SG7 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01305 | 173 | Insulation- Labor | 6375 | 7798 | 0 | 0 | 0 | 910.7143 | 5464.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01255 | 177 | Layout | 83212 | 87373 | 0 | 0 | 0 | 27737.3333 | 27737.3333 | 27737.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG7-01255 | 178 | Framing | 188663 | 198097 | 188663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG7-01255 | 179 | Insulation | 33790 | 35480 | 33790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG7-01255 | 180 | Cladding Install | 236533 | 248360 | 0 | 0 | 0 | 78844.3333 | 78844.3333 | 78844.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG7-01225 | 181 | Fireproofing | 38000 | 41800 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
SG7-01265 | 182 | P&I Cold Applied Roof Membrane | 96705 | 99622 | 0 | 0 | 96705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
SG7-01265 | 183 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 98847 | 101829 | 0 | 0 | 98847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
SG7-01265 | 184 | P&I Aluminum Coping | 7684 | 7458 | 0 | 0 | 7684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 087 - SG7 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
SG7-01245 | 187 | Doors, Frames & Hardware - Labor | 8125 | 18070 | 2031.25 | 6093.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01317 | 188 | Louvers Install | 30974 | 61948 | 0 | 0 | 0 | 10324.6667 | 10324.6667 | 10324.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 088 - SG7 - Division 8 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG7-01305 | 190 | Sheathing & Drywall - Labor | 24125 | 49634 | 0 | 0 | 0 | 3446.4286 | 9721.1589 | 7304.9417 | 3652.4708 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01245 | 191 | Tape/ Spackle finishes | 6875 | 14144 | 0 | 6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01315 | 192 | ACT ceilings - Materials | 1875 | 3858 | 0 | 0 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01315 | 193 | ACT ceilings - Labor | 6250 | 12788 | 0 | 0 | 0 | 0 | 977.4789 | 3515.0141 | 1757.507 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01280 | 194 | Direct Applied Stucco | 26750 | 53251 | 0 | 13375 | 13375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG7-01325 | 195 | Painting SG-7 | 55000 | 110000 | 0 | 0 | 0 | 0 | 0 | 17500 | 37500 | 0 | 0 | 0 | 0 | 0 | SG7 | 089 - SG7 - Division 9 | 0% | GG PAINT | 0 | NEW BUILDINGS
SG7-03105 | 206 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 2117.25 | 2587.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 207 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 2400 | 2290.9091 | 109.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 209 | ESCUTCHEONS FOR PLUMBING PIPING | 1980 | 2178 | 0 | 1890 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 210 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 20000 | 22000 | 0 | 19090.9091 | 909.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 211 | HANGERS AND SUPPORTS | 19680 | 21648 | 13776 | 5904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 212 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2480 | 2728 | 0 | 2367.2727 | 112.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 213 | DOMESTIC WATER PIPING | 232190 | 255409 | 104485.5 | 90909.0909 | 36795.4091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 214 | DOMESTIC WATER PIPING SPECIALTIES | 27440 | 30184 | 10976 | 16464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 215 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 82500 | 15000 | 27272.7273 | 32727.2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 216 | SANITARY WASTE PIPING | 94944 | 104439 | 71208 | 18181.7137 | 5554.2863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 217 | SANITARY WASTE PIPING SPECIALTIES | 18640 | 20504 | 17708 | 932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 218 | STORM DRAINAGE PIPING SPECIALTIES | 48640 | 53504 | 41344 | 7296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03140 | 220 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 19840 | 21824 | 0 | 6613.3333 | 13226.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03140 | 221 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 292804 | 322085 | 117121.6 | 18181.7843 | 0 | 68181.6912 | 68181.6912 | 14091.4889 | 7045.7445 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 222 | GAS SERVICE AND PIPING | 246950 | 271645 | 61737.5 | 90909.0909 | 0 | 13331.3636 | 26990.6818 | 26990.6818 | 26990.6818 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03140 | 223 | PLUMBING FIXTURES | 16720 | 18392 | 0 | 5573.3333 | 11146.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 224 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 71529 | 78682 | 71529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG7-03105 | 225 | Plumbing Pipe Insulation | 9800 | 2374 | 0 | 9354.5455 | 445.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | TRISTAN | 0 | NEW BUILDINGS
SG7-02145 | 226 | Heat Trace | 5000 | 5475 | 0 | 0 | 3333.3333 | 0 | 0 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 0 | SG7 | 091 - SG7 - Division 22 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-SGS-M-01005 | 227 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03112 | 228 | Exhaust Fans: Furnish | 6000 | 6600 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 229 | Exhaust Fans: Install | 17000 | 18700 | 12750 | 3642.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 231 | Electric Unit Heaters: Furnish | 4500 | 4950 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 232 | Steam Unit Heaters: Furnish | 3000 | 3300 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 233 | Steam Unit Heaters: Install | 29250 | 32175 | 0 | 0 | 0 | 13504.9945 | 15745.0055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 234 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 235 | Heating and Ventilation Unit: Install | 24250 | 26675 | 0 | 0 | 0 | 11196.4484 | 13053.5516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 236 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 237 | Condensate Return Unit: Install | 23250 | 25575 | 0 | 0 | 0 | 10734.7392 | 12515.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 238 | Steam Traps: Furnish | 1400 | 1540 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03142 | 239 | Steam Traps: Install | 13000 | 14300 | 0 | 0 | 0 | 6002.2198 | 6997.7802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 240 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 143150 | 157465 | 14315 | 0 | 0 | 66952.9534 | 57035.5699 | 4846.4767 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 242 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 247000 | 271700 | 0 | 0 | 0 | 115524.8305 | 98412.7542 | 24603.1886 | 8459.2267 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 243 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 80000 | 88000 | 0 | 0 | 0 | 37416.9492 | 31874.5763 | 7968.6441 | 2739.8305 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03135 | 244 | Mechanical Pipe: Hydrostatic Testing | 1850 | 2035 | 0 | 0 | 0 | 865.2669 | 737.0996 | 184.2749 | 63.3586 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03110 | 245 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 17500 | 19250 | 15750 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03110 | 246 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 35000 | 38500 | 31500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03145 | 247 | HVAC Ductwork: Testing & Balancing | 2000 | 2200 | 0 | 0 | 0 | 288.9908 | 0 | 0 | 1711.0092 | 0 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 248 | Controls: Furnish and Install: Devices | 100000 | 110000 | 15000 | 0 | 0 | 0 | 0 | 36315.7895 | 48245.614 | 438.5965 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 249 | Controls: Furnish and Install: Controls Conduit | 45000 | 49500 | 5400 | 0 | 0 | 0 | 0 | 16342.1053 | 21710.5263 | 1547.3684 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 250 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 0 | 0 | 3631.5789 | 4824.5614 | 1543.8596 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 251 | Controls: Connect to Final Termination Points | 10000 | 11000 | 0 | 0 | 0 | 0 | 0 | 3631.5789 | 4824.5614 | 1543.8596 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-03510 | 253 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 0 | 0 | 2178.9474 | 2894.7368 | 926.3158 | 0 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 254 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 3300 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 255 | Insulation: Furnish and Install: Piping Insulation | 27500 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 5500 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 256 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 3300 | 0 | 0 | 0 | SG7 | 092 - SG7 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG7-02280 | 257 | ATS Energization | 22500 | 24638 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 2812.5 | 2812.5 | 2812.5 | 2812.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02280 | 258 | ATS Installation | 315000 | 344925 | 157500 | 0 | 78750 | 0 | 0 | 0 | 0 | 19687.5 | 19687.5 | 19687.5 | 19687.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02280 | 259 | ATS Terminations | 22500 | 24638 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 2812.5 | 2812.5 | 2812.5 | 2812.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02280 | 260 | ATS Testing | 22500 | 24638 | 0 | 0 | 11250 | 0 | 0 | 0 | 0 | 2812.5 | 2812.5 | 2812.5 | 2812.5 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02125 | 261 | Cabling - Interior Branch (1/0 & Smaller) | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SGS-02125 | 262 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 0 | 0 | 0 | 0 | 501428.5714 | 0 | 0 | 9642.8571 | 9642.8571 | 9642.8571 | 9642.8571 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02115 | 264 | Conduit - Branch Circuits (1 1/2" & Smaller) | 112500 | 123188 | 39375 | 0 | 0 | 0 | 0 | 0 | 0 | 18281.25 | 18281.25 | 18281.25 | 18281.25 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02105 | 265 | Conduit - In-Slab | 148500 | 162608 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02010 | 266 | Conduit - Risers (2" & Larger) | 540000 | 591300 | 432000 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02475 | 267 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02010 | 268 | Foundation Coring | 10000 | 10500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-SG7-01040 | 269 | Generator Delivery | 75000 | 78750 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 9375 | 9375 | 9375 | 9375 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-SG7-01030 | 270 | Generator Release | 450000 | 472500 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02415 | 271 | Generator Terminations | 75000 | 78750 | 0 | 0 | 0 | 69642.8571 | 0 | 0 | 0 | 1339.2857 | 1339.2857 | 1339.2857 | 1339.2857 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02615 | 272 | Generator Test | 75000 | 78750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | 18750 | 18750 | 18750 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02150 | 273 | Lighting Controls | 11000 | 11550 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 1375 | 1375 | 1375 | 1375 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02135 | 275 | Lighting Install | 75000 | 82125 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 9375 | 9375 | 9375 | 9375 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02135 | 276 | Lighting Rough | 75000 | 82125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18750 | 18750 | 18750 | 18750 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02135 | 277 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02425 | 278 | Lightning Protection | 20000 | 21900 | 10000 | 0 | 0 | 0 | 8571.4286 | 0 | 0 | 357.1429 | 357.1429 | 357.1429 | 357.1429 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02140 | 279 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 0 | 0 | 49714.2857 | 0 | 0 | 0 | 0 | 2071.4286 | 2071.4286 | 2071.4286 | 2071.4286 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-SGS-E-01030 | 280 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02160 | 281 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02655 | 282 | Switchgear & Panelboard Energization | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 11250 | 11250 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02330 | 283 | Switchgear & Panelboard Installation | 540000 | 591300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 135000 | 135000 | 135000 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02330 | 284 | Switchgear & Panelboard Terminations | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 11250 | 11250 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02650 | 286 | Switchgear & Panelboard Testing | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11250 | 11250 | 11250 | 11250 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02005 | 287 | Temp Light & Power | 50000 | 54750 | 32500 | 0 | 0 | 0 | 0 | 0 | 0 | 4375 | 4375 | 4375 | 4375 | 0 | SG7 | 093 - SG7 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02115 | 288 | Fire Alarm Conduit | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02250 | 289 | Fire Alarm Wiring | 30000 | 32850 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 3750 | 3750 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02250 | 290 | Fire Alarm Devices | 49000 | 53655 | 24500 | 12250 | 0 | 0 | 0 | 0 | 0 | 3062.5 | 3062.5 | 3062.5 | 3062.5 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02250 | 291 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 312.5 | 312.5 | 312.5 | 312.5 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG7-02625 | 292 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 625 | 625 | 625 | 0 | SG7 | 094 - SG7 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SGN-01155 | 323 | Manhole Installation | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SGN-02215 | 324 | Site Lighting - Cable | 50000 | 54750 | 5000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SGN-02210 | 325 | Site Lighting - Conduit | 60000 | 65700 | 57000 | 1285.7143 | 1285.7143 | 428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SGN-02220 | 326 | Site Lighting - Fixtures | 50600 | 55407 | 0 | 0 | 0 | 0 | 0 | 16866.6667 | 16866.6667 | 16866.6667 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SURV-SGN-E-01000 | 327 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SGN-02125 | 328 | Underground Electric Service - Cable | 750000 | 821250 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SGN-01155 | 330 | Underground Electric Service - Conduit | 600000 | 657000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 099 - SGN - Division 26 | 0% | FIVE STAR | 0 | SITE
SG1-03005 | 340 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 10515.35 | 0 | 0 | 0 | 618.55 | 618.55 | 618.55 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGN-01640 | 345 | 4' Steel Bar Fence with Double Gates | 79007.7519 | 88000 | 0 | 0 | 0 | 0 | 67720.9302 | 11286.8217 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | 0 | SITE
SGN-01645 | 346 | 6' Chain Link Fence | 11357.3643 | 12650 | 0 | 0 | 0 | 0 | 0 | 11357.3643 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ATLAS | 0 | SITE
SGN-01610 | 348 | 4" CONCRETE | 65000 | 100100 | 0 | 0 | 32500 | 27857.1429 | 4642.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01610 | 349 | 7" CONCRETE RAMP | 2000 | 3080 | 0 | 0 | 1000 | 857.1429 | 142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01610 | 350 | 5" POROUS CONCRETE | 300000 | 462000 | 75000 | 0 | 112500 | 96428.5714 | 16071.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SG1-03005 | 351 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGN-01630 | 352 | 5" COLOR CONCRETE | 50000 | 77000 | 30000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01605 | 353 | CONCRETE CURB | 12000 | 18480 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01605 | 354 | SFC -STELL FACING CURB | 12000 | 18480 | 0 | 8571.4286 | 2857.1429 | 571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | JMC | 0 | SITE
SGN-01680 | 356 | Deciduous Trees | 14175.0087 | 14884 | 0 | 0 | 0 | 0 | 14175.0087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01680 | 357 | Evergreen Trees | 3374.6826 | 3544 | 0 | 0 | 0 | 0 | 3374.6826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01680 | 358 | Deciduous Shrubs | 2800 | 2940 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01680 | 359 | Evergreen Shrubs | 990.2344 | 1040 | 0 | 0 | 0 | 0 | 990.2344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01680 | 360 | Perennials | 7796.0859 | 8080 | 0 | 0 | 0 | 0 | 7796.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01675 | 361 | Grasses | 17652.3627 | 18295 | 0 | 0 | 0 | 8826.1814 | 8826.1814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SG1-03005 | 362 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 747 | 0 | 0 | 0 | 0 | 166 | 83 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGN-01025 | 363 | Tree Removal | 6566.8979 | 41580 | 6566.8979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01675 | 364 | Lawn Seeding (not including topsoil) | 17277.4815 | 14810 | 8638.7407 | 0 | 0 | 4319.3704 | 4319.3704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01025 | 365 | Soil Erosion Mat | 3189.4866 | 2791 | 2707.921 | 0 | 0 | 240.7828 | 240.7828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01675 | 366 | Topsoil Stockpile/Spread | 97333.6079 | 101317 | 63266.8451 | 0 | 0 | 17033.3814 | 17033.3814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01675 | 367 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 101 - SGN - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01110 | 370 | INSTALL HW, CW PIPE - SGN | 183333.34 | 403279 | 183333.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | WELKIN | 0 | SITE
SGN-01130 | 372 | INSTALL CONDENSATE AND STEAM PIPE - SGN | 130000 | 308238 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGN | 102 - SGN - Division 33 | 0% | WELKIN | 0 | SITE
SG1-03005 | 373 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3000 | 3300 | 2250 | 0 | 0 | 0 | 0 | 500 | 250 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03005 | 384 | HANGERS AND SUPPORTS | 10477.5 | 11526 | 8905.875 | 0 | 0 | 0 | 0 | 1047.75 | 523.875 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03005 | 395 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 0 | 0 | 0 | 1330 | 665 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGS-02010 | 398 | Manhole Work | 50000 | 54750 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SGS-02215 | 399 | Site Lighting - Cable | 45000 | 49275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SGS-02210 | 400 | Site Lighting - Conduit | 60000 | 65700 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SGS-02220 | 401 | Site Lighting - Fixtures | 57500 | 62963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19166.6667 | 19166.6667 | 19166.6667 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SURV-SGS-E-01030 | 402 | Survey | 64000 | 70080 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SGS-02135 | 403 | Underground Electric Service - Cable | 750000 | 821250 | 0 | 0 | 0 | 187500 | 187500 | 187500 | 187500 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SGS-01155 | 404 | Underground Electric Service - Conduit | 600000 | 657000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 105 - SGS - Division 26 | 0% | FIVE STAR | 0 | SITE
SG1-03005 | 406 | DOMESTIC WATER PIPING | 115200 | 126720 | 86400 | 0 | 0 | 0 | 0 | 19200 | 9600 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03005 | 417 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 11100 | 0 | 0 | 0 | 0 | 2466.6667 | 1233.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGS-01745 | 421 | Ametco Fence | 126166.6667 | 138050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63083.3333 | 63083.3333 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ATLAS | 0 | SITE
SGS-01710 | 422 | 4" CONCRETE | 65000 | 71500 | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29250 | 19500 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01710 | 423 | 5"POROUS CONCRETE | 424200 | 466620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254520 | 169680 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01730 | 424 | 5" COLOR CONCRETE | 140000 | 154000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01705 | 425 | CONCRETE CURB | 35000 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21666.6667 | 11666.6667 | 1666.6667 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01705 | 426 | SFC -STELL FACING CURB | 12000 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7428.5714 | 4000 | 571.4286 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | JMC | 0 | SITE
SGS-01760 | 427 | Deciduous Trees | 26325.2883 | 27642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13162.6442 | 13162.6442 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SG1-03005 | 428 | SANITARY WASTE PIPING | 108000 | 118800 | 91800 | 0 | 0 | 0 | 0 | 10800 | 5400 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGS-01760 | 429 | Evergreen Trees | 2025.3809 | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6904 | 1012.6904 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01760 | 430 | Deciduous Shrubs | 1400 | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01760 | 431 | Perennials | 4273.3743 | 4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2136.6871 | 2136.6871 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01755 | 432 | Grasses | 7699.6914 | 7980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3849.8457 | 3849.8457 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01025 | 433 | Tree Removal | 7619.6863 | 48246 | 6987.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631.7362 | 0 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01755 | 434 | Lawn Seeding (not including topsoil) | 16346.5274 | 14012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8173.2637 | 8173.2637 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01755 | 435 | Topsoil Stockpile/Spread | 92388.968 | 96170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46194.484 | 46194.484 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01755 | 436 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 0 | SGS | 107 - SGS - Division 32 | 0% | ASPEN | 0 | SITE
SG1-03005 | 439 | SANITARY WASTE PIPING SPECIALTIES | 27336 | 30070 | 24602.4 | 0 | 0 | 0 | 0 | 1822.4 | 911.2 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SGS-01355 | 440 | INSTALL HW, CW PIPE - SGS | 293333.33 | 504915 | 293333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | WELKIN | 0 | SITE
SGS-01330 | 442 | INSTALL CONDENSATE AND STEAM PIPE - SGS | 173333.34 | 516372 | 173333.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SGS | 108 - SGS - Division 33 | 0% | WELKIN | 0 | SITE
SG1-03005 | 450 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 27000 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-01005 | 452 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01010 | 453 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01015 | 454 | Assumed Flooring Material (Slab Penetrations) | 20400 | 61200 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 455 | Pipe Insulation | 50400 | 151200 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 456 | Tank Insulation | 3250 | 9750 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01015 | 457 | Fireproofing | 57040 | 171120 | 57040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01015 | 458 | Fibrous Slate | 3060 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 459 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-01020 | 460 | Underground Utility Materials | 3848 | 11544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 109 - OG1 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-03030 | 461 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 230000 | 253000 | 218500 | 0 | 0 | 0 | 3833.3333 | 3833.3333 | 3833.3333 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03005 | 472 | GAS SERVICE AND PIPING | 1920 | 2112 | 0 | 0 | 0 | 0 | 0 | 1280 | 640 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03005 | 483 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03005 | 494 | Plumbing Pipe Insulation | 21600 | 34034 | 0 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG1-01830 | 502 | 2" Face brick | 98000 | 153384 | 88200 | 0 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG1-01820 | 503 | 6" vertically reinforced CMU | 58000 | 38368 | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG1-02015 | 505 | Heat Trace | 5000 | 5475 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 011 - SG1 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-01820 | 506 | Coping stone C1/A-300 | 56000 | 24909 | 42000 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 111 - OG1 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05230 | 507 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG1-01315 | 508 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG1-01860 | 509 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 112 - OG1 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SURV-SGS-M-01005 | 516 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-01330 | 517 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 114 - OG1 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01325 | 519 | Layout | 2500 | 5143 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01325 | 520 | Loading | 3625 | 7458 | 3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01325 | 521 | Framing & Drywall - Materials | 7875 | 12087 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01325 | 522 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01330 | 523 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01330 | 524 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-01855 | 525 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 115 - OG1 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-03112 | 527 | Exhaust Fans: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03112 | 538 | Exhaust Fans: Install | 4150 | 4565 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 549 | Steam Unit Heaters: Furnish | 3000 | 3300 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03005 | 554 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 1030.9167 | 1030.9167 | 1030.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 555 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 500 | 550 | 450 | 16.6667 | 16.6667 | 16.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 556 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 557 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2200 | 2420 | 1760 | 146.6667 | 146.6667 | 146.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 558 | HANGERS AND SUPPORTS | 10500.1 | 11551 | 7875.075 | 875.0083 | 875.0083 | 875.0083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 559 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-03032 | 560 | Steam Unit Heaters: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03005 | 561 | DOMESTIC WATER PIPING | 98200 | 108020 | 73650 | 8183.3333 | 8183.3333 | 8183.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 562 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 13079.25 | 1453.25 | 1453.25 | 1453.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 563 | SANITARY WASTE PIPING | 86520 | 95172 | 77868 | 2884 | 2884 | 2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 564 | SANITARY WASTE PIPING SPECIALTIES | 31080 | 34188 | 29526 | 518 | 518 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 565 | STORM DRAINAGE PIPING SPECIALTIES | 31080 | 34188 | 15540 | 5180 | 5180 | 5180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03030 | 566 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 170000 | 187000 | 127500 | 14875 | 0 | 0 | 9208.3333 | 9208.3333 | 9208.3333 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 567 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03005 | 568 | Plumbing Pipe Insulation | 27600 | 41899 | 24840 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG1-02040 | 569 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG1 | 118 - OG1 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGE-M-01005 | 570 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 571 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 572 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 573 | Exhaust Fans: Install | 7600 | 8360 | 0 | 3800 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 574 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 575 | Steam Unit Heaters: Install | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 576 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 577 | Condensate Return Unit: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 578 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 579 | Heating and Ventilation Unit: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03015 | 580 | Steam Traps: Furnish | 1800 | 1980 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03015 | 581 | Steam Traps: Install | 13000 | 14300 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03032 | 582 | Condensate Return Unit: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 583 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 584 | Vacuum Pump Unit: Install | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 585 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 81000 | 89100 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 586 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 110000 | 121000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 587 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03025 | 588 | Mechanical Pipe: Hydrostatic Testing | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03107 | 589 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 590 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03135 | 591 | HVAC Ductwork: Testing & Balancing | 1000 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 592 | Controls: Furnish and Install: Devices | 70000 | 77000 | 64400 | 5414.0625 | 185.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03112 | 593 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 594 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 595 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 7500 | 773.4375 | 132.8125 | 0 | 0 | 1593.75 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 596 | Controls: Connect to Final Termination Points | 7000 | 7700 | 3500 | 541.4062 | 92.9688 | 0 | 0 | 2865.625 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03025 | 597 | Controls: Controls Testing | 6000 | 6600 | 0 | 464.0625 | 79.6875 | 0 | 0 | 5456.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 598 | Insulation: Furnish and Install: Ductwork Insulation | 9000 | 9900 | 0 | 7200 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 599 | Insulation: Furnish and Install: Piping Insulation | 16000 | 17600 | 2400 | 12800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 600 | Insulation: Furnish and Install: Equipment Insulation | 9000 | 9900 | 1350.9091 | 7200 | 449.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 119 - OG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-02210 | 601 | ATS Energization | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02210 | 602 | ATS Installation | 175000 | 191625 | 157500 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02210 | 603 | ATS Terminations | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-03112 | 604 | Heating and Ventilation Unit: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-02210 | 605 | ATS Testing | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02010 | 606 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02035 | 607 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG10-02395 | 608 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 270000 | 0 | 0 | 135000 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02015 | 609 | Conduit - Branch Circuits (1 1/2" & Smaller) | 225000 | 246375 | 168750 | 0 | 0 | 0 | 0 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02125 | 610 | Conduit - Risers (2" & Larger) | 540000 | 591300 | 513000 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02020 | 611 | Demolition/Temp Light & Power | 50000 | 54750 | 45000 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02145 | 612 | Firestopping | 5000 | 5250 | 0 | 4375 | 0 | 0 | 0 | 208.3333 | 208.3333 | 208.3333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02025 | 613 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02065 | 614 | Lighting Controls | 24000 | 25200 | 12000 | 10500 | 0 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-03015 | 615 | Steam Traps: Furnish | 1600 | 1760 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-02120 | 616 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 30857.1429 | 0 | 0 | 0 | 1714.2857 | 1714.2857 | 1714.2857 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG10-02160 | 617 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02070 | 618 | Mechanical Terminations(Dampers, Heaters, Motors) | 60000 | 65700 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGE-01020 | 619 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02250 | 620 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02515 | 621 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02215 | 622 | Switchgear & Panelboard Installation | 330000 | 361350 | 297000 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02265 | 623 | Switchgear & Panelboard Terminations | 27500 | 30113 | 6875 | 20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02510 | 624 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 0 | OG1 | 120 - OG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02015 | 625 | Fire Alarm Conduit | 20000 | 21900 | 0 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-03015 | 626 | Steam Traps: Install | 12000 | 13200 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-02130 | 627 | Fire Alarm Wiring | 18000 | 19710 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02115 | 628 | Fire Alarm Devices | 22000 | 24090 | 11000 | 0 | 0 | 0 | 0 | 3666.6667 | 3666.6667 | 3666.6667 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02535 | 629 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-02535 | 630 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG1 | 121 - OG1 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-01005 | 634 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 5000 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01010 | 635 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01015 | 636 | Assumed Flooring Material (Slab Penetrations) | 19200 | 57600 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-03032 | 637 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-01020 | 638 | Pipe Insulation | 37800 | 113400 | 37800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01015 | 639 | Fibrous Slate | 3060 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01020 | 640 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG2-01020 | 641 | Underground Utility Materials | 3848 | 11544 | 3848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 123 - OG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-03032 | 648 | Vacuum Pump Unit: Install | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03107 | 659 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 80625 | 88688 | 80625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03007 | 670 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 115000 | 126500 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03007 | 681 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 41000 | 45100 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-01820 | 684 | 6" vertically reinforced CMU | 38000 | 38368 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG2-01830 | 685 | 2" Face brick | 95000 | 153384 | 90250 | 0 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG2-01820 | 687 | Coping stone C1/A-300 | 45000 | 25245 | 38250 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 125 - OG2 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05080 | 688 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG2-01315 | 689 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG2-01860 | 690 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 126 - OG2 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG1-03025 | 692 | Mechanical Pipe: Hydrostatic Testing | 1375 | 1513 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-01330 | 698 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 128 - OG2 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
OG2-01325 | 700 | Layout | 2500 | 5143 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG2-01325 | 701 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG2-01325 | 702 | Framing & Drywall - Materials | 7875 | 12087 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-03107 | 703 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-01325 | 704 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG2-01330 | 705 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG2-01330 | 706 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG2-01855 | 707 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 129 - OG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG1-03110 | 714 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03310 | 725 | HVAC Ductwork: Testing & Balancing | 1000 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03005 | 735 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 7422.6 | 0 | 4948.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03120 | 736 | Controls: Furnish and Install: Devices | 65000 | 71500 | 61750 | 0 | 0 | 1083.3333 | 1083.3333 | 1083.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03005 | 737 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 500 | 550 | 450 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 738 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 739 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3399 | 3739 | 2209.35 | 0 | 1189.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 740 | HANGERS AND SUPPORTS | 10500.1 | 11551 | 7875.075 | 0 | 2625.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 741 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 742 | DOMESTIC WATER PIPING | 103400 | 113740 | 77550 | 0 | 25850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 743 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 13079.25 | 0 | 4359.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 744 | SANITARY WASTE PIPING | 89300 | 98230 | 71440 | 0 | 17860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 745 | SANITARY WASTE PIPING SPECIALTIES | 27330 | 30063 | 24597 | 0 | 2733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 746 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03120 | 747 | Controls: Furnish and Install: Controls Conduit | 30000 | 33000 | 28500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03030 | 748 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 240000 | 264000 | 204000 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 749 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG2-03005 | 750 | Plumbing Pipe Insulation | 16350 | 28886 | 14715 | 817.5 | 817.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG2-02035 | 751 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG2 | 132 - OG2 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGW-M-01005 | 752 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 753 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03112 | 754 | Exhaust Fans: Install | 8100 | 8910 | 0 | 2025 | 2025 | 2025 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 755 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03032 | 756 | Steam Unit Heaters: Install | 9500 | 10450 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 757 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 758 | Controls: Furnish and Install: Controls Wiring | 9000 | 9900 | 8550 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03032 | 759 | Condensate Return Unit: Install | 15500 | 17050 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03112 | 760 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03112 | 761 | Heating and Ventilation Unit: Install | 16500 | 18150 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03015 | 762 | Steam Traps: Furnish | 1600 | 1760 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03015 | 763 | Steam Traps: Install | 11000 | 12100 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 764 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03032 | 765 | Vacuum Pump Unit: Install | 18500 | 20350 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03107 | 766 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 78225 | 86048 | 78225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03007 | 767 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 105500 | 116050 | 105500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03007 | 768 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 31000 | 34100 | 31000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 769 | Controls: Connect to Final Termination Points | 6000 | 6600 | 5400 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03025 | 770 | Mechanical Pipe: Hydrostatic Testing | 2775 | 3053 | 2775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 771 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 38500 | 34300 | 674.3119 | 0 | 0 | 0 | 0 | 25.6881 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 772 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 70000 | 77000 | 68600 | 1348.6239 | 0 | 0 | 0 | 0 | 51.3761 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03135 | 773 | HVAC Ductwork: Testing & Balancing | 4000 | 4400 | 0 | 77.0642 | 0 | 0 | 0 | 0 | 3922.9358 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 774 | Controls: Furnish and Install: Devices | 70000 | 77000 | 66500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 775 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 776 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 7500 | 0 | 1417.9104 | 0 | 1082.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 777 | Controls: Connect to Final Termination Points | 8000 | 8800 | 4000 | 0 | 1134.3284 | 0 | 2865.6716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-03025 | 778 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 850.7463 | 0 | 5149.2537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 779 | Insulation: Furnish and Install: Ductwork Insulation | 9000 | 9900 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-03310 | 780 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 781 | Insulation: Furnish and Install: Piping Insulation | 16000 | 17600 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 782 | Insulation: Furnish and Install: Equipment Insulation | 9000 | 9900 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 133 - OG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-02210 | 783 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02210 | 784 | ATS Installation | 140000 | 153300 | 126000 | 0 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02210 | 785 | ATS Terminations | 10000 | 10950 | 5000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02210 | 786 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02010 | 787 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 17500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02025 | 788 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OGW-02115 | 789 | Cabling - Risers & Feeders (2/0 & Larger) | 360000 | 394200 | 270000 | 51428.5714 | 38571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02020 | 790 | Conduit - Branch Circuits (1 1/2" & Smaller) | 212500 | 232688 | 180625 | 0 | 0 | 0 | 0 | 10625 | 10625 | 10625 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-03040 | 791 | Insulation: Furnish and Install: Ductwork Insulation | 9000 | 9900 | 0 | 0 | 4500 | 2700 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-02130 | 792 | Conduit - Risers (2" & Larger) | 360000 | 394200 | 342000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02015 | 793 | Demolition/Temp Light & Power | 50000 | 54750 | 37500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02145 | 794 | Firestopping | 5000 | 5250 | 2500 | 2187.5 | 0 | 0 | 0 | 104.1667 | 104.1667 | 104.1667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02030 | 795 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02240 | 796 | Lighting Controls | 31000 | 32550 | 15500 | 0 | 0 | 0 | 0 | 5166.6667 | 5166.6667 | 5166.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02015 | 797 | Lighting Remove & Re-install | 36900 | 40406 | 0 | 0 | 0 | 0 | 0 | 12300 | 12300 | 12300 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02015 | 798 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02070 | 799 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 0 | 0 | 0 | 0 | 0 | 19333.3333 | 19333.3333 | 19333.3333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGW-E-01015 | 800 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02245 | 801 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-03040 | 802 | Insulation: Furnish and Install: Piping Insulation | 16000 | 17600 | 0 | 0 | 8000 | 4800 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG2-02515 | 803 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02260 | 804 | Switchgear & Panelboard Installation | 330000 | 361350 | 313500 | 14142.8571 | 2357.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02260 | 805 | Switchgear & Panelboard Terminations | 27500 | 30113 | 6875 | 23571.4286 | 0 | 0 | 0 | -982.1429 | -982.1429 | -982.1429 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02510 | 806 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 0 | OG2 | 134 - OG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02020 | 807 | Fire Alarm Conduit | 20000 | 21900 | 15000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02115 | 808 | Fire Alarm Wiring | 15000 | 16425 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02115 | 809 | Fire Alarm Devices | 21000 | 22995 | 10500 | 0 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02115 | 810 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG2-02535 | 811 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG2 | 135 - OG2 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-03040 | 813 | Insulation: Furnish and Install: Equipment Insulation | 9000 | 9900 | 0 | 0 | 4500 | 2700 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 012 - SG1 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-01005 | 816 | Gaskets | 26250 | 78750 | 0 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01010 | 817 | Wire Insulation | 12500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01015 | 818 | Assumed Flooring Material (Slab Penetrations) | 15600 | 46800 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01005 | 819 | Duct Seal | 1200 | 3600 | 0 | 0 | 0 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01015 | 820 | Fibrous Slate | 3060 | 9180 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01020 | 821 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG3-01020 | 822 | Underground Utility Materials | 3796 | 11388 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 137 - OG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG1-02010 | 824 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 18750 | 3125 | 3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02065 | 835 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02130 | 846 | Cabling - Risers & Feeders (2/0 & Larger) | 270000 | 295650 | 0 | 0 | 0 | 0 | 9132.4201 | 9132.4201 | 9132.4201 | 60650.6849 | 60650.6849 | 60650.6849 | 60650.6849 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02035 | 857 | Conduit - Branch Circuits (1 1/2" & Smaller) | 225000 | 246375 | 22500 | 36529.6804 | 18409.0909 | 0 | 0 | 0 | 0 | 36890.3072 | 36890.3072 | 36890.3072 | 36890.3072 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-01820 | 863 | 6" vertically reinforced CMU | 60000 | 38368 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG3-01830 | 864 | 2" Face brick | 100000 | 153384 | 90000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG3-01820 | 866 | Coping stone C1/A-300 | 57000 | 25245 | 42750 | 0 | 0 | 4750 | 4750 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 139 - OG3 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05110 | 867 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG1-02030 | 868 | Conduit - Risers (2" & Larger) | 270000 | 295650 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 60750 | 60750 | 60750 | 60750 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-01315 | 869 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG3-01860 | 870 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 140 - OG3 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG3-01330 | 877 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 142 - OG3 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-02025 | 879 | Demolition/Temp Light & Power | 50000 | 54750 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-01325 | 880 | Layout | 2625 | 5401 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG3-01325 | 881 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG3-01325 | 882 | Framing & Drywall - Materials | 11250 | 11829 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG3-01325 | 883 | Framing- Labor | 6625 | 13629 | 6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG3-01330 | 884 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG3-01330 | 885 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG3-01855 | 886 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 143 - OG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG1-02120 | 890 | Firestopping | 5000 | 5250 | 0 | 4375 | 0 | 0 | 0 | 0 | 0 | 156.25 | 156.25 | 156.25 | 156.25 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02030 | 901 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02115 | 912 | Lighting Controls | 25000 | 26250 | 12500 | 3571.4286 | 0 | 0 | 0 | 0 | 0 | 2232.1429 | 2232.1429 | 2232.1429 | 2232.1429 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-03005 | 915 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 7422.6 | 0 | 4948.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 916 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 714 | 786 | 499.8 | 0 | 214.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 917 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 300 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 918 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2397 | 2637 | 1438.2 | 0 | 958.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 919 | HANGERS AND SUPPORTS | 10477.5 | 11526 | 8905.875 | 0 | 1571.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 920 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 921 | DOMESTIC WATER PIPING | 117070 | 128777 | 99509.5 | 0 | 17560.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 922 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 16567.05 | 0 | 871.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG1-02025 | 923 | Lighting Remove & Re-install | 25200 | 27972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 6300 | 6300 | 6300 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-03005 | 924 | SANITARY WASTE PIPING | 133651 | 147017 | 106920.8 | 0 | 0 | 13365.1 | 13365.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 925 | SANITARY WASTE PIPING SPECIALTIES | 30720 | 33792 | 27648 | 0 | 3072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 926 | STORM DRAINAGE PIPING SPECIALTIES | 30720 | 33792 | 15360 | 0 | 15360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03030 | 927 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 240000 | 264000 | 204000 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 928 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 8470 | 9317 | 8470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG3-03005 | 929 | Plumbing Pipe Insulation | 30350 | 35464 | 7587.5 | 0 | 11381.25 | 11381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG3-02030 | 930 | Heat Trace | 5000 | 5475 | 0 | 4000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | 0 | 0 | OG3 | 146 - OG3 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGW-M-01005 | 931 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 932 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03112 | 933 | Exhaust Fans: Install | 13600 | 14960 | 6800 | 297.0736 | 6502.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-02025 | 934 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-03032 | 935 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03032 | 936 | Steam Unit Heaters: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 937 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03032 | 938 | Condensate Return Unit: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03112 | 939 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03112 | 940 | Heating and Ventilation Unit: Install | 22000 | 24200 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03015 | 941 | Steam Traps: Furnish | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03015 | 942 | Steam Traps: Install | 22750 | 25025 | 22750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 943 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03032 | 944 | Vacuum Pump Unit: Install | 24000 | 26400 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG1-02040 | 945 | Mechanical Terminations(Dampers, Heaters, Motors) | 36000 | 39420 | 0 | 0 | 30857.1429 | 0 | 0 | 0 | 0 | 1285.7143 | 1285.7143 | 1285.7143 | 1285.7143 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-03007 | 946 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 300950 | 331045 | 300950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03007 | 947 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 383000 | 421300 | 383000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 948 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 130000 | 143000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03025 | 949 | Mechanical Pipe: Hydrostatic Testing | 4050 | 4455 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03107 | 950 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 30000 | 33000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 951 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 60000 | 66000 | 57000 | 0 | 1935.4839 | 0 | 0 | 0 | 1064.5161 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03135 | 952 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 96.7742 | 0 | 0 | 0 | 2903.2258 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 953 | Controls: Furnish and Install: Devices | 70000 | 77000 | 59500 | 0 | 9768.6567 | 0 | 731.3433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 954 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 955 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 7800 | 0 | 1395.5224 | 0 | 804.4776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SURV-SGS-E-01030 | 956 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-03120 | 957 | Controls: Connect to Final Termination Points | 8000 | 8800 | 4000 | 0 | 1116.4179 | 0 | 2883.5821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-03025 | 958 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 837.3134 | 0 | 5162.6866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 959 | Insulation: Furnish and Install: Ductwork Insulation | 18000 | 19800 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 960 | Insulation: Furnish and Install: Piping Insulation | 36000 | 39600 | 25200 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 961 | Insulation: Furnish and Install: Equipment Insulation | 18000 | 19800 | 12600 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 147 - OG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG3-02210 | 962 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02210 | 963 | ATS Installation | 140000 | 153300 | 126000 | 0 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02210 | 964 | ATS Terminations | 10000 | 10950 | 2500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02210 | 965 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02010 | 966 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02105 | 967 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02025 | 968 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 150000 | 0 | 42857.1429 | 0 | 0 | 0 | 35714.2857 | 35714.2857 | 35714.2857 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02260 | 969 | Cabling - Risers & Feeders (2/0 & Larger) | 360000 | 394200 | 270000 | 51428.5714 | 38571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02020 | 970 | Conduit - Branch Circuits (1 1/2" & Smaller) | 200000 | 219000 | 160000 | 0 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02130 | 971 | Conduit - Risers (2" & Larger) | 360000 | 394200 | 342000 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02015 | 972 | Demolition/Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02150 | 973 | Firestopping | 5000 | 5250 | 2500 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02035 | 974 | Foundation Coring | 10000 | 10500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02240 | 975 | Lighting Controls | 32000 | 33600 | 16000 | 0 | 0 | 0 | 0 | 5333.3333 | 5333.3333 | 5333.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02015 | 976 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02015 | 977 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG7-02655 | 978 | Switchgear & Panelboard Energization | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02070 | 979 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 14500 | 38062.5 | 0 | 0 | 0 | 1812.5 | 1812.5 | 1812.5 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGW-E-01015 | 980 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02245 | 981 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02515 | 982 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02265 | 983 | Switchgear & Panelboard Installation | 330000 | 361350 | 313500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02265 | 984 | Switchgear & Panelboard Terminations | 27500 | 30525 | 6875 | 24062.5 | 0 | 0 | 0 | -1145.8333 | -1145.8333 | -1145.8333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02510 | 985 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 0 | OG3 | 148 - OG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02020 | 986 | Fire Alarm Conduit | 20000 | 21900 | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02115 | 987 | Fire Alarm Wiring | 15000 | 16425 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02115 | 988 | Fire Alarm Devices | 19000 | 20805 | 9500 | 0 | 0 | 0 | 0 | 3166.6667 | 3166.6667 | 3166.6667 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG7-02330 | 989 | Switchgear & Panelboard Installation | 60000 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02115 | 990 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG3-02535 | 991 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG3 | 149 - OG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-01005 | 995 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2500 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01010 | 996 | Wire Insulation | 12500 | 37500 | 11875 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01015 | 997 | Assumed Flooring Material (Slab Penetrations) | 25200 | 75600 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 998 | Pipe Insulation | 42000 | 126000 | 40000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 999 | Tank Insulation | 3250 | 9750 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG7-02330 | 1000 | Switchgear & Panelboard Terminations | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-01015 | 1001 | Fireproofing | 10850 | 32550 | 10850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01015 | 1002 | Fibrous Slate | 3060 | 9180 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 1003 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01020 | 1004 | Underground Utility Materials | 3796 | 11388 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 151 - OG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG7-02650 | 1011 | Switchgear & Panelboard Testing | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG1 | 013 - SG1 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-01820 | 1047 | 6" vertically reinforced CMU | 58000 | 44875 | 55100 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG4-01830 | 1048 | 2" Face brick | 99000 | 198275 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG4-01820 | 1050 | Coping stone C1/A-300 | 57000 | 28328 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 153 - OG4 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05140 | 1051 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG4-01315 | 1052 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG4-01860 | 1053 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 154 - OG4 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG2-01005 | 1055 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01330 | 1061 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 156 - OG4 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
OG4-01325 | 1063 | Layout | 2625 | 5401 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG4-01325 | 1064 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG4-01325 | 1065 | Framing & Drywall - Materials | 8125 | 12601 | 8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG2-01010 | 1066 | Wire Insulation | 12500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-01325 | 1067 | Framing- Labor | 10000 | 13372 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG4-01330 | 1068 | Drywall - Labor | 7625 | 15687 | 7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG4-01330 | 1069 | Tape/ Spackle finishes | 6000 | 12344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG4-01855 | 1070 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 157 - OG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG2-01015 | 1077 | Assumed Flooring Material (Slab Penetrations) | 3600 | 10800 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG2-01020 | 1088 | Pipe Insulation | 37800 | 113400 | 32592 | 0 | 0 | 5208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03005 | 1098 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 6185.5 | 1546.375 | 1546.375 | 1546.375 | 1546.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG2-01020 | 1099 | Tank Insulation | 5200 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03005 | 1100 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 714 | 786 | 428.4 | 71.4 | 71.4 | 71.4 | 71.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1101 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 400 | 150 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1102 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2983 | 3282 | 596.6 | 596.6 | 596.6 | 596.6 | 596.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1103 | HANGERS AND SUPPORTS | 10489.6 | 11539 | 7342.72 | 786.72 | 786.72 | 786.72 | 786.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1104 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 498.75 | 498.75 | 498.75 | 498.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1105 | DOMESTIC WATER PIPING | 114134 | 125548 | 79893.8 | 8560.05 | 8560.05 | 8560.05 | 8560.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1106 | DOMESTIC WATER PIPING SPECIALTIES | 17439 | 19183 | 13951.2 | 871.95 | 871.95 | 871.95 | 871.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1107 | SANITARY WASTE PIPING | 97194 | 106914 | 87474.6 | 2429.85 | 2429.85 | 2429.85 | 2429.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1108 | SANITARY WASTE PIPING SPECIALTIES | 27333 | 30067 | 24599.7 | 683.325 | 683.325 | 683.325 | 683.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1109 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 15000 | 3750 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG2-01005 | 1110 | Duct Seal | 6000 | 18000 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03030 | 1111 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 170000 | 187000 | 136000 | 17000 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1112 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 8460 | 9306 | 8460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG4-03005 | 1113 | Plumbing Pipe Insulation | 20600 | 35464 | 12360 | 4120 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG4-02045 | 1114 | Heat Trace | 5000 | 5475 | 0 | 0 | 4285.7143 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | 0 | 0 | OG4 | 160 - OG4 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGP1-M-01005 | 1115 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 1116 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03112 | 1117 | Exhaust Fans: Install | 12600 | 13860 | 0 | 1512.5084 | 11087.4916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1118 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03032 | 1119 | Steam Unit Heaters: Install | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1120 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-01015 | 1121 | Vinyl Membrane and Mastic | 12240 | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03032 | 1122 | Condensate Return Unit: Install | 20000 | 22000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03112 | 1123 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03112 | 1124 | Heating and Ventilation Unit: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03015 | 1125 | Steam Traps: Furnish | 1800 | 1980 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03015 | 1126 | Steam Traps: Install | 21000 | 23100 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1127 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03032 | 1128 | Vacuum Pump Unit: Install | 23000 | 25300 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1129 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 246300 | 270930 | 246300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1130 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 320000 | 352000 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1131 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 120000 | 132000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-01015 | 1132 | Caulk | 37500 | 112500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-03025 | 1133 | Mechanical Pipe: Hydrostatic Testing | 3700 | 4070 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 1134 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 25000 | 27500 | 23750 | 0 | 721.1538 | 0 | 176.2821 | 176.2821 | 176.2821 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 1135 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 50000 | 55000 | 49500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03032 | 1136 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 86.5385 | 0 | 0 | 0 | 2913.4615 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1137 | Controls: Furnish and Install: Devices | 70000 | 77000 | 63000 | 0 | 5171.6418 | 0 | 1828.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1138 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1139 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 9500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1140 | Controls: Connect to Final Termination Points | 8000 | 8800 | 7600 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-03025 | 1141 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 443.2836 | 0 | 5556.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1142 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-01015 | 1143 | Fibrous Slate | 4675 | 14025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG1-03040 | 1144 | Insulation: Furnish and Install: Piping Insulation | 34500 | 37950 | 20700 | 11116.6667 | 2683.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1145 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 18150 | 9900 | 5316.6667 | 1283.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 161 - OG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG4-02210 | 1146 | ATS Energization | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02210 | 1147 | ATS Installation | 175000 | 191625 | 157500 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02210 | 1148 | ATS Terminations | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02210 | 1149 | ATS Testing | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02015 | 1150 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 6250 | 0 | 0 | 0 | 0 | 6250 | 6250 | 6250 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02040 | 1151 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 200000 | 0 | 28571.4286 | 28571.4286 | 28571.4286 | 38095.2381 | 38095.2381 | 38095.2381 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OGP1-02010 | 1152 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 270000 | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02020 | 1153 | Conduit - Branch Circuits (1 1/2" & Smaller) | 237500 | 260063 | 190000 | 0 | 0 | 0 | 0 | 15833.3333 | 15833.3333 | 15833.3333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-01020 | 1154 | Waterproofing | 1657 | 4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-02130 | 1155 | Conduit - Risers (2" & Larger) | 450000 | 492750 | 427500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02025 | 1156 | Demolition/Temp Light & Power | 50000 | 54750 | 47500 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02145 | 1157 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02030 | 1158 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02240 | 1159 | Lighting Controls | 25000 | 26250 | 12500 | 0 | 10714.2857 | 0 | 0 | 595.2381 | 595.2381 | 595.2381 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02025 | 1160 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02025 | 1161 | Lighting System Program & Energize | 5000 | 5550 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02050 | 1162 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 14500 | 0 | 0 | 0 | 0 | 14500 | 14500 | 14500 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGP1-E-01010 | 1163 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02245 | 1164 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-01020 | 1165 | Underground Utility Materials | 15600 | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 015 - SG2 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG4-02515 | 1166 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 0 | 22000 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02260 | 1167 | Switchgear & Panelboard Installation | 330000 | 361350 | 297000 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02260 | 1168 | Switchgear & Panelboard Terminations | 27500 | 30525 | 6875 | 0 | 0 | 0 | 0 | 6875 | 6875 | 6875 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02510 | 1169 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 0 | 0 | 0 | 13750 | 4583.3333 | 4583.3333 | 4583.3333 | 0 | 0 | 0 | 0 | OG4 | 162 - OG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02020 | 1170 | Fire Alarm Conduit | 25000 | 27375 | 17500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02115 | 1171 | Fire Alarm Wiring | 18000 | 19710 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02115 | 1172 | Fire Alarm Devices | 20000 | 21900 | 10000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02115 | 1173 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG4-02535 | 1174 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG4 | 163 - OG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-01005 | 1179 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01010 | 1180 | Wire Insulation | 12500 | 37500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01015 | 1181 | Assumed Flooring Material (Slab Penetrations) | 19200 | 57600 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1182 | Pipe Insulation | 37800 | 113400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1183 | Tank Insulation | 3250 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01015 | 1184 | Fireproofing | 42625 | 127875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01015 | 1185 | Fibrous Slate | 3060 | 9180 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1186 | Waterproofing | 1657 | 4971 | 1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01020 | 1188 | Underground Utility Materials | 3796 | 11388 | 3036.8 | 0 | 759.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 165 - OG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG5-01820 | 1230 | 6" vertically reinforced CMU | 58000 | 44875 | 58000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG5-01830 | 1232 | 2" Face brick | 85500 | 198275 | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG5-01820 | 1234 | Coping stone C1/A-300 | 57000 | 28002 | 57000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 167 - OG5 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05260 | 1235 | MATERIAL AND FABRICATION | 15000 | 16765 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG5-01315 | 1236 | INSTALLATION | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG5-01860 | 1237 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 168 - OG5 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG5-01330 | 1245 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 170 - OG5 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01325 | 1247 | Layout | 1875 | 3858 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01325 | 1248 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01325 | 1249 | Framing & Drywall - Materials | 7750 | 11829 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01325 | 1250 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01330 | 1251 | Drywall - Labor | 8125 | 16715 | 8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01330 | 1252 | Tape/ Spackle finishes | 5875 | 12087 | 5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-01855 | 1254 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 171 - OG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG5-03005 | 1282 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 0 | 3092.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1283 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 500 | 550 | 400 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1284 | ESCUTCHEONS FOR PLUMBING PIPING | 1000 | 1100 | 750 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1285 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2600 | 2860 | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1287 | HANGERS AND SUPPORTS | 10491 | 11541 | 10491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1288 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1289 | DOMESTIC WATER PIPING | 109926 | 120919 | 109926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1290 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 11100 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1291 | SANITARY WASTE PIPING | 101808 | 111989 | 91627.2 | 0 | 10180.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1292 | SANITARY WASTE PIPING SPECIALTIES | 27335 | 30069 | 24601.5 | 0 | 2733.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1293 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03030 | 1294 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 169998 | 186998 | 135998.4 | 0 | 0 | 16999.8 | 16999.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1295 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 1296 | Plumbing Pipe Insulation | 27500 | 35464 | 24750 | 0 | 1375 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG5-02045 | 1298 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG5 | 174 - OG5 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGP1-M-01005 | 1299 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 1300 | Exhaust Fans: Furnish | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03112 | 1301 | Exhaust Fans: Install | 15600 | 17160 | 0 | 5200 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1302 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03032 | 1303 | Steam Unit Heaters: Install | 17000 | 18700 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1304 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03032 | 1305 | Condensate Return Unit: Install | 23000 | 25300 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03112 | 1306 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03112 | 1307 | Heating and Ventilation Unit: Install | 24000 | 26400 | 0 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03015 | 1309 | Steam Traps: Furnish | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03015 | 1310 | Steam Traps: Install | 23000 | 25300 | 11500 | 1594.3339 | 1414.1049 | 8491.5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1311 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03032 | 1312 | Vacuum Pump Unit: Install | 26000 | 28600 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03107 | 1313 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 318700 | 350570 | 239025 | 47533.7297 | 32141.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03007 | 1314 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 410000 | 451000 | 205000 | 102500 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1315 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 200000 | 220000 | 100000 | 29829.7645 | 70170.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03025 | 1316 | Mechanical Pipe: Hydrostatic Testing | 5300 | 5830 | 0 | 2650 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1317 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 38500 | 34300 | 0 | 0 | 674.3119 | 0 | 0 | 25.6881 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1318 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 70000 | 77000 | 68600 | 0 | 0 | 1348.6239 | 0 | 0 | 51.3761 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03310 | 1320 | HVAC Ductwork: Testing & Balancing | 4000 | 4400 | 0 | 0 | 0 | 77.0642 | 0 | 0 | 3922.9358 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1321 | Controls: Furnish and Install: Devices | 70000 | 77000 | 50400 | 0 | 18597.0149 | 0 | 1002.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1322 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1323 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 4000 | 0 | 2656.7164 | 0 | 3343.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1324 | Controls: Connect to Final Termination Points | 8000 | 8800 | 0 | 0 | 2125.3731 | 0 | 5874.6269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-03025 | 1325 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 1594.0299 | 0 | 4405.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1326 | Insulation: Furnish and Install: Ductwork Insulation | 20000 | 22000 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1327 | Insulation: Furnish and Install: Piping Insulation | 40000 | 44000 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1328 | Insulation: Furnish and Install: Equipment Insulation | 20000 | 22000 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 175 - OG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG5-02210 | 1329 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02210 | 1331 | ATS Installation | 140000 | 153300 | 126000 | 0 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02210 | 1332 | ATS Terminations | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02210 | 1333 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02010 | 1334 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02040 | 1335 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 125000 | 0 | 17857.1429 | 17857.1429 | 17857.1429 | 23809.5238 | 23809.5238 | 23809.5238 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OGP1-02025 | 1336 | Cabling - Risers & Feeders (2/0 & Larger) | 450000 | 492750 | 225000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02015 | 1337 | Conduit - Branch Circuits (1 1/2" & Smaller) | 212500 | 232688 | 180625 | 0 | 0 | 0 | 0 | 10625 | 10625 | 10625 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02125 | 1338 | Conduit - Risers (2" & Larger) | 450000 | 492750 | 427500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02025 | 1339 | Demolition/Temp Light & Power | 50000 | 54750 | 40000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02145 | 1340 | Firestopping | 5000 | 5250 | 2500 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02030 | 1342 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02240 | 1343 | Lighting Controls | 31000 | 32550 | 15500 | 0 | 13285.7143 | 0 | 0 | 738.0952 | 738.0952 | 738.0952 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02025 | 1344 | Lighting Remove & Re-install | 36000 | 39420 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02025 | 1345 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02050 | 1346 | Mechanical Terminations(Dampers, Heaters, Motors) | 60000 | 65700 | 15000 | 39375 | 0 | 0 | 0 | 1875 | 1875 | 1875 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGP1-E-01010 | 1347 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02250 | 1348 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02515 | 1349 | Switchgear & Panelboard Energization | 27500 | 30113 | 0 | 0 | 0 | 23571.4286 | 0 | 1309.5238 | 1309.5238 | 1309.5238 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02265 | 1350 | Switchgear & Panelboard Installation | 330000 | 366300 | 297000 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02265 | 1351 | Switchgear & Panelboard Terminations | 27500 | 30113 | 6875 | 0 | 0 | 0 | 0 | 6875 | 6875 | 6875 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02510 | 1353 | Switchgear & Panelboard Testing | 27500 | 30113 | 0 | 3928.5714 | 3928.5714 | 3928.5714 | 5238.0952 | 5238.0952 | 5238.0952 | 0 | 0 | 0 | 0 | 0 | OG5 | 176 - OG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02015 | 1354 | Fire Alarm Conduit | 20000 | 21900 | 15000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02115 | 1355 | Fire Alarm Wiring | 18000 | 19710 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02115 | 1356 | Fire Alarm Devices | 19000 | 20805 | 9500 | 0 | 0 | 0 | 0 | 3166.6667 | 3166.6667 | 3166.6667 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02115 | 1357 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG5-02535 | 1358 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG5 | 177 - OG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-01005 | 1362 | Gaskets | 19500 | 58500 | 14625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4875 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01010 | 1364 | Wire Insulation | 25000 | 75000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01015 | 1365 | Assumed Flooring Material (Slab Penetrations) | 21600 | 64800 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01020 | 1366 | Pipe Insulation | 30240 | 90720 | 30240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01005 | 1367 | Duct Seal | 1200 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01015 | 1368 | Asbestos Panels | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01015 | 1369 | Fibrous Slate | 4760 | 14280 | 4760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01020 | 1370 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01020 | 1371 | Underground Utility Materials | 3796 | 11388 | 3796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 179 - OG6 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG6-01820 | 1413 | 6" vertically reinforced CMU | 62000 | 34760 | 46500 | 0 | 0 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG6-01830 | 1414 | 2" Face brick | 107000 | 161546 | 0 | 53500 | 53500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG6-01820 | 1416 | Coping stone C1/A-300 | 66000 | 12375 | 0 | 0 | 0 | 22000 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 181 - OG6 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05290 | 1417 | MATERIAL AND FABRICATION | 15000 | 16765 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG6-01315 | 1419 | INSTALLATION | 18000 | 19800 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG6-01860 | 1420 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 182 - OG6 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG6-01330 | 1428 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 184 - OG6 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01325 | 1431 | Layout | 1875 | 3858 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01325 | 1432 | Loading | 3250 | 6686 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01325 | 1433 | Framing & Drywall - Materials | 7750 | 11829 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01325 | 1434 | Framing- Labor | 9625 | 12601 | 9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01330 | 1435 | Drywall - Labor | 8875 | 18260 | 8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01330 | 1436 | Tape/ Spackle finishes | 5750 | 11829 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG6-01855 | 1437 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 185 - OG6 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG2-01820 | 1440 | 6" vertically reinforced CMU | 166000 | 125840 | 157700 | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG2-01830 | 1451 | 2" Face brick | 177000 | 357280 | 141600 | 0 | 0 | 35400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG6-03005 | 1466 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 7422.6 | 1649.4667 | 1649.4667 | 1649.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1467 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 2394 | 2634 | 1915.2 | 159.6 | 159.6 | 159.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1468 | ESCUTCHEONS FOR PLUMBING PIPING | 1500 | 1650 | 1200 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1469 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3791 | 4171 | 2274.6 | 505.4667 | 505.4667 | 505.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1470 | HANGERS AND SUPPORTS | 10477.5 | 11526 | 7858.125 | 873.125 | 873.125 | 873.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1471 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1472 | DOMESTIC WATER PIPING | 178020 | 195822 | 160218 | 5934 | 5934 | 5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG2-01820 | 1473 | Coping Stone C1/A-300 | 181000 | 30958 | 181000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 017 - SG2 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG6-03005 | 1474 | DOMESTIC WATER PIPING SPECIALTIES | 14799 | 16279 | 12579.15 | 739.95 | 739.95 | 739.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1475 | SANITARY WASTE PIPING | 34117 | 37529 | 32411.15 | 568.6167 | 568.6167 | 568.6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1476 | SANITARY WASTE PIPING SPECIALTIES | 147470 | 162217 | 132723 | 4915.6667 | 4915.6667 | 4915.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1477 | STORM DRAINAGE PIPING SPECIALTIES | 48720 | 53592 | 31668 | 5684 | 5684 | 5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03030 | 1478 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 210000 | 231000 | 115500 | 31500 | 31500 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1479 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 12070 | 13277 | 12070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG6-03005 | 1480 | Plumbing Pipe Insulation | 64100 | 35464 | 48075 | 0 | 8012.5 | 8012.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OG6-02045 | 1481 | Heat Trace | 5000 | 5475 | 0 | 0 | 4285.7143 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | 0 | 0 | OG6 | 188 - OG6 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGE-M-01005 | 1482 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 1483 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
05470 | 1484 | MATERIAL AND FABRICATION | 5000 | 5824 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG6-03112 | 1485 | Exhaust Fans: Install | 11450 | 12595 | 5725 | 0 | 2024.4873 | 3700.5127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1486 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03032 | 1487 | Steam Unit Heaters: Install | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1488 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03032 | 1489 | Condensate Return Unit: Install | 20000 | 22000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03112 | 1490 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03112 | 1491 | Heating and Ventilation Unit: Install | 21000 | 23100 | 0 | 0 | 3713.0334 | 17286.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03015 | 1492 | Steam Traps: Furnish | 2600 | 2860 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03015 | 1493 | Steam Traps: Install | 25000 | 27500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 1494 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-01315 | 1495 | INSTALLATION | 6000 | 6600 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG6-03032 | 1496 | Vacuum Pump Unit: Install | 23000 | 25300 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03107 | 1497 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 239800 | 263780 | 232606 | 3597 | 3597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03007 | 1498 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 310000 | 341000 | 300700 | 4650 | 4650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1499 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 150000 | 165000 | 145500 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03025 | 1500 | Mechanical Pipe: Hydrostatic Testing | 5200 | 5720 | 0 | 2600 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 1501 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 25000 | 27500 | 24500 | 0 | 0 | 480.7692 | 0 | 0 | 0 | 19.2308 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 1502 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 50000 | 55000 | 49000 | 0 | 0 | 961.5385 | 0 | 0 | 0 | 38.4615 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03135 | 1503 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 0 | 57.6923 | 0 | 0 | 0 | 2942.3077 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1504 | Controls: Furnish and Install: Devices | 65000 | 71500 | 52000 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1505 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 33250 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-01860 | 1506 | Temporary Aluminum Over Pass Stairs | 25998 | 28598 | 0 | 0 | 0 | 0 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 018 - SG2 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
OG1-03120 | 1507 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 3109.7561 | 6890.2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 1508 | Controls: Connect to Final Termination Points | 7000 | 7700 | 0 | 0 | 0 | 2176.8293 | 4823.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-03025 | 1509 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 1865.8537 | 4134.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1510 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 0 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1511 | Insulation: Furnish and Install: Piping Insulation | 30000 | 33000 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 1512 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 18150 | 0 | 0 | 0 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 189 - OG6 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG6-02210 | 1513 | ATS Energization | 12500 | 13688 | 0 | 5000 | 5000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02210 | 1514 | ATS Installation | 175000 | 191625 | 140000 | 35000 | 35000 | 0 | 0 | -11666.6667 | -11666.6667 | -11666.6667 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02210 | 1515 | ATS Terminations | 12500 | 13688 | 0 | 5000 | 5000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02210 | 1516 | ATS Testing | 12500 | 13688 | 0 | 5000 | 5000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02015 | 1518 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27750 | 13750 | 0 | 0 | 0 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02040 | 1519 | Cabling - Interior Branch (1/0 & Smaller) | 125000 | 136875 | 0 | 100000 | 12500 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OGE-02115 | 1520 | Cabling - Risers & Feeders (2/0 & Larger) | 540000 | 591300 | 0 | 0 | 0 | 135000 | 135000 | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02020 | 1521 | Conduit - Branch Circuits (1 1/2" & Smaller) | 250000 | 273750 | 0 | 35714.2857 | 35714.2857 | 35714.2857 | 47619.0476 | 47619.0476 | 47619.0476 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02115 | 1522 | Conduit - Risers (2" & Larger) | 630000 | 689850 | 126000 | 68828.1938 | 0 | 0 | 0 | 145057.2687 | 145057.2687 | 145057.2687 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02025 | 1523 | Demolition/Temp Light & Power | 50000 | 55500 | 32500 | 2857.1429 | 2857.1429 | 2857.1429 | 2976.1905 | 2976.1905 | 2976.1905 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02145 | 1524 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 4285.7143 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02030 | 1525 | Foundation Coring | 20000 | 21000 | 13000 | 540.9091 | 0 | 0 | 0 | 2153.0303 | 2153.0303 | 2153.0303 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02240 | 1526 | Lighting Controls | 47000 | 49350 | 23500 | 0 | 0 | 0 | 10071.4286 | 4476.1905 | 4476.1905 | 4476.1905 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02025 | 1527 | Lighting Remove & Re-install | 36900 | 40406 | 0 | 10542.8571 | 0 | 0 | 0 | 8785.7143 | 8785.7143 | 8785.7143 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02025 | 1529 | Lighting System Program & Energize | 5000 | 5550 | 0 | 1428.5714 | 0 | 0 | 0 | 1190.4762 | 1190.4762 | 1190.4762 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02050 | 1530 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 0 | 0 | 49714.2857 | 0 | 0 | 2761.9048 | 2761.9048 | 2761.9048 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-OGE-01020 | 1531 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02245 | 1532 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 8571.4286 | 476.1905 | 476.1905 | 476.1905 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02515 | 1533 | Switchgear & Panelboard Energization | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02260 | 1534 | Switchgear & Panelboard Installation | 450000 | 492750 | 360000 | 0 | 0 | 0 | 192857.1429 | -34285.7143 | -34285.7143 | -34285.7143 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02260 | 1535 | Switchgear & Panelboard Terminations | 30000 | 32850 | 0 | 0 | 0 | 0 | 25714.2857 | 1428.5714 | 1428.5714 | 1428.5714 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02510 | 1536 | Switchgear & Panelboard Testing | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | OG6 | 190 - OG6 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02020 | 1537 | Fire Alarm Conduit | 25000 | 27375 | 0 | 3571.4286 | 3571.4286 | 3571.4286 | 4761.9048 | 4761.9048 | 4761.9048 | 0 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02120 | 1538 | Fire Alarm Wiring | 22500 | 24638 | 0 | 0 | 0 | 11250 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02120 | 1540 | Fire Alarm Devices | 22000 | 24090 | 11000 | 0 | 0 | 5500 | 0 | 1833.3333 | 1833.3333 | 1833.3333 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02120 | 1541 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 1250 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG6-02535 | 1542 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | OG6 | 191 - OG6 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG10-01013 | 1546 | Caulk | 3000 | 9000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG10-01013 | 1547 | Fibrous Slate | 170 | 510 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 193 - OG7 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
OG10-01015 | 1548 | Demo Existing Building/Temp Light & Power | 32100 | 35150 | 32100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG7 | 194 - OG7 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG8-01230 | 1562 | 8" CMU (3 hour rated) | 787500 | 434720 | 787500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
OG8-01275 | 1565 | Face Brick 3-5/8" | 205500 | 373450 | 205500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
OG8-01250 | 1567 | Cast Stone with SS letters | 6700 | 8650 | 0 | 6700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 196 - OG8 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG8-01105 | 1570 | STEEL (MATERIAL ONLY) | 210000 | 245175 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1571 | FABRICATION COSTS | 368000 | 338575 | 368000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1573 | METAL DECK (BUY-OUT) | 21000 | 24518 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1574 | ANCHORS & EMBEDS | 10000 | 11676 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1575 | SURVEYING | 15000 | 17514 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1576 | STEEL & DECK ERECTION | 700000 | 817248 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1577 | BOLTS AND HARDWARE | 20000 | 23351 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01105 | 1578 | TRUCKING | 10000 | 11676 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG8-01270 | 1579 | Dunnage Grating Galvanized | 66023 | 72626 | 16505.75 | 49517.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01270 | 1580 | Dunnage Guard Rail | 29625 | 32588 | 29625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01270 | 1581 | Dunnage Stair and Railing (1) | 12038 | 13242 | 10834.2 | 0 | 1203.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01290 | 1582 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 144130 | 172065 | 144130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01290 | 1584 | Stair B: Stair, Landing and Hand & Guard Rail | 74111 | 81523 | 74111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01295 | 1585 | 1st to 2nd Floor Ship Ladder with Cage and Platform Landing | 24641 | 27106 | 20944.85 | 0 | 3696.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01290 | 1586 | Egress Stair: Stair & Landing with Hand & Guard Rail | 43263 | 47590 | 10815.75 | 0 | 0 | 32447.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 197 - OG8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG8-01305 | 1587 | Layout | 11875 | 9195 | 11875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01305 | 1588 | Loading | 34000 | 26857 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01305 | 1589 | Exterior Framing, Insulation & Drywall - Materials | 102500 | 116188 | 102500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01305 | 1590 | Exterior Framing- Labor | 55500 | 64809 | 55500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 198 - OG8 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG2-01330 | 1594 | Doors, Frames & Hardware - Labor | 3500 | 7784 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 020 - SG2 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-01305 | 1596 | Insulation- Labor | 8500 | 10399 | 6375 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01255 | 1599 | Layout | 131466 | 138040 | 0 | 0 | 43822 | 43822 | 43822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG8-01255 | 1600 | Framing | 313010 | 328661 | 313010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG8-01255 | 1601 | Insulation | 56061 | 58865 | 56061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG8-01255 | 1602 | Cladding Install | 392430 | 412052 | 19621.5 | 0 | 124269.5 | 124269.5 | 124269.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG8-01225 | 1603 | Fireproofing | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
OG8-01265 | 1604 | P&I Cold Applied Roof Membrane | 152230 | 151996 | 106561 | 0 | 0 | 45669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG8-01265 | 1606 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 160940 | 160693 | 70454.6291 | 0 | 0 | 90485.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG8-01265 | 1607 | P&I Aluminum Coping | 9660 | 9240 | 0 | 0 | 0 | 9660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 199 - OG8 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG8-01245 | 1609 | Doors, Frames & Hardware - Labor | 15750 | 35030 | 5395.3754 | 2406.9354 | 4496.1462 | 3451.543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01317 | 1610 | Louvers Install | 51389 | 102778 | 0 | 0 | 17129.6667 | 17129.6667 | 17129.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | NAVILLUS | 0 | NEW BUILDINGS
08080 | 1611 | Overhead Door | 11316 | 16000 | 0 | 0 | 0 | 5658 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 200 - OG8 - Division 8 | 0% | Loading Dock | 0 | NEW BUILDINGS
OG8-01305 | 1613 | Sheathing & Drywall - Labor | 42375 | 87184 | 0 | 0 | 14581.2305 | 14581.2305 | 13212.539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01245 | 1614 | Tape/ Spackle finishes | 20125 | 41405 | 0 | 7290.7861 | 7290.7861 | 5543.4277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01315 | 1615 | ACT ceilings - Materials | 625 | 1286 | 0 | 0 | 468.75 | 156.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG2-01325 | 1616 | Layout | 3125 | 2315 | 0 | 1041.6667 | 1041.6667 | 1041.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-01315 | 1617 | ACT ceilings - Labor | 1500 | 3086 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01280 | 1618 | Direct Applied Stucco | 12800 | 26335 | 0 | 6400 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG8-01325 | 1619 | Painting OG-8 | 55000 | 110000 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 201 - OG8 - Division 9 | 0% | GG PAINT | 0 | NEW BUILDINGS
SG2-01325 | 1627 | Loading | 1750 | 3601 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-03105 | 1630 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 3764 | 294.0625 | 294.0625 | 0 | 117.625 | 117.625 | 117.625 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1631 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4560 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1632 | ESCUTCHEONS FOR PLUMBING PIPING | 2000 | 2200 | 1900 | 0 | 0 | 0 | 33.3333 | 33.3333 | 33.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1633 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 13800 | 15180 | 13110 | 345 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1634 | HANGERS AND SUPPORTS | 19803 | 21784 | 18812.85 | 495.075 | 495.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1635 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2490 | 2739 | 0 | 830 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1636 | DOMESTIC WATER PIPING | 188497 | 207347 | 179072.15 | 6126.1525 | 0 | 0 | 1099.5658 | 1099.5658 | 1099.5658 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1637 | DOMESTIC WATER PIPING SPECIALTIES | 13040 | 14344 | 12648.8 | 195.6 | 195.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG2-01325 | 1638 | Framing & Drywall - Materials | 5375 | 3858 | 0 | 1791.6667 | 1791.6667 | 1791.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-03105 | 1639 | SANITARY WASTE PIPING | 133476 | 146824 | 129471.72 | 2002.14 | 2002.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1640 | SANITARY WASTE PIPING SPECIALTIES | 27034 | 29738 | 25682.3 | 450.5667 | 450.5667 | 450.5667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1641 | STORM DRAINAGE PIPING SPECIALTIES | 67032 | 73736 | 67032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03140 | 1642 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 14880 | 16368 | 4464 | 3472 | 3472 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03140 | 1643 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 3648 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1644 | GAS SERVICE AND PIPING | 362208 | 398429 | 325987.2 | 13582.8 | 0 | 0 | 7546 | 7546 | 7546 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03140 | 1645 | PLUMBING FIXTURES | 16720 | 18392 | 0 | 5573.3333 | 5573.3333 | 5573.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03140 | 1646 | EMERGENCY PLUMBING FIXTURES | 4640 | 5104 | 0 | 1546.6667 | 1546.6667 | 1546.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1647 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 13728 | 15101 | 13728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG8-03105 | 1648 | Plumbing Pipe Insulation | 7600 | 8895 | 0 | 0 | 0 | 3800 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | TRISTAN | 0 | NEW BUILDINGS
SG2-01325 | 1649 | Framing- Labor | 2750 | 5658 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-02150 | 1650 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 203 - OG8 - Division 22 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-OGP1-M-01005 | 1651 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03112 | 1652 | Exhaust Fans: Furnish | 7200 | 7920 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1653 | Exhaust Fans: Install | 36400 | 40040 | 36400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1654 | Steam Unit Heaters: Furnish | 8000 | 8800 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1655 | Steam Unit Heaters: Install | 77500 | 85250 | 38750 | 38750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1656 | Electric Heaters: Furnish | 5000 | 5500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1657 | Condensate Return Unit: Furnish | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1658 | Condensate Return Unit: Install | 53500 | 58850 | 53500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1659 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG2-01330 | 1660 | Drywall - Labor | 2625 | 5401 | 0 | 875 | 875 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-03142 | 1661 | Heating and Ventilation Unit: Install | 42500 | 46750 | 0 | 21250 | 21250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1662 | Steam Traps: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1663 | Steam Traps: Install | 46000 | 50600 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1664 | Steam Separator: Furnish | 48000 | 52800 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1665 | Steam Separator: Install | 349500 | 384450 | 349500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03210 | 1666 | Low Pressure Steam Boilers: Install | 189500 | 208450 | 189500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1667 | Boiler Feed Unit: Furnish | 75000 | 82500 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03242 | 1668 | Boiler Feed Unit: Install | 49500 | 54450 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1669 | Fuel Oil Pump: Furnish | 70000 | 77000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 1670 | Fuel Oil Pump: Install | 49500 | 54450 | 49500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG2-01330 | 1671 | Tape/ Spackle finishes | 2250 | 4629 | 0 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-03142 | 1672 | Fuel Oil Storage Tank: Furnish | 65000 | 71500 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03110 | 1673 | Fuel Oil Storage Tank: Install | 59500 | 65450 | 59500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03110 | 1674 | Rigging | 259500 | 285450 | 259500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03107 | 1675 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 654000 | 719400 | 654000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 1676 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 863000 | 949300 | 863000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 1677 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 345000 | 379500 | 338100 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03242 | 1678 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 350000 | 385000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03135 | 1679 | Mechanical Pipe: Hydrostatic Testing | 11000 | 12100 | 9350 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 1680 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 90000 | 99000 | 81000 | 2250 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03110 | 1681 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 175000 | 192500 | 157500 | 4375 | 4375 | 4375 | 4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG2-01855 | 1682 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 021 - SG2 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
OG8-03245 | 1683 | HVAC Ductwork: Testing & Balancing | 10000 | 11000 | 0 | 481.8182 | 0 | 0 | 3172.7273 | 3172.7273 | 3172.7273 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1684 | Controls: Furnish and Install: Devices | 250000 | 275000 | 125000 | 41666.6667 | 41666.6667 | 41666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1685 | Controls: Furnish and Install: Controls Conduit | 110000 | 121000 | 82500 | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1686 | Controls: Furnish and Install: Controls Wiring | 30000 | 33000 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1687 | Controls: Connect to Final Termination Points | 20000 | 22000 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03135 | 1688 | Controls: Controls Testing | 17300 | 19030 | 0 | 5766.6667 | 5766.6667 | 5766.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 1689 | Insulation: Furnish and Install: Ductwork Insulation | 55000 | 60500 | 0 | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 1690 | Insulation: Furnish and Install: Piping Insulation | 115000 | 126500 | 23000 | 34244.4444 | 57755.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 1691 | Insulation: Furnish and Install: Equipment Insulation | 55000 | 60500 | 0 | 27500 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03242 | 1692 | Furnish and Install: Chemical Feed Equipment | 9300 | 10230 | 4650 | 1550 | 1550 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03242 | 1694 | Chemical Cleaning | 7500 | 8250 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 204 - OG8 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-02255 | 1695 | ATS Energization | 15000 | 16425 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02255 | 1696 | ATS Installation | 210000 | 229950 | 189000 | 0 | 0 | 0 | 7000 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02255 | 1697 | ATS Terminations | 15000 | 16425 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02255 | 1698 | ATS Testing | 15000 | 16425 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02130 | 1699 | Cabling - Interior Branch (1/0 & Smaller) | 200000 | 219000 | 100000 | 0 | 0 | 0 | 33333.3333 | 33333.3333 | 33333.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02490 | 1700 | Cabling - Risers & Feeders (2/0 & Larger) | 450000 | 492750 | 0 | 0 | 429545.4545 | 20454.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02115 | 1701 | Conduit - Branch Circuits (1 1/2" & Smaller) | 150000 | 164250 | 127500 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02205 | 1702 | Conduit - In-Slab | 198000 | 216810 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02010 | 1703 | Conduit - Risers (2" & Larger) | 405000 | 443475 | 384750 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02495 | 1705 | Firestopping | 5000 | 5250 | 3000 | 0 | 1000 | 500 | 166.6667 | 166.6667 | 166.6667 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-OG8-01170 | 1706 | Generator Delivery | 75000 | 78750 | 0 | 37500 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-OG8-01010 | 1707 | Generator Release | 450000 | 472500 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02420 | 1708 | Generator Terminations | 75000 | 78750 | 0 | 0 | 0 | 69642.8571 | 1785.7143 | 1785.7143 | 1785.7143 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02730 | 1709 | Generator Test | 75000 | 78750 | 37500 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02120 | 1710 | Lighting Controls | 14000 | 14700 | 7000 | 0 | 0 | 0 | 2333.3333 | 2333.3333 | 2333.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02140 | 1711 | Lighting Install | 138000 | 144900 | 124200 | 6960.5263 | 0 | 0 | 2279.8246 | 2279.8246 | 2279.8246 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02140 | 1712 | Lighting Rough | 138000 | 151110 | 131100 | 2784.2105 | 0 | 0 | 1371.9298 | 1371.9298 | 1371.9298 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02140 | 1713 | Lighting System Program & Energize | 5000 | 5475 | 0 | 1008.7719 | 0 | 0 | 1330.4094 | 1330.4094 | 1330.4094 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02425 | 1714 | Lightning Protection | 20000 | 21900 | 10000 | 0 | 0 | 8571.4286 | 476.1905 | 476.1905 | 476.1905 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02145 | 1716 | Mechanical Terminations(Dampers, Heaters, Motors) | 150000 | 164250 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-OGP1-E-01010 | 1717 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02160 | 1718 | Switches and Receptacles | 20000 | 21900 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02725 | 1719 | Switchgear & Panelboard Energization | 22500 | 24638 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02275 | 1720 | Switchgear & Panelboard Installation | 270000 | 295650 | 202500 | 9642.8571 | 9642.8571 | 9642.8571 | 12857.1429 | 12857.1429 | 12857.1429 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02275 | 1721 | Switchgear & Panelboard Terminations | 22500 | 24638 | 0 | 11250 | 0 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02720 | 1722 | Switchgear & Panelboard Testing | 22500 | 24638 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02005 | 1723 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 205 - OG8 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02115 | 1724 | Fire Alarm Conduit | 62500 | 68438 | 53125 | 0 | 0 | 0 | 3125 | 3125 | 3125 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02480 | 1725 | Fire Alarm Wiring | 60000 | 65700 | 30000 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02480 | 1727 | Fire Alarm Devices | 128000 | 140160 | 108800 | 0 | 0 | 0 | 6400 | 6400 | 6400 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02480 | 1728 | Fire Alarm Programming & Pretest | 2500 | 2750 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02740 | 1729 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG8 | 206 - OG8 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-01230 | 1749 | 8" CMU (3 hour rated) | 301500 | 101420 | 301500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
OG9-01275 | 1752 | Face Brick 3-5/8" | 70500 | 99578 | 70500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
OG9-01250 | 1754 | Cast Stone with SS letters | 105000 | 142454 | 81078.8044 | 20503.882 | 3417.3137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 209 - OG9 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG9-01105 | 1757 | STEEL (MATERIAL ONLY) | 88000 | 101945 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1758 | FABRICATION COSTS | 180000 | 173771 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1760 | METAL DECK (BUY-OUT) | 6500 | 7531 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1761 | ANCHORS & EMBEDS | 6000 | 6951 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1762 | SURVEYING | 8500 | 9848 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1763 | STEEL & DECK ERECTION | 300000 | 347540 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1764 | BOLTS AND HARDWARE | 6000 | 6951 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01105 | 1765 | TRUCKING | 5000 | 5793 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG9-01270 | 1766 | Dunnage Grating | 21443 | 23588 | 21443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01290 | 1767 | Railing | 10698 | 11768 | 10698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01270 | 1768 | Dunnage Stair and Railing | 15800 | 17380 | 15800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01290 | 1769 | Stair B: First Floor to Roof with Landing and Hand & Guard Rail | 128933 | 141827 | 128933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01295 | 1771 | 1st to 2nd Floor Ship Ladder with Safety Cage and Landing Platform with Rail | 22760 | 25036 | 22760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01295 | 1772 | Ship Ladder Bulkhead Roof | 6395 | 7035 | 6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 210 - OG9 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG9-01305 | 1773 | Layout | 7625 | 3065 | 7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01305 | 1774 | Loading | 12750 | 10218 | 12750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01305 | 1775 | Exterior Framing, Insulation & Drywall - Materials | 40875 | 37221 | 40875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01305 | 1776 | Exterior Framing- Labor | 48125 | 56196 | 48125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 211 - OG9 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01305 | 1782 | Insulation- Labor | 2375 | 2906 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01255 | 1785 | Layout | 52396 | 55016 | 52396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG9-01255 | 1786 | Framing | 109253 | 114716 | 109253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG9-01255 | 1787 | Insulation | 19567 | 20546 | 19567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG9-01255 | 1788 | Cladding Install | 136974 | 143823 | 102730.5 | 0 | 8560.875 | 8560.875 | 8560.875 | 8560.875 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG9-01225 | 1789 | Fireproofing | 27000 | 29700 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
OG9-01265 | 1790 | P&I Cold Applied Roof Membrane | 56806 | 54257 | 56806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG9-01265 | 1791 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 72352 | 69054 | 72352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG9-01265 | 1793 | P&I Aluminum Coping | 6375 | 6592 | 0 | 0 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 212 - OG9 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG9-01245 | 1795 | Doors, Frames & Hardware - Labor | 7875 | 17514 | 6975.7194 | 599.5204 | 299.7602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01317 | 1796 | Louvers Install | 17937 | 35874 | 0 | 0 | 4484.25 | 4484.25 | 4484.25 | 4484.25 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 213 - OG9 - Division 8 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG9-01305 | 1798 | Sheathing & Drywall - Labor | 9125 | 18774 | 7666.8664 | 729.0668 | 729.0668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01245 | 1799 | Tape/ Spackle finishes | 4500 | 9258 | 4050 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01315 | 1800 | ACT ceilings - Materials | 1000 | 2058 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01315 | 1801 | ACT ceilings - Labor | 2125 | 4372 | 0 | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01280 | 1802 | Direct Applied Stucco | 6400 | 13167 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG9-01325 | 1804 | Painting OG-9 | 55000 | 110000 | 0 | 0 | 0 | 23571.4286 | 31428.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 214 - OG9 - Division 9 | 0% | GG PAINT | 0 | NEW BUILDINGS
OG9-03105 | 1812 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 4469.75 | 117.625 | 117.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1813 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4656 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1815 | ESCUTCHEONS FOR PLUMBING PIPING | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1816 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 13400 | 14740 | 12998 | 134 | 134 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1817 | HANGERS AND SUPPORTS | 19936 | 21930 | 19337.92 | 199.36 | 199.36 | 199.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1818 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2490 | 2739 | 0 | 830 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1819 | DOMESTIC WATER PIPING | 153867 | 169254 | 146173.65 | 2564.45 | 2564.45 | 2564.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1820 | DOMESTIC WATER PIPING SPECIALTIES | 3120 | 3432 | 3026.4 | 31.2 | 31.2 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1821 | SANITARY WASTE PIPING | 116480 | 128128 | 112985.6 | 1456 | 1456 | 582.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1822 | SANITARY WASTE PIPING SPECIALTIES | 17318 | 19050 | 17318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1823 | STORM DRAINAGE PIPING SPECIALTIES | 37320 | 41052 | 37320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03140 | 1824 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 9200 | 10120 | 4600 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03140 | 1826 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 3648 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1827 | GAS SERVICE AND PIPING | 204340 | 224774 | 194123 | 3405.6667 | 3405.6667 | 3405.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03140 | 1828 | PLUMBING FIXTURES | 12879 | 14167 | 1287.9 | 3863.7 | 3863.7 | 3863.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1829 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG9-03105 | 1830 | Plumbing Pipe Insulation | 12500 | 3175 | 0 | 0 | 0 | 6250 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | TRISTAN | 0 | NEW BUILDINGS
OG9-02130 | 1831 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 216 - OG9 - Division 22 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-OGW-M-01005 | 1832 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03112 | 1833 | Exhaust Fans: Furnish | 6000 | 6600 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03142 | 1834 | Exhaust Fans: Install | 19750 | 21725 | 19750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1835 | Electric Unit Heaters: Furnish | 2500 | 2750 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1837 | Steam Unit Heater: Furnish | 5000 | 5500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03142 | 1838 | Steam Unit Heater: Install | 44000 | 48400 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1839 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03142 | 1840 | Condensate Return Unit: Install | 26000 | 28600 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03142 | 1841 | Steam Traps: Furnish | 600 | 660 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03142 | 1842 | Steam Traps: Install | 10000 | 11000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03107 | 1843 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 165250 | 181775 | 165250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03107 | 1844 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 193500 | 212850 | 193500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 1845 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 91500 | 100650 | 91500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03135 | 1846 | Mechanical Pipe: Hydrostatic Testing | 2750 | 3025 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03107 | 1848 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 17250 | 18975 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03110 | 1849 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03145 | 1850 | HVAC Ductwork: Testing & Balancing | 2000 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1851 | Controls: Furnish and Install: Devices | 90000 | 99000 | 28800 | 0 | 0 | 45243.2432 | 12952.7027 | 3004.0541 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1852 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 17500 | 0 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1853 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 5027.027 | 1439.1892 | 3533.7838 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 1854 | Controls: Connect to Final Termination Points | 7000 | 7700 | 0 | 0 | 0 | 3518.9189 | 1007.4324 | 2473.6486 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-03135 | 1855 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 3016.2162 | 863.5135 | 2120.2703 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 1856 | Insulation: Furnish and Install: Ductwork Insulation | 11000 | 12100 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 1857 | Insulation: Furnish and Install: Piping Insulation | 23000 | 25300 | 0 | 0 | 0 | 11500 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 1859 | Insulation: Furnish and Install: Equipment Insulation | 11000 | 12100 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 217 - OG9 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG9-02275 | 1860 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02275 | 1861 | ATS Installation | 140000 | 153300 | 133000 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02275 | 1862 | ATS Terminations | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02275 | 1863 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02125 | 1864 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 75000 | 30000 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02255 | 1865 | Cabling - Risers & Feeders (2/0 & Larger) | 324000 | 354780 | 0 | 46285.7143 | 46285.7143 | 46285.7143 | 61714.2857 | 61714.2857 | 61714.2857 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02115 | 1866 | Conduit - Branch Circuits (1 1/2" & Smaller) | 75000 | 83250 | 63750 | 0 | 0 | 0 | 3750 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02105 | 1867 | Conduit - In-Slab | 115500 | 126473 | 115500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02010 | 1868 | Conduit - Risers (2" & Larger) | 270000 | 299700 | 256500 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02400 | 1870 | Firestopping | 5000 | 5250 | 2500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-OG9-01046 | 1871 | Generator Delivery | 50000 | 52500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-OG9-01010 | 1872 | Generator Release | 300000 | 315000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02335 | 1873 | Generator Terminations | 50000 | 52500 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02530 | 1874 | Generator Test | 50000 | 52500 | 25000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02160 | 1875 | Lighting Controls | 8000 | 8400 | 4800 | 0 | 0 | 0 | 1066.6667 | 1066.6667 | 1066.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02140 | 1876 | Lighting Install | 68400 | 71820 | 54720 | 0 | 0 | 0 | 4560 | 4560 | 4560 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02140 | 1877 | Lighting Rough | 68400 | 74898 | 64980 | 1710 | 1710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02140 | 1878 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG8-02310 | 1879 | Lightning Protection | 20000 | 21900 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02145 | 1881 | Mechanical Terminations(Dampers, Heaters, Motors) | 60000 | 66600 | 18000 | 0 | 0 | 0 | 14000 | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-OGW-E-01015 | 1882 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02155 | 1883 | Switches and Receptacles | 10000 | 10950 | 1500 | 0 | 0 | 0 | 2833.3333 | 2833.3333 | 2833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02515 | 1884 | Switchgear & Panelboard Energization | 17500 | 19163 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02260 | 1885 | Switchgear & Panelboard Installation | 210000 | 229950 | 199500 | 9000 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02260 | 1886 | Switchgear & Panelboard Terminations | 17500 | 19163 | 0 | 15000 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02510 | 1887 | Switchgear & Panelboard Testing | 17500 | 19425 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02005 | 1888 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 218 - OG9 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02115 | 1889 | Fire Alarm Conduit | 25000 | 27375 | 22500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02365 | 1890 | Fire Alarm Wiring | 22500 | 24638 | 2250 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02365 | 1892 | Fire Alarm Devices | 33000 | 36135 | 16500 | 0 | 0 | 0 | 5500 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02365 | 1893 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG9-02535 | 1894 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG9 | 219 - OG9 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-01230 | 1914 | 6" CMU (2 hour rated) | 520500 | 140624 | 520500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
OG10-01275 | 1916 | Face Brick 3-5/8" | 190500 | 93486 | 190500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
OG10-01250 | 1918 | Cast Stone with SS letters | 5228.3 | 6487 | 2614.15 | 0 | 871.3833 | 871.3833 | 871.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 222 - OG10 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG10-01105 | 1921 | STEEL (MATERIAL ONLY) | 88000 | 102320 | 88000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1922 | FABRICATION COSTS | 229500 | 226149 | 229500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1923 | METAL DECK (BUY-OUT) | 10000 | 11629 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1925 | ANCHORS & EMBEDS | 6000 | 6978 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1926 | SURVEYING | 8500 | 9884 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1927 | STEEL & DECK ERECTION | 300000 | 348817 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1928 | BOLTS AND HARDWARE | 6000 | 6978 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01105 | 1929 | TRUCKING | 6000 | 6978 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
OG10-01270 | 1930 | Dunnage Grating Galvanized | 18151 | 19967 | 18151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01270 | 1931 | Dunnage Stair with Guard Railing | 19938 | 21932 | 19938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01290 | 1932 | Stair B: First Floor to Roof Stair and Landing with Hand & Guard Rail | 112703 | 123974 | 112703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01295 | 1933 | Ship Ladder First Floor to Second Floor with Cage and Upper Platform | 15236 | 16760 | 15236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01295 | 1934 | Ship Ladder Bulkhead | 6395 | 7035 | 6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 223 - OG10 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
OG10-01305 | 1936 | Layout | 7375 | 6292 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01305 | 1937 | Loading | 17875 | 17370 | 17875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01305 | 1938 | Exterior Framing, Insulation & Drywall - Materials | 53375 | 57656 | 53375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01305 | 1939 | Exterior Framing- Labor | 81375 | 84514 | 81375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 224 - OG10 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01305 | 1944 | Insulation- Labor | 3875 | 4740 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01255 | 1948 | Layout | 84988 | 89238 | 84988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG10-01255 | 1949 | Framing | 193240 | 202902 | 193240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG10-01255 | 1950 | Insulation | 34610 | 36341 | 34610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG10-01255 | 1951 | Cladding Install | 242272 | 254386 | 230158.4 | 4037.8667 | 4037.8667 | 4037.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG10-01225 | 1952 | Fireproofing | 34000 | 37400 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
OG10-01265 | 1953 | P&I Cold Applied Roof Membrane | 48880 | 48805 | 48880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG10-01265 | 1954 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 59800 | 59708 | 59800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG10-01265 | 1955 | P&I Aluminum Coping | 6417 | 6138 | 0 | 0 | 6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 225 - OG10 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
OG10-01245 | 1958 | Doors, Frames & Hardware - Labor | 8500 | 18906 | 7600.8146 | 599.457 | 0 | 299.7285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01317 | 1959 | Louvers Install | 31726 | 63452 | 0 | 15863 | 15863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 226 - OG10 - Division 8 | 0% | NAVILLUS | 0 | NEW BUILDINGS
OG10-01305 | 1961 | Sheathing & Drywall - Labor | 17750 | 36519 | 17750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01245 | 1962 | Tape/ Spackle finishes | 6875 | 14144 | 6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01315 | 1963 | ACT ceilings - Materials | 1500 | 3086 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01315 | 1964 | ACT ceilings - Labor | 7250 | 14915 | 0 | 0 | 7250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01280 | 1965 | Direct Applied Stucco | 20200 | 41559 | 0 | 10478.8806 | 9721.1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
OG10-01325 | 1966 | Painting OG-10 | 55000 | 110000 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 227 - OG10 - Division 9 | 0% | GG PAINT | 0 | NEW BUILDINGS
SG2-03005 | 1968 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 0 | 0 | 1030.9167 | 1030.9167 | 1030.9167 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-03105 | 1974 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 4234.5 | 235.25 | 235.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1975 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4560 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1976 | ESCUTCHEONS FOR PLUMBING PIPING | 2000 | 2200 | 1940 | 25 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1977 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 17200 | 18920 | 16340 | 215 | 215 | 215 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1978 | HANGERS AND SUPPORTS | 19936 | 21930 | 19337.92 | 598.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG2-03005 | 1979 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 1000 | 1100 | 700 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-03105 | 1980 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2490 | 2739 | 2241 | 0 | 0 | 0 | 0 | 166 | 83 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1981 | DOMESTIC WATER PIPING | 199920 | 219912 | 189924 | 9996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1982 | DOMESTIC WATER PIPING SPECIALTIES | 27440 | 30184 | 26068 | 1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1983 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 82500 | 71250 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1984 | SANITARY WASTE PIPING | 119990 | 131989 | 117590.2 | 799.9333 | 799.9333 | 799.9333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1985 | SANITARY WASTE PIPING SPECIALTIES | 18240 | 20064 | 18240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1986 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03140 | 1987 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 14880 | 16368 | 4910.4 | 3720 | 3720 | 2529.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03140 | 1988 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 3648 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1989 | GAS SERVICE AND PIPING | 222480 | 244728 | 211356 | 5562 | 5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG2-03005 | 1990 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 498 | 0 | 0 | 166 | 166 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-03140 | 1991 | PLUMBING FIXTURES | 16720 | 18392 | 1672 | 5016 | 5016 | 5016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1992 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 29000 | 31900 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
OG10-03105 | 1993 | Plumbing Pipe Insulation | 7800 | 2317 | 0 | 0 | 0 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | TRISTAN | 0 | NEW BUILDINGS
OG10-02145 | 1994 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 229 - OG10 - Division 22 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-OGE-M-01005 | 1995 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03112 | 1996 | Exhaust Fans: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03410 | 1997 | Exhaust Fans: Install | 15750 | 17325 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1998 | Electric Unit Heaters: Furnish | 3500 | 3850 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 1999 | Steam Unit Heater: Furnish | 4000 | 4400 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03142 | 2000 | Steam Unit Heater: Install | 34000 | 37400 | 25500 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG2-03005 | 2001 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 2600 | 2860 | 1300 | 0 | 0 | 433.3333 | 433.3333 | 433.3333 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03032 | 2002 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03142 | 2003 | Condensate Return Unit: Install | 22000 | 24200 | 11000 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03142 | 2004 | Steam Traps: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03142 | 2005 | Steam Traps: Install | 10500 | 11550 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03107 | 2006 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 123450 | 135795 | 123450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03107 | 2007 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 140000 | 154000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03007 | 2008 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 75000 | 82500 | 67500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03135 | 2009 | Mechanical Pipe: Hydrostatic Testing | 1550 | 1705 | 0 | 775 | 775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03107 | 2010 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 12500 | 13750 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03110 | 2011 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 25000 | 27500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG2-03005 | 2012 | HANGERS AND SUPPORTS | 10462.5 | 11509 | 8893.125 | 0 | 0 | 523.125 | 523.125 | 523.125 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-03145 | 2013 | HVAC Ductwork: Testing & Balancing | 1500 | 1650 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 2014 | Controls: Furnish and Install: Devices | 90000 | 99000 | 45000 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 2015 | Controls: Furnish and Install: Controls Conduit | 35000 | 38500 | 21000 | 0 | 0 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 2016 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 0 | 0 | 0 | 2925.6757 | 3358.1081 | 3716.2162 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 2017 | Controls: Connect to Final Termination Points | 7000 | 7700 | 0 | 0 | 0 | 2047.973 | 2350.6757 | 2601.3514 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-03135 | 2018 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 1755.4054 | 2014.8649 | 2229.7297 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 2019 | Insulation: Furnish and Install: Ductwork Insulation | 11000 | 12100 | 0 | 0 | 0 | 2200 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 2020 | Insulation: Furnish and Install: Piping Insulation | 22000 | 24200 | 0 | 0 | 0 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 2021 | Insulation: Furnish and Install: Equipment Insulation | 11000 | 12100 | 0 | 0 | 0 | 2200 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 230 - OG10 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG10-02335 | 2022 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG2-03005 | 2023 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-02335 | 2024 | ATS Installation | 140000 | 153300 | 133000 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02335 | 2025 | ATS Terminations | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02335 | 2026 | ATS Testing | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02125 | 2027 | Cabling - Interior Branch (1/0 & Smaller) | 75000 | 75000 | 37500 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02395 | 2028 | Cabling - Risers & Feeders (2/0 & Larger) | 270000 | 295650 | 0 | 0 | 0 | 67500 | 67500 | 67500 | 67500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02115 | 2029 | Conduit - Branch Circuits (1 1/2" & Smaller) | 75000 | 82125 | 67500 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02105 | 2030 | Conduit - In-Slab | 115500 | 126473 | 115500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02110 | 2031 | Conduit - Risers (2" & Larger) | 288000 | 315360 | 273600 | 0 | 0 | 0 | 4800 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02400 | 2032 | Firestopping | 5000 | 5250 | 3750 | 0 | 0 | 937.5 | 104.1667 | 104.1667 | 104.1667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-OG10-01145 | 2033 | Generator Delivery | 50000 | 52500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG2-03005 | 2034 | DOMESTIC WATER PIPING | 105165 | 115682 | 89390.25 | 0 | 0 | 5258.25 | 5258.25 | 5258.25 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
P-OG10-01010 | 2035 | Generator Release | 300000 | 315000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02315 | 2036 | Generator Terminations | 50000 | 52500 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02535 | 2037 | Generator Test | 50000 | 52500 | 25000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02160 | 2038 | Lighting Controls | 20000 | 21000 | 10000 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02135 | 2039 | Lighting Install | 54000 | 56700 | 40500 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02240 | 2040 | Lighting Rough | 54000 | 59940 | 48600 | 2700 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02160 | 2041 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02325 | 2042 | Lightning Protection | 20000 | 21900 | 10000 | 3750 | 0 | 0 | 2083.3333 | 2083.3333 | 2083.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02140 | 2043 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 17400 | 0 | 0 | 0 | 13533.3333 | 13533.3333 | 13533.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-OGE-01020 | 2044 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG2-03005 | 2045 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 12580 | 0 | 0 | 740 | 740 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-02155 | 2046 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02525 | 2047 | Switchgear & Panelboard Energization | 17500 | 19163 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02405 | 2048 | Switchgear & Panelboard Installation | 210000 | 229950 | 199499.0868 | 0 | 0 | 6000.5219 | 4500.3914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02405 | 2049 | Switchgear & Panelboard Terminations | 17500 | 19163 | 0 | 0 | 0 | 10000 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02520 | 2050 | Switchgear & Panelboard Testing | 17500 | 19163 | 0 | 0 | 0 | 0 | 5833.3333 | 5833.3333 | 5833.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02005 | 2051 | Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 231 - OG10 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02115 | 2052 | Fire Alarm Conduit | 30000 | 32850 | 24000 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02385 | 2053 | Fire Alarm Wiring | 30000 | 32850 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02385 | 2054 | Fire Alarm Devices | 46000 | 50370 | 23000 | 0 | 0 | 0 | 7666.6667 | 7666.6667 | 7666.6667 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
OG10-02385 | 2055 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG2-03005 | 2056 | SANITARY WASTE PIPING | 123120 | 135432 | 110808 | 0 | 0 | 4104 | 4104 | 4104 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG10-02540 | 2057 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OG10 | 232 - OG10 - Division 28 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG2-03005 | 2067 | SANITARY WASTE PIPING SPECIALTIES | 17625 | 19388 | 16743.75 | 0 | 0 | 293.75 | 293.75 | 293.75 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG2-03005 | 2078 | STORM DRAINAGE PIPING SPECIALTIES | 30000 | 33000 | 12000 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OGE-02010 | 2081 | Manhole Work | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
OGE-02215 | 2082 | Site Lighting - Cable | 62500 | 68438 | 0 | 0 | 0 | 0 | 0 | 20833.3333 | 20833.3333 | 20833.3333 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
OGE-02210 | 2083 | Site Lighting - Conduit | 80000 | 87600 | 60000 | 2857.1429 | 2857.1429 | 2857.1429 | 3809.5238 | 3809.5238 | 3809.5238 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
OGE-02220 | 2084 | Site Lighting - Fixtures | 98900 | 108296 | 0 | 0 | 0 | 0 | 0 | 32966.6667 | 32966.6667 | 32966.6667 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
SURV-OGE-01020 | 2085 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
OGE-02115 | 2086 | Underground Electric Service - Cable | 950000 | 1040250 | 617500 | 0 | 0 | 110833.3333 | 110833.3333 | 110833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
OGE-01155 | 2087 | Underground Electric Service - Conduit | 750000 | 821250 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 236 - OGE - Division 26 | 0% | FIVE STAR | 0 | SITE
SG2-03030 | 2089 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 169998 | 186998 | 144498.3 | 0 | 0 | 8499.9 | 8499.9 | 8499.9 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG2-03005 | 2100 | GAS SERVICE AND PIPING | 1920 | 2112 | 0 | 0 | 0 | 640 | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OGE-01740 | 2104 | 4' Chain Link Fence | 21233.3333 | 23650 | 0 | 0 | 0 | 0 | 0 | 19817.7778 | 1415.5556 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | 0 | SITE
OGE-01745 | 2105 | 10' Chain Link Fence | 22220.9302 | 24750 | 0 | 0 | 0 | 0 | 0 | 0 | 22220.9302 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | 0 | SITE
OGE-01745 | 2107 | Ametco Fence | 126166.6667 | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63083.3333 | 63083.3333 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ATLAS | 0 | SITE
OGE-01710 | 2108 | 4" CONCRETE | 45000 | 49500 | 22500 | 0 | 0 | 0 | 20892.8571 | 1607.1429 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01710 | 2109 | 5"POROUS CONCRETE | 501200 | 551320 | 200480 | 0 | 0 | 100240 | 100240 | 100240 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01730 | 2110 | 5" COLOR CONCRETE | 35000 | 38500 | 33250 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
SG2-03005 | 2111 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OGE-01705 | 2112 | CONCRETE CURB | 35000 | 38500 | 21000 | 0 | 0 | 13333.3333 | 666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01705 | 2113 | SFC -STELL FACING CURB | 4000 | 4400 | 0 | 0 | 0 | 3809.5238 | 190.4762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01710 | 2114 | CONCRETE STEPS | 33600 | 36960 | 25200 | 0 | 0 | 0 | 7800 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | JMC | 0 | SITE
OGE-01760 | 2118 | Deciduous Trees | 13499.7816 | 14175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749.8908 | 6749.8908 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01760 | 2119 | Evergreen Trees | 2699.5556 | 2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349.7778 | 1349.7778 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01760 | 2120 | Deciduous Shrubs | 420 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01025 | 2121 | Tree Removal | 5514.1095 | 34914 | 5514.1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
SG2-03005 | 2122 | Plumbing Pipe Insulation | 25100 | 35464 | 22590 | 0 | 1255 | 1255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
OGE-01755 | 2123 | Lawn Seeding (not including topsoil) | 11282.2771 | 9671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5641.1385 | 5641.1385 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01025 | 2124 | Soil Erosion Mat | 7664.5957 | 6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3832.2978 | 3832.2978 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01755 | 2125 | Topsoil Stockpile/Spread | 65322.6606 | 67996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32661.3303 | 32661.3303 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01755 | 2126 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 0 | OGE | 238 - OGE - Division 32 | 0% | ASPEN | 0 | SITE
OGE-01380 | 2129 | INSTALL HW, CW PIPE - OGE | 73333.33 | 231845 | 73333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | WELKIN | 0 | SITE
OGE-01280 | 2131 | INSTALL CONDENSATE AND STEAM PIPE - OGE | 260000 | 427171 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGE | 239 - OGE - Division 33 | 0% | WELKIN | 0 | SITE
SG2-02040 | 2133 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 0 | SG2 | 024 - SG2 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGS-M-01005 | 2144 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 2155 | Exhaust Fans: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-03112 | 2166 | Exhaust Fans: Install | 4150 | 4565 | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OGW-02010 | 2167 | Manhole Installation | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
OGW-02215 | 2168 | Site Lighting - Cable | 75000 | 82125 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
OGW-02210 | 2169 | Site Lighting - Conduit | 70000 | 76650 | 63000 | 1500 | 1500 | 1500 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
OG5-02250 | 2170 | Site Lighting - Fixtures | 78200 | 85629 | 0 | 0 | 0 | 0 | 0 | 26066.6667 | 26066.6667 | 26066.6667 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
SURV-OGW-E-01015 | 2171 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
OGW-02115 | 2172 | Underground Electric Service - Cable | 1000000 | 1095000 | 750000 | 142857.1429 | 107142.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
OGW-01155 | 2173 | Underground Electric Service - Conduit | 825000 | 903375 | 825000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 243 - OGW - Division 26 | 0% | FIVE STAR | 0 | SITE
OG1-03032 | 2177 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-03032 | 2188 | Steam Unit Heaters: Install | 9000 | 9900 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OGW-01740 | 2191 | 4' Chain Link Fence | 88883.7209 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88883.7209 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | 0 | SITE
OGW-01745 | 2192 | 10' Chain Link Fence | 17282.9457 | 19250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17282.9457 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | 0 | SITE
OGW-01745 | 2194 | Ametco Fence | 126166.6667 | 136950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63083.3333 | 63083.3333 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ATLAS | 0 | SITE
OGW-01710 | 2195 | 4" CONCRETE | 130000 | 143000 | 19500 | 0 | 36833.3333 | 36833.3333 | 36833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01710 | 2196 | 7" CONCRETE RAMP | 2500 | 2750 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01710 | 2197 | 5" POROUS CONCRETE | 417300 | 459030 | 0 | 139100 | 139100 | 139100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01730 | 2198 | 5" COLOR CONCRETE | 36000 | 39600 | 16200 | 0 | 6600 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OG2-03032 | 2199 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OGW-01705 | 2200 | CONCRETE CURB | 36000 | 39600 | 14400 | 0 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01705 | 2201 | SFC -STELL FACING CURB | 25000 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01710 | 2202 | CONCRETE STEPS | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | JMC | 0 | SITE
OGW-01760 | 2205 | Deciduous Trees | 8775.0961 | 9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4387.5481 | 4387.5481 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01760 | 2206 | Deciduous Shrubs | 2660 | 2793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1330 | 1330 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01760 | 2207 | Evergreen Shrubs | 3509.6191 | 3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754.8096 | 1754.8096 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01760 | 2208 | Perennials | 7892.5721 | 8180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3946.286 | 3946.286 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01755 | 2209 | Grasses | 15592.3576 | 16160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7796.1788 | 7796.1788 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
SG2-03032 | 2210 | Condensate Return Unit: Install | 15000 | 16500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OGW-01025 | 2211 | Tree Removal | 6214.8629 | 39351 | 6214.8629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01755 | 2212 | Lawn Seeding (not including topsoil) | 11191.2815 | 9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5595.6408 | 5595.6408 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01025 | 2213 | Soil Erosion Mat | 1151.9178 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575.9589 | 575.9589 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01755 | 2214 | Topsoil Stockpile/Spread | 65062.3153 | 67725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32531.1576 | 32531.1576 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
OGW-01755 | 2215 | Maintenance | 2553.5586 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276.7793 | 1276.7793 | 0 | 0 | OGW | 245 - OGW - Division 32 | 0% | ASPEN | 0 | SITE
SGS-01355 | 2218 | INSTALL HW, CW PIPE - OGW | 183333.33 | 452669 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | WELKIN | 0 | SITE
OGW-01280 | 2220 | INSTALL CONDENSATE AND STEAM PIPE - OGW | 260000 | 622421 | 254800 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OGW | 246 - OGW - Division 33 | 0% | WELKIN | 0 | SITE
SG2-03112 | 2221 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-03112 | 2232 | Heating and Ventilation Unit: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8E-01005 | 2241 | Gaskets | 33750 | 101250 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 6750 | 6750 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01010 | 2242 | Wire Insulation | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG2-03015 | 2243 | Steam Traps: Furnish | 1200 | 1320 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8E-01015 | 2244 | Assumed Flooring Material (Slab Penetrations) | 3600 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 720 | 720 | 720 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01015 | 2245 | Vinyl Membrane and Mastic | 24038 | 72114 | 0 | 0 | 0 | 0 | 0 | 0 | 4807.6 | 4807.6 | 4807.6 | 4807.6 | 4807.6 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01015 | 2246 | Caulk | 61500 | 184500 | 17250 | 0 | 0 | 0 | 0 | 0 | 8850 | 8850 | 8850 | 8850 | 8850 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01015 | 2247 | Fibrous Slate | 8500 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 1700 | 1700 | 1700 | 1700 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01020 | 2248 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 662.8 | 662.8 | 662.8 | 662.8 | 662.8 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
S8E-01020 | 2249 | Underground Utility Materials | 1560 | 4680 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 312 | 312 | 312 | 312 | 0 | S81 | 247 - S8 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG2-03015 | 2254 | Steam Traps: Install | 11000 | 12100 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-01250 | 2264 | Cast Stone with SS letters | 5370.7 | 6870 | 0 | 5370.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 249 - S8 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
OG1-03032 | 2265 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-01270 | 2266 | Dunnage Grating Galvanized | 18339 | 20173 | 18339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01270 | 2267 | Dunnage Stair and Guard Rail at 1 Location | 11850 | 13035 | 0 | 0 | 0 | 11850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01290 | 2268 | Stair A: 1st, 2nd & 3rd Floor Stair and Landing with Hand & Guard Rail | 103538 | 124892 | 93184.2 | 10353.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01295 | 2269 | Ship Ladder with Cage and Platform | 23136 | 25450 | 0 | 11568 | 11568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8A-01295 | 2270 | Bulkhead Roof Access Ship Ladder at 2 Locations | 13919 | 15311 | 0 | 6959.5 | 6959.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 250 - S8 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
S8E-01860 | 2271 | Temporary Aluminum Over Pass Stair | 103992 | 114392 | 0 | 0 | 0 | 0 | 0 | 103992 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 250 - S8 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
08080 | 2272 | Overhead Door | 11316 | 16000 | 0 | 0 | 0 | 5658 | 5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 251 - S8 - Division 8 | 0% | Loading Dock | 0 | NEW BUILDINGS
S8A-01325 | 2273 | Painting S8-2 | 55000 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 17500 | 0 | 0 | 0 | 0 | S82 | 252 - S8 - Division 9 | 0% | GG PAINT | 0 | NEW BUILDINGS
SG2-03032 | 2276 | Vacuum Pump Unit: Install | 18000 | 19800 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-03107 | 2287 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 83500 | 91850 | 83500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-03007 | 2298 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 111000 | 122100 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-03007 | 2309 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 41000 | 45100 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8E-03005 | 2313 | Plumbing Pipe Insulation | 40800 | 53797 | 0 | 0 | 0 | 20400 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 256 - S8 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
SG2-03025 | 2320 | Mechanical Pipe: Hydrostatic Testing | 1500 | 1650 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8-01740 | 2329 | 4' High Steel Bar Fence | 78513.9535 | 87450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78513.9535 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ATLAS | 0 | SITE
OG1-03007 | 2331 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 9900 | 8820 | 0 | 0 | 173.0769 | 0 | 0 | 6.9231 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8-01710 | 2332 | 4" CONCRETE | 35000 | 38500 | 0 | 0 | 0 | 0 | 0 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01710 | 2333 | 5"POROUS CONCRETE | 135400 | 148940 | 0 | 0 | 0 | 0 | 0 | 67700 | 67700 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01730 | 2334 | 5" COLOR CONCRETE | 110000 | 121000 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01705 | 2335 | CONCRETE CURB | 35000 | 38500 | 0 | 0 | 0 | 0 | 0 | 17500 | 17500 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01705 | 2336 | SFC -STELL FACING CURB | 8000 | 8800 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01710 | 2337 | CONCRETE STEPS | 8000 | 9240 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | JMC | 0 | SITE
S8-01760 | 2339 | Deciduous Trees | 10799.8253 | 11340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5399.9126 | 5399.9126 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01760 | 2340 | Evergreen Trees | 2025.3809 | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6904 | 1012.6904 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01760 | 2341 | Deciduous Shrubs | 840 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 420 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
OG1-03110 | 2342 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 15680 | 0 | 0 | 307.6923 | 0 | 0 | 12.3077 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8-01760 | 2343 | Evergreen Shrubs | 1350.1465 | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675.0732 | 675.0732 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01760 | 2344 | Perennials | 3234.2178 | 3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617.1089 | 1617.1089 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01755 | 2345 | Grasses | 6006.3382 | 6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003.1691 | 3003.1691 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01025 | 2346 | Tree Removal | 5164.4435 | 32700 | 789.6703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2582.2217 | 1792.5515 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01755 | 2347 | Lawn Seeding (not including topsoil) | 3057.6826 | 2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1528.8413 | 1528.8413 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01755 | 2348 | Topsoil Stockpile/Spread | 18217.4483 | 18963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9108.7241 | 9108.7241 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
S8-01755 | 2349 | Maintenance | 2535.7657 | 2659.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267.8828 | 1267.8828 | 0 | 0 | S8 | 258 - S8 - Division 32 | 0% | ASPEN | 0 | SITE
SGN-01135 | 2352 | INSTALL CONDENSATE AND STEAM PIPE - S8 | 43333.33 | 55999 | 0 | 0 | 0 | 20000 | 23333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S8 | 259 - S8 - Division 33 | 0% | WELKIN | 0 | SITE
SG2-03135 | 2353 | HVAC Ductwork: Testing & Balancing | 1000 | 1100 | 0 | 0 | 0 | 19.2308 | 0 | 0 | 980.7692 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2364 | Controls: Furnish and Install: Devices | 65000 | 71500 | 61750 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2375 | Controls: Furnish and Install: Controls Conduit | 30000 | 33000 | 28500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-01275 | 2378 | 2" Face Brick | 343000 | 346786 | 0 | 171500 | 171500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
S8A-01230 | 2380 | 6" CMU (2 hour rated) | 387000 | 249945 | 0 | 0 | 77417.0317 | 103194.3228 | 103194.3228 | 103194.3228 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 261 - S81 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
OG1-03120 | 2386 | Controls: Furnish and Install: Controls Wiring | 9000 | 9900 | 8550 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-01105 | 2389 | STEEL (MATERIAL ONLY) | 110000 | 117614 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2390 | FABRICATION COSTS | 265000 | 226674 | 265000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2391 | METAL DECK (BUY-OUT) | 10000 | 10693 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2392 | ANCHORS & EMBEDS | 8000 | 8554 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2393 | SURVEYING | 6000 | 6416 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2394 | STEEL & DECK ERECTION | 400000 | 433032 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2395 | BOLTS AND HARDWARE | 10000 | 9623 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
S8A-01105 | 2396 | TRUCKING | 12000 | 10693 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 262 - S81 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
OG1-03120 | 2397 | Controls: Connect to Final Termination Points | 6000 | 6600 | 5700 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-01255 | 2405 | Layout | 53137 | 55794 | 0 | 0 | 0 | 0 | 26568.5 | 26568.5 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
S8A-01255 | 2406 | Framing | 111161 | 116720 | 111161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
S8A-01255 | 2407 | Insulation | 19909 | 20905 | 19909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG2-03135 | 2408 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-01255 | 2409 | Cladding Install | 139366 | 146335 | 0 | 0 | 0 | 0 | 69683 | 69683 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 263 - S81 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
S8A-01317 | 2410 | Louvers Install | 18250 | 36500 | 0 | 0 | 0 | 0 | 9125 | 9125 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 264 - S81 - Division 8 | 0% | NAVILLUS | 0 | NEW BUILDINGS
S8E-03005 | 2414 | COMMON WORK RESULTS FOR PLUMBING | 15371 | 15371 | 8454.05 | 0 | 0 | 2305.65 | 2305.65 | 2305.65 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2415 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 6000 | 6000 | 4500 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2416 | ESCUTCHEONS FOR PLUMBING PIPING | 2500 | 2500 | 750 | 0 | 0 | 583.3333 | 583.3333 | 583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2417 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 12200 | 12200 | 1220 | 0 | 0 | 3660 | 3660 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2418 | HANGERS AND SUPPORTS | 21800 | 21800 | 10900 | 0 | 0 | 3633.3333 | 3633.3333 | 3633.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03040 | 2419 | Insulation: Furnish and Install: Ductwork Insulation | 7000 | 7700 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8E-03005 | 2420 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2975 | 2975 | 0 | 0 | 0 | 991.6667 | 991.6667 | 991.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2421 | DOMESTIC WATER PIPING | 258984 | 284883 | 90644.4 | 0 | 0 | 0 | 56113.2 | 56113.2 | 56113.2 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2422 | DOMESTIC WATER PIPING SPECIALTIES | 38000 | 38000 | 0 | 0 | 0 | 12666.6667 | 12666.6667 | 12666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2423 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 75000 | 18750 | 0 | 0 | 18750 | 18750 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2424 | SANITARY WASTE PIPING | 155246 | 170771 | 131959.1 | 0 | 0 | 7762.3 | 7762.3 | 7762.3 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2425 | SANITARY WASTE PIPING SPECIALTIES | 58485 | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2426 | STORM DRAINAGE PIPING SPECIALTIES | 58485 | 58485 | 55560.75 | 0 | 0 | 974.75 | 974.75 | 974.75 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03030 | 2427 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 359996 | 359996 | 269997 | 0 | 0 | 29999.6667 | 29999.6667 | 29999.6667 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03030 | 2428 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 145920 | 145920 | 58368 | 0 | 0 | 29184 | 29184 | 29184 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2429 | GAS SERVICE AND PIPING | 239050 | 262955 | 59762.5 | 0 | 0 | 0 | 59762.5 | 59762.5 | 59762.5 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG1-03040 | 2430 | Insulation: Furnish and Install: Piping Insulation | 16500 | 18150 | 0 | 0 | 8250 | 0 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8E-03030 | 2431 | PLUMBING FIXTURES | 5200 | 5200 | 0 | 0 | 0 | 1733.3333 | 1733.3333 | 1733.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-03005 | 2432 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 57428 | 63171 | 28714 | 0 | 0 | 9571.3333 | 9571.3333 | 9571.3333 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
S8E-02055 | 2433 | Heat Trace | 5000 | 5000 | 0 | 0 | 4285.7143 | 0 | 0 | 0 | 0 | 238.0952 | 238.0952 | 238.0952 | 0 | 0 | S81 | 267 - S81 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-S8-M-01005 | 2434 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 2435 | Exhaust Fans: Furnish | 8400 | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2436 | Exhaust Fans: Install | 19050 | 19050 | 0 | 2625.354 | 1539.2486 | 13596.0968 | 1289.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2437 | Electric Unit Heaters: Furnish | 3500 | 3500 | 0 | 482.3485 | 282.8016 | 2497.9705 | 236.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2438 | Steam Unit Heater: Install | 20000 | 20000 | 0 | 2756.2771 | 1616.0091 | 14274.1174 | 1353.5964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2439 | Steam Unit Heater: Furnish | 54000 | 54000 | 0 | 7441.9483 | 4363.2245 | 38540.117 | 3654.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2440 | Condensate Return Unit: Furnish | 14000 | 14000 | 0 | 1929.394 | 1131.2063 | 9991.8822 | 947.5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2441 | Insulation: Furnish and Install: Equipment Insulation | 7000 | 7700 | 0 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 025 - SG2 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2442 | Condensate Return Unit: Install | 35000 | 35000 | 0 | 4823.485 | 2828.0159 | 24979.7055 | 2368.7937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2443 | Steam Traps: Furnish | 4400 | 4400 | 0 | 606.381 | 355.522 | 3140.3058 | 297.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2444 | Steam Traps: Install | 34000 | 34000 | 0 | 4685.6711 | 2747.2154 | 24265.9996 | 2301.1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2445 | Heating and Ventilation Unit: Furnish | 6500 | 6500 | 0 | 895.7901 | 525.2029 | 4639.0882 | 439.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2446 | Heating and Ventilation Unit: Install | 24000 | 24000 | 0 | 3307.5326 | 1939.2109 | 17128.9409 | 1624.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2447 | Vacuum Pump Unit: Furnish | 16000 | 16000 | 0 | 2205.0217 | 1292.8072 | 11419.2939 | 1082.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03142 | 2448 | Vacuum Pump Unit : Install | 26000 | 26000 | 0 | 3583.1603 | 2100.8118 | 18556.3527 | 1759.6753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2449 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 250500 | 250500 | 25050 | 41140.3551 | 62304.7585 | 61230.1705 | 49843.8068 | 10930.9091 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2450 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 465000 | 511500 | 9300 | 76368.3239 | 115655.5398 | 113660.7955 | 92524.4318 | 57490.9091 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2451 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 160000 | 0 | 26277.2727 | 39795.4545 | 39109.0909 | 31836.3636 | 22981.8182 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-02010 | 2452 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-03135 | 2453 | Mechanical Pipe: Hydrostatic Testing | 4500 | 4950 | 0 | 739.0483 | 1119.2472 | 1099.9432 | 895.3977 | 646.3636 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2454 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 35000 | 35000 | 17500 | 0 | 8467.7419 | 8467.7419 | 8467.7419 | -2634.4086 | -2634.4086 | -2634.4086 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 2455 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 70000 | 77000 | 35000 | 0 | 16935.4839 | 16935.4839 | 16935.4839 | -5268.8172 | -5268.8172 | -5268.8172 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03145 | 2456 | HVAC Ductwork: Testing & Balancing | 3500 | 3500 | 0 | 0 | 846.7742 | 846.7742 | 846.7742 | 846.7742 | 0 | 112.9032 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2457 | Controls: Furnish and Install: Devices | 115000 | 115000 | 42550 | 0 | 0 | 0 | 0 | 22406.3625 | 50043.6375 | 0 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2458 | Controls: Furnish and Install: Controls Conduit | 60000 | 60000 | 18000 | 0 | 0 | 0 | 0 | 11690.2761 | 29135.6543 | 1174.0696 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2459 | Controls: Furnish and Install: Controls Wiring | 17250 | 17250 | 0 | 0 | 0 | 0 | 0 | 3360.9544 | 8376.5006 | 5512.545 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2460 | Controls: Connect to Final Termination Points | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 1948.3794 | 4855.9424 | 3195.6783 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-03135 | 2461 | Controls: Controls Testing | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 1169.0276 | 2913.5654 | 1917.407 | 0 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2462 | Insulation: Furnish and Install: Ductwork Insulation | 16500 | 18150 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 4950 | 3300 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG2-02035 | 2463 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 175000 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 8750 | 8750 | 8750 | 8750 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
OG1-03040 | 2464 | Insulation: Furnish and Install: Piping Insulation | 27500 | 30250 | 0 | 0 | 0 | 0 | 0 | 0 | 13750 | 8250 | 5500 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2465 | Insulation: Furnish and Install: Equipment Insulation | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 4950 | 3300 | 0 | 0 | 0 | S81 | 268 - S81 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
S8A-02345 | 2466 | ATS Energization | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02345 | 2467 | ATS Installation | 210000 | 210000 | 168000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02345 | 2468 | ATS Terminations | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02345 | 2469 | ATS Testing | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02010 | 2470 | Bypass Connections (Misc Panels, Re-routes, etc) | 5000 | 5000 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02040 | 2471 | Cabling - Interior Branch (1/0 & Smaller) | 225000 | 225000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02115 | 2472 | Cabling - Risers & Feeders (2/0 & Larger) | 810000 | 886950 | 0 | 0 | 0 | 202500 | 202500 | 202500 | 202500 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02030 | 2473 | Conduit - Branch Circuits (1 1/2" & Smaller) | 125000 | 136875 | 12500 | 16071.4286 | 16071.4286 | 16071.4286 | 21428.5714 | 21428.5714 | 21428.5714 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02135 | 2474 | Cabling - Risers & Feeders (2/0 & Larger) | 630000 | 689850 | 0 | 27397.2603 | 90000 | 90000 | 18264.8402 | 18264.8402 | 18264.8402 | 91952.0548 | 91952.0548 | 91952.0548 | 91952.0548 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02155 | 2475 | Conduit - In-Slab | 198000 | 216810 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02105 | 2476 | Conduit - Risers (2" & Larger) | 900000 | 985500 | 630000 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02010 | 2477 | Demolition | 20000 | 20000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 5666.6667 | 5666.6667 | 5666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02130 | 2478 | Firestopping | 5000 | 5000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02025 | 2479 | Foundation Coring | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
P-S8A-01100 | 2480 | Generator Delivery | 50000 | 50000 | 0 | 0 | 0 | 0 | 28571.4286 | 14285.7143 | 0 | 2380.9524 | 2380.9524 | 2380.9524 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
P-S8A-01030 | 2481 | Generator Release | 300000 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02310 | 2482 | Generator Terminations | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 46428.5714 | 0 | 1190.4762 | 1190.4762 | 1190.4762 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02510 | 2483 | Generator Test | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02160 | 2484 | Lighting Controls | 50000 | 50000 | 25000 | 0 | 0 | 12500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02020 | 2485 | Conduit - Branch Circuits (1 1/2" & Smaller) | 175000 | 191625 | 17500 | 0 | 0 | 7159.0909 | 0 | 0 | 0 | 37585.2273 | 37585.2273 | 37585.2273 | 37585.2273 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02110 | 2486 | Lighting Install | 67800 | 67800 | 33900 | 0 | 0 | 27120 | 0 | 0 | 0 | 2260 | 2260 | 2260 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02365 | 2487 | Lighting Rough | 67800 | 67800 | 0 | 0 | 0 | 0 | 54240 | 0 | 0 | 4520 | 4520 | 4520 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG1-02025 | 2488 | Lighting System Program & Energize | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02370 | 2489 | Lightning Protection | 20000 | 20000 | 10000 | 0 | 0 | 0 | 0 | 8333.3333 | 0 | 555.5556 | 555.5556 | 555.5556 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8-02010 | 2490 | Manhole Work | 25000 | 25000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02045 | 2491 | Mechanical Terminations(Dampers, Heaters, Motors) | 100000 | 100000 | 0 | 0 | 87500 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8-02215 | 2492 | Site Lighting - Cable | 22500 | 24638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8-02210 | 2493 | Site Lighting - Conduit | 30000 | 32850 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8-02220 | 2494 | Site Lighting - Fixtures | 34500 | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 11500 | 11500 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-S8-E-01015 | 2495 | Site Survey | 64000 | 64000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02050 | 2496 | Conduit - Risers (2" & Larger) | 720000 | 788400 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 162000 | 162000 | 162000 | 162000 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-S8-E-01015 | 2497 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02125 | 2498 | Switches and Receptacles | 10000 | 10000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02520 | 2499 | Switchgear & Panelboard Energization | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02520 | 2500 | Switchgear & Panelboard Installation | 360000 | 360000 | 270000 | 0 | 0 | 0 | 0 | 0 | 25714.2857 | 64285.7143 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02520 | 2501 | Switchgear & Panelboard Terminations | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 8571.4286 | 7142.8571 | 7142.8571 | 7142.8571 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02525 | 2502 | Switchgear & Panelboard Testing | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02020 | 2503 | Temp Light & Power | 50000 | 50000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 6989.5288 | 6989.5288 | 6020.9424 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02415 | 2504 | Underground Electric Service - Cable | 375000 | 410625 | 0 | 53571.4286 | 53571.4286 | 53571.4286 | 71428.5714 | 71428.5714 | 71428.5714 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8-01155 | 2505 | Underground Electric Service - Conduit | 300000 | 328500 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S81 | 269 - S81 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8E-02030 | 2506 | Fire Alarm Conduit | 30000 | 32850 | 0 | 4285.7143 | 4285.7143 | 4285.7143 | 5714.2857 | 5714.2857 | 5714.2857 | 0 | 0 | 0 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02015 | 2507 | Demolition/Temp Light & Power | 50000 | 54750 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 5625 | 5625 | 5625 | 5625 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02380 | 2508 | Fire Alarm Wiring | 30000 | 31500 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02380 | 2509 | Fire Alarm Devices | 57000 | 57000 | 28500 | 0 | 0 | 0 | 14250 | 0 | 0 | 4750 | 4750 | 4750 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02380 | 2510 | Fire Alarm Programming & Pretest | 2500 | 2500 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-02505 | 2511 | Fire Alarm FDNY Approval | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | S81 | 270 - S81 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02125 | 2518 | Firestopping | 5000 | 5250 | 0 | 4444.4444 | 0 | 0 | 0 | 0 | 0 | 138.8889 | 138.8889 | 138.8889 | 138.8889 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-01305 | 2528 | Layout | 6375 | 5109 | 0 | 0 | 0 | 0 | 5008.9286 | 910.7143 | 455.3571 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG2-02050 | 2529 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-01305 | 2530 | Loading | 14250 | 13137 | 0 | 0 | 0 | 0 | 2169.4451 | 8053.7033 | 4026.8516 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01305 | 2531 | Exterior Framing, Insulation & Drywall - Materials | 44000 | 46709 | 0 | 0 | 0 | 0 | 14130.0392 | 19913.3072 | 9956.6536 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01305 | 2532 | Exterior Framing- Labor | 55625 | 54445 | 0 | 0 | 0 | 0 | 20433.465 | 23461.0234 | 11730.5117 | 0 | 0 | 0 | 0 | 0 | S82 | 273 - S82 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01305 | 2536 | Insulation- Labor | 3875 | 4740 | 0 | 0 | 0 | 0 | 3044.6429 | 553.5714 | 276.7857 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01225 | 2539 | Fireproofing | 42000 | 46200 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
SG2-02065 | 2540 | Lighting Controls | 23000 | 24150 | 11500 | 0 | 0 | 9200 | 0 | 0 | 0 | 575 | 575 | 575 | 575 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
S8A-01265 | 2541 | P&I Cold Applied Roof Membrane | 63000 | 68145 | 0 | 0 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
S8A-01265 | 2542 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 64800 | 70092 | 0 | 0 | 64800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
S8A-01265 | 2543 | P&I Aluminum Coping | 2867 | 3102 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 274 - S82 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
S8A-01245 | 2545 | Doors, Frames & Hardware - Labor | 12125 | 26968 | 0 | 12125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 275 - S82 - Division 8 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01305 | 2547 | Sheathing & Drywall - Labor | 16500 | 33946 | 0 | 0 | 0 | 0 | 4860.661 | 7759.5593 | 3879.7797 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01245 | 2548 | Tape/ Spackle finishes | 6500 | 13372 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
S8A-01280 | 2549 | Direct Applied Stucco | 15400 | 31684 | 0 | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S82 | 276 - S82 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG2-02015 | 2551 | Lighting Remove & Re-install | 20700 | 22667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175 | 5175 | 5175 | 5175 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02015 | 2558 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02025 | 2559 | Mechanical Terminations(Dampers, Heaters, Motors) | 40000 | 43800 | 0 | 0 | 0 | 32000 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGS-E-01030 | 2560 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG2-02110 | 2561 | Switches and Receptacles | 10000 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG7-02675 | 2562 | Switchgear & Panelboard Energization | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG7-02375 | 2563 | Switchgear & Panelboard Installation | 60000 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG7-02375 | 2564 | Switchgear & Panelboard Terminations | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG7-02680 | 2565 | Switchgear & Panelboard Testing | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG2 | 026 - SG2 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-01005 | 2569 | Gaskets | 12000 | 36000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01010 | 2570 | Wire Insulation | 12500 | 37500 | 0 | 0 | 6250 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2571 | Assumed Flooring Material (Slab Penetrations) | 12000 | 36000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2572 | Vinyl Membrane and Mastic | 17884 | 53652 | 0 | 0 | 8942 | 8942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2573 | Caulk | 34500 | 103500 | 34500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01015 | 2574 | Fibrous Slate | 4675 | 14025 | 0 | 0 | 2337.5 | 2337.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01020 | 2575 | Waterproofing | 3314 | 9942 | 0 | 0 | 1657 | 1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01020 | 2576 | Underground Utility Materials | 15600 | 46800 | 0 | 0 | 7800 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 028 - SG3 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG3-01820 | 2616 | 6" vertically reinforced CMU | 198000 | 132685 | 168300 | 0 | 0 | 9900 | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG3-01830 | 2617 | 2" Face brick | 223000 | 410182 | 22300 | 37775.9563 | 34120.2186 | 42934.6084 | 42934.6084 | 42934.6084 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG3-01820 | 2619 | Coping Stone C1/A-300 | 274000 | 22968 | 27400 | 0 | 0 | 82200 | 82200 | 82200 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 030 - SG3 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05530 | 2620 | MATERIAL AND FABRICATION | 19000 | 21224 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG3-01315 | 2621 | INSTALLATION | 34000 | 37400 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG3-01860 | 2622 | Temporary Aluminum Over Pass Stairs | 51996 | 57196 | 0 | 0 | 0 | 0 | 0 | 0 | 12999 | 38997 | 0 | 0 | 0 | 0 | SG3 | 031 - SG3 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG3-01330 | 2629 | Doors, Frames & Hardware - Labor | 2625 | 5838 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 033 - SG3 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01325 | 2631 | Layout | 4750 | 5658 | 4750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01325 | 2632 | Loading | 4250 | 8744 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01325 | 2633 | Framing & Drywall - Materials | 9875 | 13115 | 9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01325 | 2634 | Framing- Labor | 9750 | 20060 | 9750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01330 | 2635 | Drywall - Labor | 11500 | 23660 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01330 | 2636 | Tape/ Spackle finishes | 9000 | 18517 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-01855 | 2637 | Stucco | 4950 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | SG3 | 034 - SG3 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG3-03005 | 2662 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9278.25 | 0 | 0 | 1030.9167 | 1030.9167 | 1030.9167 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2663 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 960 | 1056 | 96 | 0 | 0 | 288 | 288 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2664 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 0 | 0 | 0 | 332 | 332 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2665 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 5400 | 5940 | 3780 | 0 | 0 | 540 | 540 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2666 | HANGERS AND SUPPORTS | 10465 | 11512 | 8372 | 0 | 0 | 697.6667 | 697.6667 | 697.6667 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2667 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 0 | 665 | 665 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2668 | DOMESTIC WATER PIPING | 124949 | 137444 | 99959.2 | 0 | 0 | 8329.9333 | 8329.9333 | 8329.9333 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2669 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 12580 | 0 | 0 | 740 | 740 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2670 | SANITARY WASTE PIPING | 122958 | 135254 | 98366.4 | 0 | 0 | 8197.2 | 8197.2 | 8197.2 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2671 | SANITARY WASTE PIPING SPECIALTIES | 42798 | 47078 | 38518.2 | 0 | 0 | 1426.6 | 1426.6 | 1426.6 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2672 | STORM DRAINAGE PIPING SPECIALTIES | 42798 | 47078 | 17119.2 | 0 | 0 | 8559.6 | 8559.6 | 8559.6 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03030 | 2673 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 379998 | 417998 | 341998.2 | 0 | 0 | 12666.6 | 12666.6 | 12666.6 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2674 | GAS SERVICE AND PIPING | 2055 | 2261 | 0 | 0 | 0 | 685 | 685 | 685 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2675 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 12060 | 13266 | 12060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG3-03005 | 2676 | Plumbing Pipe Insulation | 35100 | 35750 | 0 | 0 | 17550 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
SG3-02040 | 2677 | Heat Trace | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG3 | 037 - SG3 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGS-M-01005 | 2678 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 2679 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2680 | Exhaust Fans: Install | 13450 | 14795 | 6725 | 2241.6667 | 2241.6667 | 2241.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2681 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2682 | Steam Unit Heaters: Install | 16000 | 17600 | 0 | 5333.3333 | 5333.3333 | 5333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2683 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2684 | Condensate Return Unit: Install | 22000 | 24200 | 0 | 7333.3333 | 7333.3333 | 7333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2685 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 0 | 2166.6667 | 2166.6667 | 2166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2686 | Heating and Ventilation Unit: Install | 23000 | 25300 | 0 | 7666.6667 | 7666.6667 | 7666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2687 | Steam Traps: Furnish | 2800 | 3080 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03112 | 2688 | Steam Traps: Install | 23500 | 25850 | 0 | 7833.3333 | 7833.3333 | 7833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2689 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2690 | Vacuum Pump Unit: Install | 25000 | 27500 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2691 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 264150 | 290565 | 211320 | 13207.5 | 13207.5 | 13207.5 | 13207.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2692 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 405000 | 445500 | 344250 | 15187.5 | 15187.5 | 15187.5 | 15187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2693 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 160000 | 176000 | 0 | 53333.3333 | 53333.3333 | 53333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03015 | 2694 | Mechanical Pipe: Hydrostatic Testing | 5850 | 6435 | 0 | 1950 | 1950 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03007 | 2695 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 30000 | 33000 | 27600 | 0 | 0 | 2338.9831 | 0 | 0 | 0 | 61.0169 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 2696 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 85000 | 93500 | 78200 | 0 | 0 | 6627.1186 | 0 | 0 | 0 | 172.8814 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03235 | 2697 | HVAC Ductwork: Testing & Balancing | 3000 | 3300 | 0 | 0 | 0 | 233.8983 | 0 | 0 | 0 | 2766.1017 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2698 | Controls: Furnish and Install: Devices | 75000 | 82500 | 71250 | 0 | 0 | 3588.1295 | 0 | 0 | 161.8705 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2699 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38000 | 0 | 0 | 1913.6691 | 0 | 0 | 86.3309 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2700 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 9500 | 0 | 0 | 478.4173 | 0 | 0 | 21.5827 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2701 | Controls: Connect to Final Termination Points | 8000 | 8800 | 7600 | 0 | 0 | 382.7338 | 0 | 0 | 17.2662 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03310 | 2702 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 287.0504 | 0 | 0 | 5712.9496 | 0 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2703 | Insulation: Furnish and Install: Ductwork Insulation | 15000 | 16500 | 0 | 0 | 0 | 0 | 3750 | 0 | 9750 | 1500 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2704 | Insulation: Furnish and Install: Piping Insulation | 30000 | 33000 | 0 | 0 | 0 | 0 | 7500 | 0 | 19500 | 3000 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2705 | Insulation: Furnish and Install: Equipment Insulation | 15000 | 16500 | 0 | 0 | 0 | 0 | 3750 | 0 | 9750 | 1500 | 0 | 0 | 0 | 0 | SG3 | 038 - SG3 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-02210 | 2706 | ATS Energization | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 10416.6667 | 520.8333 | 520.8333 | 520.8333 | 520.8333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02210 | 2707 | ATS Installation | 175000 | 194250 | 87500 | 0 | 0 | 0 | 0 | 0 | 72916.6667 | 3645.8333 | 3645.8333 | 3645.8333 | 3645.8333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02210 | 2708 | ATS Terminations | 12500 | 13875 | 0 | 0 | 0 | 0 | 0 | 0 | 10416.6667 | 520.8333 | 520.8333 | 520.8333 | 520.8333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02210 | 2709 | ATS Testing | 12500 | 13688 | 0 | 0 | 0 | 0 | 0 | 0 | 10416.6667 | 520.8333 | 520.8333 | 520.8333 | 520.8333 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02010 | 2710 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 3125 | 3125 | 3125 | 3125 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02035 | 2711 | Cabling - Interior Branch (1/0 & Smaller) | 150000 | 164250 | 0 | 21428.5714 | 21428.5714 | 21428.5714 | 28571.4286 | 28571.4286 | 28571.4286 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SGS-02105 | 2712 | Cabling - Risers & Feeders (2/0 & Larger) | 360000 | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02015 | 2713 | Conduit - Branch Circuits (1 1/2" & Smaller) | 200000 | 222000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02115 | 2714 | Conduit - Risers (2" & Larger) | 360000 | 399600 | 324000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 9000 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02020 | 2715 | Demolition/Temp Light & Power | 50000 | 54750 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | 1875 | 1875 | 1875 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02145 | 2716 | Firestopping | 5000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02025 | 2717 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02125 | 2718 | Lighting Controls | 30000 | 31500 | 15000 | 12857.1429 | 0 | 0 | 0 | 0 | 0 | 535.7143 | 535.7143 | 535.7143 | 535.7143 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02020 | 2719 | Lighting Remove & Re-install | 49500 | 54203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 12375 | 12375 | 12375 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02020 | 2720 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02045 | 2721 | Mechanical Terminations(Dampers, Heaters, Motors) | 58000 | 63510 | 17400 | 34800 | 0 | 0 | 0 | 0 | 0 | 1450 | 1450 | 1450 | 1450 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGS-E-01030 | 2722 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02515 | 2723 | Switchgear & Panelboard Energization | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02265 | 2724 | Switchgear & Panelboard Installation | 360000 | 394200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02265 | 2725 | Switchgear & Panelboard Terminations | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02510 | 2726 | Switchgear & Panelboard Testing | 30000 | 32850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | SG3 | 039 - SG3 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02015 | 2727 | Fire Alarm Conduit | 25000 | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 6250 | 6250 | 6250 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02120 | 2728 | Fire Alarm Wiring | 22500 | 24638 | 0 | 16875 | 0 | 0 | 0 | 0 | 0 | 1406.25 | 1406.25 | 1406.25 | 1406.25 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02120 | 2729 | Fire Alarm Devices | 18000 | 19710 | 9000 | 6750 | 0 | 0 | 0 | 0 | 0 | 562.5 | 562.5 | 562.5 | 562.5 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02120 | 2730 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 156.25 | 156.25 | 156.25 | 156.25 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG3-02535 | 2731 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 625 | 625 | 625 | 0 | SG3 | 040 - SG3 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-01005 | 2735 | Gaskets | 15000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 3000 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01010 | 2736 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2737 | Assumed Flooring Material (Slab Penetrations) | 15600 | 46800 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01020 | 2738 | Pipe Insulation | 5250 | 15750 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2739 | Vinyl Membrane and Mastic | 14416 | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2740 | Caulk | 30000 | 90000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01015 | 2741 | Fibrous Slate | 4845 | 14535 | 4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01020 | 2742 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01020 | 2743 | Underground Utility Materials | 18200 | 54600 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 042 - SG4 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG4-01820 | 2783 | 6" vertically reinforced CMU | 210000 | 126280 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG4-01830 | 2784 | 2" Face brick | 226000 | 538422 | 203400 | 22600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG4-01820 | 2786 | Coping Stone C1/A-300 | 213000 | 18586 | 213000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 044 - SG4 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05350 | 2787 | MATERIAL AND FABRICATION | 19000 | 21224 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG4-01315 | 2788 | INSTALLATION | 34000 | 37400 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG4-01860 | 2789 | Temporary Aluminum Over Pass Stairs | 51996 | 57196 | 0 | 25998 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 045 - SG4 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG4-01330 | 2797 | Doors, Frames & Hardware - Labor | 5875 | 13066 | 5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 047 - SG4 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01325 | 2799 | Layout | 5750 | 7715 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01325 | 2800 | Loading | 7875 | 9001 | 7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01325 | 2801 | Framing & Drywall - Materials | 8500 | 17638 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01325 | 2802 | Framing- Labor | 3625 | 7458 | 3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01330 | 2803 | Drywall - Labor | 7750 | 15944 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01330 | 2804 | Tape/ Spackle finishes | 11500 | 23660 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-01855 | 2805 | Stucco | 4950 | 10183 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 048 - SG4 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG4-03005 | 2833 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 13609 | 9896.8 | 618.55 | 618.55 | 618.55 | 618.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2834 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 960 | 1056 | 864 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2835 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1096 | 896.4 | 0 | 99.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2836 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 4200 | 4620 | 2520 | 0 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2837 | HANGERS AND SUPPORTS | 10462.5 | 11509 | 8370 | 0 | 2092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2838 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2195 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2839 | DOMESTIC WATER PIPING | 128180 | 140998 | 115362 | 0 | 12818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 2840 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 16280 | 11100 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2841 | SANITARY WASTE PIPING | 110976 | 122074 | 110976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2842 | SANITARY WASTE PIPING SPECIALTIES | 41426 | 45569 | 41426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2843 | STORM DRAINAGE PIPING SPECIALTIES | 41426 | 45569 | 41426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03030 | 2844 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 295000 | 324500 | 280250 | 0 | 14750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2845 | GAS SERVICE AND PIPING | 5790 | 6369 | 5211 | 0 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2846 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 4870 | 5357 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG4-03005 | 2847 | Plumbing Pipe Insulation | 29800 | 35464 | 20860 | 0 | 4470 | 4470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
SG4-02260 | 2848 | Heat Trace | 5000 | 5475 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 051 - SG4 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGN-M-01005 | 2849 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 2850 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03112 | 2851 | Exhaust Fans: Install | 10450 | 11495 | 0 | 2612.5 | 2612.5 | 2612.5 | 2612.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2852 | Steam Unit Heaters: Furnish | 1000 | 1100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03032 | 2853 | Steam Unit Heaters: Install | 13000 | 14300 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2854 | Condensate Return Unit: Furnish | 7000 | 7700 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03032 | 2855 | Condensate Return Unit: Install | 19000 | 20900 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03112 | 2856 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03112 | 2857 | Heating and Ventilation Unit: Install | 20000 | 22000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03310 | 2858 | Steam Traps: Furnish | 2200 | 2420 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG3-03310 | 2859 | Steam Traps: Install | 16500 | 18150 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 2860 | Vacuum Pump Unit: Furnish | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03032 | 2861 | Vacuum Pump Unit: Install | 22000 | 24200 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03107 | 2862 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 172375 | 189613 | 172375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03007 | 2863 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 284000 | 312400 | 284000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03007 | 2864 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 87500 | 96250 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03025 | 2865 | Mechanical Pipe: Hydrostatic Testing | 2875 | 3163 | 2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03107 | 2866 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 17500 | 19250 | 12250 | 1685.7798 | 0 | 1188.0734 | 1188.0734 | 1188.0734 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 2867 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 35000 | 38500 | 24500 | 3371.5596 | 0 | 2376.1468 | 2376.1468 | 2376.1468 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03140 | 2868 | HVAC Ductwork: Testing & Balancing | 2000 | 2200 | 0 | 192.6606 | 0 | 602.4465 | 602.4465 | 602.4465 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2869 | Controls: Furnish and Install: Devices | 75000 | 82500 | 72000 | 1645.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2870 | Controls: Furnish and Install: Controls Conduit | 40000 | 44000 | 38400 | 877.4194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2871 | Controls: Furnish and Install: Controls Wiring | 10000 | 11000 | 9600 | 219.3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 2872 | Controls: Connect to Final Termination Points | 80000 | 88000 | 68000 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-03310 | 2873 | Controls: Controls Testing | 6000 | 6600 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2874 | Insulation: Furnish and Install: Ductwork Insulation | 11500 | 12650 | 8050 | 1725 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2875 | Insulation: Furnish and Install: Piping Insulation | 23000 | 25300 | 21850 | 575 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 2876 | Insulation: Furnish and Install: Equipment Insulation | 11500 | 12650 | 10925 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 052 - SG4 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG4-02430 | 2877 | ATS Energization | 12500 | 13688 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02430 | 2878 | ATS Installation | 175000 | 191625 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02430 | 2879 | ATS Terminations | 12500 | 13688 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02430 | 2880 | ATS Testing | 12500 | 13688 | 11875 | 0 | 0 | 0 | 208.3333 | 208.3333 | 208.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02225 | 2881 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 27375 | 23750 | 0 | 0 | 0 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02245 | 2882 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SGN-02125 | 2883 | Cabling - Risers & Feeders (2/0 & Larger) | 432000 | 473040 | 410400 | 0 | 0 | 0 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02230 | 2884 | Conduit - Branch Circuits (1 1/2" & Smaller) | 250000 | 273750 | 237500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02305 | 2885 | Conduit - Risers (2" & up) | 495000 | 542025 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02210 | 2886 | Demolition/Temp Light & Power | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02345 | 2887 | Firestopping | 5000 | 5250 | 4750 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02215 | 2888 | Foundation Coring | 20000 | 21000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02250 | 2889 | Lighting Controls | 24000 | 25200 | 22800 | 0 | 0 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02210 | 2890 | Lighting Remove & Re-install | 49500 | 54945 | 47025 | 0 | 0 | 0 | 825 | 825 | 825 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02210 | 2891 | Lighting System Program & Energize | 5000 | 5475 | 2500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02270 | 2892 | Mechanical Terminations(Dampers, Heaters, Motors) | 52000 | 56940 | 49400 | 0 | 0 | 0 | 866.6667 | 866.6667 | 866.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGN-E-01000 | 2893 | Survey | 60000 | 65700 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02425 | 2894 | Switches and Receptacles | 10000 | 10950 | 9500 | 0 | 0 | 0 | 166.6667 | 166.6667 | 166.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02515 | 2895 | Switchgear & Panelboard Energization | 27500 | 30113 | 24750 | 0 | 0 | 0 | 916.6667 | 916.6667 | 916.6667 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02455 | 2896 | Switchgear & Panelboard Installation | 330000 | 361350 | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02455 | 2897 | Switchgear & Panelboard Terminations | 27500 | 30113 | 26125 | 0 | 0 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02520 | 2898 | Switchgear & Panelboard Testing | 27500 | 30113 | 22000 | 785.7143 | 785.7143 | 785.7143 | 1047.619 | 1047.619 | 1047.619 | 0 | 0 | 0 | 0 | 0 | SG4 | 053 - SG4 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02230 | 2899 | Fire Alarm Conduit | 15000 | 16650 | 14250 | 0 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02325 | 2900 | Fire Alarm Wiring | 12000 | 13140 | 11400 | 0 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02325 | 2901 | Fire Alarm Devices | 20000 | 21900 | 19000 | 0 | 0 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02325 | 2902 | Fire Alarm Programming & Pretest | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG4-02505 | 2903 | Fire Alarm FDNY Approval | 2500 | 2738 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG4 | 054 - SG4 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-01005 | 2907 | Gaskets | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01010 | 2908 | Wire Insulation | 12500 | 37500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2909 | Assumed Flooring Material (Slab Penetrations) | 14400 | 43200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01020 | 2910 | Pipe Insulation | 50400 | 151200 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2911 | Mudded Joint Packing | 8362 | 25086 | 8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2912 | Vinyl Membrane and Mastic | 14416 | 43248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2913 | Caulk | 36000 | 108000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01015 | 2914 | Fibrous Slate | 5270 | 15810 | 5270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01020 | 2915 | Waterproofing | 3314 | 9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01020 | 2916 | Underground Utility Materials | 18200 | 54600 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 056 - SG5 - Division 2 | 0% | ATCO | 0 | EXISTING BUILDINGS
SG5-01820 | 2957 | 6" vertically reinforced CMU | 244000 | 123200 | 244000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG5-01830 | 2958 | 2" Face brick | 229000 | 530612 | 206100 | 22900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
SG5-01820 | 2960 | Coping Stone C1/A-300 | 204000 | 17319 | 204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 058 - SG5 - Division 4 | 0% | FAXA | 0 | EXISTING BUILDINGS
05380 | 2961 | MATERIAL AND FABRICATION | 19000 | 38589 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG5-01315 | 2962 | INSTALLATION | 34000 | 68000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | WEIR | 0 | EXISTING BUILDINGS
SG5-01860 | 2963 | Temporary Aluminum Over Pass Stairs | 51996 | 103992 | 0 | 25998 | 25998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 059 - SG5 - Division 5 | 0% | E&Y | 0 | EXISTING BUILDINGS
SG5-01330 | 2971 | Doors, Frames & Hardware - Labor | 2250 | 5004 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 061 - SG5 - Division 8 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01325 | 2973 | Layout | 3875 | 4170 | 3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01325 | 2974 | Loading | 6625 | 6950 | 6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01325 | 2975 | Framing & Drywall - Materials | 6500 | 14456 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01325 | 2976 | Framing- Labor | 7500 | 16680 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01330 | 2977 | Drywall - Labor | 13000 | 28914 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01330 | 2978 | Tape/ Spackle finishes | 6000 | 13344 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-01855 | 2979 | Stucco | 4950 | 11008 | 0 | 2475 | 2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 062 - SG5 - Division 9 | 0% | CCC | 0 | EXISTING BUILDINGS
SG5-03005 | 3007 | COMMON WORK RESULTS FOR PLUMBING | 12371 | 14846 | 9896.8 | 618.55 | 618.55 | 618.55 | 618.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3008 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 720 | 864 | 648 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3009 | ESCUTCHEONS FOR PLUMBING PIPING | 996 | 1196 | 697.2 | 74.7 | 74.7 | 74.7 | 74.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3010 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 3400 | 4080 | 0 | 850 | 850 | 850 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3011 | HANGERS AND SUPPORTS | 10462.5 | 12555 | 2092.5 | 2092.5 | 2092.5 | 2092.5 | 2092.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3012 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 1995 | 2394 | 0 | 498.75 | 498.75 | 498.75 | 498.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3013 | DOMESTIC WATER PIPING | 98520 | 108372 | 78816 | 4926 | 4926 | 4926 | 4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3014 | DOMESTIC WATER PIPING SPECIALTIES | 14800 | 17760 | 11100 | 925 | 925 | 925 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3015 | SANITARY WASTE PIPING | 98040 | 107844 | 78432 | 4902 | 4902 | 4902 | 4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3016 | SANITARY WASTE PIPING SPECIALTIES | 18801 | 22562 | 16920.9 | 470.025 | 470.025 | 470.025 | 470.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3017 | STORM DRAINAGE PIPING SPECIALTIES | 38800 | 46560 | 32980 | 1455 | 1455 | 1455 | 1455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03030 | 3018 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 237697.2 | 270000 | 225812.34 | 2971.215 | 2971.215 | 2971.215 | 2971.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3019 | GAS SERVICE AND PIPING | 1920 | 2112 | 0 | 480 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
SG5-03005 | 3020 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 9740 | 10714 | 9740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | VITAL | 0 | EXISTING BUILDINGS
OG5-03005 | 3021 | Plumbing Pipe Insulation | 15800 | 35464 | 15800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | TRISTAN | 0 | EXISTING BUILDINGS
SG5-02240 | 3022 | Heat Trace | 5000 | 6000 | 4000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 065 - SG5 - Division 22 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGN-M-01005 | 3023 | Survey | 60000 | 72000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03112 | 3024 | Exhaust Fans: Furnish | 3600 | 4320 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03112 | 3025 | Exhaust Fans: Install | 7450 | 8940 | 0 | 0 | 0 | 7450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 3026 | Steam Unit Heaters: Furnish | 1000 | 1200 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03032 | 3027 | Steam Unit Heaters: Install | 10000 | 12000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 3028 | Condensate Return Unit: Furnish | 7000 | 8400 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03032 | 3029 | Condensate Return Unit: Install | 16000 | 19200 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03112 | 3030 | Heating and Ventilation Unit: Furnish | 6500 | 7800 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03112 | 3031 | Heating and Ventilation Unit: Install | 17000 | 20400 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03015 | 3032 | Steam Traps: Furnish | 1600 | 1920 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03015 | 3033 | Steam Traps: Install | 13000 | 15600 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03032 | 3034 | Vacuum Pump Unit: Furnish | 16000 | 19200 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03032 | 3035 | Vacuum Pump Unit: Install | 19000 | 22800 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03107 | 3036 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 87250 | 104700 | 87250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03007 | 3037 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 152000 | 167200 | 152000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03007 | 3038 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 42000 | 50400 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03025 | 3039 | Mechanical Pipe: Hydrostatic Testing | 1750 | 1925 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03107 | 3040 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 9000 | 10800 | 8820 | 0 | 0 | 339.2308 | 0 | -159.2308 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03110 | 3041 | HVAC Ductwork: Furnish and Install: Sheetmetal and RGDs | 16000 | 17600 | 15200 | 0 | 0 | 603.0769 | 0 | 196.9231 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03035 | 3042 | HVAC Ductwork: Testing & Balancing | 1000 | 1200 | 0 | 0 | 0 | 37.6923 | 0 | 962.3077 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 3043 | Controls: Furnish and Install: Devices | 75000 | 90000 | 69583.3333 | 0 | 0 | 2708.3333 | 2708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 3044 | Controls: Furnish and Install: Controls Conduit | 35000 | 42000 | 33600 | 466.6667 | 466.6667 | 466.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 3045 | Controls: Furnish and Install: Controls Wiring | 10000 | 12000 | 9600 | 133.3333 | 133.3333 | 133.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03120 | 3046 | Controls: Connect to Final Termination Points | 7500 | 9000 | 7125 | 125 | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-03235 | 3047 | Controls: Controls Testing | 6000 | 7200 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 3048 | Insulation: Furnish and Install: Ductwork Insulation | 11500 | 12650 | 0 | 5750 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 3049 | Insulation: Furnish and Install: Piping Insulation | 23000 | 25300 | 21850 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
OG1-03040 | 3050 | Insulation: Furnish and Install: Equipment Insulation | 11500 | 13800 | 0 | 5750 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 066 - SG5 - Division 23 | 0% | WELKIN | 0 | EXISTING BUILDINGS
SG5-02420 | 3051 | ATS Energization | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02420 | 3052 | ATS Installation | 140000 | 168000 | 126000 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02420 | 3053 | ATS Terminations | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02420 | 3054 | ATS Testing | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02210 | 3055 | Bypass Connections (Misc Panels, Re-routes, etc) | 25000 | 30000 | 12500 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02235 | 3056 | Cabling - Interior Branch (1/0 & Smaller) | 160000 | 160000 | 0 | 22857.1429 | 22857.1429 | 22857.1429 | 30476.1905 | 30476.1905 | 30476.1905 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02475 | 3057 | Cabling - Risers & Feeders (2/0 & Larger) | 324000 | 354780 | 243000 | 46285.7143 | 34714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02215 | 3058 | Conduit - Branch Circuits (1 1/2" & Smaller) | 200000 | 219000 | 160000 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 13333.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02325 | 3059 | Conduit - Risers (2" & Larger) | 360000 | 394200 | 342000 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02220 | 3060 | Demolition/Temp Light & Power | 50000 | 60000 | 42500 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02345 | 3061 | Firestopping | 5000 | 6000 | 3750 | 625 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02225 | 3062 | Foundation Coring | 20000 | 24000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02265 | 3063 | Lighting Controls | 28000 | 33600 | 0 | 0 | 0 | 0 | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02220 | 3064 | Lighting Remove & Re-install | 50400 | 60480 | 0 | 0 | 0 | 0 | 16800 | 16800 | 16800 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02220 | 3065 | Lighting System Program & Energize | 5000 | 6000 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02245 | 3066 | Mechanical Terminations(Dampers, Heaters, Motors) | 52000 | 62400 | 23400 | 0 | 0 | 0 | 9533.3333 | 9533.3333 | 9533.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SURV-SGN-E-01000 | 3067 | Survey | 60000 | 72000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02460 | 3068 | Switches and Receptacles | 10000 | 12000 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02515 | 3069 | Switchgear & Panelboard Energization | 27500 | 33000 | 0 | 0 | 0 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02405 | 3070 | Switchgear & Panelboard Installation | 330000 | 396000 | 297000 | 9428.5714 | 9428.5714 | 9428.5714 | 1571.4286 | 1571.4286 | 1571.4286 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02405 | 3071 | Switchgear & Panelboard Terminations | 27500 | 33000 | 0 | 17187.5 | 0 | 0 | 3437.5 | 3437.5 | 3437.5 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02530 | 3072 | Switchgear & Panelboard Testing | 27500 | 33000 | 0 | 0 | 0 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 0 | SG5 | 067 - SG5 - Division 26 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02215 | 3073 | Fire Alarm Conduit | 15000 | 16650 | 10500 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02315 | 3074 | Fire Alarm Wiring | 12000 | 13140 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02315 | 3075 | Fire Alarm Devices | 20000 | 24000 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02315 | 3076 | Fire Alarm Programming & Pretest | 2500 | 3000 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG5-02505 | 3077 | Fire Alarm FDNY Approval | 2500 | 3000 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG5 | 068 - SG5 - Division 28 | 0% | FIVE STAR | 0 | EXISTING BUILDINGS
SG6-01230 | 3094 | 8" CMU (3 hour rated) | 478000 | 349751 | 478000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
SG6-01275 | 3096 | Face Brick 3-5/8" | 191380 | 158400 | 191380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | FAXA | 0 | NEW BUILDINGS
SG6-01250 | 3098 | Cast Stone with SS letters | 6400.3 | 8521 | 4800.225 | 0 | 533.3583 | 533.3583 | 533.3583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 071 - SG6 - Division 4 | 0% | JMC | 0 | NEW BUILDINGS
SG6-01105 | 3101 | STEEL (MATERIAL ONLY) | 141000 | 165824 | 141000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3102 | FABRICATION COSTS | 272000 | 246972 | 272000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3103 | METAL DECK (BUY-OUT) | 12000 | 14113 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3104 | ANCHORS & EMBEDS | 8000 | 9410 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3105 | SURVEYING | 10000 | 11762 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3106 | STEEL & DECK ERECTION | 490000 | 576267 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3107 | BOLTS AND HARDWARE | 20000 | 23522 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01105 | 3108 | TRUCKING | 10000 | 11762 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | WEIR | 0 | NEW BUILDINGS
SG6-01270 | 3109 | Dunnage Grating Galvanized | 55019 | 60521 | 55019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01270 | 3110 | Dunnage Guard Rail | 26334 | 28968 | 26334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01270 | 3111 | Dunnage Platform Stair with Guard Rail | 11850 | 13035 | 11850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01290 | 3112 | Stair A: Ground to Roof Floor Stair and Landing with and Hand & Guard Rail | 103968 | 136365 | 103968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01290 | 3113 | Stair B: Ground to 2nd Floor Stair and Landing with Hand & Guard Rail | 53311 | 64143 | 53311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01295 | 3114 | 1st to 2nd Floor Ship Ladder with Cage and Platform | 24641 | 27106 | 24641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01120 | 3115 | Egress Stair: Stair & Landing with Hand & Guard Rail | 58311 | 64143 | 58311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 072 - SG6 - Division 5 | 0% | E&Y | 0 | NEW BUILDINGS
SG6-01305 | 3116 | Layout | 6375 | 5109 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01305 | 3117 | Loading | 18750 | 18391 | 18750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01305 | 3118 | Exterior Framing, Insulation & Drywall - Materials | 68125 | 74880 | 68125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01305 | 3119 | Exterior Framing- Labor | 84250 | 87871 | 84250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 073 - SG6 - Division 6 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01305 | 3124 | Insulation- Labor | 5250 | 6422 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01255 | 3127 | Layout | 82513 | 86622 | 82513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG6-01255 | 3128 | Framing | 186820 | 196161 | 186820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG6-01255 | 3129 | Insulation | 33460 | 35133 | 33460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG6-01255 | 3130 | Cladding Install | 234222 | 245934 | 210799.8 | 0 | 11711.1 | 11711.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG6-01225 | 3131 | Fireproofing | 38000 | 41800 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | SIG | 0 | NEW BUILDINGS
SG6-01265 | 3132 | P&I Cold Applied Roof Membrane | 99066 | 102076 | 99066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
SG6-01265 | 3133 | P&I Roof Over Burden (D-Mat, ISO, Pavers) | 120238 | 123891 | 120238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
SG6-01265 | 3134 | P&I Aluminum Coping | 8333 | 8547 | 0 | 0 | 8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 074 - SG6 - Division 7 | 0% | TRIANGLE | 0 | NEW BUILDINGS
SG6-01245 | 3136 | Doors, Frames & Hardware - Labor | 10250 | 22798 | 10250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01317 | 3137 | Louvers Install | 30671 | 61342 | 0 | 0 | 15335.5 | 15335.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 075 - SG6 - Division 8 | 0% | NAVILLUS | 0 | NEW BUILDINGS
SG6-01305 | 3139 | Sheathing & Drywall - Labor | 19750 | 40634 | 19750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01245 | 3140 | Tape/ Spackle finishes | 6500 | 13372 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01315 | 3141 | ACT ceilings - Materials | 500 | 1029 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01315 | 3142 | ACT ceilings - Labor | 2250 | 4629 | 0 | 1125 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01280 | 3143 | Direct Applied Stucco | 9100 | 18722 | 0 | 4550 | 4550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | CCC | 0 | NEW BUILDINGS
SG6-01325 | 3144 | Painting SG-6 | 55000 | 110000 | 27500 | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 076 - SG6 - Division 9 | 0% | GG PAINT | 0 | NEW BUILDINGS
SG6-03105 | 3154 | COMMON WORK RESULTS FOR PLUMBING | 4705 | 5176 | 4705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3155 | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | 4800 | 5280 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3156 | ESCUTCHEONS FOR PLUMBING PIPING | 1980 | 2178 | 1881 | 24.75 | 24.75 | 24.75 | 24.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3157 | GENERAL-DUTY VALVES FOR PLUMBING PIPING | 18000 | 19800 | 17100 | 225 | 225 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3158 | HANGERS AND SUPPORTS | 19995 | 21995 | 18995.25 | 249.9375 | 249.9375 | 249.9375 | 249.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3159 | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPMENT | 2480 | 2728 | 0 | 620 | 620 | 620 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3160 | DOMESTIC WATER PIPING | 203775 | 224153 | 193586.25 | 2547.1875 | 2547.1875 | 2547.1875 | 2547.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3161 | DOMESTIC WATER PIPING SPECIALTIES | 36239 | 39863 | 34427.05 | 452.9875 | 452.9875 | 452.9875 | 452.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3162 | DOMESTIC WATER PUMPING SYSTEMS | 75000 | 82500 | 71250 | 937.5 | 937.5 | 937.5 | 937.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3163 | SANITARY WASTE PIPING | 108000 | 118800 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3164 | SANITARY WASTE PIPING SPECIALTIES | 19998 | 21998 | 19998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3165 | STORM DRAINAGE PIPING SPECIALTIES | 29997 | 32997 | 29997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03140 | 3166 | EJECTOR PUMPS, SUMP PUMPS AND HOT WATER CIRCULATION PUMPS | 14880 | 16368 | 11904 | 744 | 744 | 744 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03140 | 3167 | DOMESTIC - STEAM-T0-WATER SEMI-INSTANTANEOUS HEATER | 218880 | 240768 | 207936 | 2736 | 2736 | 2736 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3168 | GAS SERVICE AND PIPING | 252700 | 277970 | 242592 | 2527 | 2527 | 2527 | 2527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03140 | 3169 | PLUMBING FIXTURES | 12879 | 14167 | 9659.25 | 804.9375 | 804.9375 | 804.9375 | 804.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03140 | 3170 | EMERGENCY PLUMBING FIXTURES | 4640 | 5104 | 2320 | 580 | 580 | 580 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3171 | UNDERGROUND DOMESTIC COLD AND HOT WATER DISTRIBUTION PIPING | 41300 | 45430 | 41300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | VITAL | 0 | NEW BUILDINGS
SG6-03105 | 3172 | Plumbing Pipe Insulation | 7600 | 3032 | 7600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | TRISTAN | 0 | NEW BUILDINGS
SG6-02140 | 3173 | Heat Trace | 5000 | 5475 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 078 - SG6 - Division 22 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-SGN-M-01005 | 3174 | Survey | 60000 | 66000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03112 | 3175 | Exhaust Fans: Furnish | 3600 | 3960 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3176 | Exhaust Fans: Install | 20950 | 23045 | 20950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 3177 | Steam Unit Heaters: Furnish | 4000 | 4400 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3178 | Steam Unit Heaters: Install | 41500 | 45650 | 41500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 3179 | Electric Unit Heaters: Furnish | 4500 | 4950 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03032 | 3180 | Condensate Return Unit: Furnish | 14000 | 15400 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3181 | Condensate Return Unit: Install | 41500 | 45650 | 41500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3182 | Heating and Ventilation Unit: Furnish | 6500 | 7150 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3183 | Heating and Ventilation Unit: Install | 30500 | 33550 | 30500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3184 | Steam Traps: Furnish | 2000 | 2200 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3185 | Steam Traps: Install | 16000 | 17600 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3186 | Steam Separator: Furnish | 24000 | 26400 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3187 | Steam Separator: Install | 177500 | 195250 | 177500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3188 | Low Pressure Steam Boilers: Install | 97500 | 107250 | 97500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 3189 | Boiler Feed Unit: Furnish | 35000 | 38500 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03242 | 3190 | Boiler Feed Unit: Install | 47500 | 52250 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 3191 | Fuel Oil Pump: Furnish | 50000 | 55000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03130 | 3192 | Fuel Oil Pump: Install | 47500 | 52250 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03142 | 3193 | Fuel Oil Storage Tank: Furnish | 40000 | 44000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03130 | 3194 | Fuel Oil Storage Tank: Install | 47500 | 52250 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03110 | 3195 | Rigging | 132500 | 145750 | 132500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03107 | 3196 | Mechanical Pipe: Furnish and Install: Hangers/Supports | 394450 | 433895 | 394450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03107 | 3197 | Mechanical Pipe: Furnish and Install: PVF (Mains) | 620000 | 682000 | 620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03207 | 3198 | Mechanical Pipe: Furnish and Install: PVF (Branches and Equipment Tie-ins) | 170000 | 187000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03135 | 3199 | Mechanical Pipe: Furnish and Install: Boiler Exhaust Material | 165000 | 181500 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03135 | 3200 | Mechanical Pipe: Hydrostatic Testing | 5550 | 6105 | 5550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03207 | 3201 | HVAC Ductwork: Furnish and Install: Hangers/Supports | 50000 | 55000 | 49000 | 967.7419 | 0 | 0 | 0 | 32.2581 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03110 | 3202 | HVAC Ductwork:Furnish and Install: Sheetmetal and RGDs | 100000 | 110000 | 98000 | 1935.4839 | 0 | 0 | 0 | 64.5161 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03245 | 3203 | HVAC Ductwork:Testing & Balancing | 5000 | 5500 | 0 | 96.7742 | 0 | 0 | 0 | 4903.2258 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 3204 | Controls: Furnish and Install: Devices | 190000 | 209000 | 180500 | 3166.6667 | 3166.6667 | 3166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 3205 | Controls: Furnish and Install: Controls Conduit | 85000 | 93500 | 80750 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 3206 | Controls: Furnish and Install: Controls Wiring | 25000 | 27500 | 23750 | 416.6667 | 416.6667 | 416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03120 | 3207 | Controls: Connect to Final Termination Points | 17000 | 18700 | 11050 | 1983.3333 | 1983.3333 | 1983.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03510 | 3208 | Controls Testing | 13250 | 14575 | 0 | 4416.6667 | 4416.6667 | 4416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 3209 | Furnish and Install: Ductwork Insulation | 27000 | 29700 | 0 | 10056.8807 | 0 | 16943.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 3210 | Furnish and Install: Piping Insulation | 55000 | 60500 | 44000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG1-03040 | 3211 | Furnish and Install: Equipment Insulation | 27000 | 29700 | 21600 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
OG8-03242 | 3212 | Furnish and Install: Chemical Feed Equipment | 9300 | 10230 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-03142 | 3213 | Chemical Cleaning | 7500 | 8250 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 079 - SG6 - Division 23 | 0% | WELKIN | 0 | NEW BUILDINGS
SG6-02310 | 3214 | ATS Energization | 10000 | 10950 | 0 | 0 | 0 | 0 | 3333.3333 | 3333.3333 | 3333.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02310 | 3215 | ATS Installation | 140000 | 153300 | 133000 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02310 | 3216 | ATS Terminations | 10000 | 10950 | 9500 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02310 | 3217 | ATS Testing | 10000 | 10950 | 5000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02120 | 3218 | Cabling - Interior Branch (1/0 & Smaller) | 175000 | 175000 | 166250 | 0 | 0 | 0 | 2916.6667 | 2916.6667 | 2916.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02410 | 3219 | Cabling - Risers & Feeders (2/0 & Larger) | 450000 | 492750 | 427500 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02110 | 3220 | Conduit - Branch Circuits (1 1/2" & Smaller) | 50000 | 54750 | 47500 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02155 | 3221 | Conduit - In-Slab | 198000 | 216810 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02210 | 3222 | Conduit - Risers (2" & Larger) | 270000 | 295650 | 256500 | 0 | 0 | 0 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02425 | 3223 | Firestopping | 5000 | 5250 | 4750 | 0 | 0 | 0 | 83.3333 | 83.3333 | 83.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-SG6-01025 | 3224 | Generator Delivery | 50000 | 52500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
P-SG6-01010 | 3225 | Generator Release | 300000 | 315000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02385 | 3226 | Generator Terminations | 50000 | 52500 | 45000 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02510 | 3227 | Generator Test | 50000 | 52500 | 25000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02160 | 3228 | Lighting Controls | 24000 | 25200 | 21600 | 0 | 0 | 0 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02130 | 3229 | Lighting Install | 84600 | 88830 | 80370 | 0 | 0 | 0 | 1410 | 1410 | 1410 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02130 | 3230 | Lighting Rough | 84600 | 92637 | 84600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02130 | 3231 | Lighting System Program & Energize | 5000 | 5475 | 0 | 0 | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02395 | 3232 | Lightning Protection | 20000 | 21900 | 12000 | 0 | 0 | 0 | 2666.6667 | 2666.6667 | 2666.6667 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SG6-02135 | 3233 | Mechanical Terminations(Dampers, Heaters, Motors) | 130000 | 142350 | 117000 | 0 | 0 | 0 | 4333.3333 | 4333.3333 | 4333.3333 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS
SURV-SGN-E-01000 | 3234 | Survey | 50000 | 54750 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SG6 | 080 - SG6 - Division 26 | 0% | FIVE STAR | 0 | NEW BUILDINGS

## Work Summary
Subcontractor | Category | Building | Type | February | March | April | May | June | July | August | September | October
ASPEN
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 1.757% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.91%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 30.63% | 0% | 0% | 0% | 0% | 69.37%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ATCO
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 11.43% | 34.29% | 0% | 0% | 0% | 0% | 0% | 11.43%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 42.11% | 42.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 10.84% | 58.24% | 0% | 0% | 0% | 0% | 0% | 26.86%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ATLAS
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.56% | 81.36%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 59.3% | 0% | 0% | 0% | 40.7% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CCC
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 29.63% | 59.26% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0.9505% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 1.144% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 1.148% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.769% | 11.54% | 80.53% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.3905% | 0.781% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 32.09% | 0% | 67.91% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 6.78% | 67.8% | 0% | 0% | 22.88% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 6.78% | 90.68% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 22.7% | 22.7% | 0% | 0% | 53.26% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 27.73% | 39.86% | 5.199% | 4.116% | 0% | 24.19% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 9.705% | 47.14% | 40.21% | 1.386% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 6.349% | 91.27% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 31.37% | 0% | 68.63% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 8.962% | 0% | 0% | 16.51% | 73.11% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 2.896% | 0% | 0% | 0% | 0% | 0% | 0%
CITYWIDE
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 24.65% | 75.35% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
CLOSEOUT
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 34.84% | 14.04% | 38.1% | 10.03% | 0.7519% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 8.977% | 34.03% | 46.76% | 8.977%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 8.606% | 22.35% | 0% | 0% | 0% | 0% | 35.82%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.6102% | 0% | 5.492% | 0% | 22.71% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 27.27% | 50.74% | 20.3% | 1.903%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 32.13% | 0% | 35.94% | 26.43%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 3.279% | 19.67% | 73.36% | 1.23% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 12.06% | 32.86% | 53.66% | 0.7092% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 17.7% | 0% | 5.253% | 7.782% | 46.69% | 16.15%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.71% | 2.18% | 21.8% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.509% | 15.09% | 0% | 0% | 8.113% | 0% | 22.64% | 41.32%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 18.27% | 0% | 24.7% | 43.37% | 12.45% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.5747% | 9.77% | 20.5% | 0% | 0% | 8.238% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 17.77% | 0% | 31.71% | 0% | 0% | 9.408% | 0% | 0% | 0%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 38.28% | 11.48% | 20.57% | 15.31%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 52.45% | 0% | 0% | 21.08% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 31.71% | 0% | 0% | 0% | 40.07% | 26.13%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 82.03% | 17.02%
SITE
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 46.36% | 0% | 53.64% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DSTAR
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 42.11% | 42.11% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 4.396% | 43.96% | 26.37% | 21.98% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Dynasty Elevator
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
E&Y
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 23.91% | 17.39% | 55.43% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 16.67% | 91.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ENGINEERING
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 18.73% | 36.17% | 20.67% | 3.875% | 0% | 0% | 7.104% | 14.45% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 42.37% | 43.95% | 12.95% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.45% | 18.39% | 34.4% | 16.42% | 15.35% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.43% | 19.03% | 38.3% | 3.937% | 8.529% | 15.06% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 17.05% | 52.41% | 29.36% | 0.9471%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 4.64% | 36.16% | 25.02%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 96.21% | 5.345% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 53.33% | 45.56% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 20.14% | 78.78% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.3%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.905% | 15.27% | 17.99% | 23.27% | 16.9% | 10.09% | 8.451% | 0.5452% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 11.99% | 23.16% | 25.64% | 23.57% | 16.28% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 9.273% | 11.8% | 13.07% | 12.64% | 21.23% | 16.6% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.403% | 14.9% | 8.196% | 7.931% | 13.32% | 11.1% | 8.196% | 8.196% | 7.931%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 10.72% | 13.64% | 15.1% | 14.62% | 24.06% | 6.821% | 0% | 13.64% | 0.4872%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 9.044% | 11.51% | 12.74% | 12.33% | 20.71% | 16.86% | 1.233% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 15.27% | 21.54% | 13.52% | 13.09% | 21.97% | 14.12% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 9.157% | 19.98% | 18.05% | 12.49% | 12.9% | 12.07% | 5.411% | 9.313% | 0%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.219% | 9.188% | 10.17% | 9.844% | 10.17% | 9.844% | 10.17% | 14.23% | 6.891%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.207% | 9.173% | 10.16% | 9.828% | 16.5% | 13.76% | 10.16% | 9.828% | 1.638%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.401% | 9.42% | 10.43% | 10.09% | 10.43% | 10.09% | 10.43% | 10.56% | 8.537%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 18.74% | 41.18% | 40.2%
Overhead
|  | ENG | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.1429% | 5.859% | 8.957% | 2.215% | 2.072% | 0.7859% | 0% | 0%
FAXA
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 32.88% | 54.79% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 29.63% | 59.26% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 18.6% | 74.42% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.7069% | 1.414% | 2.828% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 23.99% | 21.98% | 26.37% | 18.13% | 7.875% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.768% | 50.35% | 25.43% | 0% | 20.42% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 11.1% | 9.911% | 4.262% | 10.06% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 14.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 5.881% | 7.841% | 1.28% | 0% | 0%
FIVE STAR
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0.612% | 0.4056% | 0% | 0.5124% | 0.9892% | 0.3985% | 0.3985%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.737% | 6.789% | 8.161% | 4.993% | 8.9% | 9.229% | 7.597% | 2.984% | 1.375%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.53% | 10.47% | 1.392% | 0.4686% | 0.9003% | 0.7133% | 0.9719% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.86% | 29.65% | 5.538% | 1.482% | 0.03509% | 0.7368% | 0.6097% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.4588% | 22.51% | 3.919% | 0.8836% | 2.937% | 0.8156% | 1.344% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 6.184% | 8.016% | 7.458% | 9.449% | 3.972% | 1.69% | 2.973%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 3.687% | 0% | 0% | 27.19% | 67.74% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.836% | 9.36% | 6.807% | 3.026% | 15.69% | 30.26% | 0% | 11.63%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.804% | 1.847% | 3.506% | 3.064% | 0.8894% | 0% | 1.872% | 0.3459%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 1.032% | 1.032% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.053% | 32.84% | 0% | 0% | 0% | 0% | 60.21% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 5.99% | 5.783% | 6.403% | 6.196% | 8.159% | 11.06% | 12.91% | 3.718% | 1.549%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.036% | 7.845% | 2.563% | 0.3182% | 0.9727% | 0% | 2.409% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.623% | 5.889% | 7.261% | 0.8298% | 1.077% | 2.161% | 2.59% | 1.66% | 1.606%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.054% | 1.999% | 3.89% | 1.581% | 0.3181% | 1.068% | 1.759% | 1.127% | 1.091%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.787% | 3.389% | 5.269% | 2.468% | 0.2696% | 0.8242% | 2.141% | 0.1232% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.7418% | 1.391% | 5.164% | 1.205% | 0.7882% | 0.6201% | 1.148% | 0.5912% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.874% | 6.316% | 6.755% | 2.057% | 2.461% | 3.067% | 2.499% | 0.846%
|  | OG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 6.689% | 6.574% | 12.9% | 7.54% | 0.2307% | 1.543% | 0% | 1.605% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.08871% | 3.895% | 3.855% | 3.191% | 2.32% | 3.664% | 1.479% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0.2063% | 2.919% | 3.936% | 0.4127% | 3.271% | 2.705% | 2.514%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.09348% | 0.2974% | 0.2295% | 0.7734% | 0.6119% | 1.181% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.829% | 7.685% | 5.136% | 0.1673% | 0.7456% | 0.8029% | 0.6643% | 0% | 0%
FLOORING
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
EXISTING BUILDINGS
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 72.73% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 72.73% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 50.53% | 50.53% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 72.73% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72.73% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
GG PAINT
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 37.43% | 60.82% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 32.65% | 65.31% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 63.76% | 36.43%
General Conditions
Overhead
|  | Overhead | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
JMC
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 1.288% | 4.509% | 3.664% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 33.33% | 21.88% | 44.79% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 1.853% | 11.76% | 0% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 17.45% | 18.79% | 20.13% | 24.16% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 35.1% | 1.848% | 41.34%
EXISTING BUILDINGS
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
Loading Dock
NEW BUILDINGS
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
MEP
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 17.1% | 0% | 0% | 0% | 3.357% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 4.393% | 17.57% | 34.04% | 23.61% | 17.02% | 0% | 0% | 0% | 2.951%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 11.65% | 46.62% | 38.29% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 14.85% | 82.76% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 16.64% | 9.245% | 25.89% | 25.89% | 0% | 0% | 21.73%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 12.88% | 74.04% | 1.61% | 0%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 23.16% | 66.59% | 0% | 0% | 9.577% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 15.16% | 5.831% | 0% | 3.134% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 14.44% | 15.16% | 8.664% | 0% | 0% | 2.437%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 2.455% | 0% | 0% | 0% | 18.45% | 17.45% | 2.182% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 26.84% | 35.78% | 16.61% | 0% | 9.585% | 8.307% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 13.17% | 52.69% | 26.35% | 0% | 6.437% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 6.073% | 0% | 9.04% | 24.86% | 41.81% | 16.95% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.965% | 0% | 0% | 53.3% | 36.42% | 5.874% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 7.821% | 32.4% | 49.16% | 3.352% | 0%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 77.42% | 15.48% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 66.58% | 25.46% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 40.13% | 33.71% | 16.05% | 0%
MLJ
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 4.003% | 0.6279% | 38.38% | 13.5% | 0% | 0% | 3.14% | 13.81% | 21.35%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.98% | 18.8% | 31.67% | 18.01% | 5.267% | 1.96% | 4.9% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.593% | 18.09% | 47.2% | 8.563% | 0% | 9.061% | 10.65% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.3896% | 8.735% | 2.091% | 0% | 0% | 2.194% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0.1101% | 0.2936% | 11.93% | 6.997% | 0% | 0% | 4.22% | 0% | 3.927%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 4.019% | 1.497% | 38.85% | 26.16% | 7.644% | 0% | 0% | 0% | 16.86%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.42% | 28.66% | 4.076% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 7.135% | 7.869% | 13.32% | 15.51% | 10.36% | 4.93% | 6.381% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.292% | 5.331% | 33.09% | 14.43% | 12.47% | 13.14% | 9.926% | 6.192% | 1.938%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.881% | 12.65% | 15.52% | 20.25% | 8.515% | 2.723% | 1.709% | 2.636% | 5.184%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 4.598% | 10.43% | 5.456% | 10.87% | 4.4% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.854% | 9.813% | 6.24% | 7.012% | 4.636% | 1.082% | 0% | 0%
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.404% | 2.707% | 2.142% | 5.325% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 21.47% | 3.067% | 3.067% | 0% | 25.62% | 27.6% | 7.668%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.8348% | 4.592% | 0% | 0% | 0.574% | 1.409% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 2.313% | 4.481% | 2.183% | 3.921% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 6.358% | 34.97% | 0% | 56.29% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 4.122% | 15.11% | 18.78% | 16.34% | 5.344% | 0% | 0% | 25.55%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 26.98% | 16.28% | 17.22% | 16.54% | 12.07% | 8.063% | 2.653% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.498% | 35.21% | 24.81% | 7.022% | 2.247% | 11.99% | 0.7491% | 10.02%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 1.712% | 18.29% | 11.04% | 6.645% | 3.222% | 5.303% | 1.712% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.001% | 25.74% | 17.7% | 4.629% | 6.409% | 5.188% | 4.883% | 5.849% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 3.088% | 6.341% | 0% | 0% | 2.338% | 3.682% | 11.72% | 2.571%
|  | ALLOWANCE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
Change Orders
|  | Change Order | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Overhead
|  | OH | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NATIONAL GRID
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 22.86% | 68.57% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 11.43% | 84.29% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 22.86% | 68.57% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 22.86% | 68.57% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 73.46% | 26.82% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
NAVILLUS
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 67.72% | 0% | 32.28% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 6.689% | 41.47% | 40.13% | 2.676% | 8.528% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 32.65% | 65.31% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 15.27% | 78.28% | 5.728% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 30.95% | 68.77% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 50.88% | 48.06% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 47.56% | 0% | 52.44% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 5.654% | 39.58% | 48.06% | 8.481% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 94.98% | 3.653% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 18.71% | 79.53% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 71.17% | 26.99% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 65.78% | 0% | 0% | 0% | 34.22% | 0%
PUNCH LIST
NEW BUILDINGS
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 67.72% | 0% | 32.28% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.75%
EXISTING BUILDINGS
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 97.89% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 53.01% | 9.639% | 0% | 33.73% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.72%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 28.92% | 33.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.819%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 35.92% | 61.97% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 30.72% | 69.28% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 64.46% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.82%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.639%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 35.92%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
SITE
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 25.23% | 25.23% | 48.2% | 0% | 0%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SIG
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TONAGE
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 27.12% | 67.8% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 23.88% | 71.64% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 78.53% | 18.08% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 27.12% | 67.8% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
SITE
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
TRIANGLE
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 8.955% | 80.6% | 8.769% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.063% | 86.08% | 0% | 6.962% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 13.9% | 47.66% | 29.79% | 3.972% | 0% | 3.93% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
TRISTAN
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VITAL
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 29.96% | 44.9% | 24.97% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.442% | 92.52% | 0% | 0% | 0% | 0% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.442% | 92.52% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 6.362% | 49.3% | 39.76% | 4.771% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
WEIR
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
WELKIN
NEW BUILDINGS
|  | SG7 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 9.359% | 40.69% | 31.59% | 11.55% | 6.409% | 0% | 0% | 0% | 0%
|  | OG8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 1.248% | 4.368% | 0.8385% | 0% | 2.36% | 0% | 0% | 0% | 0%
|  | OG9 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 12.7% | 82.54% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OG10 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 43.01% | 8.29% | 47.15% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 5.008% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S82 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 10.27% | 45.01% | 22.11% | 19.83% | 1.712% | 0% | 0%
SITE
|  | SGN | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SGS | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | OGE | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 3.343% | 0% | 0% | 0% | 0% | 2.432% | 70.52%
|  | OGW | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | S8 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
EXISTING BUILDINGS
|  | SG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 51.64% | 36.07% | 0% | 0%
|  | OG1 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.969% | 15.29% | 14.36% | 1.941% | 0% | 0% | 0% | 0%
|  | OG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 3.074% | 15.09% | 5.807% | 0% | 0% | 0% | 0% | 0%
|  | OG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 3.861% | 4.226% | 2.337% | 0% | 0% | 0% | 0%
|  | OG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 5.843% | 6.806% | 3.86% | 1.356% | 0% | 0% | 0% | 0%
|  | OG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.4805% | 21.86% | 13.81% | 13.45% | 2.402% | 0% | 0% | 0%
|  | OG6 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 3.901% | 4.659% | 1.49% | 5.282% | 1.774% | 0% | 0% | 0% | 0%
|  | SG2 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.2242% | 9.893% | 0% | 0% | 0% | 0% | 0% | 0%
|  | S81 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 8.905% | 25.49% | 27.28% | 18.66% | 13.6% | 6.02% | 0% | 0%
|  | SG3 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.7821% | 0.391% | 12.73% | 16.07% | 13.86% | 1.706% | 0% | 0%
|  | SG4 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 10.55% | 16.07% | 0% | 0% | 2.186% | 3.225% | 0%
|  | SG5 | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0.4593% | 19.52% | 11.66% | 0% | 0% | 0% | 0% | 0%
Overhead
|  | OH | Billings | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Costs | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  | Activities | 0% | 0% | 0% | 0% | 0% | 0% | 44.22% | 0% | 0%

## Forecast Summary
Cost
| February | March | April | May | June | July | August | September | October | November
Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consumable/Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billing
| February | March | April | May | June | July | August | September | October | November
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Profit Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Annual Billing and Cost
| Billing | Cost | Profit
2020 Total | 5189506 | 1813875.69 | 0
2021 Total | 40215999.85 | 36132226.23 | 0
2022 Total | 89644456.9 | 81147688.19 | 0
2023 Total | 478996 | 87102317.87 | 0
Final Total | 0 | 0 | 0

## Activities
Activity Status | CODE TYPE | WBS Code | Activity ID | Sub | Area | Type | Category 2 | Category 1 | Cost Code Name | Cost Code | Sub-Code | Activity Name | Original Duration(h) | Remaining Duration(h) | (*)Start | (*)Finish | (*)Total Float(h) | During Week | week start | week end
Completed |  | CI NYCHA Update #20.Milestones | M000 | MLJ | [7 empty] | Notice of Award | 0 | 0 | 2020-02-27 17:00 |  |  | 0 | 2023-03-06 | 2023-03-12
Completed |  | CI NYCHA Update #20.Milestones.6 | M170 | MLJ | [7 empty] | Start Building S8-1 - Addition | 0 | 0 | 2022-04-20 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.6 | M175 | MLJ | S81 | [6 empty] | Complete Building S8-1 - Addition | 0 | 0 |  | 2023-12-06 17:00 | -194 | 0
Completed |  | CI NYCHA Update #20.Milestones.6 | M180 | MLJ | [7 empty] | Start Building S8-1 - Existing | 0 | 0 | 2022-04-20 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.6 | M185 | MLJ | S82 | [6 empty] | Complete Building S8-1 - Existing | 0 | 0 |  | 2023-12-06 17:00 | -194 | 0
Completed |  | CI NYCHA Update #20.Milestones.3 | M090 | MLJ | [7 empty] | Start Building OG-2 | 0 | 0 | 2021-03-13 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.3 | M095 | MLJ | OG2 | [6 empty] | Complete Building OG-2 | 0 | 0 |  | 2023-08-11 17:00 | -77 | 0
Completed |  | CI NYCHA Update #20.Milestones.3 | M080 | MLJ | [7 empty] | Start Building OG-3 | 0 | 0 | 2021-05-12 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.3 | M085 | MLJ | OG3 | [6 empty] | Complete Building OG-3 | 0 | 0 |  | 2023-10-25 17:00 | -152 | 0
Completed |  | CI NYCHA Update #20.Milestones.2 | M050 | MLJ | [7 empty] | Start Building OG-4 | 0 | 0 | 2021-09-20 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.2 | M055 | MLJ | OG4 | [6 empty] | Complete Building OG-4 | 0 | 0 |  | 2023-10-18 17:00 | -145 | 0
Completed |  | CI NYCHA Update #20.Milestones.2 | M040 | MLJ | [7 empty] | Start Building OG-8 | 0 | 0 | 2021-07-12 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.2 | M045 | MLJ | OG8 | [6 empty] | Complete Building OG-8 | 0 | 0 |  | 2023-09-19 17:00 | -116 | 0
Completed |  | CI NYCHA Update #20.Milestones.3 | M070 | MLJ | [7 empty] | Start Building OG-9 | 0 | 0 | 2021-08-10 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.3 | M075 | MLJ | OG9 | [6 empty] | Complete Building OG-9 | 0 | 0 |  | 2023-11-03 17:00 | -161 | 0
Completed |  | CI NYCHA Update #20.Milestones.4 | M120 | MLJ | [7 empty] | Start Building OG-1 | 0 | 0 | 2021-05-17 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.4 | M125 | MLJ | OG1 | [6 empty] | Complete Building OG-1 | 0 | 0 |  | 2024-01-31 17:00 | -250 | 0
Completed |  | CI NYCHA Update #20.Milestones.2 | M060 | MLJ | [7 empty] | Start Building OG-5 | 0 | 0 | 2021-04-21 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.2 | M065 | MLJ | OG5 | [6 empty] | Complete Building OG-5 | 0 | 0 |  | 2024-02-07 17:00 | -257 | 0
Completed |  | CI NYCHA Update #20.Milestones.4 | M110 | MLJ | [7 empty] | Start Building OG-6 | 0 | 0 | 2021-05-03 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.4 | M115 | MLJ | OG6 | [6 empty] | Complete Building OG-6 | 0 | 0 |  | 2024-02-23 17:00 | -273 | 0
Completed |  | CI NYCHA Update #20.Milestones.4 | M100 | MLJ | [7 empty] | Start Building OG-10 | 0 | 0 | 2021-06-30 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.4 | M105 | MLJ | OG10 | [6 empty] | Complete Building OG-10 | 0 | 0 |  | 2024-02-02 17:00 | -252 | 0
Completed |  | CI NYCHA Update #20.Milestones.1 | M020 | MLJ | [7 empty] | Start Building SG-4 | 0 | 0 | 2021-09-13 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.1 | M025 | MLJ | SG4 | [6 empty] | Complete Building SG-4 | 0 | 0 |  | 2023-08-15 17:00 | -81 | 0
Completed |  | CI NYCHA Update #20.Milestones.1 | M030 | MLJ | [7 empty] | Start Building SG-5 | 0 | 0 | 2021-06-14 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.1 | M035 | MLJ | SG5 | [6 empty] | Complete Building SG-5 | 0 | 0 |  | 2023-07-25 17:00 | -60 | 0
Completed |  | CI NYCHA Update #20.Milestones.1 | M010 | MLJ | [7 empty] | Start Building SG-6 | 0 | 0 | 2021-03-25 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.1 | M015 | MLJ | SG6 | [6 empty] | Complete Building SG-6 | 0 | 0 |  | 2023-07-25 17:00 | -60 | 0
Completed |  | CI NYCHA Update #20.Milestones.5 | M150 | MLJ | [7 empty] | Start Building SG-1 | 0 | 0 | 2021-03-08 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.5 | M155 | MLJ | SG1 | [6 empty] | Complete Building SG-1 | 0 | 0 |  | 2023-10-18 10:00 | -144 | 0
Completed |  | CI NYCHA Update #20.Milestones.5 | M160 | MLJ | [7 empty] | Start Building SG-2 | 0 | 0 | 2021-05-18 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.5 | M165 | MLJ | SG2 | [6 empty] | Complete Building SG-2 | 0 | 0 |  | 2023-10-13 17:00 | -140 | 0
Completed |  | CI NYCHA Update #20.Milestones.5 | M145 | MLJ | [7 empty] | Start Building SG-3 | 0 | 0 | 2021-05-06 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.5 | M140 | MLJ | SG3 | [6 empty] | Complete Building SG-3 | 0 | 0 |  | 2023-11-08 17:00 | -166 | 0
Completed |  | CI NYCHA Update #20.Milestones.5 | M130 | MLJ | [7 empty] | Start Building SG-7 | 0 | 0 | 2021-04-28 08:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones.5 | M135 | MLJ | SG7 | [6 empty] | Complete Building SG-7 | 0 | 0 |  | 2023-10-31 17:00 | -158 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01500 | [8 empty] | Prepare & Submit Safety Plan | 25 | 0 | 2020-07-13 | 2020-08-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01510 | [8 empty] | Initial Review of Safety Plan | 10 | 0 | 2020-08-15 | 2020-09-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01520 | [8 empty] | Prepare & Submit Safety Engineer | 30 | 0 | 2020-07-13 | 2020-09-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01530 | [8 empty] | Review & Approve Safety Engineer | 10 | 0 | 2020-09-30 | 2020-10-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01540 | [8 empty] | Prepare & Submit Quality Plan | 20 | 0 | 2020-07-13 | 2020-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01550 | [8 empty] | Review & Approve Quality Plan | 10 | 0 | 2020-09-01 | 2021-01-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02020 | [8 empty] | Prepare & Submit Pre-construction As Built Sewer and Water Main Documentation | 20 | 0 | 2020-12-21 | 2021-01-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02030 | [8 empty] | Review & Approve Pre-construction As Built Sewer and Water Main Documentation | 10 | 0 | 2021-01-20 | 2021-06-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02040 | [8 empty] | Prepare & Submit Testing, Handling, and of Contaminated Soils Plan | 60 | 0 | 2020-07-13 | 2020-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02050 | [8 empty] | Review & Approve Testing, Handling, and of Contaminated Soils Plan | 10 | 0 | 2020-10-26 | 2020-12-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02060 | [8 empty] | Prepare & Submit Site Demolition Plan | 40 | 0 | 2020-10-01 | 2020-10-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02070 | [8 empty] | Review & Approve Site Demolition Plan | 10 | 0 | 2020-10-30 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02080 | [8 empty] | Prepare & Submit Selective Demolition Plan | 40 | 0 | 2020-10-01 | 2020-10-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02090 | [8 empty] | Review & Approve Selective Demolition Plan | 10 | 0 | 2020-10-30 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02100 | [8 empty] | Prepare & Submit Interior Asbestos Abatement Plan | 40 | 0 | 2020-08-03 | 2020-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02110 | [8 empty] | Review & Approve Interior Asbestos Abatement Plan | 10 | 0 | 2020-09-02 | 2021-02-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02120 | [8 empty] | Prepare & Submit Asbestos Abatement - Masonry Removals Plan | 40 | 0 | 2020-08-03 | 2020-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02130 | [8 empty] | Review & Approve Asbestos Abatement - Masonry Removals Plan | 10 | 0 | 2020-09-02 | 2021-02-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02140 | [8 empty] | Prepare & Submit Asbestos Abatement - Site Work (Underground Utilities) Plan | 40 | 0 | 2020-08-03 | 2020-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02150 | [8 empty] | Review & Approve Asbestos Abatement - Site Work (Underground Utilities) Plan | 10 | 0 | 2020-09-02 | 2021-11-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02160 | [8 empty] | Prepare & Submit Lead Safe Work Practices Plan | 20 | 0 | 2020-11-10 | 2020-12-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 2 | 02170 | [8 empty] | Review & Approve Lead Safe Work Practices Plan | 10 | 0 | 2020-12-11 | 2021-03-23 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 2 | 02180 | [8 empty] | Obtain Lead Placards | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | 18 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03000 | [8 empty] | Prepare & Submit Strengthening of Concrete with FRP Product Data | 100 | 0 | 2020-12-28 | 2021-01-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03010 | [8 empty] | Review & Approve Strengthening of Concrete with FRP Product Data | 10 | 0 | 2021-01-29 | 2021-05-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03020 | [8 empty] | Del. Strengthening of Concrete with FRP | 5 | 0 | 2022-02-01 | 2022-02-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03030 | [8 empty] | Prepare & Submit Concrete Formwork | 80 | 0 | 2020-10-05 | 2021-02-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03040 | [8 empty] | Review & Approve Concrete Formwork | 10 | 0 | 2021-02-23 | 2021-03-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03050 | [8 empty] | Fab/Del. Concrete Formwork | 5 | 0 | 2021-03-29 | 2021-04-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03060 | [8 empty] | Prepare & Submit Concrete Reinforcement | 80 | 0 | 2020-07-13 | 2020-10-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03070 | [8 empty] | Review & Approve Concrete Reinforcement | 10 | 0 | 2020-10-22 | 2021-03-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03080 | [8 empty] | Fab/Del. Concrete Reinforcement | 5 | 0 | 2021-04-06 | 2021-04-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03090 | [8 empty] | Prepare & Submit Cast In Place Concrete Mix Design | 80 | 0 | 2020-07-13 | 2020-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03100 | [8 empty] | Review & Approve Cast In Place Concrete Mix Design | 10 | 0 | 2020-09-02 | 2020-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03120 | [8 empty] | Prepare & Submit Grouting | 100 | 0 | 2021-01-04 | 2021-06-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03130 | [8 empty] | Review & Approve Grouting | 10 | 0 | 2021-06-16 | 2021-06-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03140 | [8 empty] | Fab/Del. Grouting | 10 | 0 | 2022-02-01 | 2022-02-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03150 | [8 empty] | Prepare & Submit Concrete Repair Shop Drawings | 80 | 0 | 2021-01-01 | 2021-05-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03160 | [8 empty] | Review & Approve Concrete Repair Shop Drawings | 10 | 0 | 2021-05-25 | 2021-05-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04000 | [8 empty] | Prepare & Submit Unit Masonry | 100 | 0 | 2020-12-14 | 2021-09-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04010 | [8 empty] | Review & Approve Unit Masonry | 10 | 0 | 2021-09-23 | 2021-12-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04020 | [8 empty] | Fab/Del. Unit Masonry | 10 | 0 | 2021-12-26 | 2022-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04030 | [8 empty] | Prepare & Submit Cast Stone | 150 | 0 | 2020-11-09 | 2021-07-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04040 | [8 empty] | Review & Approve Cast Stone | 10 | 0 | 2021-07-09 08:00 | 2021-08-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04050 | [8 empty] | Fab/Del. Cast Stone | 60 | 0 | 2022-01-03 08:00 | 2022-09-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05000 | [8 empty] | Prepare & Submit Structural Steel - S8-1 - Addition | 100 | 0 | 2020-11-05 | 2021-11-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05010 | [8 empty] | Review & Approve Structural Steel - S8-1 - Addition | 10 | 0 | 2021-11-23 08:00 | 2022-03-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05020 |  | S81 | [6 empty] | Fab/Del. Structural Steel - S8-1 - Addition | 50 | 0 | 2022-01-10 | 2022-07-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05030 | [8 empty] | Prepare & Submit Structural Steel - S8 Existing - N/A | 100 | 0 | 2020-11-05 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05040 | [8 empty] | Review & Approve Structural Steel - S8 Existing - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05050 | [8 empty] | Fab/Del. Structural Steel - S8 Existing - N/A | 50 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05060 | [8 empty] | Prepare & Submit Structural Steel - OG-2 | 100 | 0 | 2020-11-05 | 2021-06-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05070 | [8 empty] | Review & Approve Structural Steel - OG-2 | 10 | 0 | 2021-06-10 08:00 | 2021-06-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05080 | [8 empty] | Fab/Del. Structural Steel - OG-2 | 50 | 0 | 2022-01-10 | 2022-04-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05090 | [8 empty] | Prepare & Submit Structural Steel - OG-3 | 100 | 0 | 2020-11-05 | 2021-06-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05100 | [8 empty] | Review & Approve Structural Steel - OG-3 | 10 | 0 | 2021-06-10 08:00 | 2021-06-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05110 | [8 empty] | Fab/Del. Structural Steel - OG-3 | 50 | 0 | 2022-01-10 | 2022-04-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05120 | [8 empty] | Prepare & Submit Structural Steel - OG-4 | 100 | 0 | 2020-11-05 | 2021-06-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05130 | [8 empty] | Review & Approve Structural Steel - OG-4 | 10 | 0 | 2021-06-10 08:00 | 2021-06-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05140 | [8 empty] | Fab/Del. Structural Steel - OG-4 | 50 | 0 | 2022-01-10 | 2022-04-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05150 | [8 empty] | Prepare & Submit Structural Steel - OG-8 (RFI #130) | 100 | 0 | 2020-11-12 | 2021-01-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05160 | [8 empty] | Review & Approve Structural Steel - OG-8 (RFI 130) | 10 | 0 | 2021-01-28 | 2021-05-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05170 | [8 empty] | Fab/Del. Structural Steel - OG-8 | 50 | 0 | 2021-05-14 | 2021-06-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05180 | [8 empty] | Prepare & Submit Structural Steel - OG-9 (RFI #127) | 100 | 0 | 2020-11-12 | 2021-05-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05190 | [8 empty] | Review & Approve Structural Steel - OG-9 | 10 | 0 | 2021-05-19 | 2021-06-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05200 | [8 empty] | Fab/Del. Structural Steel - OG-9 | 30 | 0 | 2021-09-01 | 2021-10-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05210 | [8 empty] | Prepare & Submit Structural Steel - OG -1 | 100 | 0 | 2020-11-05 | 2021-06-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05220 | [8 empty] | Review & Approve Structural Steel - OG -1 | 10 | 0 | 2021-06-10 | 2021-06-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05230 | [8 empty] | Fab/Del. Structural Steel - OG -1 | 50 | 0 | 2022-01-10 | 2022-04-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05240 | [8 empty] | Prepare & Submit Structural Steel - OG-5 | 100 | 0 | 2020-11-05 | 2021-06-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05250 | [8 empty] | Review & Approve Structural Steel - OG-5 | 10 | 0 | 2021-06-10 | 2021-06-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05260 | [8 empty] | Fab/Del. Structural Steel - OG-5 | 50 | 0 | 2022-01-10 | 2022-04-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05270 | [8 empty] | Prepare & Submit Structural Steel - OG-6 | 100 | 0 | 2020-11-05 | 2022-06-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05280 |  | OG6 |  |  |  | ENG |  |  | Review & Approve Structural Steel - OG-6 | 10 | 0 | 2022-06-15 | 2022-08-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05290 |  | OG6 | [6 empty] | Fab/Del. Structural Steel - OG-6 | 20 | 0 | 2022-08-31 | 2022-09-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05300 | [8 empty] | Prepare & Submit Structural Steel - OG-10 (RFI #131, 167 & 335) | 100 | 0 | 2020-11-12 | 2021-09-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05310 | [8 empty] | Review & Approve Structural Steel - OG-10 | 10 | 0 | 2021-09-15 | 2021-09-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05320 | [8 empty] | Fab/Del. Structural Steel - OG-10 | 40 | 0 | 2021-09-16 08:00 | 2021-10-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05330 | [8 empty] | Prepare & Submit Structural Steel - SG-4 | 100 | 0 | 2020-11-05 | 2021-10-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05340 | [8 empty] | Review & Approve Structural Steel - SG-4 | 10 | 0 | 2021-10-19 | 2021-10-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05350 | [8 empty] | Fab/Del. Structural Steel - SG-4 | 20 | 0 | 2021-10-10 | 2021-10-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05360 | [8 empty] | Prepare & Submit Structural Steel - SG-5 | 100 | 0 | 2020-11-05 | 2021-11-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05370 | [8 empty] | Review & Approve Structural Steel - SG-5 | 10 | 0 | 2021-11-10 08:00 | 2021-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05380 | [8 empty] | Fab/Del. Structural Steel - SG-5 | 50 | 0 | 2021-11-11 08:00 | 2021-12-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05390 | [8 empty] | Prepare & Submit Structural Steel - SG-6 | 100 | 0 | 2020-11-03 | 2021-01-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05400 | [8 empty] | Review & Approve Structural Steel - SG-6 (Clash with Breaching Stack) | 10 | 0 | 2021-01-14 | 2021-04-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05410 | [8 empty] | Fab/Del. Structural Steel - SG-6 | 50 | 0 | 2021-04-14 | 2021-05-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05420 | [8 empty] | Prepare & Submit Structural Steel - SG-1 - N/A | 100 | 0 | 2020-11-05 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05430 | [8 empty] | Review & Approve Structural Steel - SG-1 - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05440 | [8 empty] | Fab/Del. Structural Steel - SG-1 - N/A | 50 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05450 | [8 empty] | Prepare & Submit Structural Steel - SG-2 - N/A | 100 | 0 | 2020-11-05 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05460 | [8 empty] | Review & Approve Structural Steel - SG-2 - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05470 | [8 empty] | Fab/Del. Structural Steel - SG-2 - N/A | 50 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05510 | [8 empty] | Prepare & Submit Structural Steel - SG-3 | 100 | 0 | 2020-11-05 | 2022-06-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05520 |  | SG3 |  |  |  | ENG |  |  | Review & Approve Structural Steel - SG-3 | 10 | 0 | 2022-06-15 | 2022-09-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05530 |  | SG3 | [6 empty] | Fab/Del. Structural Steel - SG-3 | 50 | 0 | 2022-09-02 | 2022-09-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05540 | [8 empty] | Prepare & Submit Structural Steel - SG-7 | 100 | 0 | 2020-11-05 | 2021-09-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05550 | [8 empty] | Review & Approve Structural Steel - SG-7 | 10 | 0 | 2021-09-10 08:00 | 2021-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05560 | [8 empty] | Fab/Del. Structural Steel - SG-7 | 50 | 0 | 2021-09-26 | 2021-10-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05570 | [8 empty] | Prepare & Submit Metal Deck | 100 | 0 | 2020-10-07 | 2021-05-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05580 | [8 empty] | Review & Approve Metal Deck | 10 | 0 | 2021-06-22 | 2021-07-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05590 | [8 empty] | Fab/Del. Metal Deck | 30 | 0 | 2021-07-26 08:00 | 2021-08-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05600 | [8 empty] | Prepare & Submit Metal Fabrications - N/A | 100 | 0 | 2020-10-05 | 2021-07-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05610 | [8 empty] | Review & Approve Metal Fabrications - N/A | 10 | 0 | 2021-07-24 | 2021-07-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05620 | [8 empty] | Fab/Del. Metal Fabrications - N/A | 30 | 0 | 2021-07-24 | 2021-07-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05630 | [8 empty] | Prepare & Submit Metal Stairs | 100 | 0 | 2020-11-02 | 2021-06-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05640 | [8 empty] | Review & Approve Metal Stairs | 10 | 0 | 2021-06-15 | 2021-09-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05650 | [8 empty] | Fab/Del. Metal Stairs | 40 | 0 | 2021-10-01 08:00 | 2021-10-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05660 | [8 empty] | Prepare & Submit Metal Railings | 100 | 0 | 2021-01-04 | 2021-05-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05670 | [8 empty] | Review & Approve Metal Railings | 10 | 0 | 2021-05-08 | 2021-05-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05680 | [8 empty] | Fab/Del. Metal Railings | 50 | 0 | 2022-01-03 | 2022-02-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05690 | [8 empty] | Prepare & Submit Pipe and Tube Railings | 100 | 0 | 2021-01-04 | 2021-05-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05700 | [8 empty] | Review & Approve Pipe and Tube Railings | 10 | 0 | 2021-05-08 | 2021-05-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05710 | [8 empty] | Fab/Del. Pipe and Tube Railings | 50 | 0 | 2022-01-03 | 2022-02-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05720 | [8 empty] | Prepare & Submit Metal Castings (RFI #165) | 100 | 0 | 2020-11-02 | 2021-07-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05730 | [8 empty] | Review & Approve Metal Castings | 10 | 0 | 2021-07-15 | 2021-08-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05740 | [8 empty] | Fab/Del. Metal Castings | 50 | 0 | 2021-07-26 08:00 | 2022-02-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05750 | [8 empty] | Prepare & Submit Decorative Metal Railings - N/A | 100 | 0 | 2021-01-04 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05760 | [8 empty] | Review & Approve Decorative Metal Railings - N/A | 10 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05770 | [8 empty] | Fab/Del. Decorative Metal Railings - N/A | 50 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07000 | [8 empty] | Prepare & Submit Foundation Waterproofing | 80 | 0 | 2020-10-05 | 2020-12-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07010 | [8 empty] | Review & Approve Foundation Waterproofing | 10 | 0 | 2021-01-01 | 2021-05-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07020 | [8 empty] | Fab/Del. Foundation Waterproofing - N/A | 10 | 0 | 2021-03-01 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07030 | [8 empty] | Prepare & Submit Crystalline Waterproofing | 80 | 0 | 2020-12-01 | 2020-12-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07040 | [8 empty] | Review & Approve Crystalline Waterproofing | 10 | 0 | 2020-12-07 | 2021-01-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07050 | [8 empty] | Fab/Del. Crystalline Waterproofing | 20 | 0 | 2022-01-26 | 2022-02-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07060 | [8 empty] | Prepare & Submit Thermal Insulation | 80 | 0 | 2020-09-06 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07070 | [8 empty] | Review & Approve Thermal Insulation | 10 | 0 | 2020-10-07 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07080 | [8 empty] | Fab/Del. Thermal Insulation | 10 | 0 | 2022-02-28 | 2022-03-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07090 | [5 empty] | ENG |  |  | Prepare & Submit Spray Applied Insulation | 100 | 0 | 2021-01-04 | 2022-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07100 | [5 empty] | ENG |  |  | Review & Approve Spray Applied Insulation | 10 | 0 | 2022-09-17 | 2022-10-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07110 | [8 empty] | Fab/Del. Spray Applied Insulation | 10 | 0 | 2022-10-10 08:00 | 2022-10-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07120 | [8 empty] | Prepare & Submit Fluid Applied Membrane Air Barriers | 100 | 0 | 2021-01-04 | 2022-02-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07130 | [5 empty] | ENG |  |  | Review & Approve Fluid Applied Membrane Air Barriers | 10 | 0 | 2022-02-25 | 2022-07-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07140 | [8 empty] | Fab/Del. Fluid Applied Membrane Air Barriers | 10 | 0 | 2022-09-08 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07150 | [8 empty] | Prepare & Submit Insulated Metal Wall Panels | 180 | 0 | 2020-08-31 | 2021-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07160 | [8 empty] | Review & Approve Insulated Metal Wall Panels | 10 | 0 | 2021-06-16 | 2021-09-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07170 | [8 empty] | Fab/Del. Insulated Metal Wall Panels | 50 | 0 | 2022-02-15 | 2022-05-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07180 | [8 empty] | Prepare & Submit SBS Modified Bituminous Membrane Roofing | 150 | 0 | 2020-11-30 | 2020-12-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07190 | [8 empty] | Review & Approve SBS Modified Bituminous Membrane Roofing | 10 | 0 | 2020-12-30 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07200 | [8 empty] | Fab/Del. SBS Modified Bituminous Membrane Roofing | 20 | 0 | 2022-06-27 08:00 | 2022-07-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07210 | [5 empty] | ENG |  |  | Prepare & Submit Sheet Metal Flashing and Trim | 150 | 0 | 2021-01-04 | 2022-09-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07220 | [5 empty] | ENG |  |  | Review & Approve Sheet Metal Flashing and Trim | 10 | 0 | 2022-09-07 | 2022-11-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07230 | [8 empty] | Fab/Del. Sheet Metal Flashing and Trim | 10 | 0 | 2023-01-09 | 2023-01-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07240 | [8 empty] | Prepare & Submit Applied Fireproofing | 100 | 0 | 2020-11-25 | 2021-08-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07250 | [8 empty] | Review & Approve Applied Fireproofing | 10 | 0 | 2021-08-30 08:00 | 2021-10-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07260 | [8 empty] | Fab/Del. Applied Fireproofing | 20 | 0 | 2021-12-01 08:00 | 2021-12-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07270 | [5 empty] | ENG |  |  | Prepare & Submit Penetration Firestopping | 180 | 0 | 2020-11-02 | 2022-07-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07280 | [5 empty] | ENG |  |  | Review & Approve Penetration Firestopping | 10 | 0 | 2022-07-02 | 2022-11-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07290 | [8 empty] | Fab/Del. Penetration Firestopping | 20 | 0 | 2023-01-09 | 2023-01-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07300 | [8 empty] | Prepare & Submit Joint Sealants | 180 | 0 | 2020-11-02 | 2021-05-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07310 | [8 empty] | Review & Approve Joint Sealants | 10 | 0 | 2021-05-14 | 2021-05-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07320 | [8 empty] | Fab/Del. Joint Sealants | 20 | 0 | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08000 | [8 empty] | Prepare & Submit Hollow Metal Doors and Frames | 120 | 0 | 2020-07-13 | 2020-10-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08010 | [8 empty] | Review & Approve Hollow Metal Doors and Frames | 10 | 0 | 2020-10-22 | 2020-12-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08020 | [8 empty] | Fab/Del. Hollow Metal Doors and Frames | 50 | 0 | 2021-11-01 08:00 | 2022-02-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08030 | [8 empty] | Prepare & Submit Access Doors and Frames | 120 | 0 | 2020-12-01 | 2021-02-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08040 | [8 empty] | Review & Approve Access Doors and Frames | 10 | 0 | 2021-02-11 | 2021-12-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08050 | [8 empty] | Fab/Del. Access Doors and Frames | 50 | 0 | 2022-02-01 08:00 | 2022-04-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08060 | [8 empty] | Prepare & Submit Sectional Overhead Doors | 180 | 0 | 2020-10-05 | 2021-11-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08070 | [8 empty] | Review & Approve Sectional Overhead Doors | 10 | 0 | 2021-11-30 08:00 | 2021-12-17 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.Div. 8 | 08080 | [8 empty] | Fab/Del. Sectional Overhead Doors | 50 | 30 | 2021-12-20 08:00 | 2023-04-07 17:00 | -86 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08090 | [8 empty] | Prepare & Submit Flood Doors and Panels | 80 | 0 | 2020-12-01 | 2021-10-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08100 | [8 empty] | Review & Approve Flood Doors and Panels | 10 | 0 | 2021-10-23 | 2021-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08110 | [8 empty] | Fab/Del. Flood Doors and Panels | 50 | 0 | 2021-10-27 08:00 | 2022-06-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08120 | [5 empty] | ENG |  |  | Prepare & Submit Aluminum Windows | 60 | 0 | 2021-01-04 | 2022-07-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08130 | [5 empty] | ENG |  |  | Review & Approve Aluminum Windows | 10 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08140 | [8 empty] | Fab/Del. Aluminum Windows | 40 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08150 | [8 empty] | Prepare & Submit Finish Hardware | 80 | 0 | 2020-07-13 | 2020-10-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08160 | [8 empty] | Review & Approve Finish Hardware | 10 | 0 | 2020-10-20 | 2020-12-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08170 | [8 empty] | Fab/Del. Finish Hardware | 50 | 0 | 2021-11-01 08:00 | 2022-10-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08180 | [5 empty] | ENG |  |  | Prepare & Submit Glazing | 60 | 0 | 2021-01-04 | 2022-07-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08190 | [5 empty] | ENG |  |  | Review & Approve Glazing | 10 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08200 | [8 empty] | Fab/Del. Glazing | 40 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08210 | [8 empty] | Prepare & Submit Fixed Louvers | 180 | 0 | 2020-11-02 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08220 | [5 empty] | ENG |  |  | Review & Approve Fixed Louvers | 10 | 0 | 2022-04-02 | 2022-06-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 8 | 08230 | [8 empty] | Fab/Del. Fixed Louvers | 40 | 0 | 2022-06-09 | 2022-11-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09000 | [8 empty] | Prepare & Submit Non Structural Metal Framing | 100 | 0 | 2021-01-04 | 2022-03-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09010 | [8 empty] | Review & Approve Non Structural Metal Framing | 10 | 0 | 2022-03-19 | 2022-04-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09020 | [8 empty] | Fab/Del. Non Structural Metal Framing | 30 | 0 | 2022-04-12 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09030 | [5 empty] | ENG |  |  | Prepare & Submit Cement Plastering | 80 | 0 | 2021-01-04 | 2022-08-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09040 | [5 empty] | ENG |  |  | Review & Approve Cement Plastering | 10 | 0 | 2022-08-12 | 2022-08-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09050 | [8 empty] | Fab/Del. Cement Plastering | 10 | 0 | 2022-08-13 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09060 | [8 empty] | Prepare & Submit Gypsum Board | 80 | 0 | 2021-01-04 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09070 | [8 empty] | Review & Approve Gypsum Board | 10 | 0 | 2022-04-02 | 2022-04-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09080 | [8 empty] | Fab/Del. Gypsum Board | 10 | 0 | 2022-06-01 | 2022-06-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09090 | [5 empty] | ENG |  |  | Prepare & Submit Tiling | 80 | 0 | 2022-07-25 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09100 | [5 empty] | ENG |  |  | Review & Approve Tiling | 10 | 0 | 2022-08-22 08:00 | 2022-09-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09110 | [8 empty] | Fab/Del. Tiling | 10 | 0 | 2022-11-01 | 2022-11-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09120 | [5 empty] | ENG |  |  | Prepare & Submit Acoustical Panel Ceilings | 80 | 0 | 2021-08-25 08:00 | 2022-07-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09130 | [5 empty] | ENG |  |  | Review & Approve Acoustical Panel Ceilings | 10 | 0 | 2022-07-08 | 2022-07-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09140 | [8 empty] | Fab/Del. Acoustical Panel Ceilings | 10 | 0 | 2022-11-01 | 2022-11-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09150 | [8 empty] | Prepare & Submit Resilient Flooring | 80 | 0 | 2022-04-25 08:00 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09160 | [5 empty] | ENG |  |  | Review & Approve Resilient Flooring | 10 | 0 | 2022-05-13 | 2022-07-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09170 | [8 empty] | Fab/Del. Resilient Flooring | 10 | 0 | 2023-01-17 | 2023-01-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09180 | [8 empty] | Prepare & Submit Paint | 60 | 0 | 2020-10-01 | 2020-11-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09190 | [8 empty] | Review & Approve Paint | 10 | 0 | 2020-11-13 | 2021-09-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09200 | [8 empty] | Fab/Del. Paint | 10 | 0 | 2021-05-25 | 2022-04-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09210 | [5 empty] | ENG |  |  | Prepare & Submit Penetrating Concrete Sealer | 60 | 0 | 2021-01-04 | 2022-11-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09220 | [5 empty] | ENG |  |  | Review & Approve Penetrating Concrete Sealer | 10 | 0 | 2022-11-25 | 2022-11-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09230 | [8 empty] | Fab/Del. Penetrating Concrete Sealer | 10 | 0 | 2022-11-25 | 2022-11-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10000 | [8 empty] | Prepare & Submit Toilet Accessories | 80 | 0 | 2022-03-07 08:00 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10010 | [5 empty] | ENG |  |  | Review & Approve Toilet Accessories | 10 | 0 | 2022-05-13 | 2022-06-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10020 | [8 empty] | Fab/Del. Toilet Accessories | 30 | 0 | 2022-12-12 | 2022-12-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10030 | [8 empty] | Prepare & Submit Flood Control System - Aquafence/Floodbreak | 80 | 0 | 2020-11-11 | 2021-03-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10040 | [8 empty] | Review & Approve Flood Control System - Aquafence/Floodbreak | 10 | 0 | 2021-03-05 | 2021-03-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10090 | [5 empty] | AQUAFENCE |  |  | Fab/Del. Flood Control System - Aquafence/Floodbreak | 80 | 0 | 2021-09-06 | 2022-09-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 11 | 11000 | [8 empty] | Prepare & Submit Play Equipment | 180 | 0 | 2021-07-26 08:00 | 2021-08-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 11 | 11010 | [8 empty] | Review & Approve Play Equipment | 10 | 0 | 2021-08-09 08:00 | 2021-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 11 | 11020 | [8 empty] | Fab/Del. Play Equipment | 30 | 0 | 2022-06-01 | 2022-09-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 11 | 11030 | [8 empty] | Prepare & Submit Spray Shower Equipment | 180 | 0 | 2021-07-26 08:00 | 2021-08-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 11 | 11040 | [8 empty] | Review & Approve Spray Shower Equipment | 10 | 0 | 2021-08-19 08:00 | 2021-11-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 11 | 11050 | [8 empty] | Fab/Del. Spray Shower Equipment | 30 | 0 | 2022-06-01 | 2022-09-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 14 | 14000 | [8 empty] | Prepare & Submit Limited Elevator Upgrades (RFI 161, 162, 163, 164) | 120 | 0 | 2020-12-07 | 2021-06-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 14 | 14010 | [8 empty] | Review & Approve Limited Elevator Upgrades (Omitted PCOCO 69) | 10 | 0 | 2021-06-21 | 2021-11-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 14 | 14020 | [8 empty] | Fab/Del. Limited Elevator Upgrade Materials (Omitted PCOCO 69) | 80 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22000 | [8 empty] | Prepare & Submit Plumbing Layout - S8-1 - Addition | 27 | 0 | 2021-11-15 08:00 | 2021-11-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22010 | [8 empty] | Review & Approve Plumbing Layout - S8-1 - Addition | 10 | 0 | 2021-11-25 08:00 | 2021-12-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22020 | [8 empty] | Prepare & Submit Plumbing Layout - S8 Existing | 27 | 0 | 2021-11-15 08:00 | 2021-11-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22030 | [8 empty] | Review & Approve Plumbing Layout - S8 Existing | 10 | 0 | 2021-11-26 | 2021-12-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22040 | [8 empty] | Prepare & Submit Plumbing Layout - OG-2 | 27 | 0 | 2021-07-02 | 2021-07-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22050 | [8 empty] | Review & Approve Plumbing Layout - OG-2 | 10 | 0 | 2021-07-19 08:00 | 2021-08-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22060 | [8 empty] | Prepare & Submit Plumbing Layout - OG-3 | 27 | 0 | 2021-07-02 | 2021-07-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22070 | [8 empty] | Review & Approve Plumbing Layout - OG-3 | 10 | 0 | 2021-07-19 08:00 | 2021-08-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22080 | [8 empty] | Prepare & Submit Plumbing Layout - OG-4 | 27 | 0 | 2021-05-17 | 2021-08-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22090 | [8 empty] | Review & Approve Plumbing Layout - OG-4 | 10 | 0 | 2021-08-19 | 2021-09-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22100 | [8 empty] | Prepare & Submit Plumbing Layout - OG-8 | 27 | 0 | 2021-01-20 | 2021-08-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22110 | [8 empty] | Review & Approve Plumbing Layout - OG-8 | 10 | 0 | 2021-08-27 08:00 | 2021-10-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22120 | [8 empty] | Prepare & Submit Plumbing Layout - OG-9 | 27 | 0 | 2021-06-17 | 2021-08-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22130 | [8 empty] | Review & Approve Plumbing Layout - OG-9 | 10 | 0 | 2021-08-27 08:00 | 2021-10-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22140 | [8 empty] | Prepare & Submit Plumbing Layout - OG -1 | 27 | 0 | 2021-07-02 | 2021-07-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22150 | [8 empty] | Review & Approve Plumbing Layout - OG -1 | 10 | 0 | 2021-07-19 08:00 | 2021-08-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22160 | [8 empty] | Prepare & Submit Plumbing Layout - OG-5 | 27 | 0 | 2021-05-17 | 2021-06-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22170 | [8 empty] | Review & Approve Plumbing Layout - OG-5 | 10 | 0 | 2021-06-17 | 2021-07-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22180 | [8 empty] | Prepare & Submit Plumbing Layout - OG-6 | 27 | 0 | 2021-05-27 | 2021-06-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22190 | [8 empty] | Review & Approve Plumbing Layout - OG-6 | 10 | 0 | 2021-06-17 | 2021-07-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22200 | [8 empty] | Prepare & Submit Plumbing Layout - OG-10 | 27 | 0 | 2021-06-17 | 2021-09-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22210 | [8 empty] | Review & Approve Plumbing Layout - OG-10 | 10 | 0 | 2021-09-02 | 2021-10-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22220 | [8 empty] | Prepare & Submit Plumbing Layout - SG-4 | 27 | 0 | 2021-04-15 | 2021-05-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22230 | [8 empty] | Review & Approve Plumbing Layout - SG-4 | 10 | 0 | 2021-05-04 | 2021-05-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22240 | [8 empty] | Prepare & Submit Plumbing Layout - SG-5 | 27 | 0 | 2021-04-20 | 2021-07-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22250 | [8 empty] | Review & Approve Plumbing Layout - SG-5 | 10 | 0 | 2021-07-19 | 2021-08-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22260 | [8 empty] | Prepare & Submit Plumbing Layout - SG-6 | 27 | 0 | 2020-12-21 | 2021-05-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22270 | [8 empty] | Review & Approve Plumbing Layout - SG-6 | 10 | 0 | 2021-05-08 | 2021-05-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22280 | [8 empty] | Prepare & Submit Plumbing Layout - SG-1 | 27 | 0 | 2021-07-26 08:00 | 2021-08-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22290 | [8 empty] | Review & Approve Plumbing Layout - SG-1 | 10 | 0 | 2021-08-16 08:00 | 2021-09-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22300 | [8 empty] | Prepare & Submit Plumbing Layout - SG-2 | 27 | 0 | 2021-07-26 08:00 | 2021-08-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22310 | [8 empty] | Review & Approve Plumbing Layout - SG-2 | 10 | 0 | 2021-08-16 08:00 | 2021-09-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22340 | [8 empty] | Prepare & Submit Plumbing Layout - SG-3 | 27 | 0 | 2021-07-26 08:00 | 2021-08-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22350 | [8 empty] | Review & Approve Plumbing Layout - SG-3 | 10 | 0 | 2021-08-16 08:00 | 2021-09-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22360 | [8 empty] | Prepare & Submit Plumbing Layout - SG-7 | 27 | 0 | 2021-09-26 | 2021-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22370 | [8 empty] | Review & Approve Plumbing Layout - SG-7 | 10 | 0 | 2021-10-07 | 2021-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22380 | [8 empty] | Prepare & Submit Sleeves and Seals for Plumbing Piping | 27 | 0 | 2020-09-08 | 2020-10-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22390 | [8 empty] | Review & Approve Sleeves and Seals for Plumbing Piping | 10 | 0 | 2020-10-20 | 2021-03-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22400 | [8 empty] | Fab/Del. Sleeves and Seals for Plumbing Piping | 5 | 0 | 2021-04-14 | 2021-05-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22410 | [8 empty] | Prepare & Submit Escutcheons for Plumbing Piping | 27 | 0 | 2020-09-08 | 2020-10-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22420 | [8 empty] | Review & Approve Escutcheons for Plumbing Piping | 10 | 0 | 2020-10-20 | 2020-12-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22430 | [8 empty] | Fab/Del. Escutcheons for Plumbing Piping | 5 | 0 | 2021-08-02 08:00 | 2021-08-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22440 | [8 empty] | Prepare & Submit General Duty Valves | 27 | 0 | 2020-09-08 | 2020-09-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22450 | [8 empty] | Review & Approve General Duty Valves | 10 | 0 | 2020-09-24 | 2020-10-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22460 | [8 empty] | Fab/Del. General Duty Valves | 5 | 0 | 2021-08-02 08:00 | 2021-08-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22470 | [8 empty] | Prepare & Submit Plumbing Hangers and Supports | 27 | 0 | 2020-10-22 | 2020-11-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22480 | [8 empty] | Review & Approve Plumbing Hangers and Supports | 10 | 0 | 2020-11-05 | 2020-11-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22490 | [8 empty] | Fab/Del. Plumbing Hangers and Supports | 5 | 0 | 2020-10-22 | 2021-02-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22500 | [8 empty] | Prepare & Submit Heat Tracing for Plumbing Piping | 27 | 0 | 2020-09-08 | 2020-10-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22510 | [8 empty] | Review & Approve Heat Tracing for Plumbing Piping | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22520 | [8 empty] | Fab/Del. Heat Tracing for Plumbing Piping | 20 | 0 | 2022-05-27 | 2022-06-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22530 | [8 empty] | Prepare & Submit Identification for Plumbing Piping and Equipment | 27 | 0 | 2021-01-04 | 2021-06-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22540 | [8 empty] | Review & Approve Identification for Plumbing Piping and Equipment | 10 | 0 | 2021-06-28 08:00 | 2021-07-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22550 | [8 empty] | Fab/Del. Identification for Plumbing Piping and Equipment | 5 | 0 | 2022-05-27 | 2022-06-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22560 | [8 empty] | Prepare & Submit Plumbing Piping Insulation | 27 | 0 | 2021-01-04 | 2021-06-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22570 | [8 empty] | Review & Approve Plumbing Piping Insulation | 10 | 0 | 2021-07-01 | 2021-07-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22580 | [8 empty] | Fab/Del. Plumbing Piping Insulation | 20 | 0 | 2022-05-27 | 2022-06-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22590 | [8 empty] | Prepare & Submit Domestic Water Piping | 27 | 0 | 2020-09-08 | 2020-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22600 | [8 empty] | Review & Approve Domestic Water Piping | 10 | 0 | 2020-11-05 | 2020-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22610 | [8 empty] | Fab/Del. Domestic Water Piping | 10 | 0 | 2020-12-17 | 2021-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22620 | [8 empty] | Prepare & Submit Domestic Water Piping Specialties | 27 | 0 | 2020-09-08 | 2020-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22630 | [8 empty] | Review & Approve Domestic Water Piping Specialties | 10 | 0 | 2020-11-10 | 2020-12-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22640 | [8 empty] | Fab/Del. Domestic Water Piping Specialties | 10 | 0 | 2021-07-26 08:00 | 2021-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22650 | [8 empty] | Prepare & Submit Domestic Water Pumping System | 27 | 0 | 2020-09-08 | 2020-09-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22660 | [8 empty] | Review & Approve Domestic Water Pumping System | 10 | 0 | 2020-09-28 | 2020-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22670 | [8 empty] | Fab/Del. Domestic Water Pumping System | 10 | 0 | 2021-07-26 08:00 | 2021-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22680 | [8 empty] | Prepare & Submit Sanitary Waste Piping | 27 | 0 | 2020-09-08 | 2020-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22690 | [8 empty] | Review & Approve Sanitary Waste Piping | 10 | 0 | 2020-11-05 | 2021-02-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22700 | [8 empty] | Fab/Del. Sanitary Waste Piping | 10 | 0 | 2021-07-26 08:00 | 2021-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22710 | [8 empty] | Prepare & Submit Sanitary Waste Piping Specialties | 27 | 0 | 2020-10-04 | 2020-11-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22720 | [8 empty] | Review & Approve Sanitary Waste Piping Specialties | 10 | 0 | 2020-11-04 | 2021-02-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22730 | [8 empty] | Fab/Del. Sanitary Waste Piping Specialties | 10 | 0 | 2021-07-26 08:00 | 2021-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22740 | [8 empty] | Prepare & Submit Storm Drainage Piping Specialties | 27 | 0 | 2020-09-08 | 2020-11-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22750 | [8 empty] | Review & Approve Storm Drainage Piping Specialties | 10 | 0 | 2020-11-04 | 2020-11-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22760 | [8 empty] | Fab/Del. Storm Drainage Piping Specialties | 10 | 0 | 2021-07-26 08:00 | 2021-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22770 | [8 empty] | Prepare & Submit Ejector Pumps, Sump Pumps and Hot Water Circulation Pumps | 27 | 0 | 2020-09-08 | 2020-11-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22780 | [8 empty] | Review & Approve Ejector Pumps, Sump Pumps and Hot Water Circulation Pumps | 10 | 0 | 2020-11-13 | 2021-02-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22790 | [8 empty] | Fab/Del. Ejector Pumps, Sump Pumps and Hot Water Circulation Pumps | 30 | 0 | 2021-11-10 08:00 | 2022-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22800 | [8 empty] | Prepare & Submit Domestic - Steam to Water Semi-Instantaneous Heater | 27 | 0 | 2020-09-08 | 2020-11-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22810 | [8 empty] | Review & Approve Domestic - Steam to Water Semi-Instantaneous Heater | 10 | 0 | 2020-11-02 | 2020-11-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22820 | [8 empty] | Fab/Del. Domestic - Steam to Water Semi-Instantaneous Heater | 30 | 0 | 2021-11-10 08:00 | 2022-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22830 | [8 empty] | Prepare & Submit Gas Service and Piping | 27 | 0 | 2020-09-08 | 2020-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22840 | [8 empty] | Review & Approve Gas Service and Piping | 10 | 0 | 2020-11-05 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22850 | [8 empty] | Fab/Del. Gas Service and Piping | 20 | 0 | 2022-02-04 | 2022-02-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22860 | [8 empty] | Prepare & Submit Plumbing Fixtures | 27 | 0 | 2020-09-08 | 2020-11-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22870 | [8 empty] | Review & Approve Plumbing Fixtures | 10 | 0 | 2020-11-11 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22880 | [8 empty] | Fab/Del. Plumbing Fixtures | 20 | 0 | 2021-07-26 08:00 | 2021-08-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22890 | [8 empty] | Prepare & Submit Underground Domestic Cold and Hot Water Distribution Piping | 27 | 0 | 2020-09-08 | 2020-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22900 | [8 empty] | Review & Approve Underground Domestic Cold and Hot Water Distribution Piping | 10 | 0 | 2020-11-05 | 2021-08-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22910 | [8 empty] | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - SGN | 40 | 0 | 2021-06-21 | 2021-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23000 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of S8 | 30 | 0 | 2021-10-25 08:00 | 2021-11-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23010 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of S8 | 10 | 0 | 2021-11-10 08:00 | 2021-11-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23020 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-1 | 30 | 0 | 2021-04-25 | 2021-05-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23030 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-1 | 10 | 0 | 2021-05-12 | 2021-05-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23040 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-2 | 30 | 0 | 2021-11-15 08:00 | 2021-11-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23050 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-2 | 10 | 0 | 2021-11-25 | 2021-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23060 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-3 | 30 | 0 | 2021-10-25 08:00 | 2021-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23070 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-3 | 10 | 0 | 2021-11-04 08:00 | 2021-11-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23080 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-4 | 30 | 0 | 2021-05-17 | 2021-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23090 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-4 | 10 | 0 | 2021-11-08 08:00 | 2021-11-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23100 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-5 | 30 | 0 | 2021-05-17 | 2021-11-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23110 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-5 | 10 | 0 | 2021-11-18 08:00 | 2021-12-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23120 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-6 | 30 | 0 | 2021-05-17 | 2021-11-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23130 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-6 | 10 | 0 | 2021-11-10 | 2021-12-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23140 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-8 | 30 | 0 | 2021-01-11 | 2021-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23150 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-8 | 10 | 0 | 2021-10-07 | 2021-10-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23160 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-9 | 30 | 0 | 2021-09-26 | 2021-10-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23170 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-9 | 10 | 0 | 2021-10-15 | 2021-10-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23180 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-10 | 30 | 0 | 2021-06-30 08:00 | 2021-07-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23190 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of OG-10 | 10 | 0 | 2021-07-15 08:00 | 2021-07-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23200 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-1 | 30 | 0 | 2021-08-26 08:00 | 2021-09-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23210 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of SG-1 | 10 | 0 | 2021-09-17 08:00 | 2021-10-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23220 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-2 | 30 | 0 | 2021-11-15 08:00 | 2021-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23230 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of SG-2 | 10 | 0 | 2021-12-01 | 2021-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23240 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-3 | 30 | 0 | 2021-11-15 08:00 | 2021-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23250 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of SG-3 | 10 | 0 | 2021-12-01 | 2021-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23260 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-4 | 30 | 0 | 2021-02-20 | 2021-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23270 |  | SG4 |  |  |  | ENG |  |  | Review & Approve Ductwork Shop Drawings for All Levels of SG-4 | 10 | 0 | 2021-03-25 | 2022-07-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23280 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-5 | 30 | 0 | 2021-06-07 | 2021-07-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23290 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of SG-5 | 10 | 0 | 2021-07-09 | 2021-07-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23300 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-6 | 30 | 0 | 2020-12-21 | 2021-07-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23310 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of SG-6 | 10 | 0 | 2021-07-09 | 2021-07-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23320 | [8 empty] | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-7 | 30 | 0 | 2021-11-15 | 2021-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23330 | [8 empty] | Review & Approve Ductwork Shop Drawings for All Levels of SG-7 | 10 | 0 | 2021-12-01 | 2021-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23340 |  | S8 |  |  |  | ENG |  |  | Prepare & Submit Piping Shop Drawings for All Levels of S8 | 30 | 0 | 2022-01-10 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23350 |  | S8 |  |  |  | ENG |  |  | Review & Approve Piping Shop Drawings for All Levels of S8 | 10 | 0 | 2022-06-16 | 2022-06-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23360 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-1 | 30 | 0 | 2021-03-26 | 2021-04-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23370 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-1 | 10 | 0 | 2021-04-23 | 2021-05-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23380 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-2 | 30 | 0 | 2021-06-25 08:00 | 2021-06-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23390 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-2 | 10 | 0 | 2021-06-30 08:00 | 2021-07-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23400 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-3 | 30 | 0 | 2021-09-26 | 2021-10-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23410 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-3 | 10 | 0 | 2021-10-21 | 2021-11-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23420 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-4 | 30 | 0 | 2021-05-17 | 2022-02-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23430 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-4 | 10 | 0 | 2022-02-19 | 2022-04-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23440 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-5 | 30 | 0 | 2021-05-17 | 2022-03-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23450 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-5 | 10 | 0 | 2022-03-31 | 2022-04-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23460 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-6 | 30 | 0 | 2021-05-17 | 2022-03-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23470 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-6 | 10 | 0 | 2022-03-10 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23480 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-8 | 30 | 0 | 2020-12-21 | 2021-11-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23490 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-8 | 10 | 0 | 2021-11-10 | 2021-12-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23500 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-9 | 30 | 0 | 2021-10-15 | 2022-01-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23510 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-9 | 10 | 0 | 2022-01-21 | 2022-01-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23520 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of OG-10 | 30 | 0 | 2021-10-15 | 2021-11-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23530 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of OG-10 | 10 | 0 | 2021-11-04 | 2021-11-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23540 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of SG-1 | 30 | 0 | 2021-05-24 | 2021-06-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23550 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of SG-1 | 10 | 0 | 2021-06-04 | 2021-07-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23560 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of SG-2 | 30 | 0 | 2021-09-26 | 2021-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23570 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of SG-2 | 10 | 0 | 2021-10-07 | 2021-10-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23580 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of SG-3 | 30 | 0 | 2022-04-04 | 2022-04-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23590 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of SG-3 | 10 | 0 | 2022-04-21 | 2022-05-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23600 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of SG-4 | 30 | 0 | 2021-01-11 | 2021-03-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23610 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of SG-4 | 10 | 0 | 2021-03-15 | 2021-05-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23620 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of SG-5 | 30 | 0 | 2021-05-14 | 2021-05-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23630 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of SG-5 | 10 | 0 | 2021-05-18 | 2021-05-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23640 | [8 empty] | Prepare & Submit Piping Shop Drawings for All Levels of SG-6 | 30 | 0 | 2021-01-04 | 2021-07-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23650 | [8 empty] | Review & Approve Piping Shop Drawings for All Levels of SG-6 | 10 | 0 | 2021-07-09 | 2021-07-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23660 |  | SG7 |  |  |  | ENG |  |  | Prepare & Submit Piping Shop Drawings for All Levels of SG-7 | 30 | 0 | 2022-03-21 | 2022-09-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23670 |  | SG7 |  |  |  | ENG |  |  | Review & Approve Piping Shop Drawings for All Levels of SG-7 | 10 | 0 | 2022-09-22 | 2022-10-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23680 | [8 empty] | Prepare & Submit Expansion Fittings and Loops for HVAC Piping | 30 | 0 | 2021-01-04 | 2021-12-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23690 | [5 empty] | ENG |  |  | Review & Approve Expansion Fittings and Loops for HVAC Piping | 10 | 0 | 2021-12-31 | 2022-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23700 | [8 empty] | Fab/Del. Expansion Fittings and Loops for HVAC Piping | 10 | 0 | 2022-09-25 08:00 | 2022-10-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23710 | [8 empty] | Prepare & Submit Sleeves and Sleeve Seals for HVAC Piping | 30 | 0 | 2020-10-18 | 2020-11-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23720 | [8 empty] | Review & Approve Sleeves and Sleeve Seals for HVAC Piping | 10 | 0 | 2020-11-18 | 2020-12-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23730 | [8 empty] | Fab/Del. Sleeves and Sleeve Seals for HVAC Piping | 10 | 0 | 2021-08-03 08:00 | 2021-08-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23740 | [8 empty] | Prepare & Submit Meters and Gages for HVAC Piping | 30 | 0 | 2020-08-03 | 2020-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23750 | [8 empty] | Review & Approve Meters and Gages for HVAC Piping | 10 | 0 | 2020-09-02 | 2020-10-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23760 | [8 empty] | Fab/Del. Meters and Gauges for HVAC Piping | 10 | 0 | 2021-11-22 08:00 | 2021-11-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23770 | [8 empty] | Prepare & Submit meters and gauges for HVAC piping | 30 | 0 | 2020-08-03 | 2020-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23780 | [8 empty] | Review & Approve meters and gauges for HVAC piping | 10 | 0 | 2020-09-02 | 2020-10-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23790 | [8 empty] | Fab/Del. meters and gages for HVAC piping | 10 | 0 | 2021-11-22 08:00 | 2021-11-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23800 | [8 empty] | Prepare & Submit General Duty Valves for HVAC Piping Facility Fuel Oil Piping Steam and Condensate Piping | 30 | 0 | 2020-08-03 | 2020-09-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23810 | [8 empty] | Review & Approve General Duty Valves for HVAC Piping Facility Fuel Oil Piping Steam and Condensate Piping | 10 | 0 | 2020-09-04 | 2020-09-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23820 | [8 empty] | Fab/Del. General Duty Valves for HVAC Piping Facility Fuel Oil Piping Steam and Condensate Piping | 45 | 0 | 2021-04-25 | 2021-08-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23830 | [8 empty] | Prepare & Submit Facility Fuel Oil Piping | 30 | 0 | 2020-10-01 | 2020-10-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23840 | [8 empty] | Review & Approve Facility Fuel Oil Piping | 10 | 0 | 2020-10-29 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23850 | [8 empty] | Fab/Del. Facility Fuel Oil Piping | 45 | 0 | 2021-09-01 08:00 | 2022-03-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23860 | [8 empty] | Prepare & Submit Hangers and Supports for HVAC Piping and Equipment | 30 | 0 | 2020-08-03 | 2020-09-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23870 | [8 empty] | Review & Approve Hangers and Supports for HVAC Piping and Equipment | 10 | 0 | 2020-09-04 | 2020-10-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23880 | [8 empty] | Fab/Del. Hangers and Supports for HVAC Piping and Equipment | 10 | 0 | 2021-04-25 | 2021-05-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23890 | [5 empty] | ENG |  |  | Prepare & Submit Seismic Restraints and Vibration Isolation | 30 | 0 | 2020-12-08 | 2022-08-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23900 | [5 empty] | ENG |  |  | Review & Approve Seismic Restraints and Vibration Isolation | 10 | 0 | 2022-08-02 08:00 | 2022-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23910 | [8 empty] | Fab/Del. Seismic Restraints and Vibration Isolation | 10 | 0 | 2022-12-12 | 2022-12-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23920 | [8 empty] | Prepare & Submit HVAC Testing, Adjusting, Balancing Plan | 30 | 0 | 2020-08-17 | 2020-08-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23930 | [8 empty] | Review & Approve HVAC Testing, Adjusting, Balancing Plan | 10 | 0 | 2020-08-17 | 2020-09-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23940 | [8 empty] | Prepare & Submit HVAC Piping Insulation & Equipment Insulation Duct Insulation | 30 | 0 | 2020-11-25 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23950 | [8 empty] | Review & Approve HVAC Piping Insulation & Equipment Insulation Duct Insulation | 10 | 0 | 2020-12-14 | 2021-02-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23960 | [8 empty] | Fab/Del. HVAC Piping Insulation & Equipment Insulation Duct Insulation | 20 | 0 | 2022-07-22 | 2022-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23970 | [8 empty] | Prepare & Submit Metal Ducts | 30 | 0 | 2020-12-17 | 2020-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23980 | [8 empty] | Review & Approve Metal Ducts | 10 | 0 | 2020-12-17 | 2021-01-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 23990 | [8 empty] | Fab/Del. Metal Ducts | 20 | 0 | 2021-05-21 | 2021-05-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24000 | [8 empty] | Prepare & Submit Duplex Condensate Return Pumps | 30 | 0 | 2020-08-03 | 2020-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24010 | [8 empty] | Review & Approve Duplex Condensate Return Pumps | 10 | 0 | 2020-09-01 | 2020-11-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24020 | [8 empty] | Fab/Del. Duplex Condensate Return Pumps | 45 | 0 | 2021-03-26 | 2022-02-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24030 | [8 empty] | Prepare & Submit HVAC Power Ventilators | 30 | 0 | 2020-07-01 | 2020-07-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24040 | [8 empty] | Review & Approve HVAC Power Ventilators | 10 | 0 | 2020-07-01 | 2021-01-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24050 | [8 empty] | Fab/Del. HVAC Power Ventilators | 45 | 0 | 2021-03-26 | 2022-06-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24060 | [8 empty] | Prepare & Submit Air Duct Accessories Diffusers, Registers, and Grilles | 30 | 0 | 2020-08-03 | 2020-09-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24070 | [8 empty] | Review & Approve Air Duct Accessories Diffusers, Registers, and Grilles | 10 | 0 | 2020-09-21 | 2020-10-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24080 | [8 empty] | Fab/Del. Air Duct Accessories Diffusers, Registers, and Grilles | 20 | 0 | 2021-10-10 | 2022-06-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24090 | [8 empty] | Prepare & Submit Vacuum Pump Units | 30 | 0 | 2020-02-09 | 2020-10-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24100 | [8 empty] | Review & Approve Vacuum Pump Units | 10 | 0 | 2020-10-14 | 2020-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24110 | [8 empty] | Fab/Del. Vacuum Pump Units | 40 | 0 | 2021-03-26 | 2021-08-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24120 | [8 empty] | Prepare & Submit Boiler Feedwater Pumps | 30 | 0 | 2020-08-03 | 2020-09-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24130 | [8 empty] | Review & Approve Boiler Feedwater Pumps | 10 | 0 | 2020-09-09 | 2020-09-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24140 | [8 empty] | Fab/Del. Boiler Feedwater Pumps | 70 | 0 | 2021-10-10 | 2021-10-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24150 | [8 empty] | Prepare & Submit Unit Heaters | 30 | 0 | 2020-07-20 | 2020-07-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24160 | [8 empty] | Review & Approve Unit Heaters | 10 | 0 | 2020-07-20 | 2020-09-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24170 | [8 empty] | Fab/Del. Unit Heaters | 25 | 0 | 2021-10-10 | 2022-06-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24180 | [8 empty] | Prepare & Submit Steam and Condensate Piping | 30 | 0 | 2020-08-03 | 2020-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24190 | [8 empty] | Review & Approve Steam and Condensate Piping | 10 | 0 | 2020-09-12 | 2020-10-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24200 | [8 empty] | Fab/Del. Steam and Condensate Piping - SGN | 35 | 0 | 2021-03-25 08:00 | 2021-08-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24210 | [8 empty] | Prepare & Submit Facility Fuel Oil Piping | 30 | 0 | 2020-08-03 | 2020-10-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24220 | [8 empty] | Review & Approve Facility Fuel Oil Piping | 10 | 0 | 2020-10-29 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24230 | [8 empty] | Fab/Del. Facility Fuel Oil Piping | 65 | 0 | 2021-07-12 08:00 | 2021-10-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24240 | [8 empty] | Prepare & Submit Water Treatment for Steam System | 30 | 0 | 2021-03-25 08:00 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24250 | [8 empty] | Review & Approve Water Treatment for Steam System | 10 | 0 | 2021-09-27 | 2021-11-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24260 | [8 empty] | Fab/Del. Water Treatment for Steam System | 70 | 0 | 2022-06-14 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24270 | [5 empty] | ENG |  |  | Prepare & Submit Commissioning of HVAC Plan | 30 | 0 | 2022-06-15 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24280 | [5 empty] | ENG |  |  | Review & Approve Commissioning of HVAC Plan | 10 | 0 | 2022-08-16 | 2022-08-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24290 | [8 empty] | Prepare & Submit Prefabricated Breechings and Stacks | 30 | 0 | 2020-08-03 | 2020-10-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24300 | [8 empty] | Review & Approve Prefabricated Breechings and Stacks | 10 | 0 | 2020-10-13 | 2021-03-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24310 | [8 empty] | Fab/Del. Prefabricated Breechings and Stacks | 30 | 0 | 2022-01-16 | 2022-02-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24320 | [8 empty] | Prepare & Submit Fire Tube Boilers | 30 | 0 | 2020-08-03 | 2020-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24330 | [8 empty] | Review & Approve Fire Tube Boilers | 10 | 0 | 2020-09-23 | 2021-01-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24340 | [8 empty] | Fab/Del. Fire Tube Boilers | 60 | 0 | 2022-01-28 | 2022-03-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24350 | [8 empty] | Prepare & Submit HVAC Controls | 30 | 0 | 2021-01-11 | 2021-02-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24360 | [8 empty] | Review & Approve HVAC Controls | 10 | 0 | 2021-02-12 | 2021-02-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24370 | [8 empty] | Fab/Del. HVAC Controls | 40 | 0 | 2021-03-26 | 2022-06-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24380 | [8 empty] | Prepare & Submit CO & Natural Gas Sensors | 30 | 0 | 2020-07-29 | 2020-07-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24390 | [8 empty] | Review & Approve CO & Natural Gas Sensors | 10 | 0 | 2020-07-29 | 2021-03-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24400 | [8 empty] | Fab/Del. CO & Natural Gas Sensors | 30 | 0 | 2022-07-25 08:00 | 2022-08-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 28 | 28000 | [8 empty] | Prepare & Submit Smoke Detection System (Duplicate with 283100-01005) | 80 | 0 | 2020-11-16 | 2020-12-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 28 | 28010 | [8 empty] | Review & Approve Smoke Detection System (Duplicate with 283100-01010) | 10 | 0 | 2020-12-24 | 2020-12-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 28 | 28020 | [8 empty] | Fab/Del. Smoke Detection System | 60 | 0 | 2022-03-25 08:00 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 28 | 28030 | [8 empty] | Prepare & Submit Carbon-Monoxide & Natural Gas Detection Sensors | 80 | 0 | 2021-02-01 | 2021-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 28 | 28040 | [8 empty] | Review & Approve Carbon-Monoxide & Natural Gas Detection Sensors | 10 | 0 | 2021-02-26 | 2021-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 28 | 28050 | [8 empty] | Fab/Del. Carbon-Monoxide & Natural Gas Detection Sensors | 60 | 0 | 2022-07-25 08:00 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32000 | [8 empty] | Prepare & Submit Dense Graded Stone Base | 150 | 0 | 2020-11-10 | 2020-12-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32010 | [8 empty] | Review & Approve Dense Graded Stone Base | 10 | 0 | 2020-12-10 | 2020-12-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32020 | [8 empty] | Del. Dense Graded Stone Base | 1 | 0 | 2021-09-26 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32030 | [5 empty] | ENG |  |  | Prepare & Submit Concrete Base for Pavement | 150 | 0 | 2021-12-25 | 2022-12-25 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32040 | [5 empty] | ENG |  |  | Review & Approve Concrete Base for Pavement | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -57 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32050 | [8 empty] | Del. Concrete Base for Pavement | 1 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32060 | [5 empty] | ENG |  |  | Prepare & Submit Asphaltic Concrete | 150 | 0 | 2022-01-26 | 2022-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32070 | [5 empty] | ENG |  |  | Review & Approve Asphaltic Concrete | 10 | 0 | 2022-12-01 | 2023-01-09 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32260 | [8 empty] | Del. Asphaltic Concrete | 1 | 1 | 2023-02-27 08:00 | 2023-02-27 17:00 | -9 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32270 | [5 empty] | ENG |  |  | Prepare & Submit Tack Coat | 150 | 0 | 2022-01-26 | 2022-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32280 | [5 empty] | ENG |  |  | Review & Approve Tack Coat | 10 | 0 | 2022-12-01 | 2022-12-05 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32290 | [8 empty] | Fab/Del. Tack Coat | 1 | 1 | 2023-02-27 08:00 | 2023-02-27 17:00 | -9 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32300 | [8 empty] | Prepare & Submit Concrete Sidewalk Plan | 150 | 0 | 2021-09-10 08:00 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32310 | [8 empty] | Review & Approve Concrete Sidewalk Plan | 10 | 0 | 2021-09-27 | 2021-11-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32320 | [5 empty] | ENG |  |  | Prepare & Submit Porous Concrete Pavement | 150 | 0 | 2021-09-10 08:00 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32330 | [5 empty] | ENG |  |  | Review & Approve Porous Concrete Pavement | 10 | 0 | 2022-10-04 | 2022-10-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32340 | [8 empty] | Del. Porous Concrete Pavement | 1 | 0 | 2022-10-25 | 2022-10-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32350 | [8 empty] | Prepare & Submit Integrally Colored Concrete | 150 | 0 | 2021-09-01 08:00 | 2021-09-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32360 | [8 empty] | Review & Approve Integrally Colored Concrete | 10 | 0 | 2021-09-24 | 2022-05-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32370 | [8 empty] | Del. Integrally Colored Concrete | 1 | 0 | 2022-08-29 | 2022-08-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32380 | [5 empty] | ENG |  |  | Prepare & Submit Expansion Joints | 150 | 0 | 2021-08-26 | 2022-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32390 | [5 empty] | ENG |  |  | Review & Approve Expansion Joints | 10 | 0 | 2022-12-01 | 2022-12-05 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32400 | [8 empty] | Fab/Del. Expansion Joints | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -18 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32410 | [8 empty] | Prepare & Submit Concrete Curbs Plan | 150 | 0 | 2021-09-01 08:00 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32420 | [8 empty] | Review & Approve Concrete Curbs Plan | 10 | 0 | 2021-09-24 08:00 | 2022-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32430 | [5 empty] | ENG |  |  | Prepare & Submit Steel Faced Concrete Curbs | 150 | 0 | 2021-09-26 | 2022-11-30 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.Div. 32 | 32440 | [5 empty] | ENG |  |  | Review & Approve Steel Faced Concrete Curbs | 10 | 0 | 2022-12-01 | 2023-02-02 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32450 | [8 empty] | Fab/Del. Steel Faced Concrete Curbs | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -67 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32460 | [5 empty] | ENG |  |  | Prepare & Submit Pavement Markings | 150 | 0 | 2022-01-26 | 2022-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32470 | [5 empty] | ENG |  |  | Review & Approve Pavement Markings | 10 | 0 | 2022-12-01 | 2022-12-05 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32480 | [8 empty] | Fab/Del. Pavement Markings | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 8 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32490 | [5 empty] | ENG |  |  | Prepare & Submit Safety Surfacing | 150 | 0 | 2022-01-26 | 2022-11-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32500 | [5 empty] | ENG |  |  | Review & Approve Safety Surfacing | 10 | 0 | 2022-11-02 | 2022-11-02 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32510 | [8 empty] | Fab/Del. Safety Surfacing | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -28 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32520 | [8 empty] | Prepare & Submit Chain Link Fences and Gates | 150 | 0 | 2020-09-22 | 2020-10-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32530 | [8 empty] | Review & Approve Chain Link Fences and Gates | 10 | 0 | 2021-01-21 | 2021-02-04 17:00 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32540 | [8 empty] | Fab/Del. Chain Link Fences and Gates | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 17 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32550 | [5 empty] | ENG |  |  | Prepare & Submit Site Furnishings | 150 | 0 | 2021-09-01 08:00 | 2022-11-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32560 | [5 empty] | ENG |  |  | Review & Approve Site Furnishings | 10 | 0 | 2022-11-02 | 2022-11-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32570 | [8 empty] | Fab/Del. Site Furnishings | 40 | 0 | 2022-12-01 | 2022-12-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32580 | [5 empty] | ENG |  |  | Prepare & Submit Topsoil | 150 | 0 | 2021-09-01 08:00 | 2022-07-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32590 | [5 empty] | ENG |  |  | Review & Approve Topsoil | 10 | 0 | 2022-07-22 | 2022-08-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32600 | [8 empty] | Del. Topsoil | 1 | 0 | 2022-10-17 08:00 | 2022-10-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32610 | [5 empty] | ENG |  |  | Prepare & Submit Seeded Lawn | 150 | 0 | 2022-01-26 | 2022-09-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32620 | [5 empty] | ENG |  |  | Review & Approve Seeded Lawn | 10 | 0 | 2022-09-07 08:00 | 2022-09-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32630 | [8 empty] | Del. Seeded Lawn | 5 | 0 | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32640 | [5 empty] | ENG |  |  | Prepare & Submit Plant Materials | 150 | 0 | 2022-01-26 | 2022-07-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32650 | [5 empty] | ENG |  |  | Review & Approve Plant Materials | 10 | 0 | 2022-07-22 | 2022-08-10 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32660 | [8 empty] | Del. Plant Materials | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 30 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32670 | [8 empty] | Prepare & Submit Landscape Boulders | 150 | 0 | 2020-07-13 | 2020-11-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32680 | [8 empty] | Review & Approve Landscape Boulders | 10 | 0 | 2020-11-13 | 2021-03-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32690 | [8 empty] | Del. Landscape Boulders | 5 | 0 | 2022-09-23 | 2022-10-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32700 | [5 empty] | ENG |  |  | Prepare & Submit Metal Edging | 150 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32710 | [5 empty] | ENG |  |  | Review & Approve Metal Edging | 10 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32720 | [8 empty] | Fab/Del. Metal Edging | 5 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32730 | [5 empty] | ENG |  |  | Prepare & Submit Basketball Backstop | 150 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32740 | [5 empty] | ENG |  |  | Review & Approve Basketball Backstop | 10 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32750 | [8 empty] | Fab/Del. Basketball Backstop | 30 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33000 | [8 empty] | Prepare & Submit Maint. & Protect Existing Privately Owned Utilities Plan - N/A | 20 | 0 | 2021-03-01 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33010 | [8 empty] | Review & Approve Maint. & Protect Existing Privately Owned Utilities Plan - N/A | 10 | 0 | 2021-03-01 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33020 | [8 empty] | Prepare & Submit Terminate & Demo. Existing Utilities Plan - N/A | 20 | 0 | 2021-03-01 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33030 | [8 empty] | Review & Approve Terminate & Demo. Existing Utilities Plan - N/A | 10 | 0 | 2021-03-01 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33040 | [8 empty] | Prepare & Submit Cleaning & Disinfecting Water Mains Plan - N/A | 20 | 0 | 2021-03-01 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33050 | [8 empty] | Review & Approve Cleaning & Disinfecting Water Mains Plan - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33060 | [8 empty] | Prepare & Submit Cement Lined Ductile Iron Pipe & Fitting for Water Main | 20 | 0 | 2020-10-09 | 2020-11-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33070 | [8 empty] | Review & Approve Cement Lined Ductile Iron Pipe & Fitting for Water Main | 10 | 0 | 2020-11-09 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33080 | [8 empty] | Fab/Del. Cement Lined Ductile Iron Pipe & Fitting for Water Main | 20 | 0 | 2021-06-21 08:00 | 2021-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33090 | [8 empty] | Prepare & Submit Water Main & Appurtenances - N/A | 20 | 0 | 2021-07-12 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33100 | [8 empty] | Review & Approve Water Main & Appurtenances - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33110 | [8 empty] | Fab/Del. Water Main & Appurtenances - N/A | 20 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33120 | [8 empty] | Prepare & Submit Filter Fabric for Utility Pipes | 20 | 0 | 2020-11-21 | 2020-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33130 | [8 empty] | Review & Approve Filter Fabric for Utility Pipes | 10 | 0 | 2020-12-21 | 2020-12-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33140 | [8 empty] | Fab/Del. Filter Fabric for Utility Pipes | 20 | 0 | 2021-06-21 08:00 | 2021-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33150 | [8 empty] | Prepare & Submit Polyethylene Sleeve | 20 | 0 | 2020-12-28 | 2021-01-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33160 | [8 empty] | Review & Approve Polyethylene Sleeve | 10 | 0 | 2021-01-11 | 2021-02-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33170 | [8 empty] | Fab/Del. Polyethylene Sleeve | 20 | 0 | 2021-06-21 08:00 | 2021-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33180 | [8 empty] | Prepare & Submit Wet & Dry Connections to Existing Water Main Procedure - N/A | 20 | 0 | 2021-08-02 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33190 | [8 empty] | Review & Approve Wet & Dry Connections to Existing Water Main Procedure - N/A | 10 | 0 | 2021-08-02 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33200 | [8 empty] | Prepare & Submit Water Main Valves - N/A | 20 | 0 | 2021-07-24 | 2021-07-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33210 | [8 empty] | Review & Approve Water Main Valvess - N/A | 10 | 0 | 2021-07-24 | 2021-07-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33220 | [8 empty] | Fab/Del. Water Main Valvess - N/A | 20 | 0 | 2021-07-24 | 2021-07-24 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.Div. 33 | 33230 | [5 empty] | ENG |  |  | Prepare & Submit Cleaning of Drainage Structures Procedures | 20 | 1 | 2022-07-25 08:00 | 2023-02-27 17:00 | -49 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 33 | 33240 | [5 empty] | ENG |  |  | Review & Approve Cleaning of Drainage Structures Procedures | 10 | 10 | 2023-02-28 08:00 | 2023-03-13 17:00 | -49 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33250 | [5 empty] | ENG |  |  | Prepare & Submit Expansion Joints for Utility | 20 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33260 | [5 empty] | ENG |  |  | Review & Approve Expansion Joints for Utility | 10 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33270 | [8 empty] | Fab/Del. Expansion Joints for Utility | 20 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33280 | [8 empty] | Prepare & Submit Ductile Iron Pipe Sewers | 20 | 0 | 2020-11-09 | 2020-12-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33290 | [8 empty] | Review & Approve Ductile Iron Pipe Sewers | 10 | 0 | 2020-12-03 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33300 | [8 empty] | Fab/Del. Ductile Iron Pipe Sewers | 20 | 0 | 2021-07-28 | 2021-08-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33310 | [5 empty] | ENG |  |  | Prepare & Submit Catch Basin Connections | 20 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33320 | [5 empty] | ENG |  |  | Review & Approve Catch Basin Connections | 10 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33330 | [8 empty] | Fab/Del. Catch Basin Connections | 20 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33340 | [8 empty] | Prepare & Submit Structures for Sewers | 20 | 0 | 2020-08-30 | 2020-09-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33350 | [8 empty] | Review & Approve Structures for Sewers | 10 | 0 | 2020-10-01 | 2021-04-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33360 | [8 empty] | Fab/Del. Structures for Sewers | 20 | 0 | 2022-03-01 | 2022-03-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01600 | [8 empty] | Prepare & Submit Electrical Subcontractor | 5 | 0 | 2020-03-16 | 2020-03-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01610 | [8 empty] | Review & Approve Electrical Subcontractor | 10 | 0 | 2020-03-16 | 2020-11-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01620 | [8 empty] | Prepare & Submit Plumbing Subcontractor | 5 | 0 | 2020-03-16 | 2020-03-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01630 | [8 empty] | Review & Approve Plumbing Subcontractor | 10 | 0 | 2020-03-16 | 2020-09-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01640 | [8 empty] | Prepare & Submit HVAC Subcontractor | 5 | 0 | 2020-03-16 | 2020-03-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01650 | [8 empty] | Review & Approve HVAC Subcontractor | 10 | 0 | 2020-03-16 | 2020-12-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01660 | [8 empty] | Site Survey, Prepare & Submit Elevator Subcontractor | 60 | 0 | 2020-07-13 | 2020-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01670 | [8 empty] | Review & Approve Elevator Subcontractor | 10 | 0 | 2020-11-10 | 2021-07-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31000 | [8 empty] | Prepare & Submit Geotectile - Drainage | 20 | 0 | 2020-09-26 | 2020-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31010 | [8 empty] | Review & Approve Geotectile - Drainage | 10 | 0 | 2020-10-26 | 2020-11-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31020 | [8 empty] | Fab/Del. Geotectile - Drainage | 5 | 0 | 2022-03-07 08:00 | 2022-03-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31030 | [8 empty] | Prepare & Submit Geotectile - Separation & Stabilization | 20 | 0 | 2020-09-22 | 2020-10-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31040 | [8 empty] | Review & Approve Geotectile - Separation & Stabilization | 10 | 0 | 2020-10-22 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31050 | [8 empty] | Fab/Del. Geotectile - Separation & Stabilization | 5 | 0 | 2022-03-07 08:00 | 2022-03-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31060 | [8 empty] | Prepare & Submit Clearing & Grubbing Plan | 20 | 0 | 2020-07-13 | 2020-11-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31070 | [8 empty] | Review & Approve Clearing & Grubbing Plan | 10 | 0 | 2020-11-11 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31080 | [8 empty] | Prepare & Submit Tree Protection Plan | 20 | 0 | 2020-07-13 | 2020-10-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31090 | [8 empty] | Review & Approve Tree Protection Plan | 10 | 0 | 2020-10-19 | 2020-10-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31100 | [8 empty] | Prepare & Submit Selective Tree Removal Plan | 20 | 0 | 2020-07-13 | 2020-10-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31110 | [8 empty] | Review & Approve Selective Tree Removal Plan | 10 | 0 | 2020-10-19 | 2020-10-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31120 | [8 empty] | Prepare & Submit Dewatering Plan | 20 | 0 | 2020-08-20 | 2020-09-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31130 | [8 empty] | Review & Approve Dewatering Plan | 10 | 0 | 2020-09-03 | 2021-02-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31140 | [8 empty] | Prepare & Submit Excavating Backfill & Compaction for Pipes & Utility Trenches Procedure | 20 | 0 | 2021-01-04 | 2021-02-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31150 | [8 empty] | Review & Approve Excavating Backfill & Compaction for Pipes & Utility Trenches Procedure | 10 | 0 | 2021-02-06 | 2021-02-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31160 | [8 empty] | Prepare & Submit Excavating Backfill & Compaction for Pavements Plan Procedure | 20 | 0 | 2021-01-04 | 2021-02-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31170 | [8 empty] | Review & Approve Excavating Backfill & Compaction for Pavements Plan Procedure | 10 | 0 | 2021-02-06 | 2021-02-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01680 | [8 empty] | Prepare & Submit Structural Steel Subcontractor | 5 | 0 | 2020-05-18 | 2020-05-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01690 | [8 empty] | Review & Approve Structural Steel Subcontractor | 10 | 0 | 2020-05-18 | 2020-10-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01700 | [8 empty] | Prepare & Submit Misc. Metal Subcontractor | 5 | 0 | 2020-05-18 | 2020-05-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01710 | [8 empty] | Review & Approve Misc. Metal Subcontractor | 10 | 0 | 2020-05-18 | 2022-05-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01720 | [8 empty] | Prepare & Submit Masonry Subcontractor | 5 | 0 | 2020-07-07 | 2020-07-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01730 | [8 empty] | Review & Approve Masonry Subcontractor | 10 | 0 | 2020-07-07 | 2021-11-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01740 | [8 empty] | Prepare & Submit Waterproofer Subcontractor | 5 | 0 | 2020-07-13 | 2020-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01750 | [8 empty] | Review & Approve Waterproofer Subcontractor | 10 | 0 | 2020-11-10 | 2021-04-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01760 | [8 empty] | Prepare & Submit Painting Subcontractor | 5 | 0 | 2020-05-18 | 2020-05-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01770 | [8 empty] | Review & Approve Painting Subcontractor | 10 | 0 | 2020-05-18 | 2021-03-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01780 | [8 empty] | Prepare & Submit Hazardous Waste Subcontractor | 5 | 0 | 2020-03-16 | 2020-03-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01790 | [8 empty] | Review & Approve Hazardous Waste Subcontractor | 10 | 0 | 2020-03-16 | 2020-08-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01800 | [8 empty] | Prepare & Submit Roofing Subcontractor | 5 | 0 | 2020-05-27 | 2020-05-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01810 | [8 empty] | Review & Approve Roofing Subcontractor | 10 | 0 | 2020-05-28 | 2021-06-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01820 | [8 empty] | Prepare & Submit Fire Proofing Subcontractor | 5 | 0 | 2020-07-10 | 2020-07-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01830 | [8 empty] | Review & Approve Fire Proofing Subcontractor | 10 | 0 | 2020-07-10 | 2020-08-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24410 | [8 empty] | Prepare & Submit Fuel Oil Tanks | 30 | 0 | 2020-09-29 | 2020-10-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24420 | [8 empty] | Review & Approve Fuel Oil Tanks | 10 | 0 | 2020-10-29 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24430 | [8 empty] | Fab/Del. Fuel Oil Tanks | 75 | 0 | 2021-04-12 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24440 | [8 empty] | Prepare & Submit Fuel Pumps | 30 | 0 | 2020-09-29 | 2020-10-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24450 | [8 empty] | Review & Approve Fuel Pumps | 10 | 0 | 2020-10-29 | 2020-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24460 | [8 empty] | Fab/Del. Fuel Pumps | 75 | 0 | 2021-07-26 08:00 | 2021-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.1 | SURV-SGN-G-01005 | [8 empty] | Perform Survey of Site/Building - Surfside - North | 10 | 0 | 2020-10-19 | 2020-10-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.1 | SURV-OGW-G-01010 | [8 empty] | Perform Survey of Site/Building - O'Dwyer Garden - West (OG-2, OG-3 & OG-9) | 10 | 0 | 2020-11-05 | 2020-11-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.1 | SURV-OGE-01015 | [8 empty] | Perform Survey of Site/Building - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) | 10 | 0 | 2020-11-05 | 2020-11-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.1 | SURV-SGS-G-01020 | [8 empty] | Perform Survey of Site/Building - Surfside - South (SG-1, SG-2, SG-3 & SG-7) | 10 | 0 | 2020-10-26 | 2020-11-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.4 | SURV-S8-G-01005 | [8 empty] | Perform Survey of Site/Building - Site 8 (S8 & S8-1) | 10 | 0 | 2020-10-26 | 2020-11-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.Mob | MOBE-01005 | [8 empty] | Project Mobilization | 20 | 0 | 2020-07-13 | 2020-08-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01005 | [8 empty] | Install Site Fencing - Surfside Gardens - North | 10 | 0 | 2020-12-15 | 2021-01-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01560 | [8 empty] | NYCHA files TR's | 67 | 0 | 2020-07-13 | 2020-09-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-01005 | [8 empty] | File for DOT Sidewalk Permits | 10 | 0 | 2020-10-01 | 2020-10-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Milestones | M005 | [8 empty] | Notice to Proceed (July 13, 2020) | 0 | 0 | 2020-07-13 17:00 |  |  | 0
Not Started |  | CI NYCHA Update #20.Milestones | M900 | [8 empty] | Substantial Completion (NTP+1047d) - May 26, 2023 | 0 | 0 |  | 2024-04-24 17:00 | -334 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-01010 | [8 empty] | DOT Issue Sidewalk Permits | 20 | 0 | 2020-09-02 | 2020-10-06 17:00 |  | 0
Not Started |  | CI NYCHA Update #20.Milestones | M999 | [8 empty] | Final Completion (NTP+1137d) - August 24, 2023 | 0 | 0 |  | 2024-07-23 17:00 | -334 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.1 | SURV-SGN-E-01000 | [8 empty] | Conduct Electrical Site Survey - Surfside Gardens North (SG-4, SG-5) | 20 | 0 | 2020-08-13 | 2020-12-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.1 | SURV-OGW-E-01015 | [8 empty] | Conduct Electrical Site Survey - O'Dwyer Garden - Part 2 (OG-3) | 15 | 0 | 2020-09-08 | 2021-07-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.1 | SURV-OGE-01020 | [8 empty] | Conduct Electrical Site Survey - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) | 15 | 0 | 2021-02-24 | 2021-06-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.1 | SURV-SGS-E-01030 | [8 empty] | Conduct Electrical Site Survey - Surfside Gardens South (SG-1) | 10 | 0 | 2021-06-01 | 2021-07-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.4 | SURV-S8-E-01015 | [8 empty] | Conduct Electrical Site Survey - Site 8 (S8 & S8-1) | 10 | 0 | 2022-02-22 08:00 | 2022-03-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01905 | [8 empty] | Procure Vendor - Switchboard/Panelboard & GCB/Disconnect Switches | 30 | 0 | 2020-07-13 | 2020-08-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01910 | [8 empty] | Procure Vendor - ACTTS | 30 | 0 | 2020-07-13 | 2020-08-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01915 | [8 empty] | Procure Installer - Lightning Protection | 50 | 0 | 2020-07-13 | 2020-09-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01920 | [8 empty] | Procure Vendor - Generator | 20 | 0 | 2020-11-02 | 2020-11-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01925 | [8 empty] | Procure Installer - Smoke Detection System | 50 | 0 | 2020-07-13 | 2020-08-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01930 | [8 empty] | Procure Vendor - Lighting & Vacancy/Occupancy Sensors | 50 | 0 | 2020-07-13 | 2020-09-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01935 | [8 empty] | Procure Vendor - Seismic Restraint & Vibration Isolation | 50 | 0 | 2021-04-05 | 2021-04-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01940 | [8 empty] | Procure Vendor - Heat Tracing | 50 | 0 | 2020-07-13 | 2020-07-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.2 | 260519-01000 | [8 empty] | Prep/Submit Product Submittals - Wire & Cable (600 V) | 40 | 0 | 2020-04-15 | 2020-05-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.2 | 260519-01010 | [8 empty] | Rev/Apprv. Product Submittals - Wire & Cable (600 V) | 10 | 0 | 2020-05-14 | 2020-11-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.2 | 260519-01015 | [8 empty] | Fabricate & Deliver Material - Wire & Cable (600 V) | 35 | 0 | 2022-03-25 08:00 | 2022-06-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.3 | 260526-01010 | [8 empty] | Prep/Submit Product Submittals - Grounding & Bonding Equipment | 40 | 0 | 2020-06-17 | 2020-11-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.3 | 260526-01020 | [8 empty] | Rev/Apprv. Product Submittals - Grounding & Bonding Equipment | 10 | 0 | 2020-11-06 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.3 | 260526-01025 | [8 empty] | Fabricate & Deliver Material - Grounding & Bonding | 35 | 0 | 2022-05-01 | 2022-09-23 10:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.4 | 260533-01005 | [8 empty] | Prep/Submit Product Submittals - Conduits (Rigid, EMT & Flexible) | 40 | 0 | 2020-04-15 | 2020-05-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.4 | 260533-01010 | [8 empty] | Rev/Apprv. Product Submittals - Conduits (Rigid, EMT & Flexible) | 10 | 0 | 2020-05-15 | 2020-12-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.4 | 260533-01015 | [8 empty] | Prep/Submit Product Submittals - Junction & Pull Boxes | 40 | 0 | 2020-04-15 | 2020-05-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.4 | 260533-01020 | [8 empty] | Rev/Apprv. Product Submittals - Junction & Pull Boxes | 10 | 0 | 2020-05-15 | 2021-02-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.4 | 260533-01025 | [8 empty] | Fabricate & Deliver Material - Raceway Conduits & Installation Components | 25 | 0 | 2021-06-25 08:00 | 2022-08-31 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.5 | 260534-01005 | [8 empty] | Prep/Submit Product Submittals - Fire Stopping | 40 | 0 | 2020-04-15 | 2020-06-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.5 | 260534-01010 | [8 empty] | Rev/Apprv. Product Submittals - Fire Stopping | 10 | 0 | 2020-06-10 | 2020-11-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.5 | 260534-01015 | [8 empty] | Fabricate & Deliver Material - Fire Stopping | 25 | 0 | 2022-03-01 | 2022-09-02 12:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.6 | 260543-01005 | [8 empty] | Prep/Submit Product Submittals - High Density Polyethylene Conduit (HDPE) | 40 | 0 | 2020-04-15 | 2020-06-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.6 | 260543-01010 | [8 empty] | Rev/Apprv. Product Submittals - High Density Polyethylene Conduit (HDPE) | 10 | 0 | 2020-06-30 | 2021-02-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.6 | 260543-01015 | [8 empty] | Prep/Submit Product Submittals - Fiber Reinforced Epoxy Utility Duct (FRE) - N/A | 40 | 0 | 2020-11-24 | 2020-11-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.6 | 260543-01020 | [8 empty] | Rev/Apprv. Product Submittals - Fiber Reinforced Epoxy Utility Duct (FRE) | 10 | 0 | 2020-11-24 | 2020-11-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.6 | 260543-01025 | [8 empty] | Fabricate & Deliver Material - Underground Ducts for Electrical Systems (HDPE & FRE) | 25 | 0 | 2021-04-01 | 2022-03-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.7 | 260548-01005 | [8 empty] | Prep/Submit Product Submittals - Vibration Isolation Devices | 40 | 0 | 2020-10-10 | 2020-10-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.7 | 260548-01010 | [8 empty] | Rev/Apprv. Product Submittals - Vibration Isolation Devices | 10 | 0 | 2020-10-22 | 2020-11-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.7 | 260548-01015 | [8 empty] | Prep/Submit Product Submittals - Seismic Restraints | 40 | 0 | 2021-07-26 08:00 | 2021-11-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.7 | 260548-01020 | [8 empty] | Rev/Apprv. Product Submittals - Seismic Restraints | 10 | 0 | 2021-11-16 | 2021-12-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.7 | 260548-01025 | [8 empty] | Fabricate & Deliver Equipment - Seismic Vibration & Isolation - N/A | 45 | 0 | 2022-01-01 08:00 | 2022-01-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.8 | 260553-01005 | [8 empty] | Prep/Submit Product Submittals - Identification Labels & Tags | 40 | 0 | 2020-08-20 | 2020-10-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.8 | 260553-01010 | [8 empty] | Rev/Apprv. Product Submittals - Identification Labels & Tags | 10 | 0 | 2020-10-21 | 2020-11-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.8 | 260553-01015 | [8 empty] | Fabricate & Deliver Material - Identification Labels & Tags | 25 | 0 | 2022-07-01 | 2022-09-23 12:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.9 | 260573-01005 | [8 empty] | Prep/Submit Report - Short Circuit Analysis Studies | 60 | 0 | 2020-11-02 | 2022-05-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.9 | 260573-01010 | [8 empty] | Rev/Appr. Report - Short Circuit Analysis Studies - (Coordinate w/ CON-ED) | 40 | 0 | 2021-04-22 | 2022-05-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01005 | [8 empty] | Prep/Submit Product Submittals - Room Controller | 40 | 0 | 2020-08-10 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01010 | [8 empty] | Rev/Apprv. Product Submittals - Room Controller | 10 | 0 | 2020-10-09 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01015 | [8 empty] | Prep/Submit Product Submittals - Occupancy/Vacancy Sensors (Rev 1) | 40 | 0 | 2020-08-10 | 2021-09-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01020 | [8 empty] | Rev/Apprv. Product Submittals - Occupancy/Vacancy Sensors (Rev 1) | 10 | 0 | 2021-09-06 | 2021-09-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01025 | [8 empty] | Prep/Submit Product Submittals - Wall Switches | 40 | 0 | 2020-08-10 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01030 | [8 empty] | Rev/Apprv. Product Submittals - Wall Switches | 10 | 0 | 2020-10-09 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.10 | 260923-01035 | [8 empty] | Fabricate & Deliver Equipment - Vacancy & Occupancy Sensors | 25 | 0 | 2022-04-25 08:00 | 2022-05-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.11 | 260924-01005 | [8 empty] | Prep/Submit Product Submittals - Lighting Contactors | 40 | 0 | 2020-09-01 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.11 | 260924-01010 | [8 empty] | Rev/Apprv. Product Submittals - Lighting Contactors | 10 | 0 | 2020-10-09 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.11 | 260924-01015 | [8 empty] | Prep/Submit Product Submittals - Time Switches | 40 | 0 | 2020-09-01 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.11 | 260924-01020 | [8 empty] | Rev/Apprv. Product Submittals - Time Switches | 10 | 0 | 2020-10-09 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.11 | 260924-01025 | [8 empty] | Prep/Submit Product Submittals - Outdoor Photoelectric Switches | 40 | 0 | 2020-09-01 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.11 | 260924-01030 | [8 empty] | Rev/Apprv. Product Submittals - Outdoor Photoelectric Switches | 10 | 0 | 2020-10-09 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.12 | 265600-01005 | [8 empty] | Prep/Submit Product Submittals - Exterior Lighting Fixtures | 30 | 0 | 2020-09-22 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.12 | 265600-01010 | [8 empty] | Rev/Apprv. Product Submittals - Exterior Lighting Fixtures | 10 | 0 | 2020-12-15 | 2021-01-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.13 | 265100-01005 | [8 empty] | Prep/Submit Product Submittals - Lighting Fixtures | 30 | 0 | 2020-08-03 | 2020-12-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.13 | 265100-01010 | [8 empty] | Rev/Apprv. Product Submittals - Lighting Fixtures | 10 | 0 | 2020-12-03 | 2021-01-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.13 | 265100-01015 | [8 empty] | Provide Samples - Lighting Fixtures | 10 | 0 | 2021-10-18 08:00 | 2021-12-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.20 | 262416-01005 | [8 empty] | Prep/Submit Product Submittals - Panelboards | 20 | 0 | 2020-08-24 | 2021-01-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.20 | 262416-01010 | [8 empty] | Rev/Apprv. Product Submittals - Panelboards | 10 | 0 | 2020-09-24 | 2021-02-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.20 | 262416-01015 | [8 empty] | Prep/Submit Product Submittals - Generator Circuit Breaker | 20 | 0 | 2020-08-24 | 2021-01-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.20 | 262416-01020 | [8 empty] | Rev/Apprv. Product Submittals - Generator Circuit Breaker | 10 | 0 | 2020-09-24 | 2021-02-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01005 | [8 empty] | Prep/Submit Product Submittals - Smoke Detection Panels (SDP) | 30 | 0 | 2020-09-01 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01010 | [8 empty] | Rev/Apprv. Product Submittals - Smoke Detection Panels (SDP) | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01015 | [8 empty] | Prep/Submit Product Submittals - Smoke Detectors | 30 | 0 | 2020-09-01 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01020 | [8 empty] | Rev/Apprv. Product Submittals - Smoke Detectors | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01025 | [8 empty] | Prep/Submit Product Submittals - Horns/Strobes | 30 | 0 | 2020-09-01 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01030 | [8 empty] | Rev/Apprv. Product Submittals - Horns/Strobes | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01035 | [8 empty] | Prep/Submit Product Submittals - Monitor & Circuit Modules | 30 | 0 | 2020-09-01 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01040 | [8 empty] | Rev/Apprv. Product Submittals - Monitor & Circuit Modules | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01045 | [8 empty] | Prep/Submit Product Submittals - Fire Smoke Dampers (FSD) | 30 | 0 | 2020-09-01 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01050 | [8 empty] | Rev/Apprv. Product Submittals - Fire Smoke Dampers (FSD) | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01055 | [8 empty] | Prep/Submit Product Submittals - Pull Station | 30 | 0 | 2020-09-01 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.16 | 283100-01060 | [8 empty] | Rev/Apprv. Product Submittals - Pull Station | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.17 | 264100-01005 | [8 empty] | Prep/Submit Product Submittals - Lightning Protection Equipment | 60 | 0 | 2020-08-03 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.17 | 264100-01010 | [8 empty] | Rev/Apprv. Product Submittals - Lightning Protection Equipment | 10 | 0 | 2020-09-01 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.22 | 262813-01005 | [8 empty] | Prep/Submit Product Submittals - 600 Volt Fuse (Submitted with disconnect switches) | 20 | 0 | 2020-08-24 | 2020-09-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.22 | 262813-01010 | [8 empty] | Rev/Apprv. Product Submittals - 600 Volt Fuse | 10 | 0 | 2020-09-09 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.22 | 262813-01015 | [8 empty] | Fabricate - 600 Volt Fuse | 40 | 0 | 2021-12-01 08:00 | 2021-12-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.22 | 262813-01020 | [8 empty] | Deliver - 600 Volt Fuse | 5 | 0 | 2021-12-27 08:00 | 2021-12-31 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.23 | 262816-01005 | [8 empty] | Prep/Submit Product Submittals - Fused Disconnect Switches | 20 | 0 | 2020-08-24 | 2020-09-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.23 | 262816-01010 | [8 empty] | Rev/Apprv. Product Submittals - Fused Disconnect Switches | 10 | 0 | 2020-09-09 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.23 | 262816-01015 | [8 empty] | Prep/Submit Product Submittals - Switch Enclosures | 20 | 0 | 2020-08-24 | 2020-09-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.23 | 262816-01020 | [8 empty] | Rev/Apprv. Product Submittals - Switch Enclosures | 10 | 0 | 2020-09-09 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.23 | 262816-01025 | [8 empty] | Fabricate - Fused Disconnect Switches | 40 | 0 | 2021-06-25 08:00 | 2022-04-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.23 | 262816-01030 | [8 empty] | Deliver - Fused Disconnect Switches | 5 | 0 | 2022-04-18 | 2022-04-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01005 | [8 empty] | Prep/Submit Product Submittals - Generator (450 Kw) | 40 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01010 | [8 empty] | Rev/Apprv. Product Submittals - Generator (450 Kw) | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01015 | [8 empty] | Prep/Submit Product Submittals - Acoustic Generator Enclosure | 40 | 0 | 2020-07-13 | 2020-09-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01020 | [8 empty] | Rev/Apprv. Product Submittals - Acoustic Generator Enclosure | 10 | 0 | 2020-09-03 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01025 | [8 empty] | Prep/Submit Product Submittals - Generator (350 Kw) | 40 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01030 | [8 empty] | Rev/Apprv. Product Submittals - Generator (350 Kw) | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01035 | [8 empty] | Prep/Submit Product Submittals - Generator (500 Kw) | 40 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01040 | [8 empty] | Rev/Apprv. Product Submittals - Generator (500 Kw) | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01045 | [8 empty] | Prep/Submit Product Submittals - Generator (400 Kw) | 40 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.24 | 263213-01050 | [8 empty] | Rev/Apprv. Product Submittals - Generator (400 Kw) | 10 | 0 | 2020-08-04 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01005 | [8 empty] | Prep/Submit Product Submittals - ACTTS (200A) | 30 | 0 | 2020-08-24 | 2020-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01010 | [8 empty] | Rev/Apprv. Product Submittals - ACTTS (200A) | 10 | 0 | 2020-09-17 | 2020-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01015 | [8 empty] | Prep/Submit Product Submittals - ACTTS (400A) | 30 | 0 | 2020-08-24 | 2020-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01020 | [8 empty] | Rev/Apprv. Product Submittals - ACTTS (400A) | 10 | 0 | 2020-09-17 | 2020-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01025 | [8 empty] | Prep/Submit Product Submittals - ACTTS (600A) | 30 | 0 | 2020-08-24 | 2020-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01030 | [8 empty] | Rev/Apprv. Product Submittals - ACTTS (600A) | 10 | 0 | 2020-09-17 | 2020-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01035 | [8 empty] | Prep/Submit Product Submittals - ACTTS (800A) | 30 | 0 | 2020-08-24 | 2020-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01040 | [8 empty] | Rev/Apprv. Product Submittals - ACTTS (800A) | 10 | 0 | 2020-09-17 | 2020-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01045 | [8 empty] | Prep/Submit Product Submittals - ACTTS (1000A) | 30 | 0 | 2020-08-24 | 2020-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.21 | 263623-01050 | [8 empty] | Rev/Apprv. Product Submittals - ACTTS (1000A) | 10 | 0 | 2020-08-17 | 2020-12-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01005 | [8 empty] | Prep/Submit Product Submittals - Heating Cables | 30 | 0 | 2020-07-28 | 2020-08-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01010 | [8 empty] | Rev/Apprv. Product Submittals - Heating Cables | 10 | 0 | 2020-08-31 | 2020-11-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01015 | [8 empty] | Prep/Submit Product Submittals - Temperature Sensors | 30 | 0 | 2020-07-28 | 2020-08-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01020 | [8 empty] | Rev/Apprv. Product Submittals - Temperature Sensors | 10 | 0 | 2020-08-31 | 2020-11-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01025 | [8 empty] | Prep/Submit Product Submittals - Heat Trace Controls | 30 | 0 | 2020-07-28 | 2020-08-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01030 | [8 empty] | Rev/Apprv. Product Submittals - Heat Trace Controls | 10 | 0 | 2020-08-31 | 2020-11-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.14 | 220533-01035 | [8 empty] | Fabricate & Deliver Equipment - Heat Tracing - N/A | 75 | 0 | 2021-06-15 | 2022-09-01 15:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.26 | 262726-01005 | [8 empty] | Prep/Submit Product Submittals - Switches & Receptacles | 20 | 0 | 2020-04-15 | 2020-06-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.26 | 262726-01010 | [8 empty] | Rev/Apprv. Product Submittals - Switches & Receptacles | 10 | 0 | 2020-06-10 | 2020-11-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.26 | 262726-01015 | [8 empty] | Fabricate & Deliver Equipment - Switches & Receptacles | 25 | 0 | 2022-04-15 | 2022-09-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01315 | [8 empty] | Prep/Submit Product Submittals - OG1 Switchboard (MSSB-OG-1) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01320 | [8 empty] | Rev/Apprv. Product Submittals - OG1 Switchboard (MSSB-OG-1) | 10 | 0 | 2021-02-24 | 2021-11-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01325 | [8 empty] | Prep/Submit Product Submittals - OG10 Switchboard (DB-OG-10) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01330 | [8 empty] | Rev/Apprv. Product Submittals - OG10 Switchboard (DB-OG-10) | 10 | 0 | 2021-02-24 | 2021-11-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01305 | [8 empty] | Prep/Submit Product Submittals - OG1 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01310 | [8 empty] | Rev/Apprv. Product Submittals - OG1 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-11-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01365 | [8 empty] | Prep/Submit Product Submittals - OG6 Switchboard (MSSB-OG-6) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01370 | [8 empty] | Rev/Apprv. Product Submittals - OG6 Switchboard (MSSB-OG-6) | 10 | 0 | 2021-02-24 | 2021-11-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01355 | [8 empty] | Prep/Submit Product Submittals - OG6 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01360 | [8 empty] | Rev/Apprv. Product Submittals - OG6 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-11-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01345 | [8 empty] | Prep/Submit Product Submittals - OG5 Switchboard (MSSB-OG-5) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01350 | [8 empty] | Rev/Apprv. Product Submittals - OG5 Switchboard (MSSB-OG-5) | 10 | 0 | 2021-02-24 | 2021-07-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01335 | [8 empty] | Prep/Submit Product Submittals - OG5 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.1 | 262413-01340 | [8 empty] | Rev/Apprv. Product Submittals - OG5 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-07-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01115 | [8 empty] | Prep/Submit Product Submittals - OG2 Switchboard (MSSB-OG-2) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01120 | [8 empty] | Rev/Apprv. Product Submittals - OG2 Switchboard (MSSB) | 10 | 0 | 2021-02-24 | 2021-03-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01105 | [8 empty] | Prep/Submit Product Submittals - OG2 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01110 | [8 empty] | Rev/Apprv. Product Submittals - OG2 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-03-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01195 | [8 empty] | Prep/Submit Product Submittals - OG9 Switchboard (ESB-OG-2) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01200 | [8 empty] | Rev/Apprv. Product Submittals - OG9 Switchboard (ESB-OG-2) | 10 | 0 | 2021-02-24 | 2021-04-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01185 | [8 empty] | Prep/Submit Product Submittals - OG9 Switchboard (DB-OG-9) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01190 | [8 empty] | Rev/Apprv. Product Submittals - OG9 Switchboard (DB-OG-9) | 10 | 0 | 2021-02-24 | 2021-04-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01135 | [8 empty] | Prep/Submit Product Submittals - OG3 Switchboard (MSSB-OG-3) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01140 | [8 empty] | Rev/Apprv. Product Submittals - OG3 Switchboard (MSSB-OG-3) | 10 | 0 | 2021-02-24 | 2021-03-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01125 | [8 empty] | Prep/Submit Product Submittals - OG3 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01130 | [8 empty] | Rev/Apprv. Product Submittals - OG3 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-03-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01165 | [8 empty] | Prep/Submit Product Submittals - OG4 Switchboard (MSSB-OG-4) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01170 | [8 empty] | Rev/Apprv. Product Submittals - OG4 Switchboard (MSSB-OG-4) | 10 | 0 | 2021-02-24 | 2021-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01145 | [8 empty] | Prep/Submit Product Submittals - OG4 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01150 | [8 empty] | Rev/Apprv. Product Submittals - OG4 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01155 | [8 empty] | Prep/Submit Product Submittals - OG4 Switchboard (ESB-G) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01160 | [8 empty] | Rev/Apprv. Product Submittals - OG4 Switchboard (ESB-G) | 10 | 0 | 2021-02-24 | 2021-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01175 | [8 empty] | Prep/Submit Product Submittals - OG8 Switchboard (DB-OG-8) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.2 | 262413-01180 | [8 empty] | Rev/Apprv. Product Submittals - OG8 Switchboard (DB-OG-8) | 10 | 0 | 2021-02-24 | 2021-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01445 | [8 empty] | Prep/Submit Product Submittals - SG1 Switchboard (MSSB-SG-1) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01450 | [8 empty] | Rev/Apprv. Product Submittals - SG1 Switchboard (MSSB-SG-1) | 10 | 0 | 2021-02-24 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01425 | [8 empty] | Prep/Submit Product Submittals - SG1 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01430 | [8 empty] | Rev/Apprv. Product Submittals - SG1 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01455 | [8 empty] | Prep/Submit Product Submittals - SG2 Switchboard (MSSB-SG-2) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01460 | [8 empty] | Rev/Apprv. Product Submittals - SG2 Switchboard (MSSB-SG-2) | 10 | 0 | 2021-02-24 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01435 | [8 empty] | Prep/Submit Product Submittals - SG2 Switchboard (ESB-SG-2) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01440 | [8 empty] | Rev/Apprv. Product Submittals - SG2 Switchboard (ESB-SG-2) | 10 | 0 | 2021-02-24 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01415 | [8 empty] | Prep/Submit Product Submittals - SG3 Switchboard (MSSB-SG-3) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01420 | [8 empty] | Rev/Apprv. Product Submittals - SG3 Switchboard (MSSB-SG-3) | 10 | 0 | 2021-02-24 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01405 | [8 empty] | Prep/Submit Product Submittals - SG3 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.3 | 262413-01410 | [8 empty] | Rev/Apprv. Product Submittals - SG3 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01015 | [8 empty] | Prep/Submit Product Submittals - SG4 Switchboard (MSSB-SG-4) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01020 | [8 empty] | Rev/Apprv. Product Submittals - SG4 Switchboard (MSSB-SG-4) | 10 | 0 | 2021-02-24 | 2021-04-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01005 | [8 empty] | Prep/Submit Product Submittals - SG4 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01010 | [8 empty] | Rev/Apprv. Product Submittals - SG4 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-04-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01035 | [8 empty] | Prep/Submit Product Submittals - SG5 Switchboard (MSSB-SG-5) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01040 | [8 empty] | Rev/Apprv. Product Submittals - SG5 Switchboard (MSSB-SG-5) | 10 | 0 | 2021-02-24 | 2021-04-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01025 | [8 empty] | Prep/Submit Product Submittals - SG5 Switchboard (ESB) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01030 | [8 empty] | Rev/Apprv. Product Submittals - SG5 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-04-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01045 | [8 empty] | Prep/Submit Product Submittals - SG6 Switchboard (DB-SG-6) | 20 | 0 | 2020-11-02 | 2021-02-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.4 | 262413-01050 | [8 empty] | Rev/Apprv. Product Submittals - SG6 Switchboard (DB-SG-6) | 10 | 0 | 2021-02-24 | 2021-04-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.5 | 262413-01515 | [8 empty] | Prep/Submit Product Submittals - S8-1 Switchboard (MSSB) (Resubmittal) | 20 | 0 | 2020-11-02 | 2021-06-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.5 | 262413-01520 | [8 empty] | Rev/Apprv. Product Submittals - S8-1 Switchboard (MSSB) | 10 | 0 | 2021-02-24 | 2021-07-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.5 | 262413-01505 | [8 empty] | Prep/Submit Product Submittals - S8-1 Switchboard (ESB) (Resubmittal) | 20 | 0 | 2020-11-02 | 2021-06-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.27.5 | 262413-01510 | [8 empty] | Rev/Apprv. Product Submittals - S8-1 Switchboard (ESB) | 10 | 0 | 2021-02-24 | 2021-07-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01010 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-04-06 | 2021-08-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01015 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2021-08-26 08:00 | 2021-08-31 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01005 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-04-05 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01090 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-05-06 | 2021-07-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01100 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2021-07-13 | 2021-07-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01030 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2021-04-06 | 2021-08-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01070 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2021-08-16 | 2021-08-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-01020 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-04-05 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-1105 |  | SG4 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 2021-07-06 | 2022-08-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-1120 |  | SG4 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 0 | 2022-03-25 08:00 | 2022-10-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.1 | P-SG4-1130 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Cellar Lighting Controls | 60 | 0 | 2021-05-10 | 2021-12-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01075 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Cellar Lighting Controls | 10 | 0 | 2021-12-08 | 2021-12-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2021-05-10 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01150 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-15 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-02-01 | 2021-03-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-03-15 | 2021-04-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2020-11-02 | 2021-06-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2021-06-03 | 2021-06-21 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01000 |  | SG4 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 0 | 2021-05-10 | 2023-02-24 15:24 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01005 |  | SG4 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 0 | 2023-02-24 15:24 | 2023-02-24 15:24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2020-08-03 | 2020-09-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2020-08-15 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-10 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-06 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2021-05-21 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.8.7 | E-SG4-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01010 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-06-08 | 2021-10-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01015 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2021-10-04 08:00 | 2021-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01005 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-06-07 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01030 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2021-07-06 | 2022-01-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01035 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-02-01 | 2022-02-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01025 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-07-05 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01060 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-06-07 | 2021-08-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01100 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2021-08-23 08:00 | 2021-08-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01105 |  | SG5 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 2021-07-06 | 2022-10-24 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01110 |  | SG5 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -88 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.1 | P-SG5-01120 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Cellar Lighting Controls | 60 | 0 | 2022-01-03 | 2022-02-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01075 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-02-16 08:00 | 2022-03-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 2021-02-15 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-03-02 | 2021-03-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2021-04-26 | 2021-06-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2021-06-03 | 2021-06-21 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01000 |  | SG5 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 0 | 2021-09-01 | 2023-02-24 17:00 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01040 |  | SG5 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 0 | 2023-02-24 08:00 | 2023-02-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2020-08-03 | 2020-09-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2020-09-15 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-02-25 08:00 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.1.7 | E-SG5-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01190 |  | SG6 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 0 | 2022-03-25 08:00 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01200 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01105 |  | SG6 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 2021-07-06 08:00 | 2022-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01000 | [8 empty] | Release for Fabrication - Generators (SG4 & SG5) | 0 | 0 | 2021-06-01 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01015 | [8 empty] | Fabricate - Generator Enclosure (SG4 & SG5) | 40 | 0 | 2021-11-15 | 2022-04-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01020 | [8 empty] | FAT - Generator w/ Enclosure (SG4 & SG5) | 10 | 0 | 2022-04-07 08:00 | 2022-04-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01025 | [8 empty] | Deliver - Generator w/ Enclosure (SG4 & SG5) | 2 | 0 | 2022-04-18 08:00 | 2022-04-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01010 | [8 empty] | Fabricate - Generator (SG4 & SG5) | 120 | 0 | 2021-06-02 | 2021-11-08 13:48 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01050 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-06-08 | 2021-10-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01055 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2021-10-12 08:00 | 2021-10-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01045 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-06-07 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01065 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2021-10-11 | 2022-01-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01070 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-02-15 08:00 | 2022-02-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01110 | [8 empty] | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 2021-06-07 | 2021-07-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01115 | [8 empty] | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 2021-07-20 08:00 | 2021-07-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01090 | [8 empty] | Fabricate - Lightning Protection System | 60 | 0 | 2021-11-22 | 2022-04-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01095 | [8 empty] | Deliver - Lightning Protection System | 5 | 0 | 2021-12-13 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.1 | P-SG6-01060 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-10-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01005 | [8 empty] | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01010 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01055 | [8 empty] | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 2020-11-02 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01060 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 2020-12-09 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01035 | [8 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2021-05-26 | 2022-05-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01040 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-04-01 | 2022-04-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01045 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2021-06-09 08:00 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01050 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-23 08:00 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-02-25 | 2021-03-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01075 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-03-02 | 2021-03-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01015 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01020 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01025 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.2.7 | E-SG6-01030 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Site Lighting Installation - N/A | 30 | 0 | 2022-02-25 08:00 | 2022-02-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation - N/A | 10 | 0 | 2022-02-25 08:00 | 2022-02-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Underground Ducts Installation (Rev 1) | 30 | 0 | 2021-02-25 | 2021-06-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 2021-03-12 | 2021-06-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01000 | [8 empty] | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 2021-01-25 | 2022-04-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations | 20 | 0 | 2021-04-06 | 2021-05-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.2.3 | E-SGN-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01010 |  | OG2 | [6 empty] | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01015 |  | OG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 0 | 2022-08-12 08:00 | 2022-09-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01020 |  | OG2 | [6 empty] | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 2021-09-22 | 2021-09-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01025 |  | OG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 2021-09-27 08:00 | 2021-10-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01000 | [8 empty] | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 2021-02-15 | 2022-04-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.3 | E-OG2A-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01030 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-07-14 | 2022-03-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01120 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2022-03-04 | 2022-03-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01020 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-07-09 08:00 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01050 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-10-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01060 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2021-11-25 | 2022-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01150 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-03-18 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01110 | [8 empty] | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 2021-07-14 | 2022-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01160 | [8 empty] | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 2022-01-10 | 2022-01-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01000 | [8 empty] | Release for Fabrication - Generators (OG4 & OG5) | 0 | 0 | 2021-06-01 |  |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01040 |  | OG8 | [6 empty] | Fabricate - Generator Enclosure (OG4 & OG5) | 40 | 33 | 2022-01-31 | 2023-04-12 17:00 | -140 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01140 |  | OG8 | [6 empty] | FAT - Generator w/ Enclosure (OG4 & OG5) | 10 | 10 | 2023-04-13 08:00 | 2023-04-26 17:00 | -140 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01170 |  | OG8 | [6 empty] | Deliver - Generator w/ Enclosure (OG4 & OG5) | 2 | 2 | 2023-04-27 08:00 | 2023-04-28 17:00 | -140 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01010 | [8 empty] | Fabricate - Generator (OG4 & OG5) | 120 | 0 | 2021-06-02 | 2022-01-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01090 | [8 empty] | Fabricate - Lightning Protection System | 60 | 0 | 2022-03-25 | 2022-05-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01180 | [8 empty] | Deliver - Lightning Protection System | 5 | 0 | 2022-05-20 | 2022-05-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-1105 |  | OG8 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 08:00 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01210 |  | OG8 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 15 | 2022-01-25 | 2023-03-17 17:00 | -67 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.1 | P-OG8-01200 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01005 | [8 empty] | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01010 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01055 | [8 empty] | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 2020-08-03 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01060 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 2020-12-09 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01035 |  | OG8 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-03-25 | 2022-10-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01040 |  | OG8 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-10-17 08:00 | 2022-12-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01045 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01050 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-06-01 | 2021-07-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01075 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-07-02 | 2021-07-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01015 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-10 | 2021-01-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01020 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01025 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing- N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.2.7 | E-OG8-01030 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01010 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-07-14 | 2022-03-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01050 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2022-03-04 08:00 | 2022-03-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01000 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-07-09 08:00 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01020 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-10-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01030 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2021-11-26 | 2022-03-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01070 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-03-18 08:00 | 2022-03-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01090 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-07-14 | 2022-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01100 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2022-01-10 | 2022-01-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01105 |  | OG4 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01110 |  | OG4 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -77 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.1 | P-OG4-01120 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01070 |  | OG4 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2021-11-01 08:00 | 2022-10-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01075 |  | OG4 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-10-28 08:00 | 2022-12-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-06-01 | 2021-07-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-07-02 | 2021-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2021-11-01 08:00 | 2022-04-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2022-04-06 | 2022-04-28 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01000 |  | OG4 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01005 |  | OG4 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-05-10 | 2021-06-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-06-11 | 2021-07-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.8.7 | E-OG4-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01010 | [8 empty] | Fabricate, Assemble & Wire - Switchboards - N/A for Exist. Bldg | 120 | 0 | 2021-07-14 | 2022-03-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01070 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2022-03-04 08:00 | 2022-03-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01000 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-07-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01020 | [8 empty] | Release for Fabrication - ACTTS - N/A for Exist. Bldg | 0 | 0 | 2021-10-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01030 | [8 empty] | Fabricate - ACTTS - N/A for Exist. Bldg | 80 | 0 | 2021-11-26 | 2022-03-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01090 | [8 empty] | Deliver - ACTTS - N/A for Exist. Bldg | 5 | 0 | 2022-03-18 08:00 | 2022-03-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01060 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-07-14 | 2022-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01100 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2022-02-25 08:00 | 2022-03-04 08:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01105 |  | OG5 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01110 |  | OG5 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -63 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.1 | P-OG5-01120 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01070 |  | OG5 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-01-03 | 2022-06-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01075 |  | OG5 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-06-08 08:00 | 2022-07-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 2021-06-01 | 2021-07-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-07-02 | 2021-07-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2021-12-27 08:00 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2022-03-28 | 2022-04-11 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01000 |  | OG5 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01005 |  | OG5 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-04-26 | 2021-05-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-05-21 | 2021-06-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.1.1.7 | E-OG5-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01010 |  | OGW | [6 empty] | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 2022-08-08 08:00 | 2022-08-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01015 |  | OGW | [6 empty] | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 0 | 2022-08-12 08:00 | 2022-09-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 2021-08-23 08:00 | 2021-09-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 2021-09-27 | 2021-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01000 | [8 empty] | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 2021-02-24 | 2022-05-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.3 | E-OGW-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01030 |  | OG9 | [6 empty] | Fabricate, Assemble & Wire - Switchboards (Supply Chain Delay) | 120 | 0 | 2022-01-25 08:00 | 2022-08-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01035 |  | OG9 | [6 empty] | Deliver - Switchboards | 5 | 0 | 2022-09-01 08:00 | 2022-09-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01020 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-12-16 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01050 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-12-17 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01060 | [8 empty] | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 2021-12-17 | 2022-06-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01065 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-06-09 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01110 | [8 empty] | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 2022-01-14 | 2022-06-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01115 | [8 empty] | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 2022-06-03 08:00 | 2022-06-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01000 | [8 empty] | Release for Fabrication - Generators (OG2 & OG3) | 0 | 0 | 2021-06-01 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01040 | [8 empty] | Fabricate - Generator Enclosure (OG2 & OG3) | 40 | 0 | 2022-02-23 | 2022-04-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01045 | [8 empty] | FAT - Generator w/ Enclosure (OG2 & OG3) | 10 | 0 | 2022-04-29 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01046 |  | OG9 | [6 empty] | Deliver - Generator w/ Enclosure (OG2 & OG3) | 2 | 0 | 2022-08-25 08:00 | 2022-08-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01010 | [8 empty] | Fabricate - Generator (OG2 & OG3) | 120 | 0 | 2021-06-01 | 2022-03-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01090 | [8 empty] | Fabricate - Lightning Protection System | 60 | 0 | 2022-03-25 | 2022-04-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01095 | [8 empty] | Deliver - Lightning Protection System | 5 | 0 | 2022-04-25 | 2022-04-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01190 |  | OG9 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01200 |  | OG9 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -84 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.1 | P-OG9-01210 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01000 | [8 empty] | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01005 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 2020-08-03 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 2020-12-09 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01030 |  | OG9 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-10-03 08:00 | 2022-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01035 |  | OG9 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-10-26 08:00 | 2022-11-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01040 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-03-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01045 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-03-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01110 |  | OG9 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-11-26 | 2022-01-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01115 |  | OG9 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-01-25 08:00 | 2022-02-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.2.7 | E-OG9-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01010 |  | OG2 | [6 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-03-08 08:00 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01015 |  | OG2 | [6 empty] | Deliver - Switchboards | 5 | 0 | 2022-07-11 | 2022-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01000 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-03-08 08:00 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01020 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-12-17 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01030 | [8 empty] | Fabricate - ACTTS | 120 | 0 | 2021-12-17 | 2022-06-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01070 |  | OG2 | [6 empty] | Deliver - ACTTS | 5 | 0 | 2022-07-11 | 2022-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01090 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2022-01-14 | 2022-05-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01095 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2022-05-31 | 2022-06-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01110 |  | OG2 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01120 |  | OG2 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | 35 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.1 | P-OG2-01130 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-01-03 | 2022-05-18 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01075 |  | OG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 5 | 2022-05-19 | 2023-03-03 17:00 | 33 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2022-01-03 08:00 | 2022-02-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-02-02 | 2022-04-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2021-09-24 | 2022-03-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2022-03-03 | 2022-03-18 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01000 |  | OG2 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01005 |  | OG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-05-26 | 2021-06-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-06-29 | 2021-08-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.8.7 | E-OG2-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01010 |  | OG3 | [6 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-03-08 08:00 | 2022-08-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01015 |  | OG3 | [6 empty] | Deliver - Switchboards | 5 | 0 | 2022-08-25 08:00 | 2022-09-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01000 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-03-08 08:00 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01020 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-12-17 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01030 | [8 empty] | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 2021-12-17 | 2022-06-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01035 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-06-09 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01060 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-12-14 | 2022-05-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01065 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2022-05-31 08:00 | 2022-06-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01110 |  | OG3 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01120 |  | OG3 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | 37 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.1 | P-OG3-01130 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-01-03 | 2022-05-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01075 |  | OG3 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-05-19 | 2022-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 2021-12-27 08:00 | 2022-01-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-01-19 08:00 | 2022-02-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2021-09-24 | 2022-01-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (Con-Ed) | 10 | 0 | 2022-01-19 | 2022-02-09 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01000 |  | OG3 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01005 |  | OG3 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-05-26 | 2021-07-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-07-02 | 2021-08-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.3.1.7 | E-OG3-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01010 |  | OGE | [6 empty] | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01015 |  | OGE | [6 empty] | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 10 | 2022-08-12 08:00 | 2023-03-10 17:00 | 46 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 2021-09-01 | 2021-09-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 2021-09-23 08:00 | 2021-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01000 | [8 empty] | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 2021-04-29 15:00 | 2022-05-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.3 | E-OGE-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01030 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-11-08 | 2022-03-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01035 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2022-03-21 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01020 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-11-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01050 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-11-05 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01060 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2022-02-25 | 2022-06-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01065 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-06-09 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01110 | [8 empty] | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 2021-11-12 | 2022-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01115 | [8 empty] | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 2022-03-18 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01000 | [8 empty] | Release for Fabrication - Generators (OG6 & OG1) | 0 | 0 | 2021-06-01 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01040 | [8 empty] | Fabricate - Generator Enclosure (OG6 & OG1) | 40 | 0 | 2022-02-11 | 2022-05-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01140 | [8 empty] | FAT - Generator w/ Enclosure (OG6 & OG1) | 10 | 0 | 2022-05-09 | 2022-05-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01145 |  | OG10 | [6 empty] | Deliver - Generator w/ Enclosure (OG6 & OG1) | 2 | 0 | 2022-08-25 08:00 | 2022-08-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01010 | [8 empty] | Fabricate - Generator (OG6 & OG1) | 120 | 0 | 2021-08-02 08:00 | 2022-02-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01090 | [8 empty] | Fabricate - Lightning Protection System | 60 | 0 | 2022-03-25 | 2022-05-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01095 | [8 empty] | Deliver - Lightning Protection System | 5 | 0 | 2022-05-11 | 2022-05-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01190 |  | OG10 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 2022-01-25 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01200 |  | OG10 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -44 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.1 | P-OG10-01210 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01000 | [8 empty] | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01005 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 2020-08-03 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 2020-12-09 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01030 |  | OG10 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-10-03 08:00 | 2022-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01035 |  | OG10 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-10-27 08:00 | 2022-11-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01040 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01045 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01110 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-09-27 | 2021-10-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01130 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-10-28 08:00 | 2021-11-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.2.7 | E-OG10-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01010 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-11-08 | 2022-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01015 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2022-03-17 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01000 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-11-08 08:00 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01020 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-11-05 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01030 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2022-02-25 08:00 | 2022-06-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01035 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-06-09 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01090 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-11-12 | 2022-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01100 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2022-03-18 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01110 |  | OG6 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01120 |  | OG6 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -48 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.1 | P-OG6-01130 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01070 |  | OG6 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2021-11-01 08:00 | 2022-07-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01075 |  | OG6 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-07-18 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2021-04-05 | 2021-05-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-05-20 | 2021-06-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2021-09-01 | 2021-09-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2021-09-23 | 2021-10-15 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01000 |  | OG6 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01040 |  | OG6 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-04-01 | 2021-04-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-04-26 | 2021-05-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.8.7 | E-OG6-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01010 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-11-08 08:00 | 2022-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01015 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2022-03-18 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01000 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-11-08 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01020 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2021-11-05 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01030 | [8 empty] | Fabricate - ACTTS | 80 | 0 | 2022-01-25 08:00 | 2022-06-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01035 | [8 empty] | Deliver - ACTTS | 5 | 0 | 2022-06-09 | 2022-06-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01060 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-11-12 | 2022-03-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01070 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2022-03-18 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01110 |  | OG1 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01120 |  | OG1 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-03-25 08:00 | 2023-03-08 17:00 | 11 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.1 | P-OG1-01130 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01070 | [8 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-04-04 | 2022-05-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01075 |  | OG1 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-05-04 | 2022-07-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01160 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 2021-04-05 | 2021-05-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01170 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2021-05-20 | 2021-06-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01020 |  | OG1 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2022-05-25 08:00 | 2022-08-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01025 |  | OG1 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2022-08-02 08:00 | 2022-08-15 17:00 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01000 |  | OG1 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01040 |  | OG1 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-04-05 | 2021-05-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-05-10 | 2021-06-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.4.1.7 | E-OG1-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01010 |  | SGS | [6 empty] | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01015 |  | SGS | [6 empty] | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 0 | 2022-08-12 08:00 | 2022-09-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 5 | 0 | 2022-04-15 | 2022-05-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 2022-05-02 | 2022-05-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01000 | [8 empty] | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 2021-09-06 | 2022-05-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.3 | E-SGS-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 2021-04-25 | 2021-04-25 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01070 |  | SG7 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 5 | 2022-01-25 | 2023-03-03 17:00 | -24 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01045 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01050 |  | SG7 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01020 | [8 empty] | Release for Fabrication - Generators (SG1, SG2 & SG3) | 0 | 0 | 2021-06-01 |  |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01035 |  | SG7 | [6 empty] | Fabricate - Generator Enclosure (SG1, SG2 & SG3) | 40 | 5 | 2022-06-15 | 2023-03-03 17:00 | -57 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01037 |  | SG7 | [6 empty] | FAT - Generator w/ Enclosure (SG1, SG2 & SG3) | 10 | 10 | 2023-03-06 08:00 | 2023-03-17 17:00 | -57 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01040 |  | SG7 | [6 empty] | Deliver - Generator w/ Enclosure (SG1, SG2 & SG3) | 2 | 2 | 2023-03-20 08:00 | 2023-03-21 17:00 | -57 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01030 | [8 empty] | Fabricate - Generator (SG1, SG2 & SG3) | 120 | 0 | 2021-10-04 | 2022-06-08 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01060 |  | SG7 | [6 empty] | Fabricate, Assemble & Wire - Switchboards | 200 | 44 | 2022-05-03 08:00 | 2023-04-27 17:00 | -106 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01065 |  | SG7 | [6 empty] | Deliver - Switchboards | 5 | 5 | 2023-04-28 08:00 | 2023-05-04 17:00 | -106 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01055 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2022-05-03 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01080 |  | SG7 | [6 empty] | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 2022-05-25 | 2022-10-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01085 |  | SG7 | [6 empty] | Deliver - ACTTS | 5 | 0 | 2022-10-10 08:00 | 2022-10-14 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01100 |  | SG7 | [6 empty] | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 40 | 2022-05-25 08:00 | 2023-04-21 17:00 | -87 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01105 |  | SG7 | [6 empty] | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 5 | 2023-04-24 08:00 | 2023-04-28 17:00 | -87 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01140 |  | SG7 | [6 empty] | Fabricate - Lightning Protection System | 60 | 0 | 2022-09-26 08:00 | 2022-10-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01145 |  | SG7 | [6 empty] | Deliver - Lightning Protection System | 5 | 0 | 2022-10-24 08:00 | 2022-10-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.1 | P-SG7-01075 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2022-05-25 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01000 | [8 empty] | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01005 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 2020-08-03 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 2020-12-09 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01030 |  | SG7 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-08-25 08:00 | 2022-09-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01035 |  | SG7 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-09-16 08:00 | 2022-10-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01040 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01045 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01110 |  | SG7 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2022-07-05 08:00 | 2022-07-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01115 |  | SG7 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-07-21 08:00 | 2022-09-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01140 |  | SG7 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) | 5 | 0 | 2022-07-23 | 2022-07-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.2.7 | E-SG7-01150 |  | SG7 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (Con-Ed) | 5 | 0 | 2022-07-26 08:00 | 2022-09-12 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.8.1 | P-SG1-01090 |  | SG1 | [6 empty] | Fabricate - Panelboards | 30 | 8 | 2022-05-20 | 2023-03-08 12:00 | -37 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.8.1 | P-SG1-01100 |  | SG1 | [6 empty] | Deliver - Panelboards | 5 | 5 | 2023-03-08 13:00 | 2023-03-15 12:00 | -37 | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.8.1 | P-SG1-01050 |  | SG1 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -12 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01070 |  | SG1 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-07-01 08:00 | 2022-07-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01075 |  | SG1 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-07-12 08:00 | 2022-09-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01160 |  | SG1 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2022-04-01 08:00 | 2022-04-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01170 |  | SG1 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-04-04 08:00 | 2022-04-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2022-04-04 | 2022-04-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) (NYCHA Approval Only) | 10 | 0 | 2022-04-28 | 2022-05-11 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01000 |  | SG1 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01005 |  | SG1 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-05-26 | 2021-08-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-08-17 08:00 | 2021-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.8.7 | E-SG1-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.1.1 | P-SG2-01070 |  | SG2 | [6 empty] | Fabricate - Panelboards | 30 | 8 | 2022-05-20 | 2023-03-08 12:00 | -40 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.1.1 | P-SG2-01100 |  | SG2 | [6 empty] | Deliver - Panelboards | 5 | 5 | 2023-03-08 13:00 | 2023-03-15 12:00 | -40 | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.1.1 | P-SG2-01040 |  | SG2 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -6 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01070 |  | SG2 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2021-07-12 08:00 | 2022-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01075 |  | SG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-08-08 08:00 | 2022-09-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01160 |  | SG2 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 2022-04-01 08:00 | 2022-04-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01170 |  | SG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-04-04 08:00 | 2022-04-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2022-04-01 | 2022-04-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2022-04-28 | 2022-05-11 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01000 |  | SG2 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01005 |  | SG2 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-05-26 | 2021-08-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-08-17 08:00 | 2021-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.1.7 | E-SG2-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01050 |  | SG3 | [6 empty] | Fabricate, Assemble & Wire - Switchboards | 200 | 44 | 2022-05-04 | 2023-04-27 17:00 | -112 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01055 |  | SG3 | [6 empty] | Deliver - Switchboards | 5 | 5 | 2023-04-28 08:00 | 2023-05-04 17:00 | -112 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01045 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2022-05-03 |  |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01060 |  | SG3 | [6 empty] | Fabricate - ACTTS | 120 | 20 | 2022-05-25 | 2023-06-05 17:00 | -128 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01065 |  | SG3 | [6 empty] | Deliver - ACTTS | 5 | 5 | 2023-06-06 08:00 | 2023-06-12 17:00 | -128 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01059 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2022-05-25 |  |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01070 |  | SG3 | [6 empty] | Fabricate - Panelboards | 30 | 40 | 2022-08-01 08:00 | 2023-04-21 17:00 | -89 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01075 |  | SG3 | [6 empty] | Deliver - Panelboards | 5 | 5 | 2023-04-24 08:00 | 2023-04-28 17:00 | -89 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01020 |  | SG3 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01040 |  | SG3 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | 24 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.1 | P-SG3-01030 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01070 |  | SG3 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-07-25 08:00 | 2022-08-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01075 |  | SG3 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 2022-08-18 08:00 | 2022-10-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01090 |  | SG3 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 2022-04-01 | 2022-05-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01095 |  | SG3 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-05-19 08:00 | 2022-09-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 2022-04-01 | 2022-04-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 2022-04-28 | 2022-05-11 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01000 |  | SG3 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01005 |  | SG3 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Existing Conditions | 60 | 0 | 2021-05-26 | 2021-09-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2021-09-20 08:00 | 2021-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.5.4.7 | E-SG3-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01010 |  | S8 | [6 empty] | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01015 |  | S8 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 10 | 2022-08-12 08:00 | 2023-03-10 17:00 | 37 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 2022-05-13 08:00 | 2022-06-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01025 |  | S8 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 2022-06-02 08:00 | 2022-10-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01000 | [8 empty] | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 2022-03-07 | 2022-05-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 2021-04-25 | 2021-04-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.3 | E-S8-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 2021-04-25 | 2021-04-25 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01070 |  | S81 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-01-25 | 2023-03-08 17:00 | -33 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01040 | [8 empty] | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 2021-10-28 | 2021-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01050 |  | S81 | [6 empty] | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 2022-10-11 | 2022-10-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01020 | [8 empty] | Release for Fabrication - Generators (S8E) | 0 | 0 | 2021-06-01 |  |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01090 |  | S81 | [6 empty] | Fabricate - Generator Enclosures (S8E) | 40 | 65 | 2022-09-12 08:00 | 2023-05-26 17:00 | -44 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01095 |  | S81 | [6 empty] | FAT - Generators w/ Enclosures (S8E) | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -44 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01100 |  | S81 | [6 empty] | Deliver - Generators w/ Enclosures (S8E) | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -44 | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01030 |  | S81 | [6 empty] | Fabricate - Generator (S8E) | 120 | 65 | 2022-01-25 | 2023-05-26 17:00 | -44 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01060 | [8 empty] | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 2021-08-02 08:00 | 2021-11-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01065 | [8 empty] | Deliver - Switchboards | 5 | 0 | 2021-11-29 | 2021-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01055 | [8 empty] | Release for Fabrication - Switchboards | 0 | 0 | 2021-06-29 08:00 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01080 |  | S81 | [6 empty] | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 2022-05-17 | 2022-10-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01085 |  | S81 | [6 empty] | Deliver - ACTTS | 5 | 0 | 2022-10-12 08:00 | 2022-10-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01120 | [8 empty] | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 2021-06-29 08:00 | 2022-04-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01130 | [8 empty] | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 2022-04-15 08:00 | 2022-04-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01015 |  | S81 | [6 empty] | Fabricate - Lightning Protection System | 60 | 0 | 2022-08-12 08:00 | 2022-10-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01017 |  | S81 | [6 empty] | Deliver - Lightning Protection System | 5 | 0 | 2022-10-18 08:00 | 2022-10-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.1 | P-S8A-01075 | [8 empty] | Release for Fabrication - ACTTS | 0 | 0 | 2022-05-16 |  |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01000 | [8 empty] | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 2020-07-13 | 2020-08-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01005 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 2020-08-05 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 2020-08-03 | 2020-12-08 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 2020-12-09 | 2021-01-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01030 |  | S81 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 2022-11-01 08:00 | 2022-12-30 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01035 |  | S81 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 5 | 2022-12-30 08:00 | 2023-03-03 17:00 | -54 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01040 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01045 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01110 |  | S81 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2022-06-10 08:00 | 2022-06-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01115 |  | S81 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-06-20 08:00 | 2022-07-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01020 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.2.7 | E-S8A-01025 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.1 | P-S8E-01090 | [8 empty] | Fabricate - Panelboards | 30 | 0 | 2021-06-29 08:00 | 2021-11-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.1 | P-S8E-01100 | [8 empty] | Deliver - Panelboards | 5 | 0 | 2021-11-29 | 2021-12-01 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.8.1 | P-S8E-01050 |  | S82 | [6 empty] | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 2022-03-25 08:00 | 2023-03-08 17:00 | 9 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01070 |  | S82 | [6 empty] | Prep/Submit Engineering Dwgs. - Lighting | 60 | 60 | 2023-02-27 08:00 | 2023-05-19 17:00 | -74 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01075 |  | S82 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 2023-05-22 08:00 | 2023-06-05 17:00 | -74 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01080 | [8 empty] | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01085 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01160 |  | S82 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 2022-06-01 08:00 | 2022-06-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01170 |  | S82 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 2022-06-20 08:00 | 2022-07-13 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01020 |  | S82 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 15 | 2022-05-25 08:00 | 2023-03-17 17:00 | -82 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01025 |  | S82 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 10 | 2023-03-20 08:00 | 2023-03-31 17:00 | -82 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01000 |  | S82 | [6 empty] | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 2023-02-27 08:00 | 2023-04-21 17:00 | -20 | 0
Not Started |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01005 |  | S82 | [6 empty] | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -20 | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01010 | [8 empty] | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 2021-12-01 | 2022-03-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01015 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 2022-03-14 | 2022-04-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01050 | [8 empty] | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 2020-12-01 | 2021-01-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01055 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 2021-01-08 | 2021-02-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01030 | [8 empty] | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01035 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01060 | [8 empty] | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 2020-09-08 | 2020-10-27 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1.1.6.8.7 | E-S8E-01065 | [8 empty] | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 2020-10-27 | 2020-11-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1 | PROC-E-01010 | [8 empty] | Prep/Submit Detailed Coordinated Phasing Plan (Pending RFI #535) | 30 | 0 | 2020-06-03 | 2022-07-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1 | PROC-E-01015 | [8 empty] | Rev/Appr. Detailed Coordinated Phasing Plan | 10 | 0 | 2022-07-05 | 2022-07-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1 | PROC-E-01020 | [8 empty] | Prep/Submit Electrical Vendor/Manufacturer List | 20 | 0 | 2020-07-13 | 2020-10-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.1 | PROC-E-01025 | [8 empty] | Rev/Appr. Electrical Vendor/Manufacturer List | 10 | 0 | 2020-10-06 | 2020-11-06 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01000 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - SG4 | 5 | 4 | 2022-12-01 08:00 | 2023-05-03 15:00 | 17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01010 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - SG5 | 5 | 5 | 2023-05-17 08:00 | 2023-05-23 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01020 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - OG4 | 5 | 5 | 2023-07-26 08:00 | 2023-08-01 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01030 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - OG5 | 5 | 5 | 2023-08-01 08:00 | 2023-08-07 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01040 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - OG6 | 5 | 5 | 2023-08-14 08:00 | 2023-08-18 17:00 | -58 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01050 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - OG1 | 5 | 5 | 2023-08-18 08:00 | 2023-08-24 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01060 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - SG1 | 5 | 5 | 2023-08-29 10:00 | 2023-09-06 10:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01070 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - SG2 | 5 | 5 | 2023-08-18 13:00 | 2023-08-25 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01080 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - SG3 | 5 | 5 | 2023-09-14 08:00 | 2023-09-20 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01090 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - S8E | 5 | 5 | 2023-08-01 13:00 | 2023-08-08 12:00 | -50 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01100 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - OG3 | 5 | 5 | 2023-05-08 08:00 | 2023-05-12 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.6 | R-01110 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove & Dispose (E) Switchgear Equipment - OG2 | 5 | 5 | 2023-05-16 08:00 | 2023-05-22 17:00 | 4 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-02005 | FIVE STAR | SGN |  | Utilities | SITE |  |  |  | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 0 | 2023-02-13 | 2023-02-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02105 | FIVE STAR | SGN | [6 empty] | Pull CON-ED Feeder Cable - 32nd St. to SG-5 Cellar | 10 | 0 | 2022-11-01 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02120 | FIVE STAR | SGN | [6 empty] | Pull CON-ED Feeder Cable - 33rd St. to SG-4 Cellar | 10 | 0 | 2022-07-18 | 2022-07-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02125 | FIVE STAR | SGN | [6 empty] | Pull Feeder Cable - SG-4 Switchgear to SG-6 Foundation | 10 | 0 | 2022-07-11 | 2022-07-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02110 | FIVE STAR | SGN | [6 empty] | Pull Generator Feeder Cable from SG-6 to SG-5 Switchgear | 5 | 0 | 2022-12-15 08:00 | 2023-01-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02115 | FIVE STAR | SGN | [6 empty] | Pull Generator Feeder Cable from SG-6 to SG-4 Switchgear | 5 | 0 | 2022-07-11 | 2022-07-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.3 | SGN-02205 | FIVE STAR | SGN |  | Utilities | SITE |  |  |  | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 2023-05-17 08:00 | 2023-05-23 17:00 | -20 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.3 | SGN-02210 | FIVE STAR | SGN | [6 empty] | Furnish & Install Site Lighting Conduit | 10 | 0 | 2022-08-23 13:00 | 2022-12-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.3 | SGN-02215 | FIVE STAR | SGN |  | Utilities | SITE |  |  |  | Pull Site Lighting Wire | 5 | 5 | 2023-05-30 08:00 | 2023-06-05 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.3 | SGN-02220 | FIVE STAR | SGN |  | Utilities | SITE |  |  |  | Install Site Lighting Fixtures & Terminate | 10 | 10 | 2023-06-06 08:00 | 2023-06-19 17:00 | -20 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02205 |  | SG4 | [6 empty] | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 0 | 2022-02-22 08:00 | 2022-12-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02225 |  | SG4 | [6 empty] | Install Bypass Connections - Cellar | 6 | 0 | 2021-10-15 | 2022-12-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02210 | [8 empty] | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 0 | 2021-10-15 | 2021-12-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02215 | [8 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 2021-08-30 | 2021-10-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02230 | FIVE STAR | SG4 | [6 empty] | Install Branch Conduit - Cellar | 20 | 0 | 2021-12-06 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02220 | FIVE STAR | SG4 | [6 empty] | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 0 | 2022-04-11 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02255 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 12 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02240 | FIVE STAR | SG4 | [6 empty] | Pull Lighting Wiring - Cellar | 6 | 0 | 2022-06-13 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02250 | FIVE STAR | SG4 | [6 empty] | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 6 | 0 | 2022-10-06 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02245 | FIVE STAR | SG4 | [6 empty] | Pull Branch Wiring - Cellar | 8 | 0 | 2022-06-13 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02260 | FIVE STAR | SG4 | [6 empty] | Install Heat Trace for Plumbing Lines - Cellar | 5 | 0 | 2022-08-01 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02265 | [8 empty] | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 20 | 0 | 2021-12-02 | 2022-02-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02235 | FIVE STAR | SG4 | [6 empty] | Install Panelboards (Misc.) - Cellar | 2 | 0 | 2022-02-07 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02270 | FIVE STAR | SG4 | [6 empty] | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 0 | 2022-07-01 08:00 | 2022-09-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02305 | [8 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 15 | 0 | 2022-01-03 | 2022-03-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02310 | [8 empty] | Install Pull/Splice Boxes - 1st Floor | 3 | 0 | 2022-02-01 | 2022-02-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02315 | FIVE STAR | SG4 | [6 empty] | Install Branch Conduit - 1st Floor | 15 | 0 | 2022-02-07 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02320 | FIVE STAR | SG4 | [6 empty] | Pull Branch Wiring - 1st Floor | 6 | 0 | 2022-06-06 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02325 | FIVE STAR | SG4 | [6 empty] | Install Fire Alarm Control Panel & Equipment - 1st Floor | 2 | 0 | 2022-06-08 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02330 | FIVE STAR | SG4 | [6 empty] | Pull Fire Alarm Wiring - 1st Floor | 2 | 0 | 2022-09-26 13:00 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02335 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 6 | 0 | 2022-06-13 | 2023-02-27 10:24 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02340 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -75 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02345 | MLJ | SG4 | FIRESTOPPING | [5 empty] | Install Firestopping - 1st Floor | 5 | 0 | 2022-03-07 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-02350 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 0 | 2022-06-20 | 2023-02-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02405 | [8 empty] | Install Switchboards - 2nd Floor | 12 | 0 | 2022-02-14 | 2022-04-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02430 | [8 empty] | Install ACTTS - 2nd Floor | 6 | 0 | 2022-02-15 | 2022-04-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02435 | [8 empty] | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 0 | 2022-01-03 | 2022-03-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02410 | FIVE STAR | SG4 | [6 empty] | Install Panelboards - 2nd Floor | 5 | 0 | 2022-02-14 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02420 | FIVE STAR | SG4 | [6 empty] | Install Branch Conduit - 2nd Floor | 20 | 0 | 2022-06-13 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02440 | FIVE STAR | SG4 | [6 empty] | Pull Branch Wiring - 2nd Floor | 6 | 0 | 2022-06-13 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02470 | FIVE STAR | SG4 | [6 empty] | Install Light Fixtures & Controls - 2nd Floor | 5 | 0 | 2022-09-23 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02415 | FIVE STAR | SG4 | [6 empty] | Install Fire Alarm Equipment - 2nd Floor | 6 | 0 | 2022-06-10 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02425 |  | SG4 | [6 empty] | Install Receptacles - 2nd Floor | 5 | 0 | 2022-06-13 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02445 |  | SG4 | FIRESTOPPING | [5 empty] | Install Fire Stopping - 2nd Floor | 5 | 0 | 2022-03-23 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02450 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 0 | 2022-08-01 15:00 | 2023-02-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02455 | FIVE STAR | SG4 | [6 empty] | Tag & Terminate Switchgear Equipment | 5 | 0 | 2022-07-15 | 2022-09-26 15:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02475 |  | SG4 | [6 empty] | Ground Equipment | 5 | 0 | 2022-08-22 15:00 | 2022-12-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02480 | FIVE STAR | SG4 | [6 empty] | Tag & Terminate Fire Alarm System | 5 | 0 | 2022-09-23 | 2022-12-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02465 | FIVE STAR | SG4 | [6 empty] | Pull CON-ED Feeder Cable - Cellar to Switchgear Equipment - 2nd Floor | 20 | 0 | 2022-07-01 | 2022-07-22 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-02460 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 0 | 2022-07-01 | 2023-03-17 17:00 | -88 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02505 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - SG4 | 5 | 5 | 2023-07-12 08:00 | 2023-07-18 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02515 | FIVE STAR | SG4 | [6 empty] | Energize Switchgear - SG4 | 5 | 0 | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02535 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - SG4 | 4 | 4 | 2023-04-24 08:00 | 2023-04-27 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02510 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - SG4 | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -88 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02520 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test - SG4 | 2 | 1 | 2022-07-01 08:00 | 2023-04-21 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02525 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing - SG4 | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02530 |  | SG4 | [6 empty] | Perform Tie-in's to Exisiting | 3 | 0 | 2022-12-15 08:00 | 2023-01-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02205 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | -92 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02210 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 3 | 2021-12-01 | 2023-03-02 17:00 | -54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02220 | FIVE STAR | SG5 | [6 empty] | Relocate (E) & Install Temporary Lighting - Cellar | 4 | 0 | 2021-11-29 | 2022-10-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02225 | [8 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 2021-08-23 | 2021-09-22 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02215 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 20 | 5 | 2021-12-15 | 2023-03-17 10:00 | -92 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02230 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 2 | 2022-09-30 08:00 | 2023-02-28 17:00 | -87 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02260 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02255 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-03-01 08:00 | 2023-03-07 17:00 | -87 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02265 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 1 | 2022-12-15 08:00 | 2023-03-09 12:00 | -88 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02235 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 7 | 7 | 2023-03-17 10:00 | 2023-03-28 10:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02240 | FIVE STAR | SG5 | [6 empty] | Install Heat Trace for Plumbing Lines - Cellar | 2 | 0 | 2022-12-12 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02250 | FIVE STAR | SG5 | CORE DRILL | [5 empty] | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 15 | 0 | 2022-01-03 08:00 | 2022-01-04 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02270 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) - Cellar | 5 | 0 | 2022-11-22 08:00 | 2023-03-03 10:00 | -92 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02245 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 3 | 2022-06-21 | 2023-03-01 12:00 | -71 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02325 | FIVE STAR | SG5 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 0 | 2021-12-01 08:00 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02335 |  | SG5 | [6 empty] | Install Pull/Splice Boxes - 1st Floor | 4 | 0 | 2022-09-26 08:00 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02305 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 12 | 1 | 2022-10-03 08:00 | 2023-02-27 13:48 | -83 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02310 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 6 | 3 | 2023-01-15 08:00 | 2023-03-02 13:48 | -83 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02315 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 2023-03-02 13:48 | 2023-03-06 13:48 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02320 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-03-06 13:48 | 2023-03-08 13:48 | 24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02330 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 2023-03-09 13:00 | 2023-03-16 12:00 | -88 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02340 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-03-02 13:48 | 2023-03-06 13:48 | -76 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02345 | MLJ | SG5 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 2 | 2022-12-15 08:00 | 2023-03-08 13:48 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-02350 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 3 | 2023-01-02 08:00 | 2023-03-22 12:00 | -86 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02415 | FIVE STAR | SG5 | [6 empty] | Install Switchboards - 2nd Floor | 10 | 0 | 2022-10-15 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02420 |  | SG5 | [6 empty] | Install ACTTS - 2nd Floor | 4 | 0 | 2022-10-10 08:00 | 2022-12-15 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02425 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 1 | 2022-10-10 08:00 | 2023-02-27 17:00 | -71 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02430 | FIVE STAR | SG5 | [6 empty] | Install Panelboards - 2nd Floor | 4 | 0 | 2022-10-10 08:00 | 2023-01-02 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02440 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 15 | 2 | 2022-11-02 08:00 | 2023-02-28 12:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02445 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 3 | 2023-01-02 13:00 | 2023-03-02 17:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02450 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Light Fixtures & Controls - 2nd Floor | 4 | 3 | 2023-02-13 13:00 | 2023-03-21 14:36 | -88 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02455 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection Equipment - 2nd Floor | 5 | 4 | 2023-02-10 13:00 | 2023-03-14 13:48 | 24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02460 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 4 | 3 | 2023-02-10 13:00 | 2023-03-08 09:36 | -75 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02465 | MLJ | SG5 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 4 | 3 | 2023-02-17 13:00 | 2023-03-24 16:12 | -88 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02405 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 1 | 2022-12-15 08:00 | 2023-03-09 13:48 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02410 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards - 2nd Floor | 2 | 1 | 2023-02-08 13:48 | 2023-03-10 08:48 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02470 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 3 | 2023-02-01 13:48 | 2023-03-09 08:48 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02480 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Fire Alarm System - 2nd Floor | 2 | 2 | 2023-03-14 13:48 | 2023-03-16 13:48 | 36 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02475 | FIVE STAR | SG5 | [6 empty] | Pull CON-ED Feeder Cable - Cellar to SG-5 Switchgear - 2nd Floor | 10 | 0 | 2022-12-01 08:00 | 2022-12-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-02435 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 3 | 2023-02-10 13:00 | 2023-03-08 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02535 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - SG-5 | 4 | 4 | 2023-05-11 08:00 | 2023-05-16 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02505 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - SG5 | 5 | 5 | 2023-07-12 08:00 | 2023-07-18 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02515 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear (By CON-ED) - SG5 | 5 | 5 | 2023-05-01 08:00 | 2023-05-05 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02510 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - SG5 | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02525 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-Ins to Existing | 3 | 3 | 2023-05-08 08:00 | 2023-05-10 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02530 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test | 2 | 1 | 2022-12-01 08:00 | 2023-04-28 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02520 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02125 | FIVE STAR | SG6 | [6 empty] | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 5 | 0 | 2022-06-01 | 2022-09-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02130 | FIVE STAR | SG6 | [6 empty] | Install Light/Emergency Fixtures - 1st Floor | 5 | 0 | 2022-06-03 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02115 | FIVE STAR | SG6 | [6 empty] | Pull Fire Alarm Wiring - 1st Floor | 5 | 0 | 2022-03-30 15:00 | 2022-09-26 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02135 | FIVE STAR | SG6 | [6 empty] | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 5 | 0 | 2022-09-23 | 2023-01-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02150 |  | SG6 | [6 empty] | Install Receptacles - 1st Floor | 2 | 0 | 2022-06-06 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02145 |  | SG6 | [6 empty] | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 0 | 2022-06-06 | 2022-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02105 | [8 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 2021-11-30 | 2022-02-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02110 | [8 empty] | Install Branch Conduits - 1st Floor | 15 | 0 | 2021-07-01 | 2022-03-30 15:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02120 | FIVE STAR | SG6 | [6 empty] | Pull Branch Wiring - 1st Floor | 5 | 0 | 2022-04-11 08:00 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02140 | FIVE STAR | SG6 | [6 empty] | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 0 | 2022-09-21 | 2022-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02155 | [8 empty] | Install In-slab Conduits - drop from roof of 1st floor=2nd floor slab | 5 | 0 | 2021-08-02 08:00 | 2021-08-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02160 | FIVE STAR | SG6 | [6 empty] | Install Exterior Lighting & Controls - 1st Floor | 2 | 0 | 2022-06-06 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02210 | FIVE STAR | SG6 | [6 empty] | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 0 | 2021-12-14 | 2022-04-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02220 | FIVE STAR | SG6 | [6 empty] | Install Controls & Pull Wire for Mechanical & Plumbing Equipment - 2nd Floor | 10 | 0 | 2022-06-13 | 2023-01-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02215 | FIVE STAR | SG6 | [6 empty] | Install Branch Conduits - 2nd Floor | 15 | 0 | 2022-01-10 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02225 | FIVE STAR | SG6 | [6 empty] | Pull Branch Wiring - 2nd Floor | 5 | 0 | 2022-04-11 10:48 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02230 | FIVE STAR | SG6 | [6 empty] | Pull Fire Alarm Wiring - 2nd Floor | 5 | 0 | 2022-08-15 13:00 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02235 | FIVE STAR | SG6 | [6 empty] | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 5 | 0 | 2022-06-13 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02240 | FIVE STAR | SG6 | [6 empty] | Install Light/Emergency Fixtures - 2nd Floor | 5 | 0 | 2022-06-13 | 2023-01-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02205 | [8 empty] | Install In-slab Conduits - drop from roof of 2nd floor=roof slab | 10 | 0 | 2021-11-26 08:00 | 2021-12-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-02245 |  | SG6 | [6 empty] | Install Receptacles - 2nd Floor | 2 | 0 | 2022-06-13 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02325 | FIVE STAR | SG6 | [6 empty] | Install Feeder Conduit & Racks - Roof | 15 | 0 | 2022-01-10 | 2022-07-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02375 | [8 empty] | Rig Generator SG-5 - Roof | 1 | 0 | 2022-04-22 08:00 | 2022-04-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02385 | FIVE STAR | SG6 | [6 empty] | Install Generator Circuit Breakers & Wire Generator SG-4 - Roof | 10 | 0 | 2022-05-25 08:00 | 2022-12-15 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02320 | FIVE STAR | SG6 | [6 empty] | Install Branch Conduit - Roof | 5 | 0 | 2022-02-14 | 2023-01-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02330 | FIVE STAR | SG6 | [6 empty] | Pull Branch Wiring - Roof | 5 | 0 | 2022-06-15 | 2023-01-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02380 | [8 empty] | Rig Generator SG-4 - Roof | 1 | 0 | 2022-04-22 08:00 | 2022-04-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02390 | FIVE STAR | SG6 | [6 empty] | Install Generator Circuit Breakers & Wire Generator SG-5 - Roof | 10 | 0 | 2022-05-25 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02350 | FIVE STAR | SG6 | [6 empty] | Terminate all Mech. & Plumbing Equipment at Panel (PP-SG6) - Roof | 5 | 0 | 2022-07-18 13:00 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02340 | FIVE STAR | SG6 | [6 empty] | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 0 | 2022-06-15 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02305 | [8 empty] | Install Switchboards - Roof | 4 | 0 | 2022-04-22 08:00 | 2022-05-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02310 | [8 empty] | Install ACTTS - Roof | 5 | 0 | 2022-05-26 08:00 | 2022-06-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02315 | FIVE STAR | SG6 | [6 empty] | Install Panelboards - Roof | 10 | 0 | 2022-06-03 08:00 | 2022-07-22 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02335 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Roof | 5 | 0 | 2022-06-15 | 2023-02-27 10:00 | 24 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02360 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - Roof | 3 | 1 | 2022-06-20 | 2023-03-01 17:00 | -85 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02355 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Roof | 5 | 1 | 2022-06-20 | 2023-03-01 17:00 | -85 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02395 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Lightning protection Air terminals - Roof | 5 | 1 | 2022-06-01 | 2023-03-01 17:00 | 15 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02400 |  | SG6 | [6 empty] | Install Grounding & Ground Equipment | 5 | 0 | 2022-04-15 | 2023-01-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02365 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 0 | 2022-06-17 | 2023-02-27 08:48 | 10 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02345 | FIVE STAR | SG6 | [6 empty] | Pull Fire Alarm Wiring - Roof | 5 | 0 | 2022-07-18 13:00 | 2023-01-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02370 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Terminate Light Fixtures - Roof | 5 | 5 | 2023-03-02 08:00 | 2023-03-08 17:00 | -85 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02425 | MLJ | SG6 | FIRESTOPPING | Interior | NEW BUILDINGS |  |  |  | Install Firestopping | 4 | 0 | 2022-03-07 | 2023-02-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02405 | FIVE STAR | SG6 | [6 empty] | Tag & Terminate Switchgear Equipment - Roof | 5 | 0 | 2022-08-08 15:00 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02415 | FIVE STAR | SG6 | [6 empty] | Tag & Terminate Panelboards - Roof | 2 | 0 | 2022-08-08 15:00 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02420 | FIVE STAR | SG6 | [6 empty] | Tag & Terminate Fire Alarm Equipment | 2 | 0 | 2022-08-08 15:00 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-02410 | FIVE STAR | SG6 | [6 empty] | Pull Feeder Cable from Foundation to Roof - Roof | 10 | 0 | 2022-08-08 15:00 | 2022-09-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-02010 | [8 empty] | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 0 | 2022-06-09 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-02025 | [8 empty] | Install Temporary Lighting & Temporary Power for SG-6 | 5 | 0 | 2021-06-01 | 2021-09-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-02005 | [8 empty] | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 8 | 0 | 2021-07-01 | 2021-11-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-02015 | FIVE STAR | SG6 | [6 empty] | Pull Wire to Light Fixtures & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 0 | 2022-04-11 08:00 | 2022-09-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-02020 | [8 empty] | Install Pull Box - Foundation | 2 | 0 | 2021-10-24 | 2021-10-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02505 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - SG6 | 5 | 5 | 2023-07-12 08:00 | 2023-07-18 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02510 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator SG4 - SG6 | 2 | 2 | 2023-04-17 08:00 | 2023-04-18 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02520 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Perform Electrical Inspections for SG6 | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -87 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02525 | FIVE STAR | SG6 | [6 empty] | Energize Switchgear Equipment - SG6 | 3 | 0 | 2022-12-15 08:00 | 2022-12-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02530 |  | SG6 | [6 empty] | Perform 3rd Party Testing - SG6 | 2 | 0 | 2022-08-23 08:00 | 2022-10-07 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02535 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Testing - SG6 | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02515 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator SG5 - SG6 | 2 | 2 | 2023-04-19 08:00 | 2023-04-20 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02540 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Generator Acceptance Testing - SG6 | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -107 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-02005 | FIVE STAR | OGW |  | Utilities | SITE |  |  |  | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 0 | 2021-11-26 | 2023-02-20 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-02010 | [8 empty] | Install Manholes & Grounding | 8 | 0 | 2021-11-24 | 2021-11-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02105 | FIVE STAR | OGW | [6 empty] | Pull CON-ED Feeder Cable - 35th St. to OG3 Cellar | 10 | 0 | 2022-12-01 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02110 | FIVE STAR | OGW | [6 empty] | Pull CON-ED Feeder Cable - 33rd St. to OG2 Cellar | 9 | 0 | 2022-12-01 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02115 | FIVE STAR | OGW | [6 empty] | Pull Feeder Cable - OG2 Switchgear to OG9 Foundation | 10 | 0 | 2022-12-26 08:00 | 2023-01-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02125 | FIVE STAR | OGW | [6 empty] | Pull Generator Feeder Cable from OG9 to OG3 | 5 | 0 | 2022-12-26 08:00 | 2023-01-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02120 | FIVE STAR | OGW | [6 empty] | Pull Generator Feeder Cable from OG9 to OG2 | 5 | 0 | 2022-12-26 08:00 | 2023-01-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.2 | OGW-02205 | FIVE STAR | OGW |  | Utilities | SITE |  |  |  | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 2023-05-16 08:00 | 2023-05-22 17:00 | -13 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.2 | OGW-02210 | FIVE STAR | OGW |  | Utilities | SITE |  |  |  | Furnish & Install Site Lighting Conduit | 5 | 1 | 2022-09-21 | 2023-05-26 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.2 | OGW-02215 | FIVE STAR | OGW |  | Utilities | SITE |  |  |  | Pull Site Lighting Wire | 3 | 3 | 2023-05-30 08:00 | 2023-06-01 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.2 | OGW-02220 | FIVE STAR | OGW |  | Utilities | SITE |  |  |  | Install Site Lighting Fixtures & Terminate | 5 | 5 | 2023-06-02 08:00 | 2023-06-08 17:00 | -13 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-02015 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 1 | 2022-05-25 08:00 | 2023-02-27 17:00 | -78 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-02005 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Temporary Lighting & Temporary Power for OG-9 | 5 | 1 | 2021-10-15 | 2023-02-27 15:00 | -72 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-02010 | [8 empty] | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 2021-10-06 | 2022-02-16 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-02025 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 1 | 2022-05-25 | 2023-02-27 17:00 | -78 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-02020 | [8 empty] | Install Pull Box - Foundation | 2 | 0 | 2022-01-27 | 2022-01-31 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02135 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 3 | 0 | 2023-02-02 08:00 | 2023-02-28 13:48 | -78 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02140 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 1st Floor | 3 | 0 | 2022-12-15 08:00 | 2023-02-28 11:36 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02120 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 3 | 0 | 2023-02-01 08:00 | 2023-02-27 14:12 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02145 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 0 | 2023-01-02 | 2023-02-28 13:48 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02155 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 1st Floor | 2 | 1 | 2023-02-01 | 2023-03-10 09:36 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02150 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 0 | 2023-02-01 | 2023-02-28 15:24 | -78 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02110 | FIVE STAR | OG9 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 2022-02-21 | 2022-07-01 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02115 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduits - 1st Floor | 10 | 1 | 2022-02-21 | 2023-02-27 12:00 | -79 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02125 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 3 | 0 | 2023-01-15 08:00 | 2023-02-28 10:24 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02130 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 2023-02-28 10:24 | 2023-03-03 10:24 | -67 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02105 | [8 empty] | Install In-slab Conduits - 1st floor slab | 3 | 0 | 2021-12-17 08:00 | 2021-12-21 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02160 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Exterior Lighting & Controls - 1st Floor | 2 | 0 | 2022-12-15 08:00 | 2023-03-09 09:36 | -84 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02215 | FIVE STAR | OG9 | [6 empty] | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 0 | 2022-02-01 08:00 | 2022-07-01 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02240 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -76 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02220 | [8 empty] | Install Branch Conduits - 2nd Floor | 10 | 0 | 2021-12-20 | 2022-02-16 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02225 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 3 | 1 | 2022-12-15 08:00 | 2023-02-27 15:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02230 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 2nd Floor | 3 | 0 | 2023-02-01 08:00 | 2023-02-27 16:36 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02210 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 3 | 0 | 2023-02-01 | 2023-02-28 16:12 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02245 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 2nd Floor | 3 | 0 | 2023-01-15 | 2023-02-27 16:12 | -72 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02205 | [8 empty] | Install In-slab Conduits - 2nd floor slab - 2nd Floor | 10 | 0 | 2021-12-21 | 2022-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02235 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 2 | 1 | 2023-02-01 08:00 | 2023-03-13 09:36 | -84 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02270 | FIVE STAR | OG9 | [6 empty] | Install Switchboards - 2nd Floor | 3 | 0 | 2022-09-07 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02275 |  | OG9 | [6 empty] | Install ACTTS - 2nd Floor | 3 | 0 | 2022-09-07 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02280 | FIVE STAR | OG9 | [6 empty] | Install Panelboards - 2nd Floor | 6 | 0 | 2022-09-07 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02250 | FIVE STAR | OG9 | [6 empty] | Install Feeder Conduits & Racks - 2nd Floor | 15 | 0 | 2022-02-17 | 2022-07-01 10:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02255 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Feeder Cable from Foundation Level - 2nd Floor | 5 | 0 | 2023-01-15 08:00 | 2023-02-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02260 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Switchgear - 2nd Floor | 5 | 1 | 2023-01-15 08:00 | 2023-03-16 12:00 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-02265 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Panelboards - 2nd Floor | 5 | 3 | 2023-02-15 08:00 | 2023-03-20 12:00 | -79 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02325 | FIVE STAR | OG9 | [6 empty] | Install Feeder Conduit & Racks - Roof | 5 | 0 | 2022-06-20 | 2022-07-01 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02310 | WELKIN | OG9 | GENERATOR | [5 empty] | Rig Generator OG2 - Roof | 1 | 0 | 2022-08-24 08:00 | 2022-08-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02335 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generator OG3- Roof | 10 | 3 | 2023-02-01 08:00 | 2023-03-01 12:00 | -92 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02330 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit - Roof | 4 | 0 | 2022-01-17 | 2023-02-27 11:12 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02340 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - Roof | 3 | 2 | 2023-02-01 08:00 | 2023-02-28 16:12 | -80 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02315 | WELKIN | OG9 | GENERATOR | [5 empty] | Rig Generator OG3 - Roof | 1 | 0 | 2022-08-24 08:00 | 2022-08-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02360 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generator OG2 - Roof | 10 | 10 | 2023-03-01 13:00 | 2023-03-15 12:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02415 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Terminate all Mech. & Plumbing Equipment at Panel (PP-OG9) - Roof | 3 | 3 | 2023-03-30 13:00 | 2023-04-04 12:00 | -90 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02345 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 2023-02-27 15:00 | 2023-03-06 15:00 | -72 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02320 | FIVE STAR | OG9 | [6 empty] | Install Panelboards - Roof | 1 | 0 | 2022-08-24 08:00 | 2022-08-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02375 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Roof | 3 | 3 | 2023-03-03 16:12 | 2023-03-08 16:12 | 40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02370 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - Roof | 3 | 3 | 2023-03-13 09:36 | 2023-03-16 09:36 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02350 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Roof | 3 | 3 | 2023-02-28 16:12 | 2023-03-03 16:12 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02380 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Lightning protection Air terminals - Roof | 5 | 5 | 2023-03-15 13:00 | 2023-03-22 12:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02385 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Grounding & Ground Equipment | 3 | 3 | 2023-03-22 13:00 | 2023-03-27 12:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02365 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 1 | 2023-02-02 | 2023-03-06 16:12 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02355 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - Roof | 3 | 3 | 2023-02-28 16:12 | 2023-03-03 16:12 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02420 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Terminate Light Fixtures - Roof | 5 | 5 | 2023-03-30 13:00 | 2023-04-06 12:00 | -92 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02400 | MLJ | OG9 | FIRESTOPPING | Interior | NEW BUILDINGS |  |  |  | Install Firestopping | 4 | 2 | 2022-06-21 | 2023-02-28 17:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02395 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment - Roof | 2 | 1 | 2023-02-15 08:00 | 2023-03-28 12:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02405 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Panelboards - Roof | 2 | 2 | 2023-03-28 13:00 | 2023-03-30 12:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02410 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Fire Alarm Equipment | 2 | 2 | 2023-03-30 13:00 | 2023-04-03 12:00 | 25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-02390 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Pull CON-ED Feeder Cable from Foundation Level - Roof | 5 | 0 | 2023-02-01 | 2023-02-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02535 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG9 | 5 | 5 | 2023-07-12 08:00 | 2023-07-18 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02520 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator OG3 - OG9 | 2 | 2 | 2023-04-24 08:00 | 2023-04-25 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02505 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Perform Electrical Inspections for OG9 | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02515 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Energize Switchgear Equipment - OG9 | 3 | 3 | 2023-04-26 08:00 | 2023-04-28 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02510 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Perform 3rd Party Testing - OG9 | 2 | 2 | 2023-04-24 08:00 | 2023-04-25 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02525 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Testing - OG9 | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02530 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator OG2 - OG9 | 2 | 2 | 2023-04-26 08:00 | 2023-04-27 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02540 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Generator Acceptance Testing- OG9 | 15 | 15 | 2023-04-03 08:00 | 2023-04-21 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02005 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02010 |  | OG2 | [6 empty] | Install Bypass Connections - Cellar | 6 | 0 | 2022-05-17 | 2022-05-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02015 | FIVE STAR | OG2 | [6 empty] | Relocate (E) & Install Temporary Lighting Cellar | 5 | 0 | 2021-12-20 | 2022-09-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02030 | [8 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 18 | 0 | 2022-02-18 | 2022-05-16 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02020 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 20 | 2 | 2022-06-16 | 2023-03-06 09:36 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02040 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | 18 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02045 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02050 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02055 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-04-03 08:00 | 2023-04-07 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02025 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 8 | 8 | 2023-03-06 09:36 | 2023-03-16 09:36 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02035 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 2023-03-16 09:36 | 2023-03-23 09:36 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02060 | FIVE STAR | OG2 | CORE DRILL | [5 empty] | Cored Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 18 | 0 | 2022-05-12 | 2022-07-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02065 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) | 2 | 0 | 2023-01-23 08:00 | 2023-03-06 09:36 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02070 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 2023-03-16 09:36 | 2023-03-23 09:36 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02130 | FIVE STAR | OG2 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 2022-06-01 | 2022-07-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02135 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pull Boxes - 1st Floor | 6 | 0 | 2022-06-13 | 2022-10-15 13:48 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02105 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 15 | 2 | 2022-06-10 | 2023-02-28 12:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02110 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 5 | 5 | 2023-02-28 13:00 | 2023-03-07 12:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02115 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel & Equipment - 1st Floor | 2 | 2 | 2023-03-07 13:00 | 2023-03-09 12:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02120 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-03-09 13:00 | 2023-03-13 12:00 | 26 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02125 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 4 | 2022-06-13 | 2023-03-02 15:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02140 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-04-10 08:00 | 2023-04-11 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02145 | MLJ | OG2 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-02-28 13:00 | 2023-03-07 12:00 | -83 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-02150 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 4 | 2022-06-14 | 2023-03-03 10:00 | -75 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02205 | FIVE STAR | OG2 | [6 empty] | Install Switchboards - 2nd Floor | 12 | 0 | 2022-07-01 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02210 |  | OG2 | [6 empty] | Install ACTTS - 2nd Floor | 5 | 0 | 2022-07-01 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02215 | FIVE STAR | OG2 | [6 empty] | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 18 | 0 | 2022-06-15 | 2022-10-06 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02220 | FIVE STAR | OG2 | [6 empty] | Install Panelboards - 2nd Floor | 5 | 0 | 2022-10-07 08:00 | 2022-10-13 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02230 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 18 | 1 | 2022-06-15 | 2023-02-27 16:12 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02235 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 6 | 6 | 2023-02-27 16:12 | 2023-03-07 16:12 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02240 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 2023-03-07 16:12 | 2023-03-13 16:12 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02270 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Equipment - 2nd Floor | 5 | 0 | 2022-12-22 15:48 | 2023-02-23 15:48 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02245 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 4 | 4 | 2023-03-07 16:12 | 2023-03-13 16:12 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02275 | MLJ | OG2 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 5 | 5 | 2023-03-13 16:12 | 2023-03-20 16:12 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02255 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-03-14 08:00 | 2023-03-15 17:00 | -84 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02260 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 1 | 2023-01-15 08:00 | 2023-03-14 12:00 | -83 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02225 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 3 | 2023-01-15 15:00 | 2023-03-13 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02280 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 5 | 5 | 2023-03-14 13:00 | 2023-03-21 12:00 | 34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02250 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull CON-ED Feeder Cable - Cellar to Switchgear - 2nd Floor | 18 | 0 | 2023-01-23 | 2023-02-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-02265 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-03-07 16:12 | 2023-03-14 16:12 | -83 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02535 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG2 | 5 | 5 | 2023-07-12 08:00 | 2023-07-18 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02515 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - OG2 | 5 | 5 | 2023-04-26 08:00 | 2023-05-02 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02525 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - OG2 | 4 | 4 | 2023-05-10 08:00 | 2023-05-15 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02505 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - OG2 | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02510 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test - OG2 | 2 | 2 | 2023-04-24 08:00 | 2023-04-25 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02530 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing - OG2 | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02520 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-in's to Exisiting - OG2 | 5 | 5 | 2023-05-03 08:00 | 2023-05-09 17:00 | -106 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02005 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 3 | 2022-06-06 | 2023-03-02 11:12 | -55 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02010 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 3 | 2022-02-15 | 2023-03-09 11:12 | 12 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02015 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting Cellar | 4 | 1 | 2022-02-16 | 2023-03-13 11:12 | 12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02035 | FIVE STAR | OG3 | CORE DRILL | [5 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 18 | 0 | 2021-12-20 | 2022-06-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02020 | FIVE STAR | OG3 | [6 empty] | Install Branch Conduit - Cellar | 20 | 0 | 2022-02-16 | 2022-12-16 11:12 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02040 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 18 | 18 | 2023-03-13 11:12 | 2023-04-06 11:12 | 12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02050 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02045 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-04-06 11:12 | 2023-04-13 11:12 | 12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02055 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-04-13 11:12 | 2023-04-20 11:12 | 12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02025 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 7 | 7 | 2023-03-02 13:48 | 2023-03-13 13:48 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02030 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 2023-03-13 13:48 | 2023-03-15 13:48 | -52 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02060 | FIVE STAR | OG3 | CORE DRILL | [5 empty] | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 18 | 0 | 2022-05-10 | 2022-07-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02065 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) | 2 | 0 | 2023-01-03 | 2023-03-02 13:48 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02070 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipmen - Cellar | 5 | 5 | 2023-03-13 13:48 | 2023-03-20 13:48 | -55 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02130 | FIVE STAR | OG3 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 0 | 2022-05-23 | 2022-07-01 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02135 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pull Boxes - 1st Floor | 4 | 0 | 2022-06-24 | 2022-10-03 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02105 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 11 | 1 | 2022-06-13 | 2023-02-28 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02110 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 6 | 6 | 2023-02-28 08:48 | 2023-03-08 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02115 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 2023-03-08 08:48 | 2023-03-10 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02120 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-03-10 08:48 | 2023-03-14 08:48 | 20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02125 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 4 | 2022-06-14 | 2023-03-02 15:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02140 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-03-08 08:48 | 2023-03-10 08:48 | -48 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02150 | MLJ | OG3 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 1 | 2022-06-17 | 2023-03-08 08:48 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-02145 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 2023-03-08 08:48 | 2023-03-15 08:48 | -51 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02205 | FIVE STAR | OG3 | [6 empty] | Install Switchboards - 2nd Floor | 12 | 0 | 2022-09-23 | 2022-10-14 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02210 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install ACTTS - 2nd Floor | 4 | 0 | 2022-10-03 08:00 | 2023-02-27 09:36 | -53 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02215 | FIVE STAR | OG3 | [6 empty] | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 18 | 0 | 2022-06-15 | 2022-07-01 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02220 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards - 2nd Floor | 4 | 0 | 2022-10-03 08:00 | 2023-02-27 09:36 | -53 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02230 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 18 | 2 | 2022-11-01 | 2023-03-06 09:36 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02235 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-03-06 09:36 | 2023-03-13 09:36 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02240 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 2023-03-13 09:36 | 2023-03-17 09:36 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02250 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 2023-03-14 08:48 | 2023-03-21 08:48 | 20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02245 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 4 | 3 | 2022-06-17 | 2023-03-01 17:00 | -45 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02255 | MLJ | OG3 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 4 | 3 | 2022-06-17 | 2023-03-06 09:36 | -44 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02265 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 1 | 2022-12-20 08:00 | 2023-03-13 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02270 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-03-13 08:48 | 2023-03-15 08:48 | -51 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02225 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 1 | 2022-12-15 13:00 | 2023-03-10 13:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02275 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 2 | 2 | 2023-03-21 08:48 | 2023-03-23 08:48 | 32 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02260 | FIVE STAR | OG3 | [6 empty] | Pull CON-ED Feeder Cable - Cellar to OG-3 Switchgear - 2nd Floor | 18 | 0 | 2022-12-01 08:00 | 2022-12-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-02280 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-04-04 08:00 | 2023-04-10 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02525 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - OG3 | 4 | 4 | 2023-05-02 08:00 | 2023-05-05 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02535 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG3 | 5 | 5 | 2023-07-12 08:00 | 2023-07-18 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02515 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - OG3 | 5 | 5 | 2023-04-20 08:00 | 2023-04-26 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02505 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - OG3 | 5 | 5 | 2023-04-11 08:00 | 2023-04-17 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02520 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-Ins to Existing | 3 | 3 | 2023-04-27 08:00 | 2023-05-01 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02510 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test | 2 | 2 | 2023-04-18 08:00 | 2023-04-19 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02530 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-02005 | FIVE STAR | S8 | [6 empty] | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 0 | 2022-09-06 08:00 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-02010 |  | S8 | [6 empty] | Install Manholes & Grounding | 3 | 0 | 2022-08-05 | 2022-10-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.2 | S8-02105 | FIVE STAR | S8 |  | Utilities | SITE |  |  |  | Pull CON-ED Feeder Cable - Surf Ave to S8-ADD Cellar | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -36 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.2 | S8-02110 | FIVE STAR | S8 |  | Utilities | SITE |  |  |  | Pull Generator Cable - S8-ADD to S8(E) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 2 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.3 | S8-02205 | FIVE STAR | S8 |  | Utilities | SITE |  |  |  | Remove Existing Lighting Conduit, Cable & Fixtures - S8 | 5 | 5 | 2023-08-01 13:00 | 2023-08-08 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.3 | S8-02210 | FIVE STAR | S8 |  | Utilities | SITE |  |  |  | Install Site Lighting Conduit - S8 | 5 | 5 | 2023-08-08 13:00 | 2023-08-15 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.3 | S8-02215 | FIVE STAR | S8 |  | Utilities | SITE |  |  |  | Pull Site Lighting Wire - S8 | 3 | 3 | 2023-08-15 13:00 | 2023-08-18 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.3 | S8-02220 | FIVE STAR | S8 |  | Utilities | SITE |  |  |  | Install Site Lighting Fixtures & Terminate - S8 | 5 | 5 | 2023-08-18 13:00 | 2023-08-25 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02005 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 2023-03-02 08:00 | 2023-03-08 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02010 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 6 | 2023-03-09 08:00 | 2023-03-16 17:00 | -71 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02020 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 4 | 2022-06-07 | 2023-03-16 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02045 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment & Terminate - Cellar | 5 | 5 | 2023-05-15 08:00 | 2023-05-19 17:00 | -60 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02035 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 15 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02050 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 6 | 6 | 2023-06-27 08:00 | 2023-07-05 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02060 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 3 | 3 | 2023-07-06 08:00 | 2023-07-10 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02055 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 2023-05-22 08:00 | 2023-05-26 17:00 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02025 | FIVE STAR | S82 | CORE DRILL | Interior | NEW BUILDINGS |  |  |  | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 20 | 20 | 2023-04-03 08:00 | 2023-04-28 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02015 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Panelboards (Misc.) - Cellar | 2 | 2 | 2023-03-09 08:00 | 2023-03-10 17:00 | -35 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02030 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit | 15 | 15 | 2023-03-17 08:00 | 2023-04-06 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02040 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring | 5 | 5 | 2023-04-07 08:00 | 2023-04-13 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02065 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 15 | 15 | 2023-06-06 08:00 | 2023-06-26 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-02105 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 20 | 2023-05-01 08:00 | 2023-05-26 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-02110 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Pull/Splice Boxes - 1st Floor | 5 | 5 | 2023-05-30 08:00 | 2023-06-05 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-02125 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-06-20 08:00 | 2023-06-21 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-02130 | MLJ | S81 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-06-22 08:00 | 2023-06-28 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-02120 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 3 | 3 | 2023-07-11 08:00 | 2023-07-13 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-02115 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Pull Feeder Cable from Cellar to 1st Floor - 1st Floor | 10 | 10 | 2023-06-06 08:00 | 2023-06-19 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-02505 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Perform Tie-In's to Exisiting Equipment - S8E | 5 | 5 | 2023-07-19 13:00 | 2023-07-26 12:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-02510 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Perform Electrical Inspections - S8E | 2 | 2 | 2023-06-29 08:00 | 2023-06-30 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-02005 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -51 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-02010 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Temporary Lighting & Temporary Power for S8A | 5 | 3 | 2021-07-01 | 2023-03-01 17:00 | -60 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-02015 |  | S81 | [6 empty] | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 2022-06-17 | 2022-11-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-02020 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 2 | 2023-03-06 08:00 | 2023-03-07 17:00 | -54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-02025 |  | S81 | [6 empty] | Install Pull Box - Foundation | 2 | 0 | 2022-06-17 | 2022-11-07 12:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02105 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 5 | 5 | 2023-03-15 08:00 | 2023-03-21 17:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02110 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 1st Floor | 5 | 5 | 2023-03-15 08:00 | 2023-03-21 17:00 | -40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02115 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 5 | 5 | 2023-03-06 10:00 | 2023-03-13 10:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02120 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 5 | 5 | 2023-05-03 13:00 | 2023-05-10 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02125 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 1st Floor | 2 | 2 | 2023-05-10 13:00 | 2023-05-12 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02130 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 2023-03-22 08:00 | 2023-03-23 17:00 | -42 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02135 | FIVE STAR | S81 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 2022-11-01 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02140 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduits - 1st Floor | 15 | 5 | 2022-09-23 | 2023-03-06 10:00 | -52 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02145 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 5 | 5 | 2023-03-08 08:00 | 2023-03-14 17:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02150 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 2023-05-19 13:00 | 2023-05-24 12:00 | -67 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02155 |  | S81 | [6 empty] | Install In-slab Conduits - 1st floor slab | 5 | 0 | 2022-07-11 08:00 | 2022-07-14 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02160 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 2023-03-15 08:00 | 2023-03-16 17:00 | -37 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02205 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 2 | 2022-11-10 | 2023-02-28 17:00 | -33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02210 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire for Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 2023-06-12 13:00 | 2023-06-26 12:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02215 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduits - 2nd Floor | 15 | 9 | 2022-12-01 13:00 | 2023-03-27 17:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02220 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-03-28 08:00 | 2023-04-03 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02225 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 2nd Floor | 5 | 5 | 2023-03-28 08:00 | 2023-04-03 17:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02230 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 5 | 5 | 2023-04-04 08:00 | 2023-04-10 17:00 | 11 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02235 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 2nd Floor | 5 | 5 | 2023-04-04 08:00 | 2023-04-10 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02240 |  | S81 | [6 empty] | Install In-slab Conduits - 2nd floor slab | 10 | 0 | 2022-09-13 | 2022-09-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-02245 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 2 | 2 | 2023-05-12 13:00 | 2023-05-16 12:00 | -76 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02305 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduit & Racks - Roof | 15 | 1 | 2022-11-15 | 2023-03-07 17:00 | -33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02310 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generators - Roof | 10 | 10 | 2023-06-21 08:00 | 2023-07-05 17:00 | -44 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02315 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Roof | 5 | 4 | 2022-11-15 08:00 | 2023-04-13 15:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02320 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Roof | 5 | 5 | 2023-04-13 15:00 | 2023-04-20 15:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02325 | WELKIN | S81 | GENERATOR | Interior | EXISTING BUILDINGS |  |  |  | Rig Generator S8 (2 No's) - Roof | 1 | 1 | 2023-06-20 08:00 | 2023-06-20 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02330 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate all Mech. & Plumbing Equipment at Panel - Roof | 5 | 5 | 2023-06-26 13:00 | 2023-07-03 12:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02335 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 2023-04-13 15:00 | 2023-04-20 15:00 | -48 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02340 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Switchboards - Roof | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02345 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install ACTTS - Roof | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02350 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards - Roof | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02355 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Roof | 5 | 5 | 2023-04-27 15:00 | 2023-05-04 15:00 | -2 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02360 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - Roof | 3 | 3 | 2023-05-16 13:00 | 2023-05-19 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02365 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Roof | 5 | 5 | 2023-04-20 15:00 | 2023-04-27 15:00 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02370 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lightning protection Air terminals - Roof | 4 | 4 | 2023-05-05 08:00 | 2023-05-10 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02375 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Grounding & Ground Equipment | 5 | 5 | 2023-05-11 08:00 | 2023-05-17 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02380 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 2023-04-27 15:00 | 2023-05-01 15:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02385 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - Roof | 5 | 5 | 2023-04-20 15:00 | 2023-04-27 15:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02390 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Light Fixtures - Roof | 5 | 5 | 2023-05-31 13:00 | 2023-06-07 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02395 | MLJ | S81 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - Roof | 4 | 4 | 2023-04-13 15:00 | 2023-04-19 15:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02400 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment - Roof | 5 | 5 | 2023-05-19 13:00 | 2023-05-26 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02405 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards - Roof | 2 | 2 | 2023-05-26 13:00 | 2023-05-31 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02410 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Fire Alarm Equipment | 2 | 2 | 2023-05-31 13:00 | 2023-06-02 12:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-02415 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Feeder Cable from Foundation to Roof - Roof | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -36 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02505 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - S8A | 5 | 5 | 2023-08-01 13:00 | 2023-08-08 12:00 | -61 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02510 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator SG4 - S8A | 2 | 2 | 2023-07-19 13:00 | 2023-07-21 12:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02515 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections for S8A | 5 | 5 | 2023-07-03 13:00 | 2023-07-11 12:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02520 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear Equipment - S8A | 4 | 4 | 2023-07-13 13:00 | 2023-07-19 12:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02525 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Testing - S8A | 2 | 2 | 2023-07-11 13:00 | 2023-07-13 12:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02530 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Testing - S8A | 14 | 14 | 2023-07-12 13:00 | 2023-08-01 12:00 | -61 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02535 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Generator Acceptance Testing - S8A | 5 | 5 | 2023-07-12 13:00 | 2023-07-19 12:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02540 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Switchgear/Generator S8E - S8A | 4 | 4 | 2023-07-26 13:00 | 2023-08-01 12:00 | -71 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02025 | FIVE STAR | OGE | [6 empty] | Pull CON-ED Feeder Cable - 33rd St. to OG-5 Cellar | 10 | 0 | 2022-12-01 13:48 | 2022-12-15 13:48 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02005 | FIVE STAR | OGE | [6 empty] | Pull CON-ED Feeder Cable - 33rd St. to OG-4 Cellar | 10 | 0 | 2022-10-28 15:00 | 2022-11-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02010 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Feeder Cable - OG-4 Switchgear to OG-8 Foundation | 10 | 0 | 2023-02-01 08:00 | 2023-02-20 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02020 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Generator Feeder Cable from OG-8 to OG-5 | 5 | 1 | 2022-04-10 | 2023-06-16 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02015 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Generator Feeder Cable from OG-8 to OG-4 | 5 | 1 | 2023-02-01 08:00 | 2023-06-02 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.3 | OGP1-02105 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 2023-08-01 08:00 | 2023-08-07 17:00 | -54 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.3 | OGP1-02110 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Furnish & Install Site Lighting Conduit | 5 | 1 | 2022-11-01 | 2023-02-27 12:00 | 52 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.3 | OGP1-02115 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Site Lighting Wire | 3 | 3 | 2023-02-27 13:00 | 2023-03-02 12:00 | 52 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.3 | OGP1-02120 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Install Site Lighting Fixtures & Terminate | 5 | 5 | 2023-08-01 08:00 | 2023-08-07 17:00 | -54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-02015 | FIVE STAR | OG8 | [6 empty] | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 0 | 2022-05-25 08:00 | 2023-01-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-02005 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Temporary Lighting & Temporary Power for OG8 | 5 | 1 | 2022-02-07 08:00 | 2023-02-27 17:00 | -72 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-02010 | [8 empty] | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 2021-10-27 | 2021-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-02025 | FIVE STAR | OG8 | [6 empty] | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 0 | 2022-05-26 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-02020 | [8 empty] | Install Pull Box - Foundation | 2 | 0 | 2022-02-07 | 2022-04-25 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02135 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 3 | 0 | 2022-12-15 08:00 | 2023-02-27 11:36 | -59 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02140 | FIVE STAR | OG8 | [6 empty] | Install Light/Emergency Fixtures - 1st Floor | 3 | 0 | 2022-10-03 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02125 | FIVE STAR | OG8 | [6 empty] | Pull Fire Alarm Wiring - 1st Floor | 3 | 0 | 2022-11-01 | 2023-01-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02145 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 2 | 2023-01-02 | 2023-02-28 15:24 | -56 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02160 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 1st Floor | 2 | 0 | 2022-06-13 | 2023-02-27 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02155 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 0 | 2023-01-15 | 2023-01-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02110 | FIVE STAR | OG8 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 2022-03-14 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02115 | FIVE STAR | OG8 | [6 empty] | Install Branch Conduits - 1st Floor | 10 | 0 | 2022-02-21 | 2023-01-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02130 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 3 | 0 | 2022-06-13 | 2023-02-27 10:24 | -59 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02150 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 2 | 2023-01-15 | 2023-03-01 13:24 | -54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02105 | [8 empty] | Install In-slab Conduits - 1st floor slab - 1st Floor | 3 | 0 | 2022-02-21 | 2022-03-18 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02120 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Exterior Lighting & Controls - 1st Floor | 2 | 0 | 2022-11-01 | 2023-03-20 17:00 | -67 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02220 | FIVE STAR | OG8 | [6 empty] | Install Feeder Conduit Risers & Racks to 3rd Floor - 2nd Floor | 15 | 0 | 2022-03-14 | 2022-11-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02225 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 10 | 1 | 2023-01-02 | 2023-02-28 15:00 | -56 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02210 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduits - 2nd Floor | 15 | 1 | 2022-06-15 | 2023-02-27 15:00 | -75 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02230 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 3 | 0 | 2022-12-15 13:00 | 2023-02-28 08:24 | -58 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02235 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 2nd Floor | 3 | 0 | 2022-12-15 13:00 | 2023-02-28 08:24 | -63 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02215 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 3 | 0 | 2022-12-15 13:00 | 2023-02-28 10:48 | 49 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02240 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 2nd Floor | 3 | 0 | 2022-12-15 13:00 | 2023-01-27 13:24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02205 | [8 empty] | Install In-slab Conduits - 2nd floor slab - 2nd Floor | 10 | 0 | 2022-03-14 | 2022-04-04 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02245 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 2 | 0 | 2023-01-02 | 2023-02-28 09:12 | -52 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02250 | FIVE STAR | OG8 | [6 empty] | Install Switchboards - 2nd Floor | 3 | 0 | 2022-03-14 | 2022-09-26 10:24 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02255 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install ACTTS - 2nd Floor | 3 | 0 | 2022-05-03 | 2023-02-27 09:12 | -60 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02260 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Panelboards - 2nd Floor | 3 | 0 | 2022-07-28 08:00 | 2023-02-27 09:12 | -57 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02265 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Feeder Conduit & Racks - 2nd Floor | 15 | 1 | 2022-07-28 08:00 | 2023-03-01 09:12 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02275 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment - 2nd Floor | 3 | 2 | 2023-02-01 | 2023-03-03 14:12 | -56 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02280 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Panelboards - 2nd Floor | 3 | 3 | 2023-03-02 09:12 | 2023-03-07 09:12 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-02270 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull CON-ED Feeder Cable from Foundation to Switchgear Equipment - 2nd Floor | 10 | 1 | 2023-01-02 08:00 | 2023-03-02 09:12 | -60 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02455 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Feeder Conduit & Racks - Roof | 10 | 1 | 2022-06-21 | 2023-05-02 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02405 | WELKIN | OG8 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator OG-5 - Roof | 1 | 1 | 2023-05-01 08:00 | 2023-05-01 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02415 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generators OG-4 (2 No's) - Roof | 20 | 20 | 2023-05-04 08:00 | 2023-06-01 17:00 | -140 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02440 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit - Roof | 15 | 8 | 2022-08-22 08:00 | 2023-03-08 12:00 | -72 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02445 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - Roof | 3 | 2 | 2022-06-21 | 2023-03-10 12:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02410 | WELKIN | OG8 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator OG-4 (2 No's) - Roof | 2 | 2 | 2023-05-02 08:00 | 2023-05-03 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02420 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generator OG-5 - Roof | 10 | 10 | 2023-06-02 08:00 | 2023-06-15 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02510 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Terminate all Mech. & Plumbing Equipment at Panel (MEP-LR) - Roof | 3 | 3 | 2023-06-28 08:00 | 2023-06-30 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02450 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 2023-03-15 15:00 | 2023-03-22 15:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02430 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Switchboards - Roof | 2 | 2 | 2023-05-01 08:00 | 2023-05-02 17:00 | -116 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02435 |  | OG8 | [6 empty] | Install ACTTS - Roof | 2 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02470 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Roof | 3 | 3 | 2023-03-16 16:12 | 2023-03-21 16:12 | 33 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02475 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - Roof | 3 | 2 | 2022-06-21 | 2023-03-16 16:12 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02460 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Roof | 3 | 3 | 2023-03-15 15:00 | 2023-03-20 15:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02425 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Lightning protection Air terminals - Roof | 5 | 5 | 2023-06-16 08:00 | 2023-06-22 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02485 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Grounding & Ground Equipment | 3 | 3 | 2023-06-23 08:00 | 2023-06-27 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02480 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 2023-03-16 16:12 | 2023-03-20 16:12 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02465 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - Roof | 3 | 3 | 2023-03-13 16:12 | 2023-03-16 16:12 | -73 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02495 | MLJ | OG8 | FIRESTOPPING | Interior | NEW BUILDINGS |  |  |  | Install Firestopping | 4 | 0 | 2022-10-15 08:00 | 2023-05-24 09:36 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02500 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment - Roof | 3 | 3 | 2023-06-28 08:00 | 2023-06-30 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02515 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate all Fire Alarm Equipment - Roof | 3 | 3 | 2023-06-28 08:00 | 2023-06-30 17:00 | -36 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02490 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Feeder Cable from Foundation to Switchgear Equipment - Roof | 15 | 15 | 2023-05-03 08:00 | 2023-05-23 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02520 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Terminate Light Fixtures - Roof | 3 | 3 | 2023-06-28 08:00 | 2023-06-30 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02505 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Panelboards- Roof | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -66 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-02507 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Panelboards - Roof | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | -56 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02740 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG8 | 2 | 2 | 2023-07-24 08:00 | 2023-07-25 17:00 | -50 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02730 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator OG4(2 No's) - OG8 | 2 | 2 | 2023-07-18 08:00 | 2023-07-19 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02705 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Perform Electrical Inspections for OG8 | 5 | 5 | 2023-07-03 08:00 | 2023-07-10 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02725 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Energize Switchgear Equipment - OG8 | 3 | 3 | 2023-07-13 08:00 | 2023-07-17 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02720 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Perform 3rd Party Testing - OG8 | 2 | 2 | 2023-07-11 08:00 | 2023-07-12 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02710 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Testing - OG8 | 14 | 14 | 2023-07-03 08:00 | 2023-07-21 17:00 | -50 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02735 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator OG5 - OG8 | 2 | 2 | 2023-07-20 08:00 | 2023-07-21 17:00 | -138 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02715 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Generator Acceptance Testing- OG8 | 15 | 15 | 2023-06-26 08:00 | 2023-07-17 17:00 | -140 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02305 | FIVE STAR | OG8 | [6 empty] | Install Feeder Conduit Risers & Racks to Roof - Upper Second Floor | 20 | 0 | 2022-05-04 | 2023-01-02 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02310 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Upper Second Floor | 10 | 10 | 2023-03-13 15:00 | 2023-03-27 15:00 | -75 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02315 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduits - Upper Second Floor | 20 | 1 | 2022-06-20 | 2023-03-13 15:00 | -75 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02320 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - Upper Second Floor | 3 | 1 | 2022-06-20 | 2023-03-15 15:00 | -72 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02325 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - Upper Second Floor | 3 | 0 | 2022-12-15 13:00 | 2023-03-13 16:12 | -73 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02330 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Upper Second Floor | 3 | 0 | 2022-12-15 13:00 | 2023-03-14 08:24 | 39 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02335 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Upper Second Floor | 2 | 0 | 2022-12-15 13:00 | 2023-02-10 16:36 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02340 | [8 empty] | Install In-slab Conduits - 2nd Floor slab - Upper Second Floor | 10 | 0 | 2022-03-18 | 2022-05-05 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.5 | OG8-02345 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - Upper Second Floor | 2 | 0 | 2022-06-20 | 2023-02-10 15:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02005 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 4 | 2022-06-10 | 2023-03-02 15:00 | -88 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02015 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 5 | 2022-06-13 | 2023-03-03 12:00 | -89 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02025 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 3 | 2022-06-20 | 2023-03-03 12:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02030 | [8 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 2022-04-24 | 2022-04-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02020 | FIVE STAR | OG4 | [6 empty] | Install Branch Conduit - Cellar | 20 | 0 | 2022-06-15 | 2022-12-12 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02035 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 10 | 2023-01-02 08:00 | 2023-03-17 12:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02055 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02060 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-03-17 13:00 | 2023-03-24 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02070 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-03-24 13:00 | 2023-03-31 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02040 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 8 | 4 | 2023-02-02 08:00 | 2023-03-02 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02045 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 2023-04-03 08:00 | 2023-04-07 17:00 | -84 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02065 | FIVE STAR | OG4 | CORE DRILL | [5 empty] | Core Drill & Install Feeder Conduits Risers & Racks Directly to 1st Floor - Cellar | 20 | 0 | 2022-06-20 | 2022-09-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02010 | FIVE STAR | OG4 | [6 empty] | Install Panelboards (Misc.) - Cellar | 2 | 0 | 2022-09-29 15:00 | 2022-11-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02050 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 2023-03-03 08:00 | 2023-03-09 17:00 | -63 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02130 | FIVE STAR | OG4 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 15 | 0 | 2022-06-22 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02135 |  | OG4 | [6 empty] | Install Pull/Splice Boxes - 1st Floor | 5 | 0 | 2022-07-01 13:00 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02105 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 15 | 2 | 2022-07-01 15:00 | 2023-02-28 12:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02110 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 5 | 5 | 2023-02-28 13:00 | 2023-03-07 12:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02115 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel & Equipment - 1st Floor | 5 | 5 | 2023-03-07 13:00 | 2023-03-14 12:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02125 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-03-14 13:00 | 2023-03-16 12:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02120 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 2023-03-31 13:00 | 2023-04-07 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02140 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-03-07 13:00 | 2023-03-09 12:00 | -65 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02145 | MLJ | OG4 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 3 | 2022-11-01 | 2023-03-09 12:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-02150 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 2023-03-07 13:00 | 2023-03-14 12:00 | -66 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02205 | FIVE STAR | OG4 | [6 empty] | Install Switchboards - 2nd Floor | 15 | 0 | 2022-04-22 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02210 |  | OG4 | [6 empty] | Install ACTTS - 2nd Floor | 5 | 0 | 2022-06-16 | 2022-12-15 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02215 | FIVE STAR | OG4 | [6 empty] | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 0 | 2022-07-01 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02220 | FIVE STAR | OG4 | [6 empty] | Install Panelboards - 2nd Floor | 5 | 0 | 2022-10-24 | 2022-12-15 10:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02225 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 15 | 1 | 2022-10-15 | 2023-02-27 15:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02235 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-02-27 15:00 | 2023-03-06 15:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02240 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 5 | 5 | 2023-04-07 13:00 | 2023-04-14 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02265 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Equipment - 2nd Floor | 5 | 5 | 2023-03-29 13:00 | 2023-04-05 12:00 | 9 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02245 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 5 | 5 | 2023-03-06 15:00 | 2023-03-13 15:00 | -65 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02270 | MLJ | OG4 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 5 | 3 | 2022-11-15 13:00 | 2023-03-13 17:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02255 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-03-15 15:00 | 2023-03-17 15:00 | -69 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02260 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 3 | 2022-12-15 13:00 | 2023-03-29 12:00 | -77 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02230 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 1 | 2022-12-15 13:00 | 2023-03-15 15:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02275 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 5 | 5 | 2023-04-05 13:00 | 2023-04-12 12:00 | 18 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02250 | FIVE STAR | OG4 | [6 empty] | Pull CON-ED Feeder Cable from Cellar to Switchgear - 2nd Floor | 20 | 0 | 2022-11-01 | 2022-11-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-02280 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02535 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG4 | 5 | 5 | 2023-07-26 08:00 | 2023-08-01 17:00 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02515 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - OG4 | 5 | 5 | 2023-04-26 08:00 | 2023-05-02 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02530 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - OG4 | 4 | 4 | 2023-07-20 08:00 | 2023-07-25 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02505 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - OG4 | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02510 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test - OG4 | 2 | 2 | 2023-04-24 08:00 | 2023-04-25 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02525 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing - OG4 | 14 | 14 | 2023-07-06 08:00 | 2023-07-25 17:00 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02520 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-in's to Exisiting | 3 | 3 | 2023-05-03 08:00 | 2023-05-05 17:00 | -89 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02005 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 2022-06-10 | 2023-03-02 13:48 | -82 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02010 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 7 | 5 | 2022-06-13 | 2023-03-07 13:48 | -82 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02025 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting Cellar | 3 | 2 | 2022-06-15 | 2023-03-07 13:48 | -82 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02030 | FIVE STAR | OG5 | CORE DRILL | [5 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 18 | 0 | 2022-06-15 | 2022-07-01 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02015 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 19 | 5 | 2022-07-01 | 2023-03-03 15:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02035 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 15 | 15 | 2023-03-07 13:48 | 2023-03-28 13:48 | -82 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02055 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02060 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-03-28 13:48 | 2023-04-04 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02070 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-04-04 13:48 | 2023-04-11 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02040 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 7 | 7 | 2023-03-03 15:00 | 2023-03-14 15:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02045 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 2023-03-14 15:00 | 2023-03-16 15:00 | -51 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02065 | FIVE STAR | OG5 | CORE DRILL | [5 empty] | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 20 | 0 | 2022-06-20 | 2022-09-27 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02020 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) - Cellar | 2 | 0 | 2022-09-29 13:48 | 2023-02-27 09:36 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02050 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 2023-03-14 15:00 | 2023-03-21 15:00 | -54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02125 | FIVE STAR | OG5 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 0 | 2022-06-20 | 2022-09-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02135 |  | OG5 | [6 empty] | Install Pull/Splice Boxes - 1st Floor | 4 | 0 | 2022-06-20 10:00 | 2022-11-15 11:12 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02105 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 11 | 1 | 2022-07-15 15:48 | 2023-02-28 08:48 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02110 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 6 | 6 | 2023-02-28 08:48 | 2023-03-08 08:48 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02115 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 5 | 5 | 2023-03-08 08:48 | 2023-03-15 08:48 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02130 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-03-15 08:48 | 2023-03-17 08:48 | 17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02120 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 2023-04-11 13:48 | 2023-04-18 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02140 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-03-08 08:48 | 2023-03-10 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02145 | MLJ | OG5 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-03-10 08:48 | 2023-03-17 08:48 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-02150 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -52 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02205 | FIVE STAR | OG5 | [6 empty] | Install Switchboards - 2nd Floor | 12 | 0 | 2022-05-16 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02210 |  | OG5 | [6 empty] | Install ACTTS - 2nd Floor | 4 | 0 | 2022-05-16 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02215 | FIVE STAR | OG5 | [6 empty] | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 15 | 0 | 2022-07-01 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02220 | FIVE STAR | OG5 | [6 empty] | Install Panelboards - 2nd Floor | 4 | 0 | 2022-09-23 | 2022-10-21 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02225 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 15 | 1 | 2022-09-23 | 2023-02-27 15:00 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02235 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-02-27 15:00 | 2023-03-06 15:00 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02240 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 2023-04-18 13:48 | 2023-04-24 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02245 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 2023-03-17 08:48 | 2023-03-24 08:48 | 17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02250 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 4 | 4 | 2023-03-06 15:00 | 2023-03-10 15:00 | -50 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02255 | MLJ | OG5 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 4 | 4 | 2023-04-24 13:48 | 2023-04-28 13:48 | -82 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02265 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 1 | 2022-12-15 08:48 | 2023-03-17 08:48 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02275 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-03-17 08:48 | 2023-03-21 08:48 | -53 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02230 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 1 | 2023-01-15 08:48 | 2023-03-16 10:48 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02280 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 2 | 2 | 2023-03-24 08:48 | 2023-03-28 08:48 | 29 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02260 | FIVE STAR | OG5 | [6 empty] | Pull CON-ED Feeder Cable - Cellar to OG5 Switchgear - 2nd Floor | 20 | 0 | 2022-11-01 | 2022-11-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-02270 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02530 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - OG5 | 4 | 4 | 2023-07-26 08:00 | 2023-07-31 17:00 | -129 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02535 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG5 | 5 | 5 | 2023-08-01 08:00 | 2023-08-07 17:00 | -59 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02515 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - OG5 | 5 | 5 | 2023-05-05 13:48 | 2023-05-12 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02505 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - OG5 | 5 | 5 | 2023-04-28 13:48 | 2023-05-05 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02520 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-Ins to Existing | 3 | 3 | 2023-05-12 13:48 | 2023-05-17 13:48 | -82 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02510 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test | 2 | 1 | 2022-09-15 | 2023-05-05 13:48 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02525 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 2023-07-12 08:00 | 2023-07-31 17:00 | -59 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.2 | OGE-02105 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull CON-ED Feeder Cable - 33rd st. to OG1 Cellar | 10 | 0 | 2022-12-01 08:00 | 2022-12-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.2 | OGE-02110 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull CON-ED Feeder Cable - 33rd St. to OG6 Cellar | 10 | 0 | 2023-02-15 08:00 | 2023-02-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.2 | OGE-02115 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Feeder Cable - OG6 Switchgear to OG10 Foundation | 10 | 10 | 2023-04-04 13:00 | 2023-04-18 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.2 | OGE-02125 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Generator Feeder Cable from OG10 to OG1 | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -58 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.2 | OGE-02120 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Generator Feeder Cable from OG10 to OG6 | 5 | 5 | 2023-03-31 08:00 | 2023-04-06 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.3 | OGE-02205 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 2023-08-18 08:00 | 2023-08-24 17:00 | -71 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.3 | OGE-02210 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Furnish & Install Site Lighting Conduit | 5 | 1 | 2022-10-10 08:00 | 2023-08-24 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.3 | OGE-02215 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull Site Lighting Wire | 4 | 4 | 2023-08-25 08:00 | 2023-08-30 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.3 | OGE-02220 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Install Site Lighting Fixtures & Terminate | 5 | 5 | 2023-08-31 08:00 | 2023-09-07 17:00 | -71 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-02015 | FIVE STAR | OG10 | [6 empty] | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 0 | 2022-05-25 08:00 | 2022-09-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-02005 | FIVE STAR | OG10 | [6 empty] | Install Temporary Lighting & Temporary Power for OG10 | 5 | 0 | 2022-07-01 | 2022-09-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-02010 | [8 empty] | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 2021-09-21 | 2022-02-10 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-02025 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 1 | 2022-05-27 08:00 | 2023-02-27 17:00 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-02020 | [8 empty] | Install Pull Box - Foundation | 2 | 0 | 2022-02-10 | 2022-02-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02130 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 3 | 0 | 2023-01-23 | 2023-02-28 15:24 | -38 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02135 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 1st Floor | 3 | 0 | 2022-11-01 | 2023-02-28 17:00 | -36 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02120 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 3 | 2 | 2022-12-15 08:00 | 2023-02-28 12:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02140 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 2023-02-28 08:00 | 2023-03-02 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02155 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 1st Floor | 2 | 2 | 2023-03-13 08:00 | 2023-03-14 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02150 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 2023-02-28 15:24 | 2023-03-02 15:24 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02110 | [8 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 2022-02-01 | 2022-02-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02115 | FIVE STAR | OG10 | [6 empty] | Install Branch Conduits - 1st Floor | 15 | 0 | 2022-01-17 | 2022-09-09 12:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02125 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 3 | 1 | 2022-06-10 | 2023-02-27 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02145 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 2023-02-28 08:00 | 2023-03-02 17:00 | -20 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02105 | [8 empty] | Install In-slab Conduits - 1st floor slab | 3 | 0 | 2022-01-17 | 2022-02-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02160 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 2023-03-09 08:00 | 2023-03-10 17:00 | -44 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02220 | FIVE STAR | OG10 | [6 empty] | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 0 | 2022-02-14 | 2022-07-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02225 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 2023-02-27 15:00 | 2023-03-13 15:00 | -30 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02210 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduits - 2nd Floor | 15 | 1 | 2022-02-10 | 2023-02-27 15:00 | -37 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02230 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 3 | 1 | 2022-12-15 08:00 | 2023-03-01 08:24 | -34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02235 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 2nd Floor | 3 | 0 | 2022-12-22 13:00 | 2023-02-28 15:24 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02215 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 3 | 0 | 2023-01-31 13:00 | 2023-03-01 08:48 | 44 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02240 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 2nd Floor | 3 | 0 | 2022-12-01 08:00 | 2023-03-01 10:48 | -26 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02205 | [8 empty] | Install In-slab Conduits - 2nd floor slab | 10 | 0 | 2022-01-21 | 2022-02-02 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-02245 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 2 | 1 | 2022-12-22 08:00 | 2023-03-15 17:00 | -44 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02360 | FIVE STAR | OG10 | [6 empty] | Install Feeder Conduit & Racks - Roof | 5 | 0 | 2022-06-13 | 2022-07-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02305 | WELKIN | OG10 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator OG1 - Roof | 1 | 0 | 2022-08-25 | 2022-08-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02315 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generator OG6 - Roof | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -58 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02345 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit - Roof | 4 | 0 | 2022-06-08 | 2023-02-27 11:12 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02350 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - Roof | 3 | 3 | 2023-02-27 11:12 | 2023-03-02 11:12 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02310 | WELKIN | OG10 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator OG6 - Roof | 1 | 0 | 2023-02-13 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02320 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Generator Circuit Breakers & Wire Generator OG1 - Roof | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -58 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02415 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Terminate all Mech. & Plumbing Equipment at Panel (PP-OG10) - Roof | 3 | 3 | 2023-05-04 13:00 | 2023-05-09 12:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02355 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 2023-03-01 08:24 | 2023-03-08 08:24 | -26 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02330 | FIVE STAR | OG10 | [6 empty] | Install Switchboards - Roof | 3 | 0 | 2022-07-22 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02335 |  | OG10 | [6 empty] | Install ACTTS - Roof | 3 | 0 | 2022-07-22 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02340 | FIVE STAR | OG10 | [6 empty] | Install Panelboards - Roof | 8 | 0 | 2022-07-22 | 2022-09-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02375 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Roof | 3 | 3 | 2023-03-07 11:12 | 2023-03-10 11:12 | 40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02380 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - Roof | 3 | 3 | 2023-03-16 08:00 | 2023-03-20 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02365 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Roof | 3 | 3 | 2023-03-02 11:12 | 2023-03-07 11:12 | -27 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02325 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Lightning protection Air terminals - Roof | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -56 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02390 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Grounding & Ground Equipment | 3 | 3 | 2023-04-03 08:00 | 2023-04-05 17:00 | -56 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02385 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 2023-03-07 11:12 | 2023-03-09 11:12 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02370 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - Roof | 3 | 3 | 2023-03-02 11:12 | 2023-03-07 11:12 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02420 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Terminate Light Fixtures - Roof | 5 | 5 | 2023-05-04 13:00 | 2023-05-11 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02400 | MLJ | OG1 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping | 4 | 4 | 2023-04-25 13:00 | 2023-05-01 12:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02405 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment - Roof | 5 | 5 | 2023-04-25 13:00 | 2023-05-02 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02410 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Panelboards - Roof | 2 | 2 | 2023-05-02 13:00 | 2023-05-04 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02425 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Fire Alarm Equipment | 2 | 2 | 2023-05-04 13:00 | 2023-05-08 12:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-02395 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Pull Feeder Cable - Foundation to Roof - Roof | 5 | 5 | 2023-04-18 13:00 | 2023-04-25 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02540 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG10 | 4 | 4 | 2023-07-12 08:00 | 2023-07-17 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02530 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator OG6 - OG10 | 2 | 2 | 2023-05-18 13:00 | 2023-05-22 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02505 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Perform Electrical Inspections for OG10 | 5 | 5 | 2023-05-11 13:00 | 2023-05-18 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02525 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Energize Switchgear Equipment - OG10 | 3 | 3 | 2023-05-22 13:00 | 2023-05-25 12:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02520 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Perform 3rd Party Testing - OG10 | 2 | 2 | 2023-05-18 13:00 | 2023-05-22 12:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02510 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Testing - OG10 | 14 | 14 | 2023-06-21 08:00 | 2023-07-11 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02535 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator OG1 - OG10 | 2 | 2 | 2023-05-22 13:00 | 2023-05-24 12:00 | -56 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02515 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Generator Acceptance Testing- OG10 | 15 | 15 | 2023-04-27 13:00 | 2023-05-18 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02005 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02015 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02025 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting Cellar | 4 | 4 | 2023-03-13 08:00 | 2023-03-16 17:00 | -79 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02030 | FIVE STAR | OG6 | CORE DRILL | [5 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 2022-06-13 | 2022-11-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02020 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 20 | 20 | 2023-03-08 08:00 | 2023-04-04 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02035 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 2023-03-17 08:00 | 2023-04-13 17:00 | -79 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02055 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02065 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-04-14 08:00 | 2023-04-20 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02070 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-04-21 08:00 | 2023-04-27 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02040 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 8 | 8 | 2023-04-05 08:00 | 2023-04-14 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02045 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -65 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02060 | FIVE STAR | OG6 | CORE DRILL | Interior | EXISTING BUILDINGS |  |  |  | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 20 | 10 | 2022-06-15 | 2023-03-30 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02010 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) | 2 | 2 | 2023-03-06 08:00 | 2023-03-07 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02050 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -65 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02115 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 15 | 2022-06-20 | 2023-03-30 17:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02135 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pull Boxes - 1st Floor | 5 | 3 | 2023-02-01 08:00 | 2023-04-04 12:00 | -70 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02105 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02110 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02120 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel & Equipment - 1st Floor | 2 | 2 | 2023-06-20 08:00 | 2023-06-21 17:00 | -117 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02130 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-06-22 08:00 | 2023-06-23 17:00 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02125 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 2023-06-20 08:00 | 2023-06-26 17:00 | -115 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02140 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-06-20 08:00 | 2023-06-21 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02145 | MLJ | OG6 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-06-22 08:00 | 2023-06-28 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-02150 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 2023-06-20 08:00 | 2023-06-26 17:00 | -110 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02205 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Switchboards - 2nd Floor | 15 | 2 | 2022-12-23 08:00 | 2023-03-07 12:00 | -78 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02210 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install ACTTS - 2nd Floor | 5 | 1 | 2022-12-23 08:00 | 2023-03-08 12:00 | -78 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02215 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 12 | 2022-11-15 08:00 | 2023-03-24 12:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02220 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards - 2nd Floor | 5 | 3 | 2022-12-22 08:00 | 2023-03-28 17:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02225 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 20 | 20 | 2023-03-29 08:00 | 2023-04-25 17:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02235 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-04-26 08:00 | 2023-05-02 17:00 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02240 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 5 | 5 | 2023-07-10 08:00 | 2023-07-14 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02270 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Equipment - 2nd Floor | 5 | 5 | 2023-07-07 08:00 | 2023-07-13 17:00 | -61 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02245 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 5 | 5 | 2023-05-03 08:00 | 2023-05-09 17:00 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02275 | MLJ | OG6 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 6 | 6 | 2023-06-29 08:00 | 2023-07-07 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02255 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-06-29 08:00 | 2023-06-30 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02260 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 5 | 2023-06-29 08:00 | 2023-07-06 17:00 | -117 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02230 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 5 | 2023-06-22 08:00 | 2023-06-28 17:00 | -117 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02280 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 5 | 5 | 2023-07-14 08:00 | 2023-07-20 17:00 | -52 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02250 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull CON-ED Feeder Cable - Cellar to Switchgear - 2nd Floor | 20 | 0 | 2023-02-15 08:00 | 2023-02-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-02265 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-04-04 13:00 | 2023-04-11 12:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02535 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG6 | 5 | 5 | 2023-08-14 08:00 | 2023-08-18 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02515 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - OG6 | 5 | 5 | 2023-07-27 08:00 | 2023-08-02 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02530 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - OG6 | 4 | 4 | 2023-08-08 08:00 | 2023-08-11 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02505 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - OG6 | 5 | 5 | 2023-07-17 08:00 | 2023-07-21 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02510 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test - OG6 | 3 | 3 | 2023-07-24 08:00 | 2023-07-26 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02525 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing - OG6 | 14 | 14 | 2023-07-25 08:00 | 2023-08-11 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02520 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-in's to Exisiting | 3 | 3 | 2023-08-03 08:00 | 2023-08-07 17:00 | -123 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02005 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | -25 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02010 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 5 | 4 | 2022-08-01 08:00 | 2023-03-02 17:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02020 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting Cellar | 4 | 4 | 2023-03-03 08:00 | 2023-03-08 17:00 | -12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02025 | [8 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 2021-11-22 | 2021-12-09 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02015 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 20 | 8 | 2022-08-01 08:00 | 2023-03-08 17:00 | -28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02030 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 18 | 18 | 2023-03-09 08:00 | 2023-04-03 17:00 | -12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02050 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02055 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-04-04 08:00 | 2023-04-10 17:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02065 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-04-11 08:00 | 2023-04-17 17:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02035 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 7 | 7 | 2023-03-09 08:00 | 2023-03-17 17:00 | -28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02040 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 2023-03-20 08:00 | 2023-03-21 17:00 | -25 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02060 | FIVE STAR | OG1 | CORE DRILL | [5 empty] | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 15 | 0 | 2022-07-22 | 2022-11-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02045 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) - Cellar | 2 | 1 | 2023-02-01 08:00 | 2023-03-03 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02070 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -28 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02125 | FIVE STAR | OG1 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 2022-08-01 | 2022-10-31 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02135 |  | OG1 | [6 empty] | Install Pull Boxes - 1st Floor | 4 | 0 | 2022-11-01 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02105 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 11 | 2 | 2022-08-01 08:00 | 2023-03-01 09:36 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02110 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 6 | 6 | 2023-03-01 09:36 | 2023-03-09 09:36 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02115 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 2023-03-09 09:36 | 2023-03-13 09:36 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02130 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-03-13 09:36 | 2023-03-15 09:36 | 19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02120 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 2023-04-18 08:00 | 2023-04-24 17:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02140 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-03-09 09:36 | 2023-03-13 09:36 | -23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02145 | MLJ | OG1 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-03-13 09:36 | 2023-03-20 09:36 | -23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-02150 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 2023-03-09 09:36 | 2023-03-16 09:36 | -21 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02205 | FIVE STAR | OG1 | [6 empty] | Install Switchboards - 2nd Floor | 12 | 0 | 2022-06-10 | 2022-11-02 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02210 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install ACTTS - 2nd Floor | 4 | 0 | 2022-06-10 | 2023-02-27 11:12 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02215 | FIVE STAR | OG1 | [6 empty] | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 18 | 0 | 2022-08-01 08:00 | 2022-11-15 15:24 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02220 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards - 2nd Floor | 4 | 0 | 2022-11-01 | 2023-02-27 11:12 | -25 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02225 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 18 | 3 | 2022-11-01 | 2023-03-06 11:12 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02235 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 6 | 6 | 2023-03-06 11:12 | 2023-03-14 11:12 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02240 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 2023-04-25 08:00 | 2023-04-28 17:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02245 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 2023-03-15 09:36 | 2023-03-22 09:36 | 19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02250 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 4 | 4 | 2023-03-14 11:12 | 2023-03-20 11:12 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02255 | MLJ | OG1 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 4 | 4 | 2023-03-06 11:12 | 2023-03-10 11:12 | -17 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02265 | FIVE STAR | OG1 | [6 empty] | Tag & Terminate Switchgear Equipment | 5 | 0 | 2022-12-22 08:00 | 2022-12-27 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02275 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-03-20 11:12 | 2023-03-22 11:12 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02230 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 5 | 2023-03-13 09:36 | 2023-03-20 09:36 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02280 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 2 | 2 | 2023-03-22 09:36 | 2023-03-24 09:36 | 31 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02260 | FIVE STAR | OG1 | [6 empty] | Pull CON-ED Feeder Cable - Cellar to OG1 Switchgear - 2nd Floor | 20 | 0 | 2022-12-01 08:00 | 2022-12-12 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-02270 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02530 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - OG1 | 4 | 4 | 2023-08-14 08:00 | 2023-08-17 17:00 | -111 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02535 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - OG1 | 5 | 5 | 2023-08-18 08:00 | 2023-08-24 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02515 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - OG1 | 5 | 5 | 2023-04-26 08:00 | 2023-05-02 17:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02505 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - OG1 | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02520 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-Ins to Existing | 3 | 3 | 2023-05-03 08:00 | 2023-05-05 17:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02510 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test | 2 | 2 | 2023-04-24 08:00 | 2023-04-25 17:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02525 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 2023-07-31 08:00 | 2023-08-17 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02115 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull CON-ED Feeder Cable - 31st St. to SG3 Cellar | 10 | 10 | 2023-06-26 08:00 | 2023-07-10 17:00 | -120 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02105 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull Feeder Cable - SG3 Switchgear to SG7 Foundation | 10 | 10 | 2023-06-26 08:00 | 2023-07-10 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02120 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull CON-ED Feeder Cable - 31st St. to SG7 Foundation (for SG2) | 5 | 5 | 2023-06-19 08:00 | 2023-06-23 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02130 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull Generator Feeder Cable from SG7 to SG3 Switchgear | 10 | 10 | 2023-06-26 08:00 | 2023-07-10 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02125 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull Feeder Cable from SG7 to SG2 | 10 | 10 | 2023-04-21 08:00 | 2023-05-04 17:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02135 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull Feeder Cable from SG7 to SG1 | 5 | 5 | 2023-06-30 13:00 | 2023-07-10 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.2 | SGS-02110 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull CON-ED Feeder Cable - 31st St. to SG7 Foundation (for SG1) | 5 | 5 | 2023-06-12 08:00 | 2023-06-16 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.3 | SGS-02205 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 2023-09-14 08:00 | 2023-09-20 17:00 | -110 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.3 | SGS-02210 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Furnish & Install Site Lighting Conduit | 10 | 10 | 2023-09-21 08:00 | 2023-10-04 17:00 | -110 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.3 | SGS-02215 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Pull Site Lighting Wire | 5 | 5 | 2023-10-05 08:00 | 2023-10-11 17:00 | -110 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.3 | SGS-02220 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Install Site Lighting Fixtures & Terminate | 10 | 10 | 2023-10-12 08:00 | 2023-10-26 17:00 | -110 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-02015 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -38 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-02005 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Temporary Lighting & Temporary Power for SG7 | 5 | 2 | 2021-11-26 | 2023-03-01 10:00 | -59 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-02010 |  | SG7 | [6 empty] | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 20 | 0 | 2022-05-08 | 2022-12-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-02025 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 2 | 2023-03-01 08:00 | 2023-03-02 17:00 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-02020 |  | SG7 | [6 empty] | Install Pull Box - Foundation | 2 | 0 | 2022-11-01 | 2022-11-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02130 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 5 | 5 | 2023-03-13 10:00 | 2023-03-20 10:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02135 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 1st Floor | 5 | 1 | 2023-02-01 | 2023-03-09 17:00 | -26 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02120 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 5 | 5 | 2023-03-06 10:00 | 2023-03-13 10:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02140 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment (Motorized Dampers/FO Pump/EUH) - 1st Floor | 5 | 5 | 2023-03-24 13:00 | 2023-03-31 12:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02160 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 1st Floor | 2 | 2 | 2023-03-31 13:00 | 2023-04-04 12:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02155 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 2023-03-20 10:00 | 2023-03-22 10:00 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02110 | FIVE STAR | SG7 | [6 empty] | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 2022-10-03 08:00 | 2022-12-15 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02115 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduits - 1st Floor | 15 | 5 | 2022-08-23 08:00 | 2023-03-06 10:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02125 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 5 | 3 | 2023-02-01 | 2023-03-08 15:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02145 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 2023-03-17 13:00 | 2023-03-22 12:00 | -32 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02105 | [8 empty] | Install In-slab Conduits - 1st floor slab | 5 | 0 | 2022-05-10 | 2022-06-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02165 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate FIre Alarm Equipment - 2nd Floor | 5 | 5 | 2023-03-20 10:00 | 2023-03-27 10:00 | -24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02150 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 2023-03-08 15:00 | 2023-03-10 15:00 | -27 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02210 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 10 | 1 | 2022-10-03 08:00 | 2023-02-27 17:00 | -21 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02225 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire for Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 2023-06-21 13:00 | 2023-07-06 12:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02215 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduits - 2nd Floor | 15 | 8 | 2023-01-02 08:00 | 2023-06-21 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02230 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-02-01 08:00 | 2023-06-28 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02235 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 2nd Floor | 5 | 5 | 2023-06-21 13:00 | 2023-06-28 12:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02220 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 5 | 5 | 2023-06-28 13:00 | 2023-07-06 12:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02240 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - 2nd Floor | 5 | 5 | 2023-06-28 13:00 | 2023-07-06 12:00 | -106 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02205 |  | SG7 | [6 empty] | Install In-slab Conduits - 2nd floor roof slab | 2 | 0 | 2022-08-23 08:00 | 2022-09-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02245 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 2 | 2 | 2023-06-28 13:00 | 2023-06-30 12:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02255 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Terminate all Mech. & Plumbing Equipment at Panel - 2nd Floor | 5 | 5 | 2023-07-14 13:00 | 2023-07-21 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02250 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Fire Alarm Control Panel (Incl. Telephone Lines) - 2nd Floor | 2 | 2 | 2023-03-22 10:00 | 2023-03-24 10:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02260 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Instal ACTTS (ATS Room) - 2nd Floor | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02265 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Fire Alarm Equipment - 2nd Floor | 5 | 5 | 2023-07-06 13:00 | 2023-07-13 12:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02270 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Grounding & Ground Equipment | 3 | 3 | 2023-05-26 08:00 | 2023-05-31 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02275 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull SG3 Feeder Cable from Foundation & Terminate ACTTS/GCB - 2nd Floor | 5 | 5 | 2023-07-11 08:00 | 2023-07-17 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-02280 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install ACTTS & Generator Circuit Breaker (GCB) for SG3 - 2nd Floor | 2 | 2 | 2023-05-01 08:00 | 2023-05-02 17:00 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02320 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG1 Feeder Conduit & Racks - 2nd Floor | 15 | 15 | 2023-05-19 08:00 | 2023-06-09 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02305 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG1 Switchboards - 2nd Floor | 5 | 5 | 2023-05-05 08:00 | 2023-05-11 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02310 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG1 ACTTS - 2nd Floor | 5 | 5 | 2023-05-12 08:00 | 2023-05-18 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02315 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG1 Panelboards - 2nd Floor | 10 | 10 | 2023-05-19 08:00 | 2023-06-02 17:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02330 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate SG1 Switchgear Equipment - 2nd Floor | 2 | 2 | 2023-07-10 13:00 | 2023-07-12 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02335 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate SG1 Panelboards - 2nd Floor | 2 | 2 | 2023-07-12 13:00 | 2023-07-14 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.1 | SG7-02325 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull CON-ED Feeder Cable to SG1 Equipment - Foundation to 2nd Floor - 2nd Floor | 10 | 10 | 2023-06-19 08:00 | 2023-06-30 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02365 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG2 Feeder Conduit & Racks - 2nd Floor | 15 | 15 | 2023-05-26 08:00 | 2023-06-16 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02350 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG2 Switchboards - 2nd Floor | 5 | 5 | 2023-05-12 08:00 | 2023-05-18 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02355 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG2 ACTTS - 2nd Floor | 5 | 5 | 2023-05-19 08:00 | 2023-05-25 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02360 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install SG2 Panelboards - 2nd Floor | 10 | 10 | 2023-05-26 08:00 | 2023-06-09 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02375 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate SG2 Switchgear Equipment - 2nd Floor | 2 | 2 | 2023-07-12 13:00 | 2023-07-14 12:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02380 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate SG2 Panelboards - 2nd Floor | 2 | 2 | 2023-07-14 13:00 | 2023-07-18 12:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2.2 | SG7-02370 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull CON-ED Feeder Cable to SG2 Equipment - Foundation to 2nd Floor - 2nd Floor | 10 | 10 | 2023-06-26 08:00 | 2023-07-10 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02405 | WELKIN | SG7 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator SG2 - Roof | 1 | 1 | 2023-03-22 08:00 | 2023-03-22 17:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02415 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install & Wire Generator SG1 - Roof | 10 | 10 | 2023-03-24 08:00 | 2023-04-06 17:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02435 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Branch Conduit - Roof | 5 | 5 | 2023-06-05 08:00 | 2023-06-09 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02440 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Branch Wiring - Roof | 5 | 5 | 2023-06-12 08:00 | 2023-06-16 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02410 | WELKIN | SG7 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator SG1 - Roof | 1 | 1 | 2023-03-23 08:00 | 2023-03-23 17:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02420 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install & Wire Generator SG2 - Roof | 10 | 10 | 2023-04-07 08:00 | 2023-04-20 17:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02445 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 3 | 3 | 2023-06-28 13:00 | 2023-07-03 12:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02460 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Smoke Detection/Fire Alarm Equipment - Roof | 2 | 2 | 2023-07-06 13:00 | 2023-07-10 12:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02465 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Receptacles - Roof | 3 | 3 | 2023-06-30 13:00 | 2023-07-06 12:00 | -96 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02455 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Light/Emergency Fixtures - Roof | 5 | 5 | 2023-07-06 13:00 | 2023-07-13 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02425 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Lightning protection Air terminals - Roof | 5 | 5 | 2023-06-06 08:00 | 2023-06-12 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02470 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Grounding & Ground Equipment - Roof | 2 | 2 | 2023-06-13 08:00 | 2023-06-14 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02450 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Pull Fire Alarm Wiring - Roof | 2 | 2 | 2023-06-28 13:00 | 2023-06-30 12:00 | -96 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02480 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Terminate Light Fixtures - Roof | 5 | 5 | 2023-07-13 13:00 | 2023-07-20 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02475 | MLJ | SG7 | FIRESTOPPING | Interior | NEW BUILDINGS |  |  |  | Install Firestopping | 4 | 4 | 2023-07-03 08:00 | 2023-07-07 17:00 | -97 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02485 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Tag & Terminate Fire Alarm Equipment - Roof | 2 | 2 | 2023-07-10 13:00 | 2023-07-12 12:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02495 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Panelboard - Roof | 2 | 2 | 2023-05-19 08:00 | 2023-05-22 17:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02430 | WELKIN | SG7 | GENERATOR | Interior | NEW BUILDINGS |  |  |  | Rig Generator SG3 - Roof | 1 | 1 | 2023-05-19 08:00 | 2023-05-19 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02490 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install & Wire Generator SG3 - Roof | 10 | 10 | 2023-05-22 08:00 | 2023-06-05 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02500 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Feeder Conduit & Pull Cable - Roof | 10 | 10 | 2023-05-23 08:00 | 2023-06-06 17:00 | -81 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-02505 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Terminate Panelboards - Roof | 1 | 1 | 2023-06-07 08:00 | 2023-06-07 17:00 | -81 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02625 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - SG7 | 5 | 5 | 2023-08-29 10:00 | 2023-09-06 10:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02615 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator SG1 - SG7 | 2 | 2 | 2023-07-28 13:00 | 2023-08-01 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02605 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Perform Electrical Inspections for SG7 | 5 | 5 | 2023-07-21 13:00 | 2023-07-28 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02610 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Testing - SG7 | 14 | 14 | 2023-08-09 10:00 | 2023-08-29 10:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02620 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator SG2 - SG7 | 2 | 2 | 2023-08-01 13:00 | 2023-08-03 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02630 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Provide Load Bank & Perform Acceptance Testing for Generator SG3 - SG7 | 2 | 2 | 2023-08-03 13:00 | 2023-08-07 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02635 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Notify NYCHA of Generator Acceptance Testing- SG7 | 15 | 15 | 2023-07-07 13:00 | 2023-07-28 12:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6.1 | SG7-02650 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Perform 3rd Party Testing of SG1 Switchgear - SG7 | 2 | 2 | 2023-07-28 13:00 | 2023-08-01 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6.1 | SG7-02655 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Energize SG1 Switchgear Equipment - SG7 | 4 | 4 | 2023-07-28 13:00 | 2023-08-03 12:00 | -105 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6.1 | SG7-02660 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Start-Up SG1 Switchgear/Generator - SG7 | 4 | 4 | 2023-08-23 10:00 | 2023-08-29 10:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6.2 | SG7-02675 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Energize SG2 Switchgear Equipment - SG7 | 4 | 4 | 2023-08-01 13:00 | 2023-08-07 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6.2 | SG7-02680 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Perform 3rd Party Testing of SG2 Switchgear - SG7 | 2 | 2 | 2023-07-28 13:00 | 2023-08-01 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6.2 | SG7-02685 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Start-Up SG2 Switchgear/Generator - SG7 | 4 | 4 | 2023-08-14 13:00 | 2023-08-18 12:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02005 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -36 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02010 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 6 | 2023-03-06 08:00 | 2023-03-13 17:00 | -36 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02015 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 4 | 2022-06-15 | 2023-03-13 17:00 | -36 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02025 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - Cellar | 5 | 5 | 2023-04-13 15:00 | 2023-04-20 15:00 | -40 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02045 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02055 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 3 | 3 | 2023-04-20 15:00 | 2023-04-25 15:00 | -40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02065 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 3 | 3 | 2023-04-25 15:00 | 2023-04-28 15:00 | -40 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02040 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 5 | 3 | 2023-01-02 08:00 | 2023-04-25 10:00 | -36 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02050 | FIVE STAR | SG2 | CORE DRILL | Interior | EXISTING BUILDINGS |  |  |  | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 15 | 12 | 2022-06-15 | 2023-03-14 17:00 | -30 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02060 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) | 2 | 2 | 2023-03-15 13:00 | 2023-03-17 12:00 | -40 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02020 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit | 15 | 14 | 2023-01-02 08:00 | 2023-04-06 15:00 | -40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02035 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring | 5 | 5 | 2023-04-06 15:00 | 2023-04-13 15:00 | -40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02030 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 10 | 10 | 2023-03-14 08:00 | 2023-03-27 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02110 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pull/Splice Boxes - 1st Floor | 5 | 5 | 2023-03-15 08:00 | 2023-03-21 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02120 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-04-05 08:00 | 2023-04-06 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02125 | MLJ | SG2 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-04-07 08:00 | 2023-04-13 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02130 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 3 | 3 | 2023-03-29 08:00 | 2023-03-31 17:00 | -18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02135 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Feeder Cable from Cellar to 1st Floor - 1st Floor | 10 | 10 | 2023-03-22 08:00 | 2023-04-04 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02105 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 2023-04-20 15:00 | 2023-04-25 15:00 | -37 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-02115 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 5 | 5 | 2023-03-22 08:00 | 2023-03-28 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-02505 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-In's to Exisiting Equipment - SG2 | 5 | 5 | 2023-08-07 13:00 | 2023-08-14 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-02510 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - SG2 | 2 | 2 | 2023-04-28 15:00 | 2023-05-02 15:00 | -40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02005 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 2023-03-27 08:00 | 2023-03-30 17:00 | -23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02010 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 6 | 2023-03-31 08:00 | 2023-04-07 17:00 | -23 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02020 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting - Cellar | 4 | 3 | 2022-06-06 | 2023-03-29 17:00 | -16 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02025 | [8 empty] | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 2022-06-07 | 2022-06-24 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02015 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 20 | 12 | 2022-09-30 08:00 | 2023-04-11 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02030 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 2023-04-10 08:00 | 2023-05-05 17:00 | -23 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02050 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02055 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 5 | 5 | 2023-05-08 08:00 | 2023-05-12 17:00 | -23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02065 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 2023-05-15 08:00 | 2023-05-19 17:00 | -23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02035 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 7 | 7 | 2023-04-12 08:00 | 2023-04-20 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02040 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 2023-04-21 08:00 | 2023-04-24 17:00 | -50 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02060 | FIVE STAR | SG3 | CORE DRILL | Interior | EXISTING BUILDINGS |  |  |  | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 15 | 1 | 2022-06-01 | 2023-03-27 15:00 | -57 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02045 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - Cellar | 5 | 5 | 2023-05-03 08:00 | 2023-05-09 17:00 | -61 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02115 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 1 | 2022-10-15 | 2023-03-27 15:00 | -57 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02135 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pull Boxes - 1st Floor | 4 | 0 | 2022-10-23 | 2023-03-29 15:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02105 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 12 | 12 | 2023-04-21 08:00 | 2023-05-08 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02110 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 1st Floor | 6 | 6 | 2023-05-09 08:00 | 2023-05-16 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02120 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 2023-05-17 08:00 | 2023-05-18 17:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02130 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 2023-05-19 08:00 | 2023-05-22 17:00 | -34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02125 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 2023-05-22 08:00 | 2023-05-26 17:00 | -23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02140 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-07-25 08:00 | 2023-07-26 17:00 | -120 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02145 | MLJ | SG3 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-07-27 08:00 | 2023-08-02 17:00 | -120 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-02150 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 5 | 5 | 2023-05-17 08:00 | 2023-05-23 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02205 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Switchboards - 2nd Floor | 10 | 10 | 2023-05-05 08:00 | 2023-05-18 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02210 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install ACTTS - 2nd Floor | 4 | 4 | 2023-06-13 08:00 | 2023-06-16 17:00 | -128 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02215 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 5 | 2022-10-17 08:00 | 2023-06-23 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02220 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards - 2nd Floor | 4 | 4 | 2023-06-26 08:00 | 2023-06-29 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02225 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 2nd Floor | 15 | 15 | 2023-06-30 08:00 | 2023-07-21 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02235 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - 2nd Floor | 5 | 5 | 2023-07-24 08:00 | 2023-07-28 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02240 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 2023-07-31 08:00 | 2023-08-03 17:00 | -66 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02245 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 2023-07-31 08:00 | 2023-08-04 17:00 | -81 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02250 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Receptacles - 2nd Floor | 4 | 4 | 2023-07-31 08:00 | 2023-08-03 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02255 | MLJ | SG3 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Fire Stopping - 2nd Floor | 4 | 4 | 2023-07-24 08:00 | 2023-07-27 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02265 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Switchgear Equipment | 5 | 5 | 2023-08-04 08:00 | 2023-08-10 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02275 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Tag & Terminate Panelboards | 2 | 2 | 2023-08-11 08:00 | 2023-08-14 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02230 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Ground Equipment | 5 | 5 | 2023-06-30 08:00 | 2023-07-07 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02280 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Terminate Fire Alarm System | 2 | 2 | 2023-08-11 08:00 | 2023-08-14 17:00 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02260 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull CON-ED Feeder Cable - Cellar to SG-5 Switchgear - 2nd Floor | 10 | 10 | 2023-07-11 08:00 | 2023-07-24 17:00 | -120 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-02270 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 2023-07-25 08:00 | 2023-07-31 17:00 | -118 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02530 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Start-Up Generator/Switchgear - SG3 | 4 | 4 | 2023-09-08 08:00 | 2023-09-13 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02535 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Fire Alarm Operational & FDNY Acceptance Testing - SG3 | 5 | 5 | 2023-09-14 08:00 | 2023-09-20 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02515 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Energize Switchgear - SG3 | 5 | 5 | 2023-08-24 08:00 | 2023-08-30 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02505 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - SG3 | 5 | 5 | 2023-08-15 08:00 | 2023-08-21 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02520 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-Ins to Existing | 5 | 5 | 2023-08-31 08:00 | 2023-09-07 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02510 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform 3rd Party Test at SG3 | 2 | 2 | 2023-08-22 08:00 | 2023-08-23 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02525 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 2023-08-24 08:00 | 2023-09-13 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02005 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02010 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Bypass Connections - Cellar | 6 | 6 | 2023-06-20 08:00 | 2023-06-27 17:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02025 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 5 | 2023-06-28 08:00 | 2023-07-05 17:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02040 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - Cellar | 5 | 5 | 2023-08-02 10:00 | 2023-08-09 10:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02045 | [8 empty] | Link & Seal Conduit Sleeves - Cellar | 9 | 0 | 2021-10-22 | 2021-10-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02055 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Lighting Wiring - Cellar | 3 | 3 | 2023-07-20 08:00 | 2023-07-24 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02060 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 4 | 4 | 2023-07-25 08:00 | 2023-07-28 17:00 | -108 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02015 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Heat Trace for Plumbing Lines - Cellar | 5 | 3 | 2023-01-02 08:00 | 2023-08-11 15:00 | -113 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02030 | FIVE STAR | SG1 | CORE DRILL | Interior | EXISTING BUILDINGS |  |  |  | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 15 | 14 | 2022-05-15 | 2023-06-30 12:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02020 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Panelboards (Misc.) | 2 | 2 | 2023-06-20 08:00 | 2023-06-21 17:00 | -104 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02035 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - Cellar | 15 | 14 | 2023-01-02 08:00 | 2023-07-26 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02065 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Branch Wiring - Cellar | 5 | 5 | 2023-07-26 10:00 | 2023-08-02 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02050 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 10 | 10 | 2023-07-06 08:00 | 2023-07-19 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02105 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pull/Splice Boxes - 1st Floor | 4 | 4 | 2023-06-30 13:00 | 2023-07-07 12:00 | -105 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02110 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Supply Power to Exterior Building Signage | 2 | 2 | 2023-07-21 13:00 | 2023-07-25 12:00 | -105 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02120 | MLJ | SG1 | FIRESTOPPING | Interior | EXISTING BUILDINGS |  |  |  | Install Firestopping - 1st Floor | 5 | 5 | 2023-07-31 08:00 | 2023-08-04 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02115 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 3 | 3 | 2023-07-14 13:00 | 2023-07-19 12:00 | -66 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02130 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Pull Feeder Cable from Cellar to 1st Floor - 1st Floor | 10 | 10 | 2023-07-07 13:00 | 2023-07-21 12:00 | -105 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02125 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 2023-08-09 10:00 | 2023-08-14 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-02135 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Branch Conduit - 1st Floor | 5 | 5 | 2023-07-07 13:00 | 2023-07-14 12:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-02505 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Tie-In's to Exisiting Equipment - SG1 | 5 | 5 | 2023-08-16 10:00 | 2023-08-23 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-02510 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Electrical Inspections - SG1 | 2 | 2 | 2023-08-14 10:00 | 2023-08-16 10:00 | -113 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02005 | [8 empty] | File for Fence Permit | 10 | 0 | 2020-09-25 | 2020-09-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02010 | [8 empty] | DOB Issue Fence Permit (OG5 & 6 require L2 forms) | 20 | 0 | 2020-09-28 | 2021-01-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03005 | [8 empty] | File for New buildings Permit - SG-6 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03010 | [8 empty] | DOB Issue New buildings Permit - SG-6 | 20 | 0 | 2020-12-01 | 2021-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01015 | [8 empty] | Install Overhead Protection - NA | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01020 | [6 empty] | 31-1900 |  | Install Tree Protection | 10 | 0 | 2020-11-03 | 2020-11-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01025 | [8 empty] | Remove Trees | 2 | 0 | 2021-01-14 | 2021-01-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01000 | [8 empty] | Remove Curbs And Existing Fencing | 10 | 0 | 2020-12-16 | 2021-01-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01035 | [8 empty] | Install Erosion Control | 5 | 0 | 2021-03-19 | 2021-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01010 | [8 empty] | Set Up Yard and Staging | 5 | 0 | 2021-02-25 08:00 | 2021-03-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01045 | [8 empty] | Clear & Grub (South Area left for Residence Use) | 5 | 0 | 2021-01-11 | 2022-01-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01050 | [8 empty] | Scrape & Store Topsoil | 10 | 0 | 2021-01-18 | 2021-03-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01055 | [8 empty] | Soil Testing | 10 | 0 | 2021-02-11 | 2021-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01060 | [6 empty] | 02-2000 |  | Demo Playgrounds And Misc Site Furniture (South Area left for Residence Use) | 5 | 0 | 2021-01-11 | 2021-07-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01065 | [8 empty] | Remove Retaining Walls | 10 | 0 | 2021-01-18 | 2022-01-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01070 | [8 empty] | Install Deep Wells For Dewatering - N/R | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01075 | [8 empty] | Install Piping For Deep Wells - N/R | 5 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01080 | [8 empty] | Install Discharge Connection For Dewatering - N/R | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01085 | [8 empty] | Run Electric For Dewatering - N/R | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01105 | [8 empty] | Excavate for HW & CW - SG6 --> SG4 | 10 | 0 | 2021-08-15 | 2021-08-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01110 | [8 empty] | Install HW & CW piping - SG6--> SG4 | 15 | 0 | 2021-09-09 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01115 | WELKIN | [7 empty] | Test HW & CW Piping - SG6 --> SG4 | 10 | 0 | 2021-11-25 08:00 | 2021-11-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01120 | [8 empty] | Backfill HW & CW Piping - SG6 --> SG4 | 5 | 0 | 2022-04-27 | 2022-04-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01125 | [8 empty] | Excavate for Steam - SG6 --> SG4 | 10 | 0 | 2021-08-16 08:00 | 2021-08-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01130 | [8 empty] | Install Steam piping - SG6--> SG4 | 10 | 0 | 2021-09-26 | 2021-10-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01135 | [8 empty] | Test Steam Piping - SG6 --> SG4 | 4 | 0 | 2021-11-26 08:00 | 2021-11-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01140 | [8 empty] | Backfill Steam Piping - SG6 --> SG4 | 5 | 0 | 2022-05-26 | 2022-05-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01150 | [8 empty] | Excavate for Electric SG6--> SG4 | 10 | 0 | 2021-06-07 | 2021-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01155 | [8 empty] | Install Electrical Conduit SG6--> SG4 | 10 | 0 | 2021-06-14 | 2021-08-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01160 | [8 empty] | Encase conduit in concrete SG6-->SG4 | 5 | 0 | 2021-06-25 08:00 | 2021-11-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01165 | [8 empty] | Backfill Electrical SG6 --> SG4 | 5 | 0 | 2021-06-30 08:00 | 2021-09-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01175 | MLJ | SGN | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-SGN | Excavate for gas SG6 --> W33rd Street | 5 | 0 | 2022-09-20 | 2022-09-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01180 | NATIONAL GRID | SGN |  | Utilities | SITE |  |  |  | Install Gas SG6--> W33rd Street | 2 | 2 | 2023-02-14 | 2023-02-28 17:00 | 16 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01185 | MLJ | SGN | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-SGN | Backfill gas SG6 --> W33rd Street | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 55 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01205 | [8 empty] | Excavate for Electric SG4--> MH | 3 | 0 | 2021-08-24 08:00 | 2021-09-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01210 | [8 empty] | Install Electrical Conduit SG4--> MH | 2 | 0 | 2021-09-22 08:00 | 2021-10-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01215 | [8 empty] | Encase conduit in concrete SG4--> MH | 2 | 0 | 2021-09-30 | 2021-10-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01220 | [8 empty] | Backfill Elecrtical SG4 --> MH | 2 | 0 | 2021-10-06 | 2021-10-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01230 | [8 empty] | Excavate for Electric SG6 -> SG5 | 10 | 0 | 2021-07-20 08:00 | 2021-08-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01235 | [8 empty] | Install Electrical Conduit SG6--> SG5 | 5 | 0 | 2021-06-14 | 2021-08-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01240 | [8 empty] | Encase conduit in concrete SG6--> SG5 | 3 | 0 | 2021-07-26 08:00 | 2021-09-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01245 | [8 empty] | Backfill Elecrtical SG6 --> SG5 | 5 | 0 | 2021-08-02 08:00 | 2021-09-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01255 | [8 empty] | Excavate for Electric SG5--> MH | 3 | 0 | 2021-09-10 08:00 | 2021-09-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01260 | [8 empty] | Install Electrical Conduit SG5--> MH | 2 | 0 | 2021-09-13 08:00 | 2021-09-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01265 | [8 empty] | Encase conduit in concrete SG5--> MH | 2 | 0 | 2021-10-02 | 2021-10-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01270 | [8 empty] | Backfill Elecrtical SG5 --> MH | 2 | 0 | 2021-10-07 | 2021-10-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01275 | [8 empty] | Excavate for Steam & HW SG4--> SG5 | 15 | 0 | 2021-09-20 08:00 | 2021-09-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01280 | [8 empty] | Install Steam and HW piping SG4--> SG5 | 20 | 0 | 2021-09-26 | 2022-06-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01285 | [8 empty] | Test Steam & HW Piping SG4--> SG5 | 8 | 0 | 2022-06-13 | 2022-06-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01290 | [8 empty] | Backfill Steam & HW Piping SG4 --> SG5 | 10 | 0 | 2022-06-20 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01305 | MLJ | SGN | Excavation |  |  | PLAYGROUND |  |  | Excavate for water line to drinking fountain SGN --> Water Main W32nd Street | 2 | 0 | 2022-09-22 | 2022-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01310 |  | SGN |  |  |  | PLAYGROUND |  |  | Install water line to drinking fountain SGN --> Water Main W32nd Street | 5 | 0 | 2022-11-04 | 2022-11-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01315 |  | SGN |  |  |  | PLAYGROUND |  |  | Tap water main for drinking fountain water line SGN --> Water Main W32nd Street | 2 | 0 | 2022-11-01 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01320 | MLJ | SGN | BACKFILL |  |  | BACKFILL SITE |  |  | Backfill water line drinking fountain SGN --> Water Main W32nd Street | 2 | 0 | 2022-12-05 | 2022-12-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01330 | MLJ | SGN | Excavation |  |  | PLAYGROUND |  |  | Excavate for water line to water play items SGN --> Water Main W33rd Street | 2 | 0 | 2022-09-22 | 2022-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01335 |  | SGN |  |  |  | PLAYGROUND |  |  | Install water line and RPZ box for water play items SGN --> Water Main W33rd Street | 5 | 0 | 2022-12-04 | 2022-12-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01340 |  | SGN |  |  |  | PLAYGROUND |  |  | Tap water main for drinking fountain water line SGN --> Water Main W33rd Street | 2 | 0 | 2022-12-05 | 2022-12-06 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01345 | MLJ | SGN | BACKFILL | Utilities | SITE | BACKFILL SITE |  |  | Backfill water line drinking fountain SGN --> Water Main W33rd Street | 2 | 2 | 2023-02-06 | 2023-02-28 17:00 | 54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01355 | MLJ | SGN | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-SGN | Excavate for Sanitary sewer SG6 --> W32nd Street | 3 | 0 | 2022-08-29 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01360 |  | SGN | UG PIPE | [5 empty] | Install sanitary pipe SG6 --> Sanitary Sewer W32nd Street | 2 | 0 | 2022-08-31 | 2022-09-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01365 | MLJ | SGN | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-SGN | Backfill Sanitary Sewer SG6 --> Sanitary Sewer W32nd Street | 2 | 2 | 2023-03-06 08:00 | 2023-03-07 17:00 | 51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01375 | MLJ | SGN | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 10 & 11 and piping / SG4 yard pumps tie in | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01380 | MLJ | SGN | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 10 & 11 and piping | 2 | 2 | 2023-03-08 08:00 | 2023-03-09 17:00 | 51 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01385 | MLJ | SGN | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 12, 13, 14, 15 and piping | 10 | 0 | 2022-08-29 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01390 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 12, 13, 14, 15 and piping | 3 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01405 | MLJ | SGN | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 5, 6, 7, 18, 19 and piping / cellar pump tie in | 12 | 0 | 2022-08-23 | 2022-08-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01410 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 5, 6, 7, 18, 19 and piping | 5 | 0 | 2022-08-30 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01420 | MLJ | SGN | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 22 and piping / SG6 storm tie in | 3 | 0 | 2022-10-25 | 2022-10-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01425 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 22 and piping | 2 | 0 | 2022-10-28 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01435 | [8 empty] | Excavate and Install Area Drains 1, 2, 4, 9 and piping | 10 | 0 | 2022-06-06 | 2022-06-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01440 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 1, 2, 4, 9 and piping | 3 | 0 | 2022-06-27 | 2022-07-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01450 | MLJ | SGN | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 16, 17, and piping | 5 | 0 | 2022-09-12 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01455 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 16, 17, and piping | 2 | 0 | 2022-09-18 | 2022-09-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01460 | MLJ | SGN | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 3 and piping / yard pumps tie in | 3 | 0 | 2022-09-20 | 2022-10-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01465 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 3, and piping | 2 | 0 | 2022-01-26 | 2022-10-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01470 | MLJ | SGN | Excavation | [5 empty] | Excavate and Install piping - yard pumps tie in to sewer | 2 | 0 | 2022-10-26 | 2022-10-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01475 | MLJ | SGN | BACKFILL | [5 empty] | Backfill piping - yard pumps tie in to sewer | 1 | 0 | 2022-10-28 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01480 | MLJ | SGN | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGN | Excavate and Install Area Drains 8 and piping / SG5 cellar pump tie in | 2 | 0 | 2022-09-12 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01485 | MLJ | SGN | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGN | Backfill Area Drains 3, and piping | 1 | 0 | 2022-09-16 | 2022-09-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01505 | MLJ | SGN | Excavation |  |  | EXC RETAINING |  |  | Excavate for retaining wall --> SGN | 2 | 0 | 2022-08-06 | 2022-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01510 | MLJ | SGN | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-SGN | Form Retaining wall footing --> SGN | 2 | 0 | 2022-08-11 | 2022-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01515 |  | SGN | REBAR | [5 empty] | Rebar Retaining wall footing --> SGN | 2 | 0 | 2022-08-15 | 2022-08-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01520 | MLJ | SGN | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall footing --> SGN | 1 | 0 | 2022-08-16 | 2022-08-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01525 |  | SGN | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall footing --> SGN | 1 | 0 | 2022-08-19 | 2022-08-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01530 | MLJ | SGN | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-SGN | Form Retaining wall --> SGN | 3 | 0 | 2022-08-22 | 2022-08-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01535 |  | SGN | REBAR | [5 empty] | Rebar Retaining wall --> SGN | 3 | 0 | 2022-08-23 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01540 | MLJ | SGN | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall --> SGN | 1 | 0 | 2022-08-25 | 2022-08-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01545 |  | SGN | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall --> SGN | 1 | 0 | 2022-08-27 | 2022-08-27 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01605 | JMC | SGN | CURBS | Restoration | SITE |  |  |  | Install Street Curbs --> SGN | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01610 | JMC | SGN | SIDEWALKS | Restoration | SITE |  |  |  | Install sidewalks --> SGN | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01615 | MLJ | SGN | CURBS | Restoration | SITE |  |  |  | Install curb around play area --> SGN | 5 | 5 | 2023-05-15 08:00 | 2023-05-19 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01620 | MLJ | SGN |  | Restoration | SITE | PLAYGROUND |  |  | Install Safety Surface --> SGN | 5 | 5 | 2023-05-22 08:00 | 2023-05-26 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01625 | MLJ | SGN | Concrete | Restoration | SITE | SITE CONCRETE |  |  | Install site furniture concrete foundations --> SGN | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | -47 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01630 | JMC | SGN | COLORED CONCRETE | Restoration | SITE |  |  |  | Install integrally colored concrete walkways --> SGN | 20 | 15 | 2022-09-12 | 2023-06-19 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01635 | MLJ | SGN |  | Restoration | SITE | PLAYGROUND |  |  | Install Play area items --> SGN | 5 | 2 | 2023-02-07 | 2023-06-21 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01640 | MLJ | SGN |  | Restoration | SITE | PLAYGROUND |  |  | Install fence around play area --> SGN | 10 | 10 | 2023-06-22 08:00 | 2023-07-06 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01645 | ATLAS | SGN | SITE RESTORATION | Restoration | SITE |  |  |  | Install Fence at building --> SG6 | 5 | 5 | 2023-07-07 08:00 | 2023-07-13 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01650 | MLJ | SGN | SITE RESTORATION | Restoration | SITE |  |  |  | Place Site Furniture --> SGN | 10 | 10 | 2023-07-14 08:00 | 2023-07-27 17:00 | -47 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01675 | ASPEN | SGN | TOPSOIL | Restoration | SITE |  |  |  | Place topsoil --> SGN | 3 | 2 | 2022-10-05 | 2023-04-04 17:00 | 24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01680 | ASPEN | SGN |  | Restoration | SITE |  |  |  | Place trees and plantings --> SGN | 5 | 5 | 2023-04-05 08:00 | 2023-04-11 17:00 | 24 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01685 | ASPEN | SGN |  | Restoration | SITE |  |  |  | Place lawn --> SGN | 5 | 2 | 2022-10-12 | 2023-04-04 17:00 | 29 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01030 | [8 empty] | Form Plumbing Shafts & Ftgs Below Water Table --> SG6 | 10 | 0 | 2021-04-05 | 2021-04-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01035 | [8 empty] | Rebar Plumbing Shafts & Ftgs Below Water Table --> SG6 | 5 | 0 | 2021-04-08 | 2021-04-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01040 | MLJ | SG6 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG6 | Pour Plumbing Shafts & Ftgs Below Water Table --> SG6 | 2 | 0 | 2021-04-08 | 2021-04-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01045 | [8 empty] | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> SG6 | 5 | 0 | 2021-04-12 | 2021-04-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01025 | [8 empty] | Waterproof/Insulation Plumbing Shaft ----> SG6 - N/A | 5 | 0 | 2021-03-01 | 2021-03-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01005 | [8 empty] | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> SG6 | 5 | 0 | 2021-03-02 | 2021-03-31 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01020 | [8 empty] | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> SG6 | 3 | 0 | 2021-03-31 | 2021-03-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01055 |  |  | SG6 |  |  |  | 31-1400 | 31-1400-SG6 | Backfill Plumbing Shaft & Ftgs/Piers --> SG6 | 5 | 0 | 2021-04-16 | 2021-04-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01065 | [8 empty] | Excavate For Remaining Ftgs/Pier/Grade Beams --> SG6 | 10 | 0 | 2021-04-02 | 2021-05-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01070 |  | SG6 | FORMWORK |  |  | FORMWORK NB | 03-1000 | 03-1000-SG6 | Form Remaining Ftgs/Piers/Grade Beams --> SG6 | 10 | 0 | 2021-04-19 | 2021-07-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01075 | [8 empty] | Rebar Remaining Ftgs/Piers/Grade Beams --> SG6 | 10 | 0 | 2021-04-25 | 2021-07-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01080 | [8 empty] | Pour Remaining Ftgs/Piers/Grade Beams --> SG6 | 5 | 0 | 2021-07-13 | 2021-07-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01085 | [8 empty] | Strip Forms Remaining Ftgs/Piers/Grade Beams --> SG6 | 5 | 0 | 2021-07-14 | 2021-07-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01090 | [8 empty] | Install Remaining Steam Into SG6 (5' from the building) | 5 | 0 | 2021-09-26 | 2021-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01095 | [8 empty] | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> SG6 | 5 | 0 | 2021-05-06 | 2021-07-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01105 | [8 empty] | Install Structural Steel Framing - 1st Floor --> SG6 | 10 | 0 | 2021-08-03 | 2021-08-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01110 | [8 empty] | Install Metal Deck --> SG6 | 2 | 0 | 2021-08-12 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01115 | [8 empty] | Form Pour Strip Concrete Stair South Side ---> SG6 | 5 | 0 | 2021-12-06 08:00 | 2021-12-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01120 | [8 empty] | Install Metal Stairs --> SG6 | 2 | 0 | 2021-10-18 | 2021-12-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01125 |  | SG6 |  |  |  |  | 07-1100 | 07-1100-SG6 | Place Insulation Below First Floor --> SG6 | 5 | 0 | 2021-06-28 08:00 | 2021-07-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01130 | [8 empty] | Place WWF First Floor Slab --> SG6 | 2 | 0 | 2021-07-02 08:00 | 2021-07-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01135 | MLJ | SG6 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG6 | Pour First Floor Slab --> SG6 | 1 | 0 | 2021-07-13 08:00 | 2021-07-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01150 | [8 empty] | Form First Floor Concrete Walls First Face And Col Encasements--> SG6 | 3 | 0 | 2021-09-07 | 2021-09-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01155 | [8 empty] | Rebar First Floor Concrete Walls --> SG6 | 3 | 0 | 2021-09-09 08:00 | 2021-09-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01160 | [8 empty] | Form First Floor Concrete Walls 2nd Face --> SG6 | 5 | 0 | 2021-09-23 08:00 | 2021-10-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01165 | [8 empty] | Form, Rebar & Pour Concrete Pads 1st Floor --> SG6 | 6 | 0 | 2021-09-01 | 2021-09-06 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01170 | [8 empty] | Place WWF 2nd Floor Slab --> SG6 | 2 | 0 | 2021-10-06 | 2021-10-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01175 | MLJ | SG6 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG6 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements --> SG6 | 5 | 0 | 2021-10-08 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01180 | [8 empty] | Strip Forms First Floor Walls & Col Encasements --> SG6 | 3 | 0 | 2021-10-11 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01185 | [8 empty] | Form Concrete Pads 2nd Floor -->SG6 | 2 | 0 | 2022-02-08 | 2022-02-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01205 | [8 empty] | Place WWF Roof Slab --> SG6 | 2 | 0 | 2021-12-01 08:00 | 2021-12-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01210 | [8 empty] | Pour Roof Slab and 2nd Floor Conc Pads -->SG6 | 1 | 0 | 2021-12-03 08:00 | 2021-12-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01215 | [8 empty] | Strip Forms Concrete Pads 2nd Floor -->SG6 | 3 | 0 | 2022-02-09 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01225 | [8 empty] | Install Spray-On Fireproofing on St Stl --> SG6 | 5 | 0 | 2021-12-10 08:00 | 2021-12-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01230 | [8 empty] | Place CMU 1st, 2nd Floors and Roof --> SG6 | 20 | 0 | 2021-12-21 08:00 | 2022-04-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01240 | CCC | SG6 | [6 empty] | Install Stud Framing 1st, 2nd Floors and Roof --> SG6 | 5 | 0 | 2022-05-16 | 2022-07-01 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01245 | CCC | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Doors --> SG6 | 3 | 1 | 2022-10-12 | 2023-03-07 17:00 | 41 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01250 |  | SG6 | CAST STONE | [5 empty] | Install Cast Stone Panels --> SG6 | 1 | 0 | 2022-09-12 | 2022-10-14 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01255 | NAVILLUS | SG6 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulated Metal Panels/Louvers --> SG6 | 10 | 2 | 2022-06-20 | 2023-02-28 17:00 | -85 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01260 | [8 empty] | Install MEP Roof Penetrations & Drains - SG6 | 1 | 0 | 2022-03-15 | 2022-03-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01265 | TRIANGLE | SG6 | [6 empty] | Install Roofing --> SG6 | 15 | 0 | 2022-07-18 | 2022-10-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01270 | [8 empty] | Install Dunnage Gratings --> SG6 | 2 | 0 | 2021-08-18 08:00 | 2021-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01275 | [8 empty] | Install Brick Façade & Stone --> SG6 | 20 | 0 | 2022-04-22 | 2022-05-20 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01285 | MLJ | SG6 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD VENTS |  |  | Install Flood Vents And Small Louvers --> SG6 | 3 | 2 | 2023-02-07 | 2023-02-28 17:00 | 46 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01290 | [8 empty] | Install Stair And Roof Platform Railings --> SG6 | 5 | 0 | 2022-01-26 | 2022-02-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01295 | [8 empty] | Install Ladders --> SG6 | 3 | 0 | 2022-03-14 | 2022-03-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01305 | CCC | SG6 | [6 empty] | Install Sheetrock and Stucco --> SG6 | 10 | 0 | 2022-11-07 08:00 | 2022-11-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01310 |  | SG6 | FLOORING |  |  | CERAMIC |  |  | Install Ceramic Tile --> SG6 | 2 | 0 | 2022-11-18 | 2022-11-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01315 |  | SG6 | CEILING | [5 empty] | Install Acoustical Ceiling --> SG6 | 2 | 0 | 2022-11-17 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01320 | [8 empty] | Place Crystaline Waterproofing In Plumbing Shaft --> SG6 | 3 | 0 | 2022-02-16 | 2022-03-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01325 | [8 empty] | Paint All Areas --> SG6 | 15 | 0 | 2022-11-07 | 2022-12-09 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01330 | MLJ | SG6 | SIGNS | Interior | NEW BUILDINGS |  |  |  | Install Signs --> SG6 | 2 | 2 | 2023-03-27 08:00 | 2023-03-28 17:00 | 28 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01235 |  | SG6 | WATERPROOFING | [5 empty] | Install Waterproofing to Parapet --> SG6 | 3 | 0 | 2022-07-25 08:00 | 2022-07-29 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01280 | CCC | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Stucco Soffit --> SG6 | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | 38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 2021-11-28 08:00 | 2021-12-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-03005 | [8 empty] | Rough-In Plumbing - Plumbing Shaft | 10 | 0 | 2022-03-21 | 2022-06-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-03010 | [8 empty] | Install Condensate Pump - Foundation Level | 10 | 0 | 2022-01-17 08:00 | 2022-01-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03110 | [8 empty] | Rig Fuel Oil Tank & Piping - 1st Floor | 3 | 0 | 2021-09-21 08:00 | 2021-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03125 | [8 empty] | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-01-17 08:00 | 2022-01-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03130 |  | SG6 | [6 empty] | Install Conduit for Controls - 1st Floor | 20 | 0 | 2022-06-13 | 2022-09-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03135 | WELKIN | SG6 | [6 empty] | Perform Hydrostatic Testing - 1st Floor | 5 | 0 | 2022-06-27 08:00 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03140 | [8 empty] | Install Plumbing Equipment - 1st Floor | 15 | 0 | 2021-12-27 | 2022-01-11 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03145 | WELKIN | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 2 | 2022-06-20 | 2023-02-28 17:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03150 | MEP | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-03-01 08:00 | 2023-03-28 17:00 | -76 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03210 | [8 empty] | Rig Boiler Equipment & Piping - 2nd Floor | 10 | 0 | 2021-10-28 | 2022-01-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03225 |  | SG6 | [6 empty] | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 0 | 2022-02-06 | 2022-09-23 13:48 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03230 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install Conduit for Boiler Controls - 2nd Floor | 20 | 1 | 2022-08-01 08:00 | 2023-02-28 17:00 | -76 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03235 | WELKIN | SG6 | [6 empty] | Perform Hydrostatic Testing - 2nd Floor | 5 | 0 | 2022-06-20 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03240 | [8 empty] | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03245 | WELKIN | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-03-01 08:00 | 2023-03-14 17:00 | -76 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03250 | MEP | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 8 | 2022-11-21 08:00 | 2023-03-28 17:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-03505 | CLOSEOUT | SG6 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG6 | 4 | 4 | 2023-03-29 08:00 | 2023-04-03 17:00 | -76 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-03315 |  | SG6 | [6 empty] | Install Insulation - Roof | 15 | 0 | 2022-09-06 08:00 | 2022-09-23 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-03510 | MLJ | SG6 | STARTUP | Interior | NEW BUILDINGS |  |  |  | Perform Start-Up Testing & Sign-off - Boiler - SG6 | 15 | 15 | 2023-04-21 08:00 | 2023-05-11 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-03515 | CLOSEOUT | SG6 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - SG6 | 16 | 16 | 2023-05-12 08:00 | 2023-06-05 17:00 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-03520 | PUNCH LIST | SG6 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG6 | 5 | 5 | 2023-06-06 08:00 | 2023-06-12 17:00 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-03530 | MEP | SG6 | CLOSEOUT | Interior | NEW BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG6 | 4 | 4 | 2023-07-20 08:00 | 2023-07-25 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-03525 | CLOSEOUT | SG6 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG6 | 1 | 1 | 2023-07-19 08:00 | 2023-07-19 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.1 | SG4-01005 | ATCO | SG4 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - SG4 | 3 | 3 | 2023-07-19 08:00 | 2023-07-21 17:00 | -53 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.1 | SG4-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> SG4 | 3 | 0 | 2021-09-13 08:00 | 2021-09-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.1 | SG4-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations 1st floor to cellar --> SG4 | 3 | 0 | 2021-12-21 | 2021-12-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.1 | SG4-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> SG4 | 3 | 0 | 2021-09-13 | 2021-09-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.1 | SG4-01025 | [8 empty] | Asbestos Abatement - Window Sills - 1st Floor --> SG4 | 5 | 0 | 2021-04-05 | 2021-04-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.1 | SG4-01030 | [8 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> SG4 | 1 | 0 | 2021-04-25 | 2021-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01105 | [8 empty] | Selective Demo (Plaster walls, Doors, windows, pumps etc..) - Cellar --> SG4 | 10 | 0 | 2021-06-26 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01110 | [8 empty] | Selective Demo (Doors, windows) - 1st Floor --> SG4 | 5 | 0 | 2021-06-26 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01115 | [8 empty] | Selective Demo (Areaway drain, slab, wall) --> SG4 | 10 | 0 | 2021-04-29 | 2022-05-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01205 | [8 empty] | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG4 | 5 | 0 | 2022-02-14 | 2022-02-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01210 | [8 empty] | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG4 | 5 | 0 | 2021-12-28 | 2021-12-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG4 | 5 | 0 | 2021-09-22 | 2021-09-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01310 | [8 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> SG4 | 5 | 0 | 2021-12-28 | 2021-12-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> SG4 | 5 | 0 | 2021-10-15 | 2021-11-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> SG4 | 5 | 0 | 2022-02-07 | 2022-02-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01325 | CCC | SG4 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> SG4 | 3 | 0 | 2022-02-10 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01330 | CCC | SG4 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> SG4 | 5 | 0 | 2022-02-10 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01335 | CCC | SG4 | [6 empty] | Paint walls and seal floor electrical room - 2nd Floor --> SG4 | 10 | 0 | 2022-06-14 | 2022-12-16 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.4 | SG4-01340 | FLOORING | SG4 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> SG4 | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 48 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01405 |  | SG4 | EXCAVATION |  |  |  | 31-1000 | 31-1000-SG4 | Excavate at Curtain Wall for flood protection (East Side) --> SG4 | 8 | 0 | 2022-01-20 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01410 |  | SG4 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-SG4 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 10 | 0 | 2022-02-14 | 2022-02-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 5 | 0 | 2022-02-02 | 2022-02-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-02-24 | 2022-02-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 5 | 0 | 2022-02-28 | 2022-03-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01430 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 8 | 0 | 2022-03-07 | 2022-03-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01435 | [8 empty] | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 6 | 0 | 2022-03-14 | 2022-03-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01440 | [8 empty] | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01445 | [8 empty] | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-03-23 | 2022-04-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01450 | FAXA | SG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-05-17 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01455 | [8 empty] | Backfill at Curtain Wall for flood protection (East Side) --> SG4 | 5 | 0 | 2022-05-25 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01460 | MLJ | SG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG4 | Form for slab at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-06-27 | 2022-07-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01465 |  | SG4 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG4 | 6 | 0 | 2022-07-19 | 2022-07-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01470 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Pour slab at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-08-10 | 2022-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01475 | MLJ | SG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG4 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG4 | 2 | 0 | 2022-08-15 | 2022-08-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01480 | MLJ | SG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG4 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 2022-08-17 | 2022-08-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01840 | [8 empty] | Prepare & Submit Surveyor | 5 | 0 | 2020-07-13 | 2020-07-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01845 | [8 empty] | Review & Approve Surveyor | 10 | 0 | 2020-07-14 | 2022-03-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01090 | [8 empty] | Activate Dewatering System | 1 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01095 |  |  | dewatering | [5 empty] | Maintain Dewatering | 232 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.5 | SGN-01690 | MLJ | SGN | demob | Closeout | SITE |  |  |  | Demobilize from SGN | 5 | 5 | 2023-08-16 08:00 | 2023-08-22 17:00 | -60 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> SG4 | 8 | 0 | 2022-01-20 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01510 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 10 | 0 | 2022-02-14 | 2022-02-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01515 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 5 | 0 | 2022-02-02 | 2022-02-23 08:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01520 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-02-24 | 2022-02-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01525 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 5 | 0 | 2022-02-28 | 2022-03-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01530 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 8 | 0 | 2022-03-07 | 2022-03-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01535 | [8 empty] | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 6 | 0 | 2022-03-14 | 2022-03-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01540 | [8 empty] | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01545 | [8 empty] | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-03-23 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01550 | FAXA | SG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-05-19 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01555 | [8 empty] | Backfill at Curtain Wall for flood protection (South Side) --> SG4 | 5 | 0 | 2022-03-07 | 2022-03-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01560 | [8 empty] | Form for slab at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-03-14 | 2022-03-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01565 | [8 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> SG4 | 6 | 0 | 2022-03-14 | 2022-03-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01570 | [8 empty] | Pour slab at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01575 | [8 empty] | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> SG4 | 2 | 0 | 2022-03-23 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01580 | [8 empty] | Backfill surounding area at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 2022-05-25 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01605 | [8 empty] | Excavate at Curtain Wall for flood protection (North Side) --> SG4 | 8 | 0 | 2022-03-18 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 10 | 0 | 2022-03-21 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 5 | 0 | 2022-03-23 | 2022-03-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-04-15 | 2022-04-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01625 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 5 | 0 | 2022-04-18 | 2022-04-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01630 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 8 | 0 | 2022-04-22 | 2022-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01635 | [8 empty] | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 6 | 0 | 2022-04-25 | 2022-04-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01640 | [8 empty] | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-04-30 | 2022-05-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01645 | [8 empty] | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-05-06 | 2022-05-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01650 | FAXA | SG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-05-24 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01655 | [8 empty] | Backfill at Curtain Wall for flood protection (North Side) --> SG4 | 5 | 0 | 2022-05-09 | 2022-05-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01660 | MLJ | SG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG4 | Form for slab at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-12-07 | 2022-12-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01665 |  | SG4 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (North Side) --> SG4 | 6 | 0 | 2022-12-09 | 2022-12-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01670 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Pour slab at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-12-12 | 2022-12-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01675 | MLJ | SG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG4 | Strip Forms for slab at Curtain Wall for flood protection (North Side) --> SG4 | 2 | 0 | 2022-12-13 | 2022-12-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01680 | MLJ | SG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG4 | Backfill surounding area at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 2022-12-14 | 2022-12-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01705 | [8 empty] | Excavate at Curtain Wall for flood protection (West Side) --> SG4 | 8 | 0 | 2022-01-20 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01710 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 10 | 0 | 2022-02-14 | 2022-02-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01715 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 5 | 0 | 2022-02-02 | 2022-02-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01720 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 2022-02-24 | 2022-02-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01725 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 5 | 0 | 2022-04-15 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01730 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 8 | 0 | 2022-03-07 | 2022-03-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01735 | [8 empty] | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 6 | 0 | 2022-03-14 | 2022-03-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01740 | [8 empty] | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01745 | [8 empty] | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 2022-03-23 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01750 | FAXA | SG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 2022-09-01 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01755 | MLJ | SG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG4 | Backfill at Curtain Wall for flood protection (West Side) --> SG4 | 5 | 0 | 2022-09-05 | 2022-09-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01760 | MLJ | SG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG4 | Form for slab at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 2022-08-09 | 2022-08-12 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01765 | TONAGE | SG4 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG4 | 6 | 6 | 2023-03-29 08:00 | 2023-04-05 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01770 | MLJ | SG4 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG4 | Pour slab at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01775 | MLJ | SG4 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG4 | 2 | 2 | 2023-04-12 08:00 | 2023-04-13 17:00 | 11 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01780 | MLJ | SG4 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 4 | 2023-04-19 08:00 | 2023-04-24 17:00 | 8 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2021-02-08 | 2021-06-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03010 | [8 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-06-13 | 2022-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03020 | [8 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-06-13 | 2022-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03025 | WELKIN | SG4 | [6 empty] | Perform Hydrostatic Testing - Cellar | 5 | 0 | 2022-08-01 08:00 | 2022-08-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03030 | [8 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-05-26 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03035 |  | SG4 | STARTUP | [5 empty] | Pump Equipment Start-up & Balance - Cellar | 10 | 0 | 2022-06-22 | 2022-12-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03040 |  | SG4 | [6 empty] | Plumbing/Mechanical Insulation - Cellar | 20 | 0 | 2022-11-01 08:00 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2021-04-14 | 2022-01-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03120 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 15 | 2022-10-21 | 2023-03-24 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03125 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -109 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03130 | NAVILLUS | SG4 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 5 | 2023-01-23 08:00 | 2023-03-03 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03135 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-04-03 08:00 | 2023-04-14 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03140 | MEP | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-04-17 08:00 | 2023-05-12 17:00 | -109 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03115 | [8 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-01-26 | 2022-01-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03110 |  | SG4 | [6 empty] | Install Ductwork and Appurtenances - 1st Floor | 5 | 0 | 2021-05-19 | 2023-01-06 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03112 |  | SG4 | [6 empty] | Install HV & EF Units - 1st Floor | 5 | 0 | 2021-12-26 | 2022-09-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03220 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-03-20 08:00 | 2023-04-14 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03230 | NAVILLUS | SG4 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 0 | 2023-02-01 | 2023-02-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03235 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03240 | MEP | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-05-01 08:00 | 2023-05-26 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03210 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.3 | SG4-03215 | WELKIN | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03305 | CLOSEOUT | SG4 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG4 | 4 | 4 | 2023-05-30 08:00 | 2023-06-02 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03310 | MLJ | SG4 | STARTUP | Interior | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - SG4 | 15 | 15 | 2023-06-05 08:00 | 2023-06-23 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03315 | CLOSEOUT | SG4 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - SG4 | 16 | 16 | 2023-06-26 08:00 | 2023-07-18 17:00 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03320 | PUNCH LIST | SG4 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG4 | 5 | 5 | 2023-08-02 08:00 | 2023-08-08 17:00 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03330 | MEP | SG4 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG4 | 4 | 4 | 2023-08-10 08:00 | 2023-08-15 17:00 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03325 | CLOSEOUT | SG4 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG4 | 1 | 1 | 2023-08-09 08:00 | 2023-08-09 17:00 | -60 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01005 | [8 empty] | Asbestos Abatement - gaskets - cellar - SG5 | 3 | 0 | 2021-06-14 | 2021-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> SG5 | 3 | 0 | 2021-06-14 | 2021-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG5 | 3 | 0 | 2021-06-14 | 2021-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> SG5 | 3 | 0 | 2021-06-14 | 2021-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01025 | [8 empty] | Asbestos Abatement - Window Sills - 1st Floor --> SG5 | 5 | 0 | 2021-06-14 | 2021-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01030 | [8 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> SG5 | 5 | 0 | 2021-04-25 | 2021-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01105 | [8 empty] | Selective Demo (Plaster walls, Doors,Windows) - Cellar --> SG5 | 10 | 0 | 2021-04-25 | 2022-04-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01110 | [8 empty] | Selective Demo (Doors, windows) - 1st Floor --> SG5 | 5 | 0 | 2021-06-30 08:00 | 2022-04-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01115 | [8 empty] | Selective Demo (Areaway drain, slab, wall) --> SG5 | 10 | 0 | 2021-10-10 | 2022-01-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01205 | [8 empty] | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG5 | 5 | 0 | 2022-02-21 | 2022-02-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01210 | [8 empty] | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG5 | 5 | 0 | 2022-03-29 | 2022-03-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01215 | MLJ | SG5 | DEMO |  |  | DEMO 2ND FLOOR | 02-6060 | 02-6060-SG5 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG5 | 5 | 0 | 2022-09-13 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01310 | MLJ | SG5 | CORE DRILL | [5 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> SG5 | 5 | 0 | 2022-09-20 | 2022-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> SG5 | 5 | 0 | 2021-12-20 08:00 | 2022-04-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> SG5 | 5 | 0 | 2022-03-21 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01325 | CCC | SG5 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> SG5 | 3 | 0 | 2022-09-15 | 2022-11-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01330 | CCC | SG5 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> SG5 | 5 | 0 | 2022-09-20 | 2022-11-28 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01335 | CCC | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> SG5 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.4 | SG5-01340 | FLOORING | SG5 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> SG5 | 2 | 2 | 2023-03-13 08:00 | 2023-03-14 17:00 | 38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01405 |  | SG5 | EXCAVATION |  |  |  | 31-1000 | 31-1000-SG5 | Excavate at Curtain Wall for flood protection (East Side) --> SG5 | 8 | 0 | 2021-10-18 | 2021-12-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01410 |  | SG5 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-SG5 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 10 | 0 | 2022-02-16 | 2022-02-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 5 | 0 | 2022-02-17 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-02-21 | 2022-02-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 5 | 0 | 2022-05-25 | 2022-05-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01430 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 8 | 0 | 2022-07-01 | 2022-07-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01435 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 6 | 0 | 2022-07-11 08:00 | 2022-07-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01440 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-08-10 | 2022-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01445 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-08-15 | 2022-08-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01450 | FAXA | SG5 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-05-09 | 2022-05-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01455 | [8 empty] | Backfill at Curtain Wall for flood protection (East Side) --> SG5 | 5 | 0 | 2022-05-26 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01460 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form for slab at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-09-01 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01465 |  | SG5 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG5 | 6 | 0 | 2022-09-06 | 2022-09-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01470 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour slab at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-09-09 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01475 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG5 | 2 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01480 | MLJ | SG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG5 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 2022-09-14 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> SG5 | 8 | 0 | 2021-12-26 | 2021-12-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01510 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 10 | 0 | 2022-07-26 | 2022-07-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01515 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 5 | 0 | 2022-07-28 08:00 | 2022-07-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01520 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-08-01 | 2022-08-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01525 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 5 | 0 | 2022-08-02 | 2022-08-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01530 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 8 | 0 | 2022-07-26 08:00 | 2022-07-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01535 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 6 | 0 | 2022-07-28 08:00 | 2022-07-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01540 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-08-01 08:00 | 2022-08-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01545 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-08-02 08:00 | 2022-08-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01550 | FAXA | SG5 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-05-12 | 2022-09-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01555 | MLJ | SG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG5 | Backfill at Curtain Wall for flood protection (South Side) --> SG5 | 5 | 0 | 2022-09-28 08:00 | 2022-10-04 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01560 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form for slab at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-12-06 | 2022-12-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01565 |  | SG5 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> SG5 | 6 | 0 | 2022-12-08 | 2022-12-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01570 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour slab at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-12-12 | 2022-12-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01575 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> SG5 | 2 | 0 | 2022-12-13 | 2022-12-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01580 | MLJ | SG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG5 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 2022-12-15 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01605 | [8 empty] | Excavate at Curtain Wall for flood protection (North Side) --> SG5 | 8 | 0 | 2021-12-27 | 2021-12-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 10 | 0 | 2022-02-16 | 2022-02-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 5 | 0 | 2022-02-17 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-02-21 | 2022-02-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01625 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 5 | 0 | 2022-10-25 | 2022-10-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01630 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 8 | 0 | 2022-10-25 | 2022-10-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01635 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 6 | 0 | 2022-10-26 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01640 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-10-28 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01645 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-11-01 | 2022-11-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01650 | [8 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-12-02 | 2022-12-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01655 | [8 empty] | Backfill at Curtain Wall for flood protection (North Side) --> SG5 | 5 | 0 | 2022-12-05 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01660 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form for slab at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-12-06 | 2022-12-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01665 |  | SG5 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (North Side) --> SG5 | 6 | 0 | 2022-12-08 | 2022-12-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01670 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour slab at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-12-12 | 2022-12-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01675 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms for slab at Curtain Wall for flood protection (North Side) --> SG5 | 2 | 0 | 2022-12-13 | 2022-12-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01680 | MLJ | SG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG5 | Backfill surounding area at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 2022-12-15 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01705 | [8 empty] | Excavate at Curtain Wall for flood protection (West Side) --> SG5 | 8 | 0 | 2021-12-28 | 2021-12-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01710 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 10 | 0 | 2022-02-16 | 2022-02-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01715 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 5 | 0 | 2022-02-17 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01720 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-02-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01725 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 5 | 0 | 2022-07-01 | 2022-07-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01730 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 8 | 0 | 2022-07-01 | 2022-07-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01735 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 6 | 0 | 2022-07-11 08:00 | 2022-07-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01740 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-08-10 | 2022-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01745 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-08-15 | 2022-08-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01750 | [8 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-05-13 | 2022-06-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01755 | [8 empty] | Backfill at Curtain Wall for flood protection (West Side) --> SG5 | 5 | 0 | 2022-06-20 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01760 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Form for slab at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-09-01 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01765 |  | SG5 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG5 | 6 | 0 | 2022-09-06 | 2022-09-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01770 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Pour slab at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-09-09 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01775 | MLJ | SG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG5 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG5 | 2 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01780 | MLJ | SG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG5 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 2022-09-14 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2021-09-26 | 2021-12-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03010 | WELKIN | SG5 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-07-05 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03020 |  | SG5 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-09-28 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03025 | WELKIN | SG5 | [6 empty] | Perform Hydrostatic Testing - Cellar | 5 | 0 | 2022-08-01 08:00 | 2022-08-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03030 | [8 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-05-25 | 2022-06-08 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03035 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -64 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03040 | MEP | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation & Tag - Cellar | 20 | 1 | 2022-11-01 08:00 | 2023-03-10 17:00 | -64 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2021-07-26 08:00 | 2021-07-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03120 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 15 | 2022-10-21 | 2023-03-17 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03125 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03130 | NAVILLUS | SG5 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03135 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03140 | MEP | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation & Tag- 1st Floor | 20 | 20 | 2023-04-10 08:00 | 2023-05-05 17:00 | -104 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03115 | WELKIN | SG5 | [6 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-09-15 08:00 | 2022-09-16 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03110 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -104 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03112 |  | SG5 | [6 empty] | Install HV & EF Units - 1st Floor | 5 | 0 | 2022-09-19 08:00 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03220 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 15 | 15 | 2023-03-20 08:00 | 2023-04-07 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03230 | NAVILLUS | SG5 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 5 | 2023-02-21 | 2023-03-03 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03235 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-04-10 08:00 | 2023-04-21 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03240 | MEP | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation & Tag - 2nd Floor | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03210 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.3 | SG5-03215 | WELKIN | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03305 | CLOSEOUT | SG5 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG5 | 4 | 4 | 2023-05-08 08:00 | 2023-05-11 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03310 | CLOSEOUT | SG5 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - SG5 | 15 | 15 | 2023-05-17 08:00 | 2023-06-07 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03315 | CLOSEOUT | SG5 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - SG5 | 16 | 16 | 2023-06-08 08:00 | 2023-06-29 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03320 | PUNCH LIST | SG5 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG5 | 5 | 5 | 2023-06-30 08:00 | 2023-07-07 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03330 | MEP | SG5 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG5 | 4 | 4 | 2023-07-20 08:00 | 2023-07-25 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03325 | CLOSEOUT | SG5 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG5 | 1 | 1 | 2023-07-19 08:00 | 2023-07-19 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01805 | [8 empty] | Excavate for concrete shelf around bldg perimeter --> SG4 | 10 | 0 | 2022-02-28 | 2022-03-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> SG4 | 5 | 0 | 2022-03-07 | 2022-03-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> SG4 | 5 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01820 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Place infill concrete in area ways around bldg perimeter --> SG4 | 5 | 0 | 2022-03-14 08:00 | 2022-03-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01825 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Place waterproofing on concrete shelf around bldg perimeter --> SG4 | 10 | 0 | 2022-05-17 08:00 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01830 | FAXA | SG4 | CMU | [5 empty] | Place CMU around bldg perimeter --SG4 | 15 | 0 | 2022-05-17 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01835 |  | SG4 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> SG4 | 10 | 0 | 2022-06-06 | 2022-08-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01840 |  | SG4 | [6 empty] | Place window frames around bldg perimeter --> SG4 | 10 | 0 | 2022-06-13 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01845 | FAXA | SG4 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG4 | 20 | 0 | 2022-06-13 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01850 | MLJ | SG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG4 | Backfill around bdg perimeter --> SG4 | 5 | 0 | 2022-09-26 08:00 | 2022-09-30 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01855 | CCC | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> SG4 | 4 | 4 | 2023-03-27 08:00 | 2023-03-30 17:00 | 33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01860 | MLJ | SG4 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> SG4 | 5 | 5 | 2023-03-31 08:00 | 2023-04-06 17:00 | 33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01865 | MLJ | SG4 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> SG4 | 3 | 3 | 2023-04-07 08:00 | 2023-04-11 17:00 | 33 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.5 | SG4-01350 | [8 empty] | Drill dowels and place rebar for boiler room concrete walls --> SG4 | 5 | 0 | 2021-05-11 | 2021-05-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.5 | SG4-01355 | [8 empty] | Form boiler room concrete walls --> SG4 | 5 | 0 | 2021-05-12 | 2021-05-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.5 | SG4-01360 | [8 empty] | Pour Concrete boiler room walls --> SG4 | 2 | 0 | 2021-05-14 | 2021-05-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.5 | SG4-01365 | [8 empty] | Strip Forms boiler room concrete walls --> SG4 | 3 | 0 | 2021-05-19 | 2021-05-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.5 | SG4-01370 |  | SG4 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> SG4 | 10 | 0 | 2022-07-01 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.6 | SG4-01385 | [8 empty] | Refurbish Elevator 1 --> SG4 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.6 | SG4-01390 | [8 empty] | Refurbish Elevator 2 --> SG4 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.6 | SG5-01380 | [8 empty] | Refurbish Elevator 1 --> SG5 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.6 | SG5-01385 | [8 empty] | Refurbish Elevator 2 --> SG5 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01805 | [8 empty] | Excavate for concrete shelf around bldg perimeter --> SG5 | 10 | 0 | 2021-11-25 08:00 | 2021-12-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> SG5 | 5 | 0 | 2022-03-07 | 2022-03-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> SG5 | 5 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01820 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Place infill concrete in area ways around bldg perimeter --> SG5 | 5 | 0 | 2022-03-14 08:00 | 2022-03-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01825 | [8 empty] | Place waterproofing on concrete shelf around bldg perimeter --> SG5 | 10 | 0 | 2022-05-26 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01830 | [8 empty] | Place CMU around bldg perimeter --SG5 | 15 | 0 | 2022-05-09 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01835 | [8 empty] | Place waterproofing on CMU around bldg perimeter --> SG5 | 10 | 0 | 2022-05-26 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01840 | [8 empty] | Place window frames around bldg perimeter --> SG5 | 10 | 0 | 2022-06-06 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01845 | FAXA | SG5 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG5 | 20 | 0 | 2022-06-15 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01850 | [8 empty] | Backfill around bdg perimeter --> SG5 | 5 | 0 | 2022-05-05 | 2022-05-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01855 | CCC | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> SG5 | 4 | 4 | 2023-03-27 08:00 | 2023-03-30 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01860 | MLJ | SG5 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> SG5 | 5 | 5 | 2023-03-31 08:00 | 2023-04-06 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01865 | MLJ | SG5 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> SG5 | 3 | 3 | 2023-04-07 08:00 | 2023-04-11 17:00 | 18 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.6 | SG4-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01137 | [8 empty] | Install Automatic Temperature Control Conduit - SG6 --> SG4 | 2 | 0 | 2022-06-15 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02130 | FIVE STAR | SGN | [6 empty] | Pull & Terminate Automatic Temperature Control Cable - SG-6 --> SG-4 | 10 | 0 | 2022-06-15 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.2 | SGN-02150 | FIVE STAR | SGN | [6 empty] | Pull & Terminate Automatic Temperature Control Cable - SG-5 --> SG-4 | 10 | 0 | 2022-06-15 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.1 | SGN-01287 |  | SGN | [6 empty] | Install Automatic Temperature Control Conduit - SG4 --> SG5 | 2 | 0 | 2022-07-25 08:00 | 2022-07-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01317 | NAVILLUS | SG6 | [6 empty] | Install Insulated Metal Panels left out for Access --> SG6 | 5 | 0 | 2022-10-14 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.Removals | SGN-01100 | [8 empty] | De-Activate Dewatering - N/A | 1 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.7 | SG6-09005 | CLOSEOUT | SG6 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-03-29 08:00 | 2023-04-04 17:00 | 28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.7 | SG6-09010 | PUNCH LIST | SG6 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-04-05 08:00 | 2023-04-18 17:00 | 28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.7 | SG4-09005 | CLOSEOUT | SG4 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-07-24 08:00 | 2023-07-28 17:00 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.7 | SG4-09010 | PUNCH LIST | SG4 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-07-31 08:00 | 2023-08-11 17:00 | -53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.7 | SG5-09005 | CLOSEOUT | SG5 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-04-12 08:00 | 2023-04-18 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.7 | SG5-09010 | PUNCH LIST | SG5 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-04-19 08:00 | 2023-05-02 17:00 | 18 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01005 | [8 empty] | Install Site Fencing - O'Dwyer Gardens - Part 1 | 10 | 0 | 2021-02-08 | 2021-02-18 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-02000 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 0 | 2021-11-29 | 2023-02-15 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-02002 |  | OGE | [6 empty] | Install Manholes & Grounding | 8 | 0 | 2021-11-22 | 2023-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01015 | [8 empty] | Install Overhead Protection - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01020 | [6 empty] | 31-1900 |  | Install Tree Protection | 5 | 0 | 2020-11-05 | 2020-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01025 | [8 empty] | Remove Trees | 2 | 0 | 2021-01-12 | 2021-01-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01000 | [8 empty] | Remove Curbs And Existing Fencing | 10 | 0 | 2021-07-19 08:00 | 2022-03-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01035 | [8 empty] | Install Erosion Control | 5 | 0 | 2021-09-26 | 2021-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01010 | [8 empty] | Set Up Yard and Staging - N/A | 10 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01045 | [8 empty] | Clear & Grub | 10 | 0 | 2021-06-15 | 2021-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01050 | [8 empty] | Scrape & Store Topsoil | 10 | 0 | 2021-06-15 | 2021-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01055 | [8 empty] | Soil Testing | 10 | 0 | 2021-02-25 | 2021-03-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01060 | [6 empty] | 02-2000 |  | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 2021-07-19 08:00 | 2021-07-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01065 | [8 empty] | Remove Retaining Walls | 10 | 0 | 2022-03-28 | 2022-04-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01070 | [8 empty] | Install Deep Wells For Dewatering - N/A | 10 | 0 | 2021-06-23 | 2021-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01075 | [8 empty] | Install Piping For Deep Wells - N/A | 5 | 0 | 2021-06-23 | 2021-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01080 | [8 empty] | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01085 | [8 empty] | Run Electric For Dewatering - N/A | 10 | 0 | 2021-06-23 | 2021-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01105 | [8 empty] | Excavate for CW Pipe - OG4 --> OG8 | 10 | 0 | 2021-10-06 | 2021-10-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01110 | [8 empty] | Install CW Piping - OG4 --> OG8 | 15 | 0 | 2021-10-21 | 2022-01-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01115 | WELKIN | [7 empty] | Test CW Piping - OG4 --> OG8 | 10 | 0 | 2022-01-04 | 2022-01-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01120 | [8 empty] | Backfill CW Piping - OG4 --> OG8 | 5 | 0 | 2022-05-03 | 2022-05-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01150 | [8 empty] | Excavate for Electric OG4--> OG8 | 10 | 0 | 2021-10-19 | 2021-10-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01155 | [8 empty] | Install Electrical Conduit OG4--> OG8 | 10 | 0 | 2021-10-27 | 2022-04-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01160 | [8 empty] | Encase conduit in concrete OG4--> OG8 | 5 | 0 | 2022-05-12 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01165 | [8 empty] | Backfill Electrical OG4--> OG8 | 5 | 0 | 2022-05-16 | 2022-05-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01405 | MLJ | OGW | Excavation | Utilities | SITE | UTILITY EXC | 33-3100 | 33-3100-OGW | Excavate for Gas Line - OG8 --> W33rd Street | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -114 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01205 |  | OGW | EXCAVATION |  |  |  | 33-3100 | 33-3100-OGW | Excavate for Electric OG4--> MH | 3 | 0 | 2021-12-16 | 2021-12-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01210 | [8 empty] | Install Electrical Conduit OG4--> MH | 2 | 0 | 2021-12-16 | 2022-04-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01215 | [8 empty] | Encase conduit in concrete OG4--> MH | 2 | 0 | 2022-05-12 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01220 | [8 empty] | Backfill Electrical OG4 --> MH | 2 | 0 | 2022-05-16 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01230 | [8 empty] | Excavate for Electric OG8 -> OG5 | 10 | 0 | 2021-09-28 | 2021-11-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01235 | [8 empty] | Install Electrical Conduit & MH OG8 -> OG5 | 10 | 0 | 2021-10-27 | 2022-01-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01240 | [8 empty] | Encase conduit in concrete OG8 -> OG5 | 3 | 0 | 2021-12-05 08:00 | 2021-12-06 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01245 | [8 empty] | Backfill Electrical OG8 -> OG5 | 5 | 0 | 2021-12-07 08:00 | 2021-12-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01255 | [8 empty] | Excavate for Electric OG5--> MH | 3 | 0 | 2021-12-10 | 2021-12-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01260 | [8 empty] | Install Electrical Conduit OG5--> MH | 2 | 0 | 2021-12-13 | 2022-01-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01265 | [8 empty] | Encase conduit in concrete OG5--> MH | 2 | 0 | 2022-04-26 | 2022-04-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01270 | [8 empty] | Backfill Electrical OG5 --> MH | 2 | 0 | 2022-04-29 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01275 | [8 empty] | Excavate for Steam & HW OG4--> OG8 | 15 | 0 | 2021-09-28 | 2021-10-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01280 | [8 empty] | Install Steam and HW piping OG4--> OG8 | 20 | 0 | 2021-10-20 | 2021-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01285 | [8 empty] | Test Steam & HW Piping OG4--> OG8 | 8 | 0 | 2022-01-04 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01290 | [8 empty] | Backfill Steam & HW Piping OG4--> OG8 | 10 | 0 | 2022-05-16 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01505 | MLJ | SGN | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-SGN | Excavate for water line to drinking fountain SGN --> Water Main W32nd Street | 2 | 0 | 2022-11-01 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01510 |  | SGN |  |  |  | PLAYGROUND |  |  | Install water line to drinking fountain SGN --> Water Main W32nd Street | 5 | 0 | 2023-01-05 | 2023-01-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01515 |  | SGN |  |  |  | PLAYGROUND |  |  | Tap water main for drinking fountain water line SGN --> Water Main W32nd Street | 2 | 0 | 2022-12-04 | 2022-12-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01520 | MLJ | SGN | BACKFILL |  |  | BACKFILL SITE |  |  | Backfill water line drinking fountain SGN --> Water Main W32nd Street | 2 | 0 | 2022-12-05 | 2022-12-06 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01525 | MLJ | SGN | Excavation | Utilities | SITE | UTILITY EXC | 33-3100 | 33-3100-SGN | Excavate for water line to water play items SGN --> Water Main W33rd Street | 2 | 0 | 2023-02-06 | 2023-02-08 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01530 | MLJ | SGN |  | Utilities | SITE | PLAYGROUND |  |  | Install water line and RPZ box for water play items SGN --> Water Main W33rd Street | 5 | 0 | 2023-02-09 08:00 | 2023-02-23 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01535 | MLJ | SGN |  | Utilities | SITE | PLAYGROUND |  |  | Tap water main for drinking fountain water line SGN --> Water Main W33rd Street | 2 | 0 | 2023-02-16 08:00 | 2023-02-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01540 | MLJ | SGN | BACKFILL | Utilities | SITE | BACKFILL SITE |  |  | Backfill water line drinking fountain SGN --> Water Main W33rd Street | 2 | 0 | 2023-02-20 08:00 | 2023-02-21 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01545 | MLJ | OGW | Excavation | Utilities | SITE | UTILITY EXC | 33-3100 | 33-3100-OGW | Excavate for Sanitary Sewer OG4 --> OG8 | 3 | 3 | 2023-03-06 08:00 | 2023-03-08 17:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01550 | WELKIN | OGE | UG PIPE | Utilities | SITE |  |  |  | Install sanitary pipe OG4 --> OG8 | 2 | 2 | 2023-03-09 08:00 | 2023-03-10 17:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01555 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-OGW | Backfill Sanitary Sewer OG4 --> OG8 | 2 | 2 | 2023-03-20 08:00 | 2023-03-21 17:00 | -24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01560 | MLJ | OGW | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD18 to AD4 and AD6, AD5 Piping & into Tie-in to Existing | 15 | 0 | 2023-01-30 08:00 | 2023-02-14 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01565 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD18 to AD4 and AD6, AD5 & Piping | 5 | 0 | 2023-02-15 08:00 | 2023-02-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01090 | [8 empty] | Activate Dewatering System - N/A | 1 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01095 | [8 empty] | Maintain Dewatering | 172 | 0 | 2022-03-25 17:00 | 2022-04-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01287 | [8 empty] | Install Automatic Temperature Control Conduit - OG4--> OG8 | 2 | 0 | 2022-05-16 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.Removals | OGP1-01100 | [8 empty] | De-Activate Dewatering | 1 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-04005 | [8 empty] | Obtain Dewatering Permit | 60 | 0 | 2020-11-27 | 2021-10-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.2 | SG5-01220 | MLJ | SG5 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO PUMPS | 02-6010 | 02-6010-SG5 | Selective Demo (pumps etc..) - Cellar --> SG5 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -59 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-03335 | MLJ | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - SG4 | 10 | 5 | 2022-03-07 | 2023-07-25 17:00 | -60 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-03335 | MLJ | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - SG5 | 10 | 5 | 2022-03-14 | 2023-07-07 17:00 | -33 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.2 | SURV-OGP1-G-01005 | [8 empty] | Perform Survey of Site/Building - Odwyer Gardens - Part 1 (OG-4 & OG-5) | 10 | 0 | 2020-11-02 | 2020-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.2 | SURV-OGP1-E-01010 | [8 empty] | Conduct Electrical Site Survey - Odwyer Gardens - Part 1 (OG-4 & OG-5) | 10 | 0 | 2021-04-19 | 2021-06-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33505 | [8 empty] | Prepare & Submit Utility Coord. Dwgs - Surfside Gardens North | 20 | 0 | 2020-12-07 | 2021-02-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33510 | [8 empty] | Review & Approve Utility Coord. Dwgs - Surfside Gardens North | 10 | 0 | 2021-02-24 | 2021-03-04 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33520 | [8 empty] | Prepare & Submit Utility Coord. Dwgs - Odwyer Gardens - Part 1 | 20 | 0 | 2021-02-23 | 2021-07-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33525 | [8 empty] | Review & Approve Utility Coord. Dwgs - Odwyer Gardens - Part 1 | 10 | 0 | 2021-06-30 08:00 | 2021-07-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01117 | [8 empty] | Install Automatic Temperature Control Conduit - OG4 --> OG8 | 2 | 0 | 2022-05-16 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01295 | [8 empty] | Excavate for Steam & HW OG5--> OG8 | 15 | 0 | 2021-12-26 | 2022-01-04 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01300 | WELKIN | OGE | UG PIPE | Utilities | SITE |  |  |  | Install Steam and HW piping OG5--> OG8 | 20 | 20 | 2023-08-30 08:00 | 2023-09-27 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01305 | WELKIN | OGE | UG PIPE | Utilities | SITE |  |  |  | Test Steam & HW Piping OG5--> OG8 | 8 | 8 | 2023-09-28 08:00 | 2023-10-09 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01315 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-OGW | Backfill Steam & HW Piping OG5--> OG8 | 10 | 10 | 2023-10-12 08:00 | 2023-10-26 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01310 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Install Automatic Temperature Control Conduit - OG5--> OG8 | 2 | 2 | 2023-10-10 08:00 | 2023-10-11 17:00 | -200 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01092 | [8 empty] | Install Remaining HW/CW Into SG6 (5' from the building) | 5 | 0 | 2021-09-20 | 2021-09-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01094 | [8 empty] | Install Remaining Electrical POE Into SG6 | 5 | 0 | 2021-07-26 08:00 | 2021-07-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03107 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 0 | 2022-01-04 | 2022-01-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03142 | [8 empty] | Install Mechanical Equipment - 1st Floor | 20 | 0 | 2022-01-17 | 2022-01-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03207 | WELKIN | SG6 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 20 | 0 | 2022-01-06 | 2022-09-23 09:36 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03242 | WELKIN | SG6 | [6 empty] | Install Mechanical Equipment - 2nd Floor | 20 | 0 | 2022-01-17 08:00 | 2022-08-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-04-25 | 2021-10-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2021-07-30 08:00 | 2021-10-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.2 | SG4-03107 | WELKIN | SG4 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-08-15 08:00 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.6 | SG5-01370 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-07-26 08:00 | 2021-10-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2021-07-26 08:00 | 2021-10-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.2 | SG5-03107 | WELKIN | SG5 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-07-25 08:00 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01030 | [8 empty] | Form Plumbing Shafts & Ftgs Below Water Table --> OG8 | 10 | 0 | 2021-07-27 | 2021-07-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01035 | [8 empty] | Rebar Plumbing Shafts & Ftgs Below Water Table --> OG8 | 5 | 0 | 2021-07-30 08:00 | 2021-08-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01040 | MLJ | OG8 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG8 | Pour Plumbing Shafts & Ftgs Below Water Table --> OG8 | 2 | 0 | 2021-08-10 | 2021-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01045 | [8 empty] | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> OG8 | 5 | 0 | 2021-08-11 | 2021-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01025 | [8 empty] | Waterproof/Insulation Plumbing Shaft ----> OG8 | 5 | 0 | 2021-08-10 | 2021-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01005 | [8 empty] | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG8 | 5 | 0 | 2021-07-02 | 2021-07-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01020 | [8 empty] | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> OG8 | 3 | 0 | 2021-07-12 | 2021-07-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01055 |  |  | OG8 |  |  |  | 31-1400 | 31-1400-OG8 | Backfill Plumbing Shaft & Ftgs/Piers --> OG8 | 5 | 0 | 2021-08-13 08:00 | 2021-11-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01065 | [8 empty] | Excavate For Remaining Ftgs/Pier/Grade Beams --> OG8 | 10 | 0 | 2021-07-02 | 2021-10-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01070 |  | OG8 | FORMWORK |  |  | FORMWORK NB | 03-1000 | 03-1000-OG8 | Form Remaining Ftgs/Piers/Grade Beams --> OG8 | 10 | 0 | 2021-08-16 | 2021-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01075 | [8 empty] | Rebar Remaining Ftgs/Piers/Grade Beams --> OG8 | 10 | 0 | 2021-08-17 | 2021-12-06 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01080 | [8 empty] | Pour Remaining Ftgs/Piers/Grade Beams --> OG8 | 5 | 0 | 2021-12-01 08:00 | 2021-12-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01085 | [8 empty] | Strip Forms Remaining Ftgs/Piers/Grade Beams --> OG8 | 5 | 0 | 2021-12-07 | 2021-12-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01090 | [8 empty] | Install Remaining Steam Into OG8 (5' from the building) | 5 | 0 | 2021-11-01 08:00 | 2021-11-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01095 | [8 empty] | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> OG8 | 5 | 0 | 2021-12-14 08:00 | 2021-12-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01105 | [8 empty] | Install Structural Steel Framing - 1st Foor --> OG8 | 7 | 0 | 2021-12-20 08:00 | 2022-01-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01110 | [8 empty] | Install Metal Deck --> OG8 | 2 | 0 | 2022-02-22 08:00 | 2022-04-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01115 | [8 empty] | Form Pour Strip Concrete Stair South Side ---> OG8 | 5 | 0 | 2022-03-01 08:00 | 2022-03-04 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01120 | [8 empty] | Install Metal Stairs --> OG8 | 2 | 0 | 2022-03-16 | 2022-04-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01125 | [8 empty] | Place Insulation Below First Floor --> OG8 | 5 | 0 | 2022-02-28 | 2022-03-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01130 | [8 empty] | Place WWF First Floor Slab --> OG8 | 2 | 0 | 2022-03-03 | 2022-03-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01135 | MLJ | OG8 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG8 | Pour First Floor Slab --> OG8 | 1 | 0 | 2022-03-07 | 2022-03-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01150 | [8 empty] | Form First Floor Concrete Walls First Face And Col Encasements--> OG8 | 3 | 0 | 2022-03-15 | 2022-04-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01155 | [8 empty] | Rebar First Floor Concrete Walls --> OG8 | 3 | 0 | 2022-03-18 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01160 | [8 empty] | Form First Floor Concrete Walls 2Nd Face --> OG8 | 5 | 0 | 2022-04-01 | 2022-04-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01165 | [8 empty] | Form, Rebar & Pour Concrete Pads 1st Floor --> OG8 | 6 | 0 | 2022-03-28 | 2022-04-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01170 | [8 empty] | Place WWF 2nd Floor Slab --> OG8 | 2 | 0 | 2022-04-01 | 2022-04-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01175 | MLJ | OG8 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG8 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements --> OG8 | 2 | 0 | 2022-04-05 | 2022-04-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01180 | [8 empty] | Strip Forms First Floor Walls & Col Encasements --> OG8 | 3 | 0 | 2022-04-06 | 2022-04-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01185 | [8 empty] | Form Concrete Pads 2nd Floor -->OG8 | 2 | 0 | 2022-04-07 | 2022-04-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01205 | [8 empty] | Place WWF Roof Slab --> OG8 | 2 | 0 | 2022-05-05 | 2022-05-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01210 | [8 empty] | Pour Roof Slab and 2nd Floor Conc Pads -->OG8 | 1 | 0 | 2022-05-09 | 2022-05-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01215 | [8 empty] | Strip Forms Concrete Pads 2nd Floor -->OG8 | 2 | 0 | 2022-04-26 | 2022-04-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01225 | [8 empty] | Install Spray-On Fireproofing on St Stl --> OG8 | 5 | 0 | 2022-05-09 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01230 | FAXA | OG8 | CMU | [5 empty] | Place CMU 1st, 2nd Floors and Roof --> OG8 | 20 | 0 | 2022-05-16 | 2022-07-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01240 | CCC | OG8 | [6 empty] | Install Stud Framing 1st, 2nd Floors and Roof --> OG8 | 5 | 0 | 2022-12-16 | 2023-01-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01245 | CCC | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Doors --> OG8 | 3 | 1 | 2023-02-22 08:00 | 2023-04-17 17:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01250 | JMC | OG8 | CAST STONE | Structure | NEW BUILDINGS |  |  |  | Install Cast Stone Panels --> OG8 | 1 | 1 | 2023-04-18 08:00 | 2023-04-18 17:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01255 | NAVILLUS | OG8 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulated Metal Panels/Louvers --> OG8 | 10 | 10 | 2023-02-23 08:00 | 2023-05-02 17:00 | -19 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01260 | [8 empty] | Install MEP Roof Penetrations & Drains - OG8 | 1 | 0 | 2022-06-08 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01265 | TRIANGLE | OG8 | [6 empty] | Install Roofing --> OG8 | 15 | 0 | 2022-09-05 | 2023-01-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01270 | [8 empty] | Install Dunnage Gratings --> OG8 | 2 | 0 | 2022-03-12 | 2022-03-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01275 | FAXA | OG8 | [6 empty] | Install Brick Façade & Stone --> OG8 | 20 | 0 | 2022-08-22 | 2022-10-27 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01285 | MLJ | OG8 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD VENTS |  |  | Install Flood Vents And Small Louvers --> OG8 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | 33 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01290 | [8 empty] | Install Stair And Roof Platform Railings --> OG8 | 5 | 0 | 2022-04-04 | 2022-04-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01295 |  | OG8 | [6 empty] | Install Ladders --> OG8 | 3 | 0 | 2022-10-03 | 2022-10-05 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01305 | CCC | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Sheetrock and Stucco --> OG8 | 10 | 10 | 2023-04-18 08:00 | 2023-05-01 17:00 | 0 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01310 | FAXA | OG8 | FLOORING | Interior | NEW BUILDINGS | CERAMIC |  |  | Install Ceramic Tile --> OG8 | 2 | 2 | 2023-05-02 08:00 | 2023-05-03 17:00 | 0 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01315 | TRIANGLE | OG8 | CEILING | Interior | NEW BUILDINGS |  |  |  | Install Acoustical Ceiling --> OG8 | 2 | 2 | 2023-05-04 08:00 | 2023-05-05 17:00 | 0 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01320 |  | OG8 | WATERPROOFING | [5 empty] | Place Crystaline Waterproofing In Plumbing Shaft --> OG8 | 3 | 0 | 2022-11-17 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01325 | GG PAINT | OG8 | PAINT | Interior | NEW BUILDINGS |  |  |  | Paint All Areas --> OG8 | 15 | 15 | 2023-06-08 08:00 | 2023-06-28 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01330 | MLJ | OG8 | SIGNS | Interior | NEW BUILDINGS |  |  |  | Install Signs --> OG8 | 2 | 2 | 2023-06-29 08:00 | 2023-06-30 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01235 | DSTAR | OG8 | WATERPROOFING | Structure | NEW BUILDINGS |  |  |  | Install Waterproofing to Parapet --> OG8 | 3 | 0 | 2023-02-15 | 2023-02-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01280 | CCC | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Stucco Soffit --> OG8 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01317 | NAVILLUS | OG8 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulated Metal Panels left out for Access --> OG8 | 5 | 5 | 2023-06-01 08:00 | 2023-06-07 17:00 | -39 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01092 | [8 empty] | Install Remaining HW/CW Into OG8 (5' from the building) | 5 | 0 | 2022-01-04 | 2022-01-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01094 | [8 empty] | Install Remaining Electrical POE Into OG8 | 5 | 0 | 2021-11-26 | 2021-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01605 | MLJ | OGW | Excavation |  |  | EXC RETAINING |  |  | Excavate for retaining wall --> OG Phase 2A | 2 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01610 | MLJ | OGW | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-OGW | Form Retaining wall footing --> OG Phase 2A | 2 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01615 |  | OGE | REBAR | [5 empty] | Rebar Retaining wall footing --> OG Phase 2A | 2 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01620 | MLJ | OGW | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall footing --> OG Phase 2A | 1 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01625 |  | OGW | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall footing --> OG Phase 2A | 1 | 0 | 2022-09-26 | 2022-09-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01630 | MLJ | OGW | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-OGW | Form Retaining wall --> OG Phase 2A | 3 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01635 |  | OGE | REBAR | [5 empty] | Rebar Retaining wall --> OG Phase 2A | 3 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01640 | MLJ | OGW | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall --> OG Phase 2A | 1 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01645 |  | OGW | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall --> OG Phase 2A | 1 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01705 | MLJ | OGW | CURBS | Restoration | SITE |  |  |  | Install Street Curbs --> OG Phase 2A | 15 | 15 | 2023-11-14 08:00 | 2023-12-05 17:00 | -187 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01710 | JMC | OGW | SIDEWALKS | Restoration | SITE |  |  |  | Install sidewalks --> OG Phase 2A | 10 | 10 | 2023-12-06 08:00 | 2023-12-19 17:00 | -187 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01715 |  | OGW | CURBS | [5 empty] | Install curb around play area --> OG Phase 2A | 5 | 0 | 2022-10-25 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01720 |  | OGE |  |  |  | PLAYGROUND |  |  | Install Safety Surface --> OG Phase 2A | 5 | 0 | 2022-10-25 | 2022-10-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01725 | MLJ | OGW | Concrete |  |  | SITE CONCRETE |  |  | Install site furniture concrete foundations --> OG Phase 2A | 10 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01730 | JMC | OGE | COLORED CONCRETE | Restoration | SITE |  |  |  | Install integrally colored concrete walkways --> OG Phase 2A | 20 | 20 | 2023-12-20 08:00 | 2024-01-18 17:00 | -187 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01735 |  | OGW |  |  |  | PLAYGROUND |  |  | Install Play area items --> OG Phase 2A | 5 | 0 | 2022-10-25 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01740 |  | OGW |  |  |  | PLAYGROUND |  |  | Install fence around play area --> OG Phase 2A | 10 | 0 | 2022-10-25 | 2022-10-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01745 | ATLAS | OGE | SITE RESTORATION | Restoration | SITE |  |  |  | Install Fence at building --> OGP1 | 5 | 5 | 2024-01-19 08:00 | 2024-01-25 17:00 | -187 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01750 |  | OGE | SITE RESTORATION | [5 empty] | Place Site Furniture --> OG Phase 2A | 10 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01755 | ASPEN | OGE | TOPSOIL | Restoration | SITE |  |  |  | Place topsoil --> OG Phase 2A | 3 | 3 | 2024-04-01 08:00 | 2024-04-03 17:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01760 | ASPEN | OGE |  | Restoration | SITE |  |  |  | Place trees and plantings --> OG Phase 2A | 5 | 5 | 2024-04-04 08:00 | 2024-04-10 17:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01765 | ASPEN | OGE |  | Restoration | SITE |  |  |  | Place lawn --> OG Phase 2A | 5 | 5 | 2024-04-11 08:00 | 2024-04-17 17:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.5 | OGP1-01770 | MLJ | OGE |  | Closeout | SITE |  |  |  | Demobilize from OG Phase 2A | 5 | 5 | 2024-04-18 08:00 | 2024-04-24 17:00 | -228 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.7 | OGP1-01805 | CLOSEOUT | OGE | INSPECTION | Closeout | SITE |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-07-03 08:00 | 2023-07-10 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.7 | OGP1-01810 | PUNCH LIST | OGE |  | Closeout | SITE |  |  |  | Perform Punch List | 10 | 10 | 2023-07-11 08:00 | 2023-07-24 17:00 | -39 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-03005 | WELKIN | OG8 | [6 empty] | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 2022-09-27 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-03010 | WELKIN | OG8 | [6 empty] | Install Condensate Pump - Foundation Level | 10 | 0 | 2022-10-24 | 2022-11-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 2022-05-27 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03110 | [8 empty] | Rig Fuel Oil Tank & Piping - 1st Floor | 3 | 0 | 2022-03-22 | 2022-03-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03125 |  | OG8 | [6 empty] | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-06-21 | 2022-10-18 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03130 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Conduit for FOT Controls - 1st Floor | 20 | 10 | 2022-08-01 08:00 | 2023-03-10 17:00 | -79 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03135 | WELKIN | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 3 | 2023-01-23 08:00 | 2023-03-01 17:00 | -66 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03140 |  | OG8 | [6 empty] | Install Plumbing Equipment - 1st Floor | 15 | 0 | 2022-10-04 | 2022-10-21 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03145 | WELKIN | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03150 | MEP | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 19 | 2023-02-24 08:00 | 2023-04-13 17:00 | -73 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03107 | WELKIN | OG8 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 0 | 2022-06-13 | 2022-10-18 13:48 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03142 | WELKIN | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Mechanical Equipment - 1st Floor | 15 | 0 | 2022-08-01 08:00 | 2023-02-24 15:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03210 | [8 empty] | Rig Boiler Equipment & Piping - 2nd Floor | 5 | 0 | 2022-04-11 | 2022-04-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03225 |  | OG8 | [6 empty] | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 0 | 2022-06-13 08:00 | 2022-12-09 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03230 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Conduit for Boiler Controls - 2nd Floor | 20 | 16 | 2022-09-01 | 2023-03-31 17:00 | -106 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03235 | WELKIN | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 2nd Floor | 5 | 2 | 2022-11-14 | 2023-05-02 17:00 | -106 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03240 | [8 empty] | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03245 | WELKIN | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-05-03 08:00 | 2023-05-16 17:00 | -106 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03250 | MEP | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 19 | 2023-01-23 08:00 | 2023-05-31 17:00 | -106 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03207 | WELKIN | OG8 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 20 | 0 | 2022-06-13 | 2022-11-28 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03242 | WELKIN | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Mechanical Equipment - 2nd Floor | 20 | 0 | 2022-07-11 08:00 | 2023-02-03 11:12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-03405 | [8 empty] | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-03410 | [8 empty] | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.3 | OG8-03415 | TRIANGLE | OG8 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulation - Roof | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-03505 | CLOSEOUT | OG8 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG8 | 4 | 4 | 2023-06-01 08:00 | 2023-06-06 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-03510 | CLOSEOUT | OG8 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Perform Start-Up Testing & Sign-off - Boilers - OG8 | 15 | 15 | 2023-07-24 08:00 | 2023-08-11 17:00 | -138 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-03515 | CLOSEOUT | OG8 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - OG8 | 16 | 16 | 2023-08-14 08:00 | 2023-09-05 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-03520 | PUNCH LIST | OG8 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG8 | 5 | 5 | 2023-09-06 08:00 | 2023-09-12 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-03530 | MEP | OG8 | CLOSEOUT | Interior | NEW BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG8 | 4 | 4 | 2023-09-14 08:00 | 2023-09-19 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-03525 | CLOSEOUT | OG8 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG8 | 1 | 1 | 2023-09-13 08:00 | 2023-09-13 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.1 | OG4-01005 | ATCO | OG4 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - OG4 | 3 | 3 | 2023-09-22 08:00 | 2023-09-26 17:00 | -114 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.1 | OG4-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> OG4 | 3 | 0 | 2021-09-20 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.1 | OG4-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG4 | 3 | 0 | 2022-01-17 08:00 | 2022-01-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.1 | OG4-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> OG4 | 3 | 0 | 2021-09-20 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.1 | OG4-01025 | ATCO | OG4 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> OG4 | 5 | 0 | 2022-07-12 | 2022-07-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.1 | OG4-01030 | ATCO | OG4 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> OG4 | 5 | 0 | 2022-07-12 | 2022-07-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01105 | MLJ | OG4 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG4 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG4 | 10 | 0 | 2021-05-21 | 2022-09-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01110 | MLJ | OG4 | DEMO |  |  | DEMO DOORS WINDOWS |  |  | Selective Demo (Doors, windows) - 1st Floor --> OG4 | 5 | 0 | 2022-08-29 | 2022-09-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01115 | MLJ | OG4 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> OG4 | 10 | 0 | 2021-06-26 08:00 | 2022-09-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01205 | MLJ | OG4 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG4 | 5 | 0 | 2022-09-05 | 2022-09-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01210 | [8 empty] | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG4 | 5 | 0 | 2022-06-20 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG4 | 5 | 0 | 2021-10-04 | 2022-01-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01310 | [8 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG4 | 5 | 0 | 2022-03-28 | 2022-04-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> OG4 | 5 | 0 | 2022-04-18 | 2022-04-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> OG4 | 5 | 0 | 2022-05-27 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01325 | CCC | OG4 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> OG4 | 3 | 0 | 2022-03-18 | 2022-11-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01330 | CCC | OG4 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> OG4 | 5 | 0 | 2022-04-28 | 2022-11-28 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01335 | CCC | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> OG4 | 10 | 10 | 2023-04-14 13:00 | 2023-04-28 12:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.4 | OG4-01340 | FLOORING | OG4 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> OG4 | 2 | 2 | 2023-04-28 13:00 | 2023-05-02 12:00 | -12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01405 |  | OG4 | EXCAVATION |  |  |  | 31-1000 | 31-1000-OG4 | Excavate at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 2022-05-30 | 2022-06-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01410 |  | OG4 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-OG4 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 9 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 4 | 0 | 2022-06-06 | 2022-06-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 2022-06-21 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 4 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01430 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01435 | [8 empty] | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 5 | 0 | 2022-06-06 | 2022-06-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01440 | [8 empty] | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 2022-06-21 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01445 | [8 empty] | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01450 | FAXA | OG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 2022-09-26 | 2022-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01455 | MLJ | OG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG4 | Backfill at Curtain Wall for flood protection (East Side) --> OG4 | 4 | 0 | 2022-10-03 | 2022-10-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> OG4 | 8 | 0 | 2022-05-30 | 2022-06-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01510 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 10 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01515 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 5 | 0 | 2022-06-06 | 2022-06-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01520 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 0 | 2022-06-21 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01525 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 5 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01530 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 8 | 0 | 2022-10-07 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01535 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 6 | 0 | 2022-10-17 | 2022-10-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01540 | MLJ | OG4 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG4 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01545 | MLJ | OG4 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 2023-03-03 08:00 | 2023-03-08 17:00 | 2 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01550 | FAXA | OG4 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 2023-03-10 08:00 | 2023-03-15 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01555 | MLJ | OG4 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG4 | Backfill at Curtain Wall for flood protection (South Side) --> OG4 | 5 | 5 | 2023-03-16 08:00 | 2023-03-22 17:00 | 1 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01605 | MLJ | OG4 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG4 | Excavate at Curtain Wall for flood protection (North Side) --> OG4 | 8 | 0 | 2022-06-13 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 10 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 5 | 0 | 2022-06-06 | 2022-06-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 2022-06-21 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01625 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 5 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01630 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 8 | 0 | 2022-10-03 | 2022-10-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01635 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 6 | 0 | 2022-10-07 | 2022-10-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01640 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 2022-10-12 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01645 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 2022-10-17 | 2022-10-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01650 | FAXA | OG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 2022-10-18 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01655 | MLJ | OG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG4 | Backfill at Curtain Wall for flood protection (North Side) --> OG4 | 5 | 0 | 2022-10-25 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01705 | [8 empty] | Excavate at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 2022-05-30 | 2022-06-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01710 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 9 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01715 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 4 | 0 | 2022-06-06 | 2022-06-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01720 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 2022-06-21 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01725 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 4 | 0 | 2022-06-17 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01730 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 2022-09-26 | 2022-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01735 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 5 | 0 | 2022-10-03 | 2022-10-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01740 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 2022-10-07 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01745 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 2022-10-17 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01750 | FAXA | OG4 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 2022-10-25 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01755 | MLJ | OG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG4 | Backfill at Curtain Wall for flood protection (West Side) --> OG4 | 4 | 0 | 2022-10-27 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01805 | [8 empty] | Excavate for concrete shelf around bldg perimeter --> OG4 | 10 | 0 | 2022-05-30 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> OG4 | 5 | 0 | 2022-06-06 | 2022-06-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> OG4 | 5 | 0 | 2022-06-21 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01820 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Place infill concrete in area ways around bldg perimeter --> OG4 | 5 | 0 | 2022-06-29 08:00 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01825 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Place waterproofing on concrete shelf around bldg perimeter --> OG4 | 10 | 0 | 2022-07-02 08:00 | 2022-07-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01830 | FAXA | OG4 | CMU | [5 empty] | Place CMU around bldg perimeter --OG4 | 15 | 0 | 2022-07-08 | 2022-08-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01835 |  | OG4 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> OG4 | 10 | 0 | 2022-08-16 08:00 | 2022-08-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01840 | MLJ | OG4 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> OG4 | 10 | 0 | 2023-01-25 08:00 | 2023-01-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01845 | FAXA | OG4 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG4 | 20 | 0 | 2022-10-19 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01850 | MLJ | OG4 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG4 | Backfill around bdg perimeter --> OG4 | 5 | 0 | 2022-10-31 | 2022-11-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01855 | CCC | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> OG4 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | 53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01860 | MLJ | OG4 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> OG4 | 5 | 5 | 2023-03-03 08:00 | 2023-03-09 17:00 | 53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01865 | MLJ | OG4 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> OG4 | 3 | 3 | 2023-03-10 08:00 | 2023-03-14 17:00 | 53 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.5 | OG4-01350 | MLJ | OG4 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-OG4 | Drill dowels and place rebar for boiler room concrete walls --> OG4 | 5 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.5 | OG4-01355 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Form boiler room concrete walls --> OG4 | 5 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.5 | OG4-01360 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Pour Concrete boiler room walls --> OG4 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.5 | OG4-01365 | MLJ | OG4 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG4 | Strip Forms boiler room concrete walls --> OG4 | 3 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.5 | OG4-01370 |  | OG4 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> OG4 | 10 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.6 | OG4-01385 | [8 empty] | Refurbish Elevator 1 --> OG4 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.6 | OG4-01390 | [8 empty] | Refurbish Elevator 2 --> OG4 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.6 | OG4-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.7 | OG4-09005 | CLOSEOUT | OG4 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-09-27 08:00 | 2023-10-03 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.7 | OG4-09010 | PUNCH LIST | OG4 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-10-04 08:00 | 2023-10-18 17:00 | -99 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2021-05-26 | 2022-04-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03010 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Condensate Pump - Cellar | 10 | 0 | 2022-12-12 | 2022-12-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03020 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pump Controls - Cellar | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -84 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03025 | WELKIN | OG4 | [6 empty] | Perform Hydrostatic Testing - Cellar | 5 | 0 | 2022-12-09 08:00 | 2022-12-09 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03030 | VITAL | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-12-19 | 2022-12-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03035 | CLOSEOUT | OG4 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-04-03 08:00 | 2023-04-14 17:00 | -74 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03040 | MEP | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 6 | 2022-12-15 08:00 | 2023-03-06 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03015 | WELKIN | OG4 | [6 empty] | Install Steam Traps - Cellar | 2 | 0 | 2022-11-10 08:00 | 2022-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03007 | WELKIN | OG4 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2022-08-01 | 2022-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-03032 | WELKIN | OG4 | [6 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2022-09-26 08:00 | 2022-10-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03120 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 10 | 2022-04-01 08:00 | 2023-03-17 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03125 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03130 | NAVILLUS | OG4 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2023-02-07 | 2023-02-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03135 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03140 | MEP | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-04-10 08:00 | 2023-05-05 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03115 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Steam Traps - 1st Floor | 3 | 3 | 2023-03-08 13:00 | 2023-03-13 12:00 | -85 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03110 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 3 | 2022-04-01 08:00 | 2023-03-01 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03112 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 3 | 2023-02-02 08:00 | 2023-03-03 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.2 | OG4-03107 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 5 | 3 | 2023-02-06 08:00 | 2023-03-08 12:00 | -107 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03220 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-04-03 08:00 | 2023-04-28 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03230 | NAVILLUS | OG4 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03235 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03240 | MEP | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-05-15 08:00 | 2023-06-12 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03210 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.3 | OG4-03215 | WELKIN | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03305 | CLOSEOUT | OG4 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG4 | 4 | 4 | 2023-06-13 08:00 | 2023-06-16 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03310 | CLOSEOUT | OG4 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - OG4 | 15 | 15 | 2023-07-26 08:00 | 2023-08-15 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03315 | CLOSEOUT | OG4 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - OG4 | 16 | 16 | 2023-08-16 08:00 | 2023-09-07 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03320 | PUNCH LIST | OG4 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG4 | 5 | 5 | 2023-09-08 08:00 | 2023-09-14 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03330 | MEP | OG4 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG4 | 4 | 4 | 2023-09-18 08:00 | 2023-09-21 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03325 | CLOSEOUT | OG4 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG4 | 1 | 1 | 2023-09-15 08:00 | 2023-09-15 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-03335 | MLJ | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - OG4 | 10 | 10 | 2023-09-08 08:00 | 2023-09-21 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.1 | OG5-01005 | ATCO | OG5 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - OG5 | 3 | 3 | 2024-01-15 08:00 | 2024-01-17 17:00 | -189 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.1 | OG5-01010 | ATCO | OG5 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - wire insulation - cellar --> OG5 | 3 | 3 | 2024-01-15 08:00 | 2024-01-17 17:00 | -189 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.1 | OG5-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG5 | 3 | 0 | 2021-12-27 08:00 | 2021-12-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.1 | OG5-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> OG5 | 3 | 0 | 2021-11-01 08:00 | 2021-11-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.1 | OG5-01025 | ATCO | OG5 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> OG5 | 5 | 0 | 2022-07-13 08:00 | 2022-07-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.1 | OG5-01030 | ATCO | OG5 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> OG5 | 5 | 0 | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01105 | [8 empty] | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG5 | 10 | 0 | 2021-04-25 | 2022-06-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01110 | [8 empty] | Selective Demo (Doors, windows) - 1st Floor --> OG5 | 5 | 0 | 2022-06-01 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01115 | MLJ | OG5 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> OG5 | 10 | 0 | 2021-06-26 08:00 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01205 | MLJ | OG5 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG5 | 5 | 0 | 2022-10-17 08:00 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01210 | MLJ | OG5 | DEMO |  |  | DEMO SLAB OPEN FOR MECH |  |  | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG5 | 5 | 0 | 2021-10-05 | 2022-07-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG5 | 5 | 0 | 2021-10-26 08:00 | 2022-01-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01310 | [8 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG5 | 5 | 0 | 2022-06-20 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> OG5 | 5 | 0 | 2022-04-25 | 2022-04-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> OG5 | 5 | 0 | 2022-06-08 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01325 | CCC | OG5 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> OG5 | 3 | 0 | 2022-04-26 | 2022-11-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01330 | CCC | OG5 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> OG5 | 5 | 0 | 2022-05-11 | 2022-11-25 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01335 | CCC | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> OG5 | 10 | 1 | 2022-06-20 | 2023-02-27 17:00 | 32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.4 | OG5-01340 | FLOORING | OG5 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> OG5 | 2 | 2 | 2023-02-28 08:00 | 2023-03-01 17:00 | 32 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01405 |  | OG5 | EXCAVATION |  |  |  | 31-1000 | 31-1000-OG5 | Excavate at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 2022-05-26 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01410 |  | OG5 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-OG5 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 9 | 0 | 2022-05-31 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 4 | 0 | 2022-06-06 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 2022-06-09 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 4 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01430 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 2022-09-30 | 2022-10-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01435 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 5 | 0 | 2022-10-06 | 2022-10-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01440 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 2022-10-11 | 2022-10-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01445 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 2022-10-12 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01450 | FAXA | OG5 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 2022-10-17 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01455 | MLJ | OG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG5 | Backfill at Curtain Wall for flood protection (East Side) --> OG5 | 4 | 0 | 2022-10-24 | 2022-12-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> OG5 | 8 | 0 | 2022-05-26 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01510 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 10 | 0 | 2022-05-31 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01515 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 5 | 0 | 2022-06-06 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01520 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-06-09 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01525 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 5 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01530 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 8 | 0 | 2022-06-13 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01535 | [8 empty] | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 6 | 0 | 2022-06-16 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01540 | [8 empty] | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-06-24 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01545 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-08-23 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01550 | FAXA | OG5 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-08-25 08:00 | 2022-09-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01555 | MLJ | OG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG5 | Backfill at Curtain Wall for flood protection (South Side) --> OG5 | 5 | 0 | 2022-08-15 | 2022-08-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01560 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Form for slab at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-08-18 | 2022-08-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01565 |  | OG5 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> OG5 | 6 | 0 | 2022-08-19 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01570 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Pour slab at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-08-22 08:00 | 2022-08-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01575 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> OG5 | 2 | 0 | 2022-08-23 08:00 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01580 | MLJ | OG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG5 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 2022-12-05 | 2022-12-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01605 | [8 empty] | Excavate at Curtain Wall for flood protection (North Side) --> OG5 | 8 | 0 | 2022-05-16 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 10 | 0 | 2022-05-26 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 5 | 0 | 2022-05-31 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 2022-06-06 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01625 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 5 | 0 | 2022-06-09 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01630 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 8 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01635 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 6 | 0 | 2022-08-01 | 2022-08-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01640 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 2022-08-07 | 2022-08-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01645 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 2022-08-10 | 2022-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01650 | FAXA | OG5 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 2022-08-15 | 2022-08-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01655 | MLJ | OG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG5 | Backfill at Curtain Wall for flood protection (North Side) --> OG5 | 5 | 0 | 2022-08-22 | 2022-08-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01705 | MLJ | OG5 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG5 | Excavate at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 2022-05-16 08:00 | 2022-05-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01710 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 9 | 0 | 2022-05-26 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01715 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 4 | 0 | 2022-05-31 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01720 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 0 | 2022-06-06 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01725 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 4 | 0 | 2022-06-09 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01730 | [8 empty] | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01735 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 5 | 0 | 2022-12-13 | 2022-12-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01740 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 0 | 2022-12-16 | 2022-12-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01745 | MLJ | OG5 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG5 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | 33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01750 | FAXA | OG5 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 3 | 2023-03-02 08:00 | 2023-03-06 17:00 | 33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01755 | MLJ | OG5 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG5 | Backfill at Curtain Wall for flood protection (West Side) --> OG5 | 4 | 4 | 2023-03-07 08:00 | 2023-03-10 17:00 | 33 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01805 | MLJ | OG5 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG5 | Excavate for concrete shelf around bldg perimeter --> OG5 | 10 | 0 | 2022-05-05 08:00 | 2022-05-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> OG5 | 5 | 0 | 2022-06-08 | 2022-06-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> OG5 | 5 | 0 | 2022-06-09 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01820 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Place infill concrete in area ways around bldg perimeter --> OG5 | 5 | 0 | 2022-06-30 08:00 | 2022-07-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01825 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Place waterproofing on concrete shelf around bldg perimeter --> OG5 | 10 | 0 | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01830 | FAXA | OG5 | CMU | [5 empty] | Place CMU around bldg perimeter --OG5 | 15 | 0 | 2022-07-22 | 2022-08-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01835 |  | OG5 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> OG5 | 10 | 0 | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01840 | MLJ | OG5 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> OG5 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01845 | FAXA | OG5 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG5 | 20 | 0 | 2022-09-12 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01850 | MLJ | OG5 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG5 | Backfill around bdg perimeter --> OG5 | 5 | 0 | 2022-11-14 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01855 | CCC | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> OG5 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | 53 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01860 | MLJ | OG5 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> OG5 | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | 47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01865 | MLJ | OG5 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> OG5 | 3 | 3 | 2023-03-20 08:00 | 2023-03-22 17:00 | 47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.5 | OG5-01350 | MLJ | OG5 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-OG5 | Drill dowels and place rebar for boiler room concrete walls --> OG5 | 5 | 0 | 2022-10-27 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.5 | OG5-01355 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Form boiler room concrete walls --> OG5 | 5 | 0 | 2022-11-02 | 2022-11-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.5 | OG5-01360 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Pour Concrete boiler room walls --> OG5 | 2 | 0 | 2022-11-09 | 2022-11-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.5 | OG5-01365 | MLJ | OG5 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG5 | Strip Forms boiler room concrete walls --> OG5 | 3 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.5 | OG5-01370 |  | OG5 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> OG5 | 10 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.6 | OG5-01385 | [8 empty] | Refurbish Elevator 1 --> OG5 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.6 | OG5-01390 | [8 empty] | Refurbish Elevator 2 --> OG5 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.6 | OG5-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.7 | OG5-09005 | CLOSEOUT | OG5 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2024-01-18 08:00 | 2024-01-24 17:00 | -189 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.7 | OG5-09010 | PUNCH LIST | OG5 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2024-01-25 08:00 | 2024-02-07 17:00 | -174 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.2 | OG4-01220 | MLJ | OG4 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO PUMPS | 02-6010 | 02-6010-OG4 | Selective Demo (Pumps etc..) - Cellar --> OG4 | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -84 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.2 | OG5-01220 | MLJ | OG5 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-OG5 | Selective Demo (Pumps etc..) - Cellar --> OG5 | 5 | 0 | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02130 | [8 empty] | Pull & Terminate Automatic Temperature Control Cable - OG-8 --> OG-4 | 10 | 0 | 2022-04-12 | 2022-04-16 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.2 | OGP1-02150 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Pull & Terminate Automatic Temperature Control Cable - OG-8 --> OG-5 | 10 | 10 | 2023-10-27 08:00 | 2023-11-13 17:00 | -200 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03005 | WELKIN | OG5 | [6 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2022-08-01 | 2022-09-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03010 | WELKIN | OG5 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-09-26 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03020 |  | OG5 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2023-01-04 | 2023-01-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03025 | WELKIN | OG5 | [6 empty] | Perform Hydrostatic Testing - Cellar | 5 | 0 | 2022-12-09 08:00 | 2022-12-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03030 |  | OG5 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-09-01 | 2022-09-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03035 | CLOSEOUT | OG5 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -34 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03040 | MEP | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 6 | 2022-12-15 08:00 | 2023-03-06 17:00 | -30 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03015 | WELKIN | OG5 | [6 empty] | Install Steam Traps - Cellar | 2 | 0 | 2022-12-05 08:00 | 2022-12-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03007 | WELKIN | OG5 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2022-04-01 08:00 | 2022-12-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-03032 | WELKIN | OG5 | [6 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2022-12-01 08:00 | 2022-12-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03120 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 20 | 2023-03-13 08:00 | 2023-04-07 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03125 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03130 | NAVILLUS | OG5 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2023-02-07 08:00 | 2023-02-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03135 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03140 | MEP | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-05-01 08:00 | 2023-05-26 17:00 | -89 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03115 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Steam Traps - 1st Floor | 1 | 1 | 2022-11-21 08:00 | 2023-02-27 17:00 | -60 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03110 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03112 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.2 | OG5-03107 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 2023-03-06 08:00 | 2023-03-17 17:00 | -114 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03220 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-04-24 08:00 | 2023-05-19 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03230 | NAVILLUS | OG5 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 2023-04-03 08:00 | 2023-04-21 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03235 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-05-22 08:00 | 2023-06-05 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03240 | MEP | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-06-06 08:00 | 2023-07-03 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03210 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.3 | OG5-03215 | WELKIN | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03305 | CLOSEOUT | OG5 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG5 | 4 | 4 | 2023-10-27 08:00 | 2023-11-01 17:00 | -194 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03310 | MLJ | OG5 | STARTUP | Interior | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - OG5 | 15 | 15 | 2023-11-14 08:00 | 2023-12-05 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03315 | CLOSEOUT | OG5 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - OG5 | 16 | 16 | 2023-12-06 08:00 | 2023-12-28 17:00 | -189 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03320 | PUNCH LIST | OG5 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG5 | 5 | 5 | 2023-12-29 08:00 | 2024-01-05 17:00 | -161 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03330 | MEP | OG5 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG5 | 4 | 4 | 2024-01-09 08:00 | 2024-01-12 17:00 | -161 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03325 | CLOSEOUT | OG5 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG5 | 1 | 1 | 2024-01-08 08:00 | 2024-01-08 17:00 | -161 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-03335 | MLJ | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - OG5 | 10 | 10 | 2023-12-29 08:00 | 2024-01-12 17:00 | -189 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01005 | [8 empty] | Install Site Fencing - O'Dwyer Gardens - West (OG-9) | 10 | 0 | 2021-02-15 | 2021-02-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01015 | [8 empty] | Install Overhead Protection - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01020 | [6 empty] | 31-1900 |  | Install Tree Protection | 5 | 0 | 2020-11-05 | 2020-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01025 | [8 empty] | Remove Trees | 2 | 0 | 2021-01-14 | 2021-01-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01000 | [8 empty] | Remove Curbs And Existing Fencing | 10 | 0 | 2021-02-23 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01035 | [8 empty] | Install Erosion Control | 5 | 0 | 2022-02-02 | 2022-02-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01010 | [8 empty] | Set Up Yard and Staging - N/A | 10 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01045 | [8 empty] | Clear & Grub | 10 | 0 | 2021-03-26 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01050 | [8 empty] | Scrape & Store Topsoil | 10 | 0 | 2021-03-26 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01055 | [8 empty] | Soil Testing | 10 | 0 | 2021-03-04 | 2021-03-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01060 | [6 empty] | 02-2000 |  | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 2021-04-26 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01065 | [8 empty] | Remove Retaining Walls | 10 | 0 | 2022-01-21 | 2022-03-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01070 | [8 empty] | Install Deep Wells For Dewatering - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01075 | [8 empty] | Install Piping For Deep Wells - N/A | 5 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01080 | [8 empty] | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01085 | [8 empty] | Run Electric For Dewatering - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01105 | [8 empty] | Excavate for CW Pipe - OG3 --> OG9 | 10 | 0 | 2021-09-02 | 2021-09-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01110 | [8 empty] | Install CW Piping - OG3 --> OG9 | 15 | 0 | 2021-11-26 08:00 | 2021-12-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01115 | WELKIN | [7 empty] | Test CW Piping - OG3 --> OG9 | 10 | 0 | 2021-12-29 | 2022-01-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01120 | [8 empty] | Backfill CW Piping - OG3 --> OG9 | 5 | 0 | 2022-05-04 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01150 | [8 empty] | Excavate for Electric OG3--> OG9 | 10 | 0 | 2021-10-04 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01155 | [8 empty] | Install Electrical Conduit OG3--> OG9 | 10 | 0 | 2021-10-05 | 2021-12-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01160 | [8 empty] | Encase conduit in concrete OG3--> OG9 | 5 | 0 | 2021-12-01 | 2022-01-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01165 | [8 empty] | Backfill Electrical OG3--> OG9 | 5 | 0 | 2022-01-03 | 2022-01-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01405 | NATIONAL GRID | OGW |  | Utilities | SITE |  |  |  | National Gas to Install Line - W35th --> OG9 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 29 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01205 | [8 empty] | Excavate for Electric OG3--> MH | 3 | 0 | 2021-10-10 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01210 | [8 empty] | Install Electrical Conduit OG3--> MH | 2 | 0 | 2021-11-26 | 2021-12-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01215 | [8 empty] | Encase conduit in concrete OG3--> MH | 2 | 0 | 2022-01-10 | 2022-01-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01220 | [8 empty] | Backfill Electrical OG3 --> MH | 2 | 0 | 2022-01-03 | 2022-01-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01230 | [8 empty] | Excavate for Electric OG2 -> OG9 | 10 | 0 | 2021-10-13 | 2021-12-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01235 | [8 empty] | Install Electrical Conduit & MH OG2 -> OG9 | 10 | 0 | 2021-10-05 | 2022-01-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01240 | [8 empty] | Encase conduit in concrete OG2 -> OG9 | 3 | 0 | 2021-12-01 | 2022-01-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01245 | [8 empty] | Backfill Electrical OG2 -> OG9 | 5 | 0 | 2021-12-05 | 2022-01-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01255 | [8 empty] | Excavate for Electric OG2--> MH | 3 | 0 | 2022-01-14 | 2022-01-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01260 | [8 empty] | Install Electrical Conduit OG2--> MH | 2 | 0 | 2021-12-08 | 2022-02-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01265 | [8 empty] | Encase conduit in concrete OG2--> MH | 2 | 0 | 2022-01-20 | 2022-02-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01270 | [8 empty] | Backfill Electrical OG2 --> MH | 2 | 0 | 2022-02-07 | 2022-02-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01275 | [8 empty] | Excavate for Steam OG4--> OG3 | 15 | 0 | 2021-12-14 | 2022-02-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01280 | [8 empty] | Install Steam piping OG4--> OG3 - | 20 | 0 | 2022-04-18 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01285 | [8 empty] | Test Steam Piping OG4--> OG3 | 8 | 0 | 2022-06-07 | 2022-06-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01290 | [8 empty] | Backfill Steam Piping OG4--> OG3 | 10 | 0 | 2022-06-14 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01505 | MLJ | OGW | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-OGW | Excavate for water line to drinking fountain OGW --> Water Main W32nd Street | 2 | 0 | 2022-11-25 08:00 | 2022-11-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01510 |  | OGW |  |  |  | PLAYGROUND |  |  | Install water line to drinking fountain OGW --> Water Main W32nd Street | 5 | 0 | 2022-11-29 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01515 |  | OGW |  |  |  | PLAYGROUND |  |  | Tap water main for drinking fountain water line OGW --> Water Main W32nd Street | 2 | 0 | 2022-12-05 | 2022-12-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01520 | MLJ | OGW | BACKFILL |  |  | BACKFILL SITE |  |  | Backfill water line drinking fountain OGW --> Water Main W32nd Street | 2 | 0 | 2022-12-07 | 2022-12-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01560 | MLJ | OGW | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD14 to AD13 TO AD7 Piping & Tie-in to Existing | 15 | 0 | 2022-08-08 08:00 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01565 | MLJ | OGW | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD14 to AD13 TO AD7 Piping | 5 | 0 | 2022-08-25 | 2022-08-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01090 | [8 empty] | Activate Dewatering System - N/A | 1 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01095 |  |  | dewatering | [5 empty] | Maintain Dewatering | 242 | 0 | 2021-08-02 17:00 | 2022-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01287 | [8 empty] | Install Automatic Temperature Control Conduit - OG4--> OG3 | 2 | 0 | 2022-05-04 | 2022-05-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01100 | [8 empty] | De-Activate Dewatering | 1 | 0 | 2022-05-25 | 2022-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01117 | [8 empty] | Install Automatic Temperature Control Conduit - OG3 --> OG9 | 2 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01295 | [8 empty] | Excavate for Steam & HW OG3--> OG2 | 15 | 0 | 2021-12-01 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01300 | WELKIN | OGW | UG PIPE | [5 empty] | Install Steam and HW piping OG3--> OG2 | 20 | 0 | 2022-09-14 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01305 | WELKIN | OGW | UG PIPE | [5 empty] | Test Steam & HW Piping OG3--> OG2 | 8 | 0 | 2022-11-21 | 2022-11-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01315 | MLJ | OGE | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-OGE | Backfill Steam & HW Piping OG3--> OG2 | 10 | 0 | 2022-11-28 | 2022-11-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01310 |  | OGW | [6 empty] | Install Automatic Temperature Control Conduit - OG3--> OG2 | 2 | 0 | 2022-11-30 08:00 | 2022-12-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01605 | MLJ | OGW | Excavation |  |  | EXC RETAINING |  |  | Excavate for retaining wall --> OG Phase 3A | 2 | 0 | 2022-09-12 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01610 | MLJ | OGW | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-OGW | Form Retaining wall footing --> OG Phase 3A | 2 | 0 | 2022-09-19 | 2022-09-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01615 |  | OGW | REBAR | [5 empty] | Rebar Retaining wall footing --> OG Phase 3A | 2 | 0 | 2022-09-20 | 2022-09-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01620 | MLJ | OGW | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall footing --> OG Phase 3A | 1 | 0 | 2022-09-21 | 2022-09-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01625 |  | OGW | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall footing --> OG Phase 3A | 1 | 0 | 2022-09-22 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01630 | MLJ | OGW | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-OGW | Form Retaining wall --> OG Phase 3A | 3 | 0 | 2022-09-22 | 2022-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01635 |  | OGW | REBAR | [5 empty] | Rebar Retaining wall --> OG Phase 3A | 3 | 0 | 2022-10-11 | 2022-10-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01640 | MLJ | OGW | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall --> OG Phase 3A | 1 | 0 | 2022-10-18 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01645 |  | OGW | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall --> OG Phase 3A | 1 | 0 | 2022-10-19 | 2022-10-21 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01705 | JMC | OGW | CURBS | Restoration | SITE |  |  |  | Install Street Curbs --> OG Phase 3A | 15 | 15 | 2023-04-17 08:00 | 2023-05-05 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01710 | JMC | OGW | SIDEWALKS | Restoration | SITE |  |  |  | Install sidewalks --> OG Phase 3A | 10 | 10 | 2023-05-22 08:00 | 2023-06-05 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01715 | MLJ | OGW | CURBS | Restoration | SITE |  |  |  | Install curb around play area --> OG Phase 3A | 5 | 5 | 2023-06-06 08:00 | 2023-06-12 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01720 | MLJ | OGW |  | Restoration | SITE | PLAYGROUND |  |  | Install Safety Surface --> OG Phase 3A | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01725 | MLJ | OGW | Concrete | Restoration | SITE | SITE CONCRETE |  |  | Install site furniture concrete foundations --> OG Phase 3A | 10 | 10 | 2023-05-08 08:00 | 2023-05-19 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01730 | JMC | OGW | COLORED CONCRETE | Restoration | SITE |  |  |  | Install integrally colored concrete walkways --> OG Phase 3A | 20 | 20 | 2023-06-20 08:00 | 2023-07-18 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01735 | MLJ | OGW |  | Restoration | SITE | PLAYGROUND |  |  | Install Play area items --> OG Phase 3A | 5 | 0 | 2023-02-13 08:00 | 2023-02-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01740 | MLJ | OGW |  | Restoration | SITE | PLAYGROUND |  |  | Install fence around play area --> OG Phase 3A | 10 | 10 | 2023-07-19 08:00 | 2023-08-01 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01745 | ATLAS | OGW | SITE RESTORATION | Restoration | SITE |  |  |  | Install Fence at building --> OG9 | 5 | 5 | 2023-08-02 08:00 | 2023-08-08 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01750 | MLJ | OGW | SITE RESTORATION | Restoration | SITE |  |  |  | Place Site Furniture --> OG Phase 3A | 10 | 10 | 2023-08-09 08:00 | 2023-08-22 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01755 | ASPEN | OGW | TOPSOIL | Restoration | SITE |  |  |  | Place topsoil --> OG Phase 3A | 3 | 3 | 2023-09-01 08:00 | 2023-09-05 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01760 | ASPEN | OGW |  | Restoration | SITE |  |  |  | Place trees and plantings --> OG Phase 3A | 5 | 5 | 2023-09-06 08:00 | 2023-09-12 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01765 | ASPEN | OGW |  | Restoration | SITE |  |  |  | Place lawn --> OG Phase 3A | 5 | 5 | 2023-09-13 08:00 | 2023-09-19 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01770 | MLJ | OGW | demob | Closeout | SITE |  |  |  | Demobilize from OG Phase 3A | 5 | 5 | 2024-01-12 08:00 | 2024-01-18 17:00 | -160 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.7 | OGW-01805 | CLOSEOUT | OGW | INSPECTION | Closeout | SITE |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-04-05 08:00 | 2023-04-11 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.7 | OGW-01810 | PUNCH LIST | OGW |  | Closeout | SITE |  |  |  | Perform Punch List | 10 | 10 | 2023-04-12 08:00 | 2023-04-25 17:00 | 23 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01030 | [8 empty] | Form Plumbing Shafts & Ftgs Below Water Table --> OG9 | 10 | 0 | 2021-09-13 | 2021-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01035 | [8 empty] | Rebar Plumbing Shafts & Ftgs Below Water Table --> OG9 | 5 | 0 | 2021-09-14 | 2021-09-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01040 | MLJ | OG9 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG9 | Pour Plumbing Shafts & Ftgs Below Water Table --> OG9 | 2 | 0 | 2021-09-16 08:00 | 2021-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01045 | [8 empty] | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> OG9 | 5 | 0 | 2021-09-17 08:00 | 2021-09-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01025 | [8 empty] | Waterproof/Insulation Plumbing Shaft ----> OG9 | 5 | 0 | 2021-09-16 08:00 | 2021-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01005 | [8 empty] | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG9 | 5 | 0 | 2021-08-03 08:00 | 2021-08-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01020 | [8 empty] | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> OG9 | 3 | 0 | 2021-08-10 | 2021-08-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01055 |  |  | OG9 |  |  |  | 31-1400 | 31-1400-OG9 | Backfill Plumbing Shaft & Ftgs/Piers --> OG9 | 5 | 0 | 2021-09-21 08:00 | 2021-10-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01065 | [8 empty] | Excavate For Remaining Ftgs/Pier/Grade Beams --> OG9 | 10 | 0 | 2021-08-03 | 2021-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01070 |  | OG9 | FORMWORK |  |  | FORMWORK NB | 03-1000 | 03-1000-OG9 | Form Remaining Ftgs/Piers/Grade Beams --> OG9 | 10 | 0 | 2021-09-13 08:00 | 2021-11-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01075 | [8 empty] | Rebar Remaining Ftgs/Piers/Grade Beams --> OG9 | 10 | 0 | 2021-09-14 | 2021-11-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01080 | [8 empty] | Pour Remaining Ftgs/Piers/Grade Beams --> OG9 | 5 | 0 | 2021-09-16 08:00 | 2021-11-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01085 | [8 empty] | Strip Forms Remaining Ftgs/Piers/Grade Beams --> OG9 | 5 | 0 | 2021-09-17 08:00 | 2021-11-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01090 | [8 empty] | Install Remaining Steam Into OG9 (5' from the building) | 5 | 0 | 2021-10-27 08:00 | 2021-11-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01095 | [8 empty] | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> OG9 | 5 | 0 | 2021-11-01 | 2021-11-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01105 | [8 empty] | Install Structural Steel Framing - 1st Floor --> OG9 | 10 | 0 | 2021-11-09 | 2021-11-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01110 | [8 empty] | Install Metal Deck --> OG9 | 2 | 0 | 2021-11-29 08:00 | 2021-12-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01115 | [8 empty] | Form Pour Strip Concrete Stair South Side ---> OG9 | 5 | 0 | 2021-12-15 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01120 | [8 empty] | Install Metal Stairs --> OG9 | 2 | 0 | 2021-12-20 | 2022-01-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01125 |  | OG9 |  |  |  |  | 07-1100 | 07-1100-OG9 | Place Insulation Below First Floor --> OG9 | 5 | 0 | 2021-12-13 | 2021-12-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01130 | [8 empty] | Place WWF First Floor Slab --> OG9 | 2 | 0 | 2021-12-14 | 2021-12-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01135 | MLJ | OG9 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG9 | Pour First Floor Slab --> OG9 | 1 | 0 | 2021-12-15 | 2021-12-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01150 | [8 empty] | Form First Floor Concrete Walls First Face And Col Encasements--> OG9 | 3 | 0 | 2021-12-13 | 2021-12-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01155 | [8 empty] | Rebar First Floor Concrete Walls --> OG9 | 3 | 0 | 2021-12-20 | 2021-12-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01160 | [8 empty] | Form First Floor Concrete Walls 2Nd Face --> OG9 | 5 | 0 | 2021-12-24 | 2021-12-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01165 | [8 empty] | Form, Rebar & Pour Concrete Pads 1st Floor --> OG9 - N/A | 6 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01170 | [8 empty] | Place WWF 2nd Floor Slab --> OG9 | 2 | 0 | 2022-01-13 | 2022-01-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01175 | MLJ | OG9 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG9 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements --> OG9 | 2 | 0 | 2022-02-02 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01180 | [8 empty] | Strip Forms First Floor Walls & Col Encasements --> OG9 | 3 | 0 | 2022-01-03 | 2022-01-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01185 | [8 empty] | Form Concrete Pads 2nd Floor -->OG9 | 2 | 0 | 2022-05-02 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01205 | [8 empty] | Place WWF Roof Slab --> OG9 | 2 | 0 | 2022-01-24 | 2022-01-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01210 | [8 empty] | Pour Roof Slab and 2nd Floor Conc Pads -->OG9 | 1 | 0 | 2022-02-02 | 2022-02-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01215 | [8 empty] | Strip Forms Concrete Pads 2nd Floor -->OG9 | 2 | 0 | 2022-02-14 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01225 | [8 empty] | Install Spray-On Fireproofing on St Stl --> OG9 | 5 | 0 | 2022-03-17 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01230 | FAXA | OG9 | CMU | [5 empty] | Place CMU 1st, 2nd Floors and Roof --> OG9 | 20 | 0 | 2022-03-30 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01240 | CCC | OG9 | [6 empty] | Install Stud Framing 1st, 2nd Floors and Roof --> OG9 | 5 | 0 | 2022-07-05 | 2022-07-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01245 | CCC | OG9 | [6 empty] | Install Doors --> OG9 | 3 | 0 | 2022-12-16 | 2022-12-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01250 |  | OG9 | CAST STONE | [5 empty] | Install Cast Stone Panels --> OG9 | 4 | 0 | 2022-11-28 | 2022-12-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01255 | NAVILLUS | OG9 | [6 empty] | Install Insulated Metal Panels/Louvers --> OG9 | 10 | 0 | 2022-09-08 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01260 | [8 empty] | Install MEP Roof Penetrations & Drains - OG9 | 1 | 0 | 2022-06-15 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01265 | TRIANGLE | OG9 | [6 empty] | Install Roofing --> OG9 | 15 | 0 | 2022-07-13 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01270 | [8 empty] | Install Dunnage Gratings --> OG9 | 2 | 0 | 2021-12-02 08:00 | 2021-12-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01275 | FAXA | OG9 | [6 empty] | Install Brick Façade & Stone --> OG9 | 20 | 0 | 2022-06-16 08:00 | 2022-08-05 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01285 | MLJ | OG9 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD VENTS |  |  | Install Flood Vents And Small Louvers --> OG9 | 3 | 2 | 2023-02-23 | 2023-02-28 17:00 | 19 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01290 | [8 empty] | Install Stair And Roof Platform Railings --> OG9 | 5 | 0 | 2022-03-10 | 2022-03-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01295 | [8 empty] | Install Ladders --> OG9 | 3 | 0 | 2022-05-01 | 2022-05-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01305 | CCC | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Sheetrock and Stucco --> OG9 | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | 11 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01310 | FAXA | OG9 | FLOORING | Interior | NEW BUILDINGS | CERAMIC |  |  | Install Ceramic Tile --> OG9 | 2 | 0 | 2023-02-20 | 2023-02-21 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01315 | TRIANGLE | OG9 | CEILING | Interior | NEW BUILDINGS |  |  |  | Install Acoustical Ceiling --> OG9 | 2 | 2 | 2023-03-27 08:00 | 2023-03-28 17:00 | 11 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01320 | [8 empty] | Place Crystaline Waterproofing In Plumbing Shaft --> OG9 | 3 | 0 | 2022-03-01 | 2022-03-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01325 |  | OG9 | PAINT | [5 empty] | Paint All Areas --> OG9 | 15 | 0 | 2022-11-19 | 2022-12-09 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01330 | MLJ | OG9 | SIGNS | Interior | NEW BUILDINGS |  |  |  | Install Signs --> OG9 | 2 | 2 | 2023-04-03 08:00 | 2023-04-04 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01235 | DSTAR | OG9 | WATERPROOFING | Structure | NEW BUILDINGS |  |  |  | Install Waterproofing to Parapet --> OG9 | 3 | 0 | 2023-02-21 | 2023-02-23 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01280 | CCC | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Install Stucco Soffit --> OG9 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01317 | NAVILLUS | OG9 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulated Metal Panels left out for Access --> OG9 | 5 | 5 | 2023-03-24 08:00 | 2023-03-30 17:00 | 9 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01092 | [8 empty] | Install Remaining HW/CW Into OG9 (5' from the building) | 5 | 0 | 2022-01-04 | 2022-01-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01094 | [8 empty] | Install Remaining Electrical POE Into OG9 | 5 | 0 | 2021-10-05 | 2021-10-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-03005 | WELKIN | OG9 | [6 empty] | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 2022-09-26 | 2022-10-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-03010 | [8 empty] | Install Condensate Pump - Foundation Level | 10 | 0 | 2022-06-01 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 2022-04-10 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03110 | [8 empty] | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03125 | [8 empty] | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-06-01 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03130 |  | OG9 | [6 empty] | Install FOT Controls - 1st Floor | 20 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03135 | WELKIN | OG9 | [6 empty] | Perform Hydrostatic Testing - 1st Floor | 5 | 0 | 2023-01-23 08:00 | 2023-01-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03140 | [8 empty] | Install Plumbing Equipment - 1st Floor | 15 | 0 | 2022-05-26 | 2022-06-06 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03145 | WELKIN | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -13 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03150 | MEP | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 19 | 2023-01-24 08:00 | 2023-03-23 17:00 | -27 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03107 | WELKIN | OG9 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 0 | 2022-01-24 | 2023-01-16 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-03142 | WELKIN | OG9 | [6 empty] | Install Mechanical Equipment - 1st Floor | 20 | 0 | 2022-08-25 13:00 | 2022-09-16 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03225 |  | OG9 | [6 empty] | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 0 | 2022-04-04 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03235 | WELKIN | OG9 | [6 empty] | Perform Hydrostatic Testing - 2nd Floor | 5 | 0 | 2023-01-18 08:00 | 2023-01-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03240 | [8 empty] | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03245 | WELKIN | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -18 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03250 | MEP | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 19 | 2023-01-24 08:00 | 2023-03-23 17:00 | -27 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03207 | WELKIN | OG9 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 0 | 2022-03-07 | 2023-01-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.2 | OG9-03242 | [8 empty] | Install Mechanical Equipment - 2nd Floor | 20 | 0 | 2022-05-25 | 2022-06-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-03405 | [8 empty] | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-03410 | [8 empty] | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.3 | OG9-03415 | [8 empty] | Install Insulation - Roof - N/A | 15 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-03505 | CLOSEOUT | OG9 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG9 | 4 | 4 | 2023-03-24 08:00 | 2023-03-29 17:00 | -27 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-03510 | CLOSEOUT | OG9 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Perform Start-Up Testing - OG9 | 15 | 15 | 2023-09-07 08:00 | 2023-09-27 17:00 | -139 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-03515 | CLOSEOUT | OG9 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - OG9 | 16 | 16 | 2023-09-28 08:00 | 2023-10-20 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-03520 | PUNCH LIST | OG9 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG9 | 5 | 5 | 2023-10-23 08:00 | 2023-10-27 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-03530 | MEP | OG9 | CLOSEOUT | Interior | NEW BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG9 | 4 | 4 | 2023-10-31 08:00 | 2023-11-03 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-03525 | CLOSEOUT | OG9 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG9 | 1 | 1 | 2023-10-30 08:00 | 2023-10-30 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.1 | OG3-01005 | ATCO | OG3 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - OG3 | 3 | 3 | 2023-09-29 08:00 | 2023-10-03 17:00 | -119 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.1 | OG3-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> OG3 | 3 | 0 | 2021-11-01 08:00 | 2021-11-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.1 | OG3-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG3 | 3 | 0 | 2022-01-13 08:00 | 2022-01-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.1 | OG3-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> OG3 | 3 | 0 | 2021-11-01 08:00 | 2021-11-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.1 | OG3-01025 | ATCO | OG3 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> OG3 | 5 | 0 | 2022-07-11 08:00 | 2022-07-11 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.1 | OG3-01030 | ATCO | OG3 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - caulk @ windows and areaway vents --> OG3 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 21 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01105 | MLJ | OG3 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG3 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG3 | 10 | 0 | 2021-05-12 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01110 | [8 empty] | Selective Demo (Doors, windows) - 1st Floor --> OG3 | 5 | 0 | 2022-06-08 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01115 | MLJ | OG3 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> OG3 | 10 | 0 | 2021-06-28 08:00 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01205 | MLJ | OG3 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG3 | 5 | 0 | 2022-09-19 08:00 | 2022-09-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01210 | [8 empty] | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG3 | 5 | 0 | 2022-05-09 | 2022-05-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG3 | 5 | 0 | 2021-10-07 | 2022-01-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01310 | [8 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG3 | 5 | 0 | 2022-05-09 | 2022-05-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> OG3 | 5 | 0 | 2022-04-22 | 2022-04-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> OG3 | 5 | 0 | 2022-03-21 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01325 | CCC | OG3 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> OG3 | 3 | 0 | 2022-04-29 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01330 | CCC | OG3 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> OG3 | 5 | 0 | 2022-03-07 | 2022-11-30 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01335 | CCC | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> OG3 | 10 | 1 | 2022-05-13 | 2023-02-27 17:00 | 32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.4 | OG3-01340 | FLOORING | OG3 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> OG3 | 2 | 2 | 2023-02-28 08:00 | 2023-03-01 17:00 | 32 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01405 |  | OG3 | EXCAVATION |  |  |  | 31-1000 | 31-1000-OG3 | Excavate at Curtain Wall for flood protection (East Side) --> OG3 | 8 | 0 | 2022-05-19 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01410 |  | OG3 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-OG3 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 10 | 0 | 2022-06-07 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 5 | 0 | 2022-05-24 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 0 | 2022-06-07 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 5 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01430 | MLJ | OG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG3 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 8 | 8 | 2023-02-27 08:00 | 2023-03-08 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01435 | MLJ | OG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 6 | 6 | 2023-03-09 08:00 | 2023-03-16 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01440 | MLJ | OG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 4 | 2023-03-17 08:00 | 2023-03-22 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01445 | MLJ | OG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 4 | 2023-03-23 08:00 | 2023-03-28 17:00 | 4 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01450 | FAXA | OG3 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 4 | 2023-03-30 08:00 | 2023-04-04 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01455 | MLJ | OG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG3 | Backfill at Curtain Wall for flood protection (East Side) --> OG3 | 5 | 5 | 2023-04-05 08:00 | 2023-04-11 17:00 | 3 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 2022-05-19 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01510 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 9 | 0 | 2022-06-07 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01515 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 4 | 0 | 2022-05-24 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01520 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 2022-06-07 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01525 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 4 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01530 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 2022-09-01 08:00 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01535 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 5 | 0 | 2022-09-06 | 2022-09-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01540 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 2022-09-09 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01545 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 2022-09-12 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01550 | FAXA | OG3 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 2022-09-15 | 2022-09-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01555 | MLJ | OG3 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG3 | Backfill at Curtain Wall for flood protection (South Side) --> OG3 | 4 | 0 | 2022-09-20 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01605 | [8 empty] | Excavate at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 2022-05-19 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 9 | 0 | 2022-06-07 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 4 | 0 | 2022-05-24 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 2022-06-07 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01625 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 4 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01630 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 2022-09-01 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01635 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 5 | 0 | 2022-09-06 | 2022-09-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01640 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 2022-09-09 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01645 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 2022-09-12 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01650 | FAXA | OG3 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 2022-09-15 | 2022-09-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01655 | MLJ | OG3 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG3 | Backfill at Curtain Wall for flood protection (North Side) --> OG3 | 4 | 0 | 2022-09-20 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01705 | [8 empty] | Excavate at Curtain Wall for flood protection (West Side) --> OG3 | 8 | 0 | 2022-05-06 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01710 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 10 | 0 | 2022-06-07 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01715 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 5 | 0 | 2022-05-24 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01720 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-06-07 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01725 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 5 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01730 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 8 | 0 | 2022-09-01 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01735 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 6 | 0 | 2022-09-06 | 2022-09-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01740 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-09-09 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01745 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-09-12 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01750 | FAXA | OG3 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-09-15 | 2022-09-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01755 | MLJ | OG3 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG3 | Backfill at Curtain Wall for flood protection (West Side) --> OG3 | 5 | 0 | 2022-09-20 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01760 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Form for slab at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-09-26 | 2022-10-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01765 |  | OG3 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG3 | 6 | 0 | 2022-10-06 | 2022-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01770 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Pour slab at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-10-14 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01775 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG3 | 2 | 0 | 2022-10-17 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01780 | MLJ | OG3 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG3 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 2022-10-18 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01805 | [8 empty] | Excavate for concrete shelf around bldg perimeter --> OG3 | 10 | 0 | 2022-06-07 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> OG3 | 5 | 0 | 2022-06-07 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> OG3 | 5 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01820 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Place infill concrete in area ways around bldg perimeter --> OG3 | 5 | 0 | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01825 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Place waterproofing on concrete shelf around bldg perimeter --> OG3 | 10 | 0 | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01830 | FAXA | OG3 | CMU | [5 empty] | Place CMU around bldg perimeter --OG3 | 15 | 0 | 2022-06-13 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01835 |  | OG3 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> OG3 | 10 | 0 | 2022-08-15 08:00 | 2022-08-19 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01840 | MLJ | OG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> OG3 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01845 | FAXA | OG3 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG3 | 20 | 0 | 2022-10-28 08:00 | 2022-11-18 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01850 | MLJ | OG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG3 | Backfill around bdg perimeter --> OG3 | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | 38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01855 | CCC | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> OG3 | 4 | 4 | 2023-03-20 08:00 | 2023-03-23 17:00 | 38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01860 | MLJ | OG3 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> OG3 | 5 | 5 | 2023-03-24 08:00 | 2023-03-30 17:00 | 38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01865 | MLJ | OG3 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> OG3 | 3 | 3 | 2023-03-31 08:00 | 2023-04-04 17:00 | 38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.5 | OG3-01350 | MLJ | OG3 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-OG3 | Drill dowels and place rebar for boiler room concrete walls --> OG3 | 5 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.5 | OG3-01355 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Form boiler room concrete walls --> OG3 | 5 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.5 | OG3-01360 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Pour Concrete boiler room walls --> OG3 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.5 | OG3-01365 | MLJ | OG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG3 | Strip Forms boiler room concrete walls --> OG3 | 3 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.5 | OG3-01370 |  | OG3 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> OG3 | 10 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.6 | OG3-01385 | [8 empty] | Refurbish Elevator 1 --> OG3 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.6 | OG3-01390 | [8 empty] | Refurbish Elevator 2 --> OG3 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.6 | OG3-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.7 | OG3-09005 | CLOSEOUT | OG3 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-10-04 08:00 | 2023-10-10 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.7 | OG3-09010 | PUNCH LIST | OG3 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-10-11 08:00 | 2023-10-25 17:00 | -104 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.2 | OG3-01220 | MLJ | OG3 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-OG3 | Selective Demo (Pumps etc..) - Cellar --> OG3 | 5 | 0 | 2022-10-10 | 2022-10-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2021-05-18 | 2022-02-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03010 | WELKIN | OG3 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-10-13 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03020 |  | OG3 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-12-27 08:00 | 2023-01-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03025 | WELKIN | OG3 | [6 empty] | Perform Hydrostatic Testing - Cellar | 5 | 0 | 2023-01-02 08:00 | 2023-01-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03030 |  | OG3 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2021-11-18 08:00 | 2022-09-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03035 | CLOSEOUT | OG3 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -40 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03040 | MEP | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 6 | 2023-01-10 08:00 | 2023-03-20 17:00 | -40 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2022-03-14 | 2022-03-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-12-28 | 2022-03-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2022-01-23 | 2022-03-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03120 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 10 | 2022-08-08 08:00 | 2023-03-10 17:00 | -44 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03125 | WELKIN | OG3 | [6 empty] | Perform Hydrostatic Testing - 1st Floor | 5 | 0 | 2023-01-02 08:00 | 2023-01-09 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03130 | NAVILLUS | OG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2023-01-30 | 2023-02-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03135 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -44 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03140 | MEP | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 6 | 2023-01-10 08:00 | 2023-03-06 17:00 | -30 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03115 | WELKIN | OG3 | [6 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-11-02 08:00 | 2022-11-02 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03110 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 2022-10-30 08:00 | 2023-02-27 12:00 | -45 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03112 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 0 | 2022-10-30 08:00 | 2023-02-03 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.2 | OG3-03107 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 1 | 2022-10-31 08:00 | 2023-02-27 17:00 | -100 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03220 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-04-04 08:00 | 2023-05-01 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03230 | NAVILLUS | OG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 2023-03-14 08:00 | 2023-04-03 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03235 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-05-02 08:00 | 2023-05-15 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03240 | MEP | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-05-16 08:00 | 2023-06-13 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03210 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-02-28 08:00 | 2023-03-06 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.3 | OG3-03215 | WELKIN | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-03-07 08:00 | 2023-03-13 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03305 | CLOSEOUT | OG3 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG3 | 4 | 4 | 2023-06-14 08:00 | 2023-06-19 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03310 | CLOSEOUT | OG3 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - OG3 | 15 | 15 | 2023-08-16 08:00 | 2023-09-06 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03315 | CLOSEOUT | OG3 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing Mechanical/Plumbing - OG3 | 16 | 16 | 2023-09-07 08:00 | 2023-09-28 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03320 | PUNCH LIST | OG3 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG3 | 5 | 5 | 2023-09-29 08:00 | 2023-10-05 17:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03330 | MEP | OG3 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG3 | 4 | 4 | 2023-10-09 08:00 | 2023-10-12 17:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03325 | CLOSEOUT | OG3 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG3 | 1 | 1 | 2023-10-06 08:00 | 2023-10-06 17:00 | -101 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-03335 |  | OG3 | [6 empty] | Remove Redundant Services - OG3 | 10 | 0 | 2022-08-01 08:00 | 2022-08-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01325 | [8 empty] | Excavate for Steam & HW OG3--> OG9 | 15 | 0 | 2021-09-02 08:00 | 2021-09-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01330 | WELKIN | OGW | UG PIPE | [5 empty] | Install Steam and HW piping OG3--> OG9 (OTCR) | 20 | 0 | 2022-01-27 | 2022-08-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01335 | WELKIN | OGW | UG PIPE | [5 empty] | Test Steam & HW Piping OG3--> OG9 | 8 | 0 | 2022-01-04 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01345 | MLJ | OGW | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-OGW | Backfill Steam & HW Piping OG3--> OG9 | 10 | 0 | 2022-09-14 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01340 |  | OGW | [6 empty] | Install Automatic Temperature Control Conduit - OG3--> OG9 | 2 | 0 | 2022-09-01 08:00 | 2022-09-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01575 | MLJ | OGW | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD7 to AD8 to Existing & Piping | 15 | 0 | 2022-08-22 08:00 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01580 | MLJ | OGW | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD7 to AD8 TO Existing & Piping | 5 | 0 | 2022-09-09 08:00 | 2022-09-09 08:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01590 | MLJ | OGW | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD15 to AD9 to Existing & Piping | 15 | 0 | 2022-09-12 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01595 | MLJ | OGW | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD15 to AD9 TO Existing & Piping | 5 | 0 | 2022-09-18 | 2022-09-21 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01650 | MLJ | OGW | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD10 to Existing to AD11 to Existing & Piping | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01655 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD10 to Existing to AD11 to Existing & Piping | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01660 | MLJ | OGW | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD12 to Existing & Piping | 15 | 0 | 2023-02-03 08:00 | 2023-02-23 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01665 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD12 to Existing & Piping | 5 | 0 | 2023-02-23 08:00 | 2023-02-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01670 | MLJ | OGW | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains Cellar Pump to Existing & Piping (inc DIP7) | 15 | 15 | 2023-03-20 08:00 | 2023-04-07 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01675 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains Cellar Pump to Existing & Piping (inc DIP7) | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -82 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01680 | MLJ | OGW | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains AD16 to Existing & Piping | 15 | 0 | 2023-01-09 | 2023-01-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01685 | MLJ | OGW | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains AD16 to Existing & Piping | 5 | 0 | 2023-01-12 | 2023-01-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01690 | MLJ | OGW | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGW | Excavate and Install Area Drains -OG9 POE to Existing & Piping (inc DIP 10) | 15 | 0 | 2023-02-06 08:00 | 2023-02-13 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01695 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGW | Backfill Area Drains - OG9 POE to Existing & Piping (inc DIP 10) | 5 | 0 | 2023-02-14 08:00 | 2023-02-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02130 | FIVE STAR | OGW | [6 empty] | Pull & Terminate Automatic Temperature Control Cable - OG-9 --> OG-3 | 5 | 0 | 2022-11-28 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.4 | OGW-02135 | FIVE STAR | OGW | [6 empty] | Pull & Terminate Automatic Temperature Control Cable - OG-9 --> OG-2 | 5 | 0 | 2022-11-28 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2021-05-18 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03010 | WELKIN | OG2 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-12-12 | 2022-12-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03020 |  | OG2 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-11-25 | 2022-12-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03025 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03030 |  | OG2 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-09-01 | 2022-12-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03035 | CLOSEOUT | OG2 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-03-06 08:00 | 2023-03-17 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03040 | MEP | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-03-20 08:00 | 2023-04-14 17:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2021-07-12 | 2021-07-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-09-20 08:00 | 2021-11-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2021-09-06 | 2021-09-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03120 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03125 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03130 | NAVILLUS | OG2 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2023-02-03 | 2023-02-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03135 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-04-03 08:00 | 2023-04-14 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03140 | MEP | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-04-17 08:00 | 2023-05-12 17:00 | -109 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03115 | WELKIN | OG2 | [6 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-09-06 08:00 | 2022-09-06 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03110 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 2022-09-26 08:00 | 2023-02-27 12:00 | -90 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03112 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 0 | 2022-09-06 08:00 | 2023-02-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.2 | OG2-03107 | WELKIN | OG2 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-09-12 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03220 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-03-02 08:00 | 2023-03-29 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03230 | NAVILLUS | OG2 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 3 | 2023-02-22 08:00 | 2023-03-01 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03235 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-03-30 08:00 | 2023-04-12 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03240 | MEP | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-04-13 08:00 | 2023-05-10 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03210 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 3 | 2023-02-22 08:00 | 2023-03-01 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.3 | OG2-03215 | WELKIN | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 0 | 2023-02-06 08:00 | 2023-02-10 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03305 | CLOSEOUT | OG2 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG2 | 4 | 4 | 2023-05-15 08:00 | 2023-05-18 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03310 | CLOSEOUT | OG2 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - OG2 | 15 | 15 | 2023-05-19 08:00 | 2023-06-09 17:00 | -109 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03315 | CLOSEOUT | OG2 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - OG2 | 16 | 16 | 2023-06-12 08:00 | 2023-07-03 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03320 | PUNCH LIST | OG2 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG2 | 5 | 5 | 2023-07-05 08:00 | 2023-07-11 17:00 | -40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03330 | MEP | OG2 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG2 | 4 | 4 | 2023-07-20 08:00 | 2023-07-25 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03325 | CLOSEOUT | OG2 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG2 | 1 | 1 | 2023-07-19 08:00 | 2023-07-19 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-03335 | MLJ | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - OG2 | 10 | 10 | 2023-07-05 08:00 | 2023-07-18 17:00 | -68 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-02005 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 0 | 2021-11-26 | 2023-02-23 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-02010 | [8 empty] | Install Manholes & Grounding | 8 | 0 | 2021-11-24 | 2021-11-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01005 | [8 empty] | Install Site Fencing - O'Dwyer Gardens - East | 10 | 0 | 2021-07-26 08:00 | 2021-12-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01015 | [8 empty] | Install Overhead Protection - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01020 | [8 empty] | Install Tree Protection | 5 | 0 | 2020-11-05 | 2020-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01025 | [8 empty] | Remove Trees | 2 | 0 | 2021-01-14 | 2021-01-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01000 | [8 empty] | Remove Curbs And Existing Fencing | 10 | 0 | 2021-07-26 08:00 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01035 | [8 empty] | Install Erosion Control | 5 | 0 | 2021-10-30 08:00 | 2022-02-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01010 | [8 empty] | Set Up Yard and Staging | 10 | 0 | 2021-08-26 08:00 | 2021-08-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01045 | [8 empty] | Clear & Grub | 10 | 0 | 2021-08-26 08:00 | 2022-02-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01050 | [8 empty] | Scrape & Store Topsoil | 10 | 0 | 2022-02-28 | 2022-03-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01055 | [8 empty] | Soil Testing | 10 | 0 | 2021-05-18 | 2021-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01060 | [8 empty] | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 2022-02-08 | 2022-05-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01065 | [8 empty] | Remove Retaining Walls | 10 | 0 | 2022-02-09 | 2022-05-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01070 | [8 empty] | Install Deep Wells For Dewatering - N/R | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01075 | [8 empty] | Install Piping For Deep Wells - N/R | 5 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01080 | [8 empty] | Install Discharge Connection For Dewatering - N/R | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01085 | [8 empty] | Run Electric For Dewatering - N/R | 10 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01105 | [8 empty] | Excavate for CW Pipe - OG10 --> OG6 | 10 | 0 | 2021-10-11 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01110 | [8 empty] | Install CW Piping - OG10 --> OG6 | 15 | 0 | 2022-01-25 | 2022-02-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01115 | [8 empty] | Test CW Piping - OG10 --> OG6 | 10 | 0 | 2022-02-23 | 2022-03-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01120 | [8 empty] | Backfill CW Piping - OG10 --> OG6 | 5 | 0 | 2022-05-11 | 2022-05-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01150 | [8 empty] | Excavate for Electric OG6--> OG10 | 10 | 0 | 2021-10-04 | 2021-10-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01155 | [8 empty] | Install Electrical Conduit OG6--> OG10 | 10 | 0 | 2021-09-17 08:00 | 2022-04-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01160 | [8 empty] | Encase conduit in concrete OG6--> OG10 | 5 | 0 | 2021-11-15 08:00 | 2022-04-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01165 | [8 empty] | Backfill Electrical OG6--> OG10 | 5 | 0 | 2022-01-04 | 2022-05-11 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01405 | NATIONAL GRID | OGE |  | Utilities | SITE |  |  |  | National Gas to Install Line OG10 --> W33rd Street | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -19 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01205 |  | OGE | EXCAVATION |  |  |  | 33-3100 | 33-3100-OGE | Excavate for Electric OG6--> MH | 3 | 0 | 2022-03-21 | 2022-04-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01210 | [8 empty] | Install Electrical Conduit OG6--> MH | 2 | 0 | 2022-04-04 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01215 | [8 empty] | Encase conduit in concrete OG6--> MH | 2 | 0 | 2022-04-20 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01220 | [8 empty] | Backfill Electrical OG6 --> MH | 2 | 0 | 2022-04-21 | 2022-04-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01230 | [8 empty] | Excavate for Electric OG1 -> OG10 | 10 | 0 | 2021-10-04 | 2021-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01235 | [8 empty] | Install Electrical Conduit & MH OG1 -> OG10 | 10 | 0 | 2021-09-24 08:00 | 2021-12-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01240 | [8 empty] | Encase conduit in concrete OG1 -> OG10 | 3 | 0 | 2021-10-15 08:00 | 2021-12-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01245 | [8 empty] | Backfill Electrical OG1 -> OG10 | 5 | 0 | 2021-10-20 08:00 | 2021-12-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01255 | MLJ | OGE | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-OGE | Excavate for Electric OG1--> MH | 3 | 0 | 2022-06-24 | 2022-07-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01260 |  | OGE | [6 empty] | Install Electrical Conduit OG1--> MH (Awaiting NYCHA Direction) | 2 | 0 | 2022-07-15 | 2022-07-29 09:36 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01265 | MLJ | OGE | Concrete |  |  | SITE CONCRETE |  |  | Encase conduit in concrete OG1--> MH | 2 | 0 | 2022-08-01 | 2022-08-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01270 | MLJ | OGE | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-OGE | Backfill Electrical OG1 --> MH | 2 | 0 | 2022-08-02 | 2022-08-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01275 | [8 empty] | Excavate for Steam OG5--> OG3 | 15 | 0 | 2021-11-30 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01280 | [8 empty] | Install Steam piping OG5--> SG3 | 20 | 0 | 2022-03-02 | 2022-04-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01285 | WELKIN | [7 empty] | Test Steam Piping OG5--> SG3 | 8 | 0 | 2022-04-15 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01290 | [8 empty] | Backfill Steam Piping OG5--> SG3 | 10 | 0 | 2022-05-10 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01505 | MLJ | OGE | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-OGE | Excavate for water line to drinking fountain OGE --> Water Main W33rd Street | 2 | 0 | 2022-11-25 | 2022-11-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01510 |  | OGE |  |  |  | PLAYGROUND |  |  | Install water line to drinking fountain OGE --> Water Main W33rd Street | 5 | 0 | 2022-11-29 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01515 |  | OGE |  |  |  | PLAYGROUND |  |  | Tap water main for drinking fountain water line OGE --> Water Main W33rd Street | 2 | 0 | 2022-11-30 | 2022-12-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01520 | MLJ | OGE | BACKFILL |  |  | BACKFILL SITE |  |  | Backfill water line drinking fountain OGE --> Water Main W33rd Street | 2 | 0 | 2022-12-02 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01560 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains AD14>AD13>AD12>AD10 to Existing+ Piping | 15 | 0 | 2022-08-29 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01565 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains AD14>AD13>AD12>AD10 to Existing+ Piping | 5 | 0 | 2022-09-19 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01090 | [8 empty] | Activate Dewatering System | 1 | 0 | 2022-03-02 | 2022-03-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01095 |  |  | dewatering | [5 empty] | Maintain Dewatering | 282 | 0 | 2022-03-02 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01287 | [8 empty] | Install Automatic Temperature Control Conduit - OG5--> SG3 | 2 | 0 | 2022-05-19 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01100 | [8 empty] | De-Activate Dewatering | 1 | 0 | 2022-05-02 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01117 | [8 empty] | Install Automatic Temperature Control Conduit - OG10 --> OG6 | 2 | 0 | 2022-05-12 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01295 | [8 empty] | Excavate for Steam & HW OG6--> OG10 | 15 | 0 | 2021-10-13 | 2021-10-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01300 | [8 empty] | Install Steam and HW piping OG6--> OG10 | 20 | 0 | 2022-01-04 | 2022-04-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01305 | [8 empty] | Test Steam & HW Piping OG6--> OG10 | 8 | 0 | 2022-04-11 | 2022-04-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01315 | [8 empty] | Backfill Steam & HW Piping OG6--> OG10 | 10 | 0 | 2022-05-02 | 2022-05-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01310 | [8 empty] | Install Automatic Temperature Control Conduit - OG6--> OG10 | 2 | 0 | 2022-05-12 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01605 | MLJ | OGE | Excavation |  |  | EXC RETAINING |  |  | Excavate for retaining wall --> OG Phase 4 | 2 | 0 | 2022-10-13 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01610 | MLJ | OGE | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-OGE | Form Retaining wall footing --> OG Phase 4 | 2 | 0 | 2022-10-17 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01615 |  | OGE | REBAR | [5 empty] | Rebar Retaining wall footing --> OG Phase 4 | 2 | 0 | 2022-10-19 | 2022-10-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01620 | MLJ | OGE | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall footing --> OG Phase 4 | 1 | 0 | 2022-10-21 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01625 |  | OGE | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall footing --> OG Phase 4 | 1 | 0 | 2022-10-24 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01630 | MLJ | OGE | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-OGE | Form Retaining wall --> OG Phase 4 | 3 | 0 | 2022-11-18 | 2022-11-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01635 |  | OGE | REBAR | [5 empty] | Rebar Retaining wall --> OG Phase 4 | 3 | 0 | 2022-11-16 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01640 | MLJ | OGE | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall --> OG Phase 4 | 1 | 0 | 2022-11-22 | 2022-11-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01645 |  | OGE | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall --> OG Phase 4 | 1 | 0 | 2022-11-25 | 2022-11-28 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01705 | JMC | OGE | CURBS | Restoration | SITE |  |  |  | Install Street Curbs --> OG Phase 4 | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01710 | JMC | OGE | SIDEWALKS | Restoration | SITE |  |  |  | Install sidewalks --> OG Phase 4 | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | -17 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01715 |  | OGE | CURBS | [5 empty] | Install curb around play area --> OG Phase 4 | 5 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01720 |  | OGE |  |  |  | PLAYGROUND |  |  | Install Safety Surface --> OG Phase 4 | 5 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01725 | MLJ | OGE | Concrete | Restoration | SITE | SITE CONCRETE |  |  | Install site furniture concrete foundations --> OG Phase 4 | 10 | 10 | 2023-03-23 08:00 | 2023-04-05 17:00 | -10 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01730 | JMC | OGE | COLORED CONCRETE | Restoration | SITE |  |  |  | Install integrally colored concrete walkways --> OG Phase 4 | 20 | 18 | 2022-10-17 | 2023-03-22 17:00 | -62 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01735 |  | OGE |  |  |  | PLAYGROUND |  |  | Install Play area items --> OG Phase 4 | 5 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01740 |  | OGE |  |  |  | PLAYGROUND |  |  | Install fence around play area --> OG Phase 4 | 10 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01745 | ATLAS | OGE | SITE RESTORATION | Restoration | SITE |  |  |  | Install Fence at building --> OG10 | 5 | 5 | 2023-05-01 08:00 | 2023-05-05 17:00 | -17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01750 | MLJ | OGE | SITE RESTORATION | Restoration | SITE |  |  |  | Place Site Furniture --> OG Phase 4 | 10 | 10 | 2023-05-08 08:00 | 2023-05-19 17:00 | -17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01755 | ASPEN | OGE | TOPSOIL | Restoration | SITE |  |  |  | Place topsoil --> OG Phase 4 | 3 | 3 | 2023-09-01 08:00 | 2023-09-05 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01760 | ASPEN | OGE |  | Restoration | SITE |  |  |  | Place trees and plantings --> OG Phase 4 | 5 | 5 | 2023-09-06 08:00 | 2023-09-12 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01765 | ASPEN | OGE |  | Restoration | SITE |  |  |  | Place lawn --> OG Phase 4 | 5 | 5 | 2023-09-13 08:00 | 2023-09-19 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01770 | MLJ | OGE | demob | Closeout | SITE |  |  |  | Demobilize from OG Phase 4 | 5 | 5 | 2024-02-05 08:00 | 2024-02-09 17:00 | -176 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01325 | [8 empty] | Excavate for Steam OG5--> OG6 | 15 | 0 | 2022-06-01 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01330 |  | OGE | [6 empty] | Install Steam and piping OG5--> OG6 | 20 | 0 | 2022-06-20 | 2022-08-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01335 | WELKIN | OGE | UG PIPE | [5 empty] | Test Steam & Piping OG5--> OG6 | 8 | 0 | 2022-08-30 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01345 | MLJ | OGW | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-OGW | Backfill Steam & Piping OG5--> OG6 | 10 | 0 | 2022-09-06 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01340 |  | OGE | [6 empty] | Install Automatic Temperature Control Conduit - OG5--> OG6 | 2 | 0 | 2022-09-24 08:00 | 2022-09-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01575 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - Yard Drain to AD23 + Piping | 15 | 0 | 2022-08-25 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01580 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - Yard Drain to AD23 + Piping | 5 | 0 | 2022-09-01 | 2022-09-05 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01590 | MLJ | OGE | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - Yard Drain to AD9 + Piping | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01595 | MLJ | OGE | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - Yard Drain to AD9 + Piping | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -17 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01650 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD6 > AD9 > AD8 to MH2 & Piping | 15 | 0 | 2022-09-15 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01655 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD6 > AD9 > AD8 to MH2 & Piping | 5 | 0 | 2022-10-17 | 2022-10-21 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01660 | MLJ | OGE | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - Cellar Ramp Pump to Existing & Piping (Incl DIP8 & DIP9) | 15 | 2 | 2022-08-27 | 2023-02-28 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01665 | MLJ | OGE | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - Cellar Ramp Pump to Existing & Piping (Incl DIP8 & DIP9) | 5 | 5 | 2023-03-01 08:00 | 2023-03-07 17:00 | 18 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01670 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - Yard Drain > AD7 > MH2 > AD18 > AD7 to Existing + Piping | 15 | 0 | 2022-06-13 | 2022-07-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01675 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - Yard Drain > AD7 > MH2 > AD18 > AD7 to Existing + Piping | 5 | 0 | 2022-07-10 | 2022-07-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01680 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD23 > MH3 > MH2 & Piping | 15 | 0 | 2022-06-20 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01685 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD23 > MH3 > MH2 & Piping | 5 | 0 | 2022-08-29 | 2022-09-05 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01690 | MLJ | OGE | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD15 > AD20 > Existing + Piping | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01695 | MLJ | OGE | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD15 > AD20 > Existing + Piping | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -5 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.1 | OG2-01005 | ATCO | OG2 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - OG2 | 3 | 3 | 2023-07-19 08:00 | 2023-07-21 17:00 | -68 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.1 | OG2-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> OG2 | 3 | 0 | 2021-07-19 08:00 | 2021-08-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.1 | OG2-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG2 | 3 | 0 | 2022-04-11 08:00 | 2022-04-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.1 | OG2-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> OG2 | 3 | 0 | 2021-07-19 08:00 | 2021-08-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.1 | OG2-01025 | ATCO | OG2 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> OG2 | 5 | 0 | 2022-08-29 | 2022-08-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.1 | OG2-01030 | ATCO | OG2 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> OG2 | 5 | 0 | 2022-09-02 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01105 | MLJ | OG2 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG2 | 10 | 0 | 2021-05-18 | 2022-07-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01110 | MLJ | OG2 | DEMO |  |  | DEMO DOORS WINDOWS |  |  | Selective Demo (Doors, windows) - 1st Floor --> OG2 | 5 | 0 | 2022-09-26 | 2022-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01115 | MLJ | OG2 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> OG2 | 10 | 0 | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01205 | MLJ | OG2 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG2 | 5 | 0 | 2022-09-01 08:00 | 2022-09-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01210 | [8 empty] | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG2 - N/A | 5 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG2 | 5 | 0 | 2021-10-08 | 2022-01-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01310 | [8 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG2 | 5 | 0 | 2022-05-17 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> OG2 | 5 | 0 | 2022-04-25 | 2022-04-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> OG2 | 5 | 0 | 2022-04-25 | 2022-05-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01325 | CCC | OG2 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> OG2 | 3 | 0 | 2022-03-14 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01330 | CCC | OG2 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> OG2 | 5 | 0 | 2022-04-27 | 2022-11-30 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01335 | CCC | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> OG2 | 10 | 1 | 2022-05-12 | 2023-02-27 17:00 | 32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.4 | OG2-01340 | FLOORING | OG2 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> OG2 | 2 | 2 | 2023-02-28 08:00 | 2023-03-01 17:00 | 32 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01405 |  | OG2 | EXCAVATION |  |  |  | 31-1000 | 31-1000-OG2 | Excavate at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 2022-03-16 | 2022-03-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01410 |  | OG2 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-OG2 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 9 | 0 | 2022-05-10 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 4 | 0 | 2022-05-10 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 2022-05-19 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 4 | 0 | 2022-05-20 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01430 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 2022-08-03 | 2022-08-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01435 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 5 | 0 | 2022-08-08 | 2022-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01440 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 2022-08-11 | 2022-08-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01445 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 2022-08-12 | 2022-08-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01450 | FAXA | OG2 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 2022-08-16 | 2022-08-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01455 | MLJ | OG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG2 | Backfill at Curtain Wall for flood protection (East Side) --> OG2 | 4 | 0 | 2022-08-22 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> OG2 | 8 | 0 | 2022-03-16 | 2022-03-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01510 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 10 | 0 | 2022-05-10 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01515 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 5 | 0 | 2022-05-10 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01520 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 2022-05-19 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01525 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 5 | 0 | 2022-05-20 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01530 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 8 | 0 | 2022-08-03 | 2022-08-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01535 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 6 | 0 | 2022-08-08 | 2022-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01540 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 2022-08-11 | 2022-08-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01545 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 2022-08-12 | 2022-08-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01550 | FAXA | OG2 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 2022-08-16 | 2022-08-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01555 | MLJ | OG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG2 | Backfill at Curtain Wall for flood protection (South Side) --> OG2 | 5 | 0 | 2022-08-22 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01605 | [8 empty] | Excavate at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 2022-03-16 | 2022-03-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 9 | 0 | 2022-05-10 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 4 | 0 | 2022-05-10 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 2022-05-19 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01625 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 4 | 0 | 2022-05-20 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01630 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 2022-08-03 | 2022-08-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01635 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 5 | 0 | 2022-08-08 | 2022-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01640 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 2022-08-11 | 2022-08-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01645 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 2022-08-12 | 2022-08-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01650 | FAXA | OG2 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 2022-08-16 | 2022-08-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01655 | MLJ | OG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG2 | Backfill at Curtain Wall for flood protection (North Side) --> OG2 | 4 | 0 | 2022-08-22 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01705 | [8 empty] | Excavate at Curtain Wall for flood protection (West Side) --> OG2 | 8 | 0 | 2022-03-16 | 2022-03-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01710 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 10 | 0 | 2022-05-10 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01715 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 5 | 0 | 2022-05-10 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01720 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 0 | 2022-05-19 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01725 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 5 | 0 | 2022-05-20 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01730 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 8 | 0 | 2022-11-25 08:00 | 2022-11-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01735 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 6 | 0 | 2022-11-30 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01740 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 0 | 2022-12-09 | 2022-12-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01745 | MLJ | OG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 0 | 2022-12-12 | 2022-12-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01750 | FAXA | OG2 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01755 | MLJ | OG2 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG2 | Backfill at Curtain Wall for flood protection (West Side) --> OG2 | 5 | 5 | 2023-03-03 08:00 | 2023-03-09 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01760 | MLJ | OG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG2 | Form for slab at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 2023-03-10 08:00 | 2023-03-15 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01765 | TONAGE | OG2 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG2 | 6 | 6 | 2023-03-16 08:00 | 2023-03-23 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01770 | MLJ | OG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG2 | Pour slab at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 2023-03-24 08:00 | 2023-03-29 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01775 | MLJ | OG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG2 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG2 | 2 | 2 | 2023-03-30 08:00 | 2023-03-31 17:00 | 13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01780 | MLJ | OG2 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG2 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | 10 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01805 | [8 empty] | Excavate for concrete shelf around bldg perimeter --> OG2 | 10 | 0 | 2022-05-02 | 2022-05-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> OG2 | 5 | 0 | 2022-05-10 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> OG2 | 5 | 0 | 2022-05-19 | 2022-05-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01820 | [8 empty] | Place infill concrete in area ways around bldg perimeter --> OG2 | 5 | 0 | 2022-05-26 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01825 | [8 empty] | Place waterproofing on concrete shelf around bldg perimeter --> OG2 | 10 | 0 | 2022-06-01 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01830 | FAXA | OG2 | CMU | [5 empty] | Place CMU around bldg perimeter --OG2 | 15 | 0 | 2022-06-07 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01835 |  | OG2 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> OG2 | 10 | 0 | 2022-07-11 | 2022-08-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01840 | MLJ | OG2 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> OG2 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 43 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01845 | FAXA | OG2 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG2 | 20 | 0 | 2022-08-08 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01850 | MLJ | OG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG2 | Backfill around bdg perimeter --> OG2 | 5 | 0 | 2022-11-25 | 2022-12-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01855 | CCC | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> OG2 | 4 | 4 | 2023-03-13 08:00 | 2023-03-16 17:00 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01860 | MLJ | OG2 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> OG2 | 5 | 5 | 2023-03-17 08:00 | 2023-03-23 17:00 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01865 | MLJ | OG2 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> OG2 | 3 | 3 | 2023-03-24 08:00 | 2023-03-28 17:00 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.5 | OG2-01350 | MLJ | OG2 |  | Interior | EXISTING BUILDINGS | DRILL & DOWEL | 03-1400 | 03-1400-OG2 | Drill dowels and place rebar for boiler room concrete walls --> OG2 | 5 | 0 | 2023-01-30 | 2023-02-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.5 | OG2-01355 | MLJ | OG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG2 | Form boiler room concrete walls --> OG2 | 5 | 0 | 2023-02-03 | 2023-02-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.5 | OG2-01360 | MLJ | OG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG2 | Pour Concrete boiler room walls --> OG2 | 2 | 0 | 2023-02-10 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.5 | OG2-01365 | MLJ | OG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG2 | Strip Forms boiler room concrete walls --> OG2 | 3 | 0 | 2023-02-13 | 2023-02-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.5 | OG2-01370 |  | OG2 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> OG2 | 10 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.6 | OG2-01385 | [8 empty] | Refurbish Elevator 1 --> OG2 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.6 | OG2-01390 | [8 empty] | Refurbish Elevator 2 --> OG2 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.6 | OG2-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.7 | OG2-09005 | CLOSEOUT | OG2 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-07-24 08:00 | 2023-07-28 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.7 | OG2-09010 | PUNCH LIST | OG2 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-07-31 08:00 | 2023-08-11 17:00 | -53 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.2 | OG2-01220 | MLJ | OG2 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-OG2 | Selective Demo (Pumps etc..) - Cellar --> OG2 | 5 | 0 | 2022-12-05 08:00 | 2022-12-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33530 | [8 empty] | Prepare & Submit Utility Coord. Dwgs - Odwyer Gardens - West | 20 | 0 | 2021-05-01 08:00 | 2021-06-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33535 | [8 empty] | Review & Approve Utility Coord. Dwgs - Odwyer Gardens - West | 10 | 0 | 2021-06-30 08:00 | 2021-07-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33540 | [8 empty] | Prepare & Submit Utility Coord. Dwgs - Odwyer Gardens - East | 20 | 0 | 2021-05-01 08:00 | 2021-06-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33545 | [8 empty] | Review & Approve Utility Coord. Dwgs - Odwyer Gardens - East | 10 | 0 | 2021-06-30 08:00 | 2021-07-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33550 | [8 empty] | Prepare & Submit Utility Coord. Dwgs - Surfside Gardens South | 20 | 0 | 2021-07-23 | 2021-07-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33555 | [8 empty] | Review & Approve Utility Coord. Dwgs - Surfside Gardens South | 10 | 0 | 2021-07-24 | 2021-08-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33560 | [8 empty] | Prepare & Submit Utility Coord. Dwgs - Site 8 | 20 | 0 | 2021-07-23 | 2022-05-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 33 | 33565 | [8 empty] | Review & Approve Utility Coord. Dwgs - Site 8 | 10 | 0 | 2022-05-13 08:00 | 2022-05-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01350 | [8 empty] | Excavate for Steam OG1--> OG6 | 15 | 0 | 2021-10-11 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01355 | [8 empty] | Install Steam and piping OG1--> OG6 | 20 | 0 | 2021-11-22 08:00 | 2022-02-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01360 | [8 empty] | Test Steam & Piping OG1--> OG6 | 8 | 0 | 2022-02-22 | 2022-02-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01370 | [8 empty] | Backfill Steam & Piping OG1--> OG6 | 10 | 0 | 2022-05-09 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01365 | [8 empty] | Install Automatic Temperature Control Conduit - OG1--> OG6 | 2 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01375 | [8 empty] | Excavate for HW OG1--> OG10 | 15 | 0 | 2021-10-11 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01380 | [8 empty] | Install HW piping OG1--> OG10 | 20 | 0 | 2022-01-25 08:00 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01385 | [8 empty] | Test HW Piping OG1--> OG10 | 8 | 0 | 2022-02-11 | 2022-02-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01395 | [8 empty] | Backfill HW Piping OG1--> OG10 | 10 | 0 | 2022-05-09 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01390 | [8 empty] | Install Automatic Temperature Control Conduit - OG1--> OG10 | 2 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01700 | MLJ | OGE | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD16 > AD21 > Existing + Piping | 15 | 15 | 2023-03-20 08:00 | 2023-04-07 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01775 | MLJ | OGE | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD16 > AD21 > Existing + Piping | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -15 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01780 | MLJ | OGE | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD17 > AD22 > Existing + Piping | 15 | 15 | 2023-04-10 08:00 | 2023-04-28 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01785 | MLJ | OGE | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD17 > AD22 > Existing + Piping | 5 | 5 | 2023-05-01 08:00 | 2023-05-05 17:00 | -25 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01790 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD5 > AD4 > AD3 > Existing + Piping | 15 | 0 | 2022-11-14 08:00 | 2022-11-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01795 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD5 > AD4 > AD3 > Existing + Piping | 5 | 0 | 2022-11-21 | 2022-11-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01800 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - Ramp Pump > AD1 > AD2 > AD16 > AD21 > Existing + Piping | 15 | 0 | 2023-01-04 | 2023-01-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01805 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - Ramp Pump > AD1 > AD2 > AD16 > AD21 > Existing + Piping | 5 | 0 | 2023-01-10 | 2023-01-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01810 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD19 > Existing + Piping | 15 | 0 | 2023-01-09 08:00 | 2023-01-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01815 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD19 > Existing + Piping | 5 | 0 | 2023-01-19 08:00 | 2023-01-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01820 | MLJ | OGE | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-OGE | Excavate and Install Area Drains - AD1 > AD7 > AD3 > Existing + Piping | 15 | 0 | 2023-01-04 | 2023-01-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.6 | OGE-01825 | MLJ | OGE | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-OGE | Backfill Area Drains - AD1 > AD7 > AD3 > Existing + Piping | 5 | 0 | 2023-01-10 | 2023-01-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01030 | [8 empty] | Form Plumbing Shafts & Ftgs Below Water Table --> OG10 | 10 | 0 | 2021-08-23 | 2021-08-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01035 | TONAGE | OG10 | REBAR | Structure | NEW BUILDINGS |  |  |  | Rebar Plumbing Shafts & Ftgs Below Water Table --> OG10 | 5 | 0 | 2021-08-26 08:00 | 2021-08-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01040 | MLJ | OG10 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG10 | Pour Plumbing Shafts & Ftgs Below Water Table --> OG10 | 2 | 0 | 2021-08-27 08:00 | 2021-08-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01045 | [8 empty] | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> OG10 | 5 | 0 | 2021-08-30 08:00 | 2021-08-31 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01027 | [8 empty] | Waterproof/Insulation Plumbing Shaft ----> OG10 | 5 | 0 | 2021-08-27 | 2021-08-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01020 | [8 empty] | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG10 | 10 | 0 | 2021-07-26 08:00 | 2021-08-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01025 | [8 empty] | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> OG10 | 3 | 0 | 2021-08-04 | 2021-08-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01055 |  |  | OG10 |  |  |  | 31-1400 | 31-1400-OG10 | Backfill Plumbing Shaft & Ftgs/Piers --> OG10 | 5 | 0 | 2021-09-09 | 2021-09-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01065 | [8 empty] | Excavate For Remaining Ftgs/Pier/Grade Beams --> OG10 | 10 | 0 | 2021-08-04 | 2021-08-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01070 |  | OG10 | FORMWORK |  |  | FORMWORK NB | 03-1000 | 03-1000-OG10 | Form Remaining Ftgs/Piers/Grade Beams --> OG10 | 10 | 0 | 2021-08-19 | 2021-09-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01075 | [8 empty] | Rebar Remaining Ftgs/Piers/Grade Beams --> OG10 | 10 | 0 | 2021-09-10 | 2021-09-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01080 | [8 empty] | Pour Remaining Ftgs/Piers/Grade Beams --> OG10 | 5 | 0 | 2021-09-23 08:00 | 2021-09-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01085 | [8 empty] | Strip Forms Remaining Ftgs/Piers/Grade Beams --> OG10 | 5 | 0 | 2021-09-28 | 2021-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01090 | [8 empty] | Install Remaining Steam Into OG10 (5' from the building) | 5 | 0 | 2022-03-28 | 2022-04-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01095 | [8 empty] | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> OG10 | 5 | 0 | 2021-09-30 | 2021-10-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01105 | [8 empty] | Install Structural Steel Framing - 1st Floor --> OG10 | 10 | 0 | 2021-12-10 | 2021-12-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01110 | [8 empty] | Install Metal Deck --> OG10 | 2 | 0 | 2021-12-18 08:00 | 2021-12-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01115 | [8 empty] | Form Pour Strip Concrete Stair South Side ---> OG10 | 5 | 0 | 2021-11-15 08:00 | 2021-11-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01120 | [8 empty] | Install Metal Stairs --> OG10 | 2 | 0 | 2022-04-04 08:00 | 2022-05-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01125 |  | OG10 |  |  |  |  | 07-1100 | 07-1100-OG10 | Place Insulation Below First Floor --> OG10 | 5 | 0 | 2021-11-09 08:00 | 2021-11-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01130 | [8 empty] | Place WWF First Floor Slab --> OG10 | 2 | 0 | 2021-11-10 08:00 | 2021-11-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01135 | MLJ | OG10 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG10 | Pour First Floor Slab --> OG10 | 1 | 0 | 2021-11-15 08:00 | 2021-11-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01150 | [8 empty] | Form First Floor Concrete Walls First Face And Col Encasements--> OG10 | 3 | 0 | 2021-11-03 08:00 | 2021-11-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01155 | [8 empty] | Rebar First Floor Concrete Walls --> OG10 | 3 | 0 | 2021-11-15 08:00 | 2021-11-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01160 | [8 empty] | Form First Floor Concrete Walls 2Nd Face --> OG10 | 5 | 0 | 2021-11-18 | 2021-11-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01165 | [8 empty] | Form, Rebar & Pour Concrete Pads 1st Floor --> OG10 - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01170 | [8 empty] | Place WWF 2nd Floor Slab --> OG10 | 2 | 0 | 2022-02-08 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01175 | MLJ | OG10 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-OG10 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> OG10 | 2 | 0 | 2022-02-10 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01180 | [8 empty] | Strip Forms First Floor Walls & Col Encasements And 1st Floor Pads --> OG10 | 3 | 0 | 2022-02-28 | 2022-03-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01185 | [8 empty] | Form Concrete Pads 2nd Floor -->OG10 | 2 | 0 | 2022-03-28 | 2022-04-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01205 | [8 empty] | Place WWF Roof Slab --> OG10 | 2 | 0 | 2022-02-08 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01210 | [8 empty] | Pour Roof Slab and 2nd Floor Conc Pads -->OG10 | 1 | 0 | 2022-02-10 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01215 | [8 empty] | Strip Forms Concrete Pads 2nd Floor -->OG10 | 2 | 0 | 2022-02-08 | 2022-03-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01225 | [8 empty] | Install Spray-On Fireproofing on St Stl --> OG10 | 5 | 0 | 2022-04-12 | 2022-05-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01230 | FAXA | OG10 | CMU | [5 empty] | Place CMU 1st, 2nd Floors and Roof --> OG10 | 20 | 0 | 2022-05-09 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01240 | CCC | OG10 | [6 empty] | Install Stud Framing 1st, 2nd Floors and Roof --> OG10 | 5 | 0 | 2022-08-10 | 2022-10-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01245 | CCC | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Doors --> OG10 | 3 | 0 | 2023-02-14 | 2023-02-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01250 |  | OG10 | CAST STONE | [5 empty] | Install Cast Stone Panels --> OG10 | 1 | 0 | 2022-10-13 | 2022-10-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01255 | NAVILLUS | OG10 | [6 empty] | Install Insulated Metal Panels/Louvers --> OG10 | 10 | 0 | 2022-10-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01260 |  | OG10 | [6 empty] | Install MEP Roof Penetrations & Drains - OG10 | 1 | 0 | 2022-08-26 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01265 | TRIANGLE | OG10 | [6 empty] | Install Roofing --> OG10 | 15 | 0 | 2022-08-08 08:00 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01270 | [8 empty] | Install Dunnage Gratings --> OG10 | 2 | 0 | 2022-01-03 10:00 | 2022-01-04 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01275 | FAXA | OG10 | [6 empty] | Install Brick Façade & Stone --> OG10 | 20 | 0 | 2022-09-20 | 2022-10-12 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01285 | MLJ | OG10 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD VENTS |  |  | Install Flood Vents And Small Louvers --> OG10 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | 15 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01290 |  | OG10 | [6 empty] | Install Stair And Roof Platform Railings --> OG10 | 5 | 0 | 2022-10-19 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01295 | [8 empty] | Install Ladders --> OG10 | 3 | 0 | 2022-04-15 | 2022-04-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01305 | [8 empty] | Install Sheetrock and Stucco --> OG10 | 10 | 0 | 2022-02-03 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01310 |  | OG10 | FLOORING |  |  | CERAMIC |  |  | Install Ceramic Tile --> OG10 | 2 | 0 | 2022-12-27 08:00 | 2022-12-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01315 |  | OG10 | CEILING | [5 empty] | Install Acoustical Ceiling --> OG10 | 2 | 0 | 2023-01-05 | 2023-01-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01320 |  | OG10 | WATERPROOFING | [5 empty] | Place Crystaline Waterproofing In Plumbing Shaft --> OG10 | 3 | 0 | 2022-06-15 08:00 | 2022-06-16 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01325 | GG PAINT | OG10 | PAINT | Interior | NEW BUILDINGS |  |  |  | Paint All Areas --> OG10 | 15 | 15 | 2023-04-24 08:00 | 2023-05-12 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01330 | MLJ | OG10 | SIGNS | Interior | NEW BUILDINGS |  |  |  | Install Signs --> OG10 | 2 | 2 | 2023-05-15 08:00 | 2023-05-16 17:00 | -22 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01235 |  | OG10 | WATERPROOFING | [5 empty] | Install Waterproofing to Parapet --> OG10 | 3 | 0 | 2022-08-10 | 2022-08-12 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01280 | CCC | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Stucco Soffit --> OG10 | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -22 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01317 | NAVILLUS | OG10 | [6 empty] | Install Insulated Metal Panels left out for Access --> OG10 | 5 | 0 | 2022-11-16 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01092 | [8 empty] | Install Remaining HW/CW Into OG10 (5' from the building) | 5 | 0 | 2021-09-20 | 2021-09-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01094 | [8 empty] | Install Remaining Electrical POE Into OG10 | 5 | 0 | 2021-09-21 | 2021-10-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 2022-02-03 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03110 | [8 empty] | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03125 | [8 empty] | Install Remaining Piping & Appurtenances - 1st Floor | 5 | 0 | 2022-02-15 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03130 |  | OG10 | [6 empty] | Install FOT Controls - 1st Floor | 20 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03135 | WELKIN | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 0 | 2023-01-25 08:00 | 2023-01-31 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03140 | [8 empty] | Install Plumbing Equipment - 1st Floor | 15 | 0 | 2022-06-06 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03145 | [8 empty] | Mechanical Equipment Start-up & Balance - 1st Floor - N/A | 5 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03150 | MEP | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 10 | 0 | 2023-01-31 08:00 | 2023-02-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03107 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-06-06 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-03142 | [8 empty] | Install Mechanical Equipment - 1st Floor - N/A | 15 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-03005 | WELKIN | OG10 | [6 empty] | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 2022-08-15 | 2022-08-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-03010 | WELKIN | OG10 | [6 empty] | Install Condensate Pump - Foundation Level | 10 | 0 | 2022-08-25 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03225 | VITAL | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 0 | 2022-10-25 08:00 | 2023-01-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03235 | WELKIN | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 2nd Floor | 5 | 0 | 2023-01-27 08:00 | 2023-02-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03240 | [8 empty] | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03245 | WELKIN | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-03-06 08:00 | 2023-03-17 17:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03250 | MEP | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 0 | 2023-01-25 08:00 | 2023-02-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03207 | WELKIN | OG10 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 0 | 2022-03-28 | 2022-08-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.2 | OG10-03242 | WELKIN | OG10 | [6 empty] | Install Mechanical Equipment - 2nd Floor | 20 | 0 | 2023-01-02 08:00 | 2023-01-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-03405 | [8 empty] | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-03410 | [8 empty] | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.3 | OG10-03415 | [8 empty] | Install Insulation - Roof - N/A | 15 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-03505 | CLOSEOUT | OG10 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG10 | 4 | 4 | 2023-03-20 08:00 | 2023-03-23 17:00 | 0 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-03510 | CLOSEOUT | OG10 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Perform Start-Up Testing - OG10 | 15 | 15 | 2023-12-06 08:00 | 2023-12-27 17:00 | -176 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-03515 | CLOSEOUT | OG10 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Start-Up Testing & Commissioning Mechanical/Plumbing - OG10 | 16 | 16 | 2023-12-28 08:00 | 2024-01-19 17:00 | -176 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-03520 | PUNCH LIST | OG10 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG10 | 5 | 5 | 2024-01-22 08:00 | 2024-01-26 17:00 | -176 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-03530 | MEP | OG10 | CLOSEOUT | Interior | NEW BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG10 | 4 | 4 | 2024-01-30 08:00 | 2024-02-02 17:00 | -176 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-03525 | CLOSEOUT | OG10 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG10 | 1 | 1 | 2024-01-29 08:00 | 2024-01-29 17:00 | -176 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.7 | OGE-01850 | CLOSEOUT | OGE | INSPECTION | Closeout | SITE |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-05-17 08:00 | 2023-05-23 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.7 | OGE-01855 | PUNCH LIST | OGE |  | Closeout | SITE |  |  |  | Perform Punch List | 10 | 10 | 2023-05-24 08:00 | 2023-06-07 17:00 | -7 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.1 | OG6-01005 | ATCO | OG6 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - OG6 | 3 | 3 | 2024-01-30 08:00 | 2024-02-01 17:00 | -200 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.1 | OG6-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> OG6 | 3 | 0 | 2021-08-23 08:00 | 2021-08-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.1 | OG6-01015 | ATCO | OG6 | ABESTOS | [5 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG6 | 3 | 0 | 2022-11-14 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.1 | OG6-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> OG6 | 3 | 0 | 2021-08-23 08:00 | 2021-08-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.1 | OG6-01025 | ATCO | OG6 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> OG6 | 5 | 0 | 2022-08-09 08:00 | 2022-08-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.1 | OG6-01030 | ATCO | OG6 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> OG6 | 5 | 0 | 2022-11-14 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01105 | MLJ | OG6 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG6 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG6 | 10 | 0 | 2021-05-06 | 2022-08-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01110 | MLJ | OG6 | DEMO |  |  | DEMO DOORS WINDOWS |  |  | Selective Demo (Doors, windows) - 1st Floor --> OG6 | 5 | 0 | 2022-12-19 08:00 | 2022-12-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01115 | MLJ | OG6 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> OG6 | 10 | 0 | 2022-11-15 | 2022-11-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01205 | MLJ | OG6 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG6 | 5 | 0 | 2022-12-12 08:00 | 2022-12-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01210 | MLJ | OG6 | DEMO |  |  | DEMO SLAB OPEN FOR MECH |  |  | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG6 | 5 | 0 | 2022-12-12 | 2022-12-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG6 | 5 | 0 | 2021-10-07 | 2022-02-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01310 | MLJ | OG6 | CORE DRILL | [5 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG6 | 5 | 0 | 2022-12-12 | 2022-12-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01315 | WEIR | OG6 | [6 empty] | Install beams below floor - 2nd floor apartments --> OG6 | 5 | 0 | 2022-11-21 | 2022-12-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01320 | MLJ | OG6 |  |  |  | FRP | 03-6000 | 03-6000-OG6 | Install FRP around floor openings - 2nd floor apartments --> OG6 | 5 | 0 | 2022-11-21 | 2022-11-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01325 | CCC | OG6 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> OG6 | 3 | 0 | 2022-12-27 08:00 | 2022-12-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01330 | CCC | OG6 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> OG6 | 5 | 0 | 2023-01-03 | 2023-01-05 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01335 | CCC | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> OG6 | 10 | 10 | 2023-07-17 08:00 | 2023-07-28 17:00 | -75 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.4 | OG6-01340 | FLOORING | OG6 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> OG6 | 2 | 2 | 2023-07-31 08:00 | 2023-08-01 17:00 | -75 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01405 | MLJ | OG6 | Excavation | Exterior | EXISTING BUILDINGS | EB EXC | 31-1000 | 31-1000-OG6 | Excavate at Curtain Wall for flood protection (East Side) --> OG6 | 8 | 8 | 2023-02-27 08:00 | 2023-03-08 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01410 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 10 | 10 | 2023-03-09 08:00 | 2023-03-22 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01415 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 5 | 5 | 2023-03-23 08:00 | 2023-03-29 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01420 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 2023-03-30 08:00 | 2023-04-04 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01425 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 5 | 5 | 2023-04-05 08:00 | 2023-04-11 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01430 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 8 | 8 | 2023-04-12 08:00 | 2023-04-21 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01435 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 6 | 6 | 2023-04-24 08:00 | 2023-05-01 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01440 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 2023-05-02 08:00 | 2023-05-05 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01445 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 2023-05-08 08:00 | 2023-05-11 17:00 | -28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01450 | FAXA | OG6 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 2023-05-15 08:00 | 2023-05-18 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01455 | MLJ | OG6 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG6 | Backfill at Curtain Wall for flood protection (East Side) --> OG6 | 5 | 5 | 2023-05-19 08:00 | 2023-05-25 17:00 | -29 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01505 | MLJ | OG6 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG6 | Excavate at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 0 | 2022-11-25 | 2022-11-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01510 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 9 | 0 | 2022-11-28 | 2022-11-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01515 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 4 | 0 | 2022-11-30 | 2022-12-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01520 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 0 | 2022-12-01 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01525 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 4 | 0 | 2022-12-05 | 2022-12-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01530 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 0 | 2022-12-07 | 2022-12-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01535 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 5 | 0 | 2022-12-09 | 2022-12-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01540 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 0 | 2022-12-11 | 2022-12-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01545 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 0 | 2022-12-12 | 2022-12-12 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01550 | FAXA | OG6 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | 36 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01555 | MLJ | OG6 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG6 | Backfill at Curtain Wall for flood protection (South Side) --> OG6 | 4 | 4 | 2023-03-02 08:00 | 2023-03-07 17:00 | 36 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01605 | MLJ | OG6 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG6 | Excavate at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 0 | 2022-12-27 08:00 | 2022-12-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01610 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 9 | 0 | 2022-12-29 | 2022-12-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01615 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 4 | 0 | 2023-01-03 | 2023-01-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01620 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 0 | 2023-01-05 | 2023-01-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01625 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 4 | 0 | 2023-01-06 | 2023-01-06 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01630 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 0 | 2023-01-30 08:00 | 2023-02-03 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01635 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 5 | 0 | 2023-02-06 08:00 | 2023-02-08 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01640 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 0 | 2023-02-08 08:00 | 2023-02-10 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01645 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 0 | 2023-02-13 08:00 | 2023-02-13 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01650 | FAXA | OG6 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 2 | 2023-02-21 08:00 | 2023-02-28 17:00 | 41 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01655 | MLJ | OG6 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG6 | Backfill at Curtain Wall for flood protection (North Side) --> OG6 | 4 | 0 | 2023-02-22 08:00 | 2023-02-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01705 | MLJ | OG6 | Excavation | Exterior | EXISTING BUILDINGS | EB EXC | 31-1000 | 31-1000-OG6 | Excavate at Curtain Wall for flood protection (West Side) --> OG6 | 8 | 8 | 2023-03-23 08:00 | 2023-04-03 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01710 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 10 | 10 | 2023-04-04 08:00 | 2023-04-17 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01715 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 5 | 5 | 2023-04-18 08:00 | 2023-04-24 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01720 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-04-25 08:00 | 2023-04-28 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01725 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 5 | 5 | 2023-05-01 08:00 | 2023-05-05 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01730 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 8 | 8 | 2023-05-08 08:00 | 2023-05-17 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01735 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 6 | 6 | 2023-05-18 08:00 | 2023-05-25 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01740 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-05-26 08:00 | 2023-06-01 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01745 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-06-02 08:00 | 2023-06-07 17:00 | -61 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01750 | FAXA | OG6 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-06-09 08:00 | 2023-06-14 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01755 | MLJ | OG6 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG6 | Backfill at Curtain Wall for flood protection (West Side) --> OG6 | 5 | 5 | 2023-06-15 08:00 | 2023-06-21 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01760 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form for slab at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-06-22 08:00 | 2023-06-27 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01765 | TONAGE | OG6 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG6 | 6 | 6 | 2023-06-28 08:00 | 2023-07-06 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01770 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour slab at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-07-07 08:00 | 2023-07-12 17:00 | -62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01775 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG6 | 2 | 2 | 2023-07-13 08:00 | 2023-07-14 17:00 | -59 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01780 | MLJ | OG6 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG6 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 2023-07-20 08:00 | 2023-07-25 17:00 | -62 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01805 | MLJ | OG6 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG6 | Excavate for concrete shelf around bldg perimeter --> OG6 | 10 | 0 | 2022-11-01 | 2022-11-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01810 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Place rebar for concrete shelf around bldg perimeter --> OG6 | 5 | 0 | 2022-11-08 | 2022-11-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01815 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour concrete shelf around bldg perimeter --> OG6 | 5 | 0 | 2022-11-15 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01820 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Place infill concrete in area ways around bldg perimeter --> OG6 | 5 | 0 | 2022-11-15 | 2022-11-15 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01825 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Place waterproofing on concrete shelf around bldg perimeter --> OG6 | 10 | 5 | 2023-01-07 | 2023-03-03 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01830 | FAXA | OG6 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU around bldg perimeter --OG6 | 15 | 7 | 2023-02-20 08:00 | 2023-03-14 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01835 | DSTAR | OG6 | WATERPROOFING | Exterior | EXISTING BUILDINGS |  |  |  | Place waterproofing on CMU around bldg perimeter --> OG6 | 10 | 10 | 2023-03-15 08:00 | 2023-03-28 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01840 | MLJ | OG6 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> OG6 | 10 | 10 | 2023-03-29 08:00 | 2023-04-11 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01845 | FAXA | OG6 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG6 | 20 | 20 | 2023-04-12 08:00 | 2023-05-09 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01850 | MLJ | OG6 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG6 | Backfill around bdg perimeter --> OG6 | 5 | 2 | 2023-02-23 08:00 | 2023-05-11 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01855 | CCC | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> OG6 | 4 | 4 | 2023-05-12 08:00 | 2023-05-17 17:00 | -1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01860 | MLJ | OG6 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> OG6 | 5 | 0 | 2023-01-25 08:00 | 2023-01-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01865 | MLJ | OG6 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> OG6 | 3 | 3 | 2023-05-18 08:00 | 2023-05-22 17:00 | -1 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.5 | OG6-01350 | MLJ | OG6 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-OG6 | Drill dowels and place rebar for boiler room concrete walls --> OG6 | 5 | 0 | 2022-08-15 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.5 | OG6-01355 | MLJ | OG6 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG6 | Form boiler room concrete walls --> OG6 | 5 | 0 | 2022-09-05 | 2022-09-05 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.5 | OG6-01360 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Pour Concrete boiler room walls --> OG6 | 2 | 1 | 2022-09-06 | 2023-02-27 17:00 | 29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.5 | OG6-01365 | MLJ | OG6 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG6 | Strip Forms boiler room concrete walls --> OG6 | 3 | 3 | 2023-02-28 08:00 | 2023-03-02 17:00 | 31 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.5 | OG6-01370 |  | OG6 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> OG6 | 10 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.6 | OG6-01385 | [8 empty] | Refurbish Elevator 1 --> OG6 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.6 | OG6-01390 | [8 empty] | Refurbish Elevator 2 --> OG6 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.6 | OG6-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.7 | OG6-09005 | CLOSEOUT | OG6 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2024-02-02 08:00 | 2024-02-08 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.7 | OG6-09010 | PUNCH LIST | OG6 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2024-02-09 08:00 | 2024-02-23 17:00 | -185 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.2 | OG6-01220 | MLJ | OG6 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-OG6 | Selective Demo (Pumps etc..) - Cellar --> OG6 | 5 | 0 | 2022-10-17 | 2022-10-20 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.1 | OG1-01005 | ATCO | OG1 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - OG1 | 3 | 3 | 2024-01-08 08:00 | 2024-01-10 17:00 | -184 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.1 | OG1-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> OG1 | 3 | 0 | 2021-06-28 08:00 | 2021-07-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.1 | OG1-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG1 | 3 | 0 | 2022-01-03 08:00 | 2022-01-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.1 | OG1-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> OG1 | 3 | 0 | 2021-06-28 08:00 | 2021-07-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.1 | OG1-01025 | ATCO | OG1 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> OG1 | 5 | 0 | 2022-06-27 08:00 | 2022-06-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.1 | OG1-01030 | ATCO | OG1 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> OG1 | 5 | 0 | 2022-06-27 08:00 | 2022-06-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01105 | MLJ | OG1 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG1 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG1 | 10 | 0 | 2021-04-25 | 2022-08-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01110 | [8 empty] | Selective Demo (Doors, windows) - 1st Floor --> OG1 | 5 | 0 | 2022-06-09 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01115 | MLJ | OG1 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> OG1 | 10 | 0 | 2022-08-25 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01205 | MLJ | OG1 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG1 | 5 | 0 | 2022-08-31 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01210 | [8 empty] | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG1 | 5 | 0 | 2022-06-08 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG1 | 5 | 0 | 2021-10-06 | 2022-01-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01310 | [8 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG1 | 5 | 0 | 2022-06-08 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01315 | [8 empty] | Install beams below floor - 2nd floor apartments --> OG1 | 5 | 0 | 2022-04-15 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01320 | [8 empty] | Install FRP around floor openings - 2nd floor apartments --> OG1 | 5 | 0 | 2022-04-21 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01325 | CCC | OG1 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> OG1 | 3 | 0 | 2022-03-25 | 2022-12-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01330 | CCC | OG1 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> OG1 | 5 | 0 | 2022-05-02 | 2022-12-28 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01335 | CCC | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> OG1 | 10 | 1 | 2022-05-12 | 2023-04-28 17:00 | -12 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.4 | OG1-01340 | FLOORING | OG1 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> OG1 | 2 | 2 | 2023-05-01 08:00 | 2023-05-02 17:00 | -12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01405 |  | OG1 | EXCAVATION |  |  |  | 31-1000 | 31-1000-OG1 | Excavate at Curtain Wall for flood protection (East Side) --> OG1 | 8 | 0 | 2022-04-26 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01410 |  | OG1 | FORMWORK |  |  | FORMWORK EB | 03-1100 | 03-1100-OG1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 10 | 0 | 2022-05-20 | 2022-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01415 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 5 | 0 | 2022-05-06 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01420 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 2022-05-24 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01425 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 5 | 0 | 2022-05-25 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01430 | MLJ | OG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 8 | 0 | 2022-10-07 | 2022-10-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01435 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 6 | 0 | 2022-10-14 | 2022-10-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01440 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 2022-10-18 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01445 | MLJ | OG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 2022-10-19 | 2022-10-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01450 | FAXA | OG1 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 2022-10-20 | 2022-10-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01455 | MLJ | OG1 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG1 | Backfill at Curtain Wall for flood protection (East Side) --> OG1 | 5 | 0 | 2022-12-27 08:00 | 2022-12-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01505 | [8 empty] | Excavate at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 2022-02-16 | 2022-03-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01510 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 9 | 0 | 2022-02-21 | 2022-03-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01515 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 4 | 0 | 2022-02-22 | 2022-03-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01520 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 2022-02-24 | 2022-03-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01525 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 4 | 0 | 2022-05-25 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01530 | MLJ | OG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 2022-08-25 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01535 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 5 | 0 | 2022-09-01 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01540 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01545 | MLJ | OG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 2022-09-08 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01550 | FAXA | OG1 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 2022-09-15 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01555 | MLJ | OG1 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG1 | Backfill at Curtain Wall for flood protection (South Side) --> OG1 | 4 | 0 | 2022-10-27 | 2022-11-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01605 | [8 empty] | Excavate at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 2022-05-25 | 2022-06-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01610 | [8 empty] | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 9 | 0 | 2022-05-20 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01615 | [8 empty] | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 4 | 0 | 2022-05-06 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01620 | [8 empty] | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 2022-05-24 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01625 | [8 empty] | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 4 | 0 | 2022-06-01 | 2022-06-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01630 | MLJ | OG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 2022-08-25 08:00 | 2022-08-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01635 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 5 | 0 | 2022-09-01 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01640 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01645 | MLJ | OG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 2022-09-08 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01650 | FAXA | OG1 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 2022-09-15 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01655 | MLJ | OG1 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG1 | Backfill at Curtain Wall for flood protection (North Side) --> OG1 | 4 | 0 | 2022-10-27 | 2022-11-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01705 | MLJ | OG1 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-OG1 | Excavate at Curtain Wall for flood protection (West Side) --> OG1 | 8 | 0 | 2022-11-01 | 2022-11-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01710 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01715 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01720 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 2023-03-20 08:00 | 2023-03-23 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01725 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 5 | 5 | 2023-03-24 08:00 | 2023-03-30 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01730 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 8 | 8 | 2023-03-31 08:00 | 2023-04-11 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01735 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 6 | 6 | 2023-04-12 08:00 | 2023-04-19 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01740 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 2023-04-20 08:00 | 2023-04-25 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01745 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 2023-04-26 08:00 | 2023-05-01 17:00 | 4 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01750 | FAXA | OG1 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 2023-05-03 08:00 | 2023-05-08 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01755 | MLJ | OG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG1 | Backfill at Curtain Wall for flood protection (West Side) --> OG1 | 5 | 0 | 2023-02-03 | 2023-02-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01760 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form for slab at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 0 | 2023-02-10 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01765 | TONAGE | OG1 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG1 | 6 | 0 | 2023-02-13 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01770 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour slab at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 0 | 2023-02-16 | 2023-02-17 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01775 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG1 | 2 | 0 | 2023-02-17 | 2023-02-20 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01780 | MLJ | OG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG1 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 0 | 2023-02-21 | 2023-02-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01805 | [8 empty] | Excavate for concrete shelf around bldg perimeter --> OG1 | 10 | 0 | 2022-05-04 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01810 | [8 empty] | Place rebar for concrete shelf around bldg perimeter --> OG1 | 5 | 0 | 2022-05-16 | 2022-05-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01815 | [8 empty] | Pour concrete shelf around bldg perimeter --> OG1 | 5 | 0 | 2022-05-26 | 2022-05-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01820 | [8 empty] | Place infill concrete in area ways around bldg perimeter --> OG1 | 5 | 0 | 2022-05-27 | 2022-05-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01825 | [8 empty] | Place waterproofing on concrete shelf around bldg perimeter --> OG1 | 10 | 0 | 2022-06-01 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01830 | FAXA | OG1 | CMU | [5 empty] | Place CMU around bldg perimeter --OG1 | 15 | 0 | 2022-06-14 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01835 |  | OG1 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> OG1 | 10 | 0 | 2022-08-25 | 2022-09-05 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01840 | MLJ | OG1 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> OG1 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 43 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01845 | FAXA | OG1 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG1 | 20 | 0 | 2022-09-20 | 2022-10-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01850 | MLJ | OG1 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-OG1 | Backfill around bdg perimeter --> OG1 | 5 | 0 | 2022-01-21 | 2022-10-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01855 | CCC | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> OG1 | 4 | 4 | 2023-03-13 08:00 | 2023-03-16 17:00 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01860 | MLJ | OG1 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> OG1 | 5 | 5 | 2023-03-17 08:00 | 2023-03-23 17:00 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01865 | MLJ | OG1 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> OG1 | 3 | 3 | 2023-03-24 08:00 | 2023-03-28 17:00 | 43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.5 | OG1-01350 | MLJ | OG1 |  | Interior | EXISTING BUILDINGS | DRILL & DOWEL | 03-1400 | 03-1400-OG1 | Drill dowels and place rebar for boiler room concrete walls --> OG1 | 5 | 0 | 2023-01-30 | 2023-02-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.5 | OG1-01355 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Form boiler room concrete walls --> OG1 | 5 | 0 | 2023-02-03 | 2023-02-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.5 | OG1-01360 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Pour Concrete boiler room walls --> OG1 | 2 | 0 | 2023-02-10 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.5 | OG1-01365 | MLJ | OG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG1 | Strip Forms boiler room concrete walls --> OG1 | 3 | 0 | 2023-02-13 | 2023-02-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.5 | OG1-01370 |  | OG1 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> OG1 | 10 | 0 | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.6 | OG1-01385 | [8 empty] | Refurbish Elevator 1 --> OG1 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.6 | OG1-01390 | [8 empty] | Refurbish Elevator 2 --> OG1 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.6 | OG1-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.7 | OG1-09005 | CLOSEOUT | OG1 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2024-01-11 08:00 | 2024-01-17 17:00 | -184 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.7 | OG1-09010 | PUNCH LIST | OG1 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2024-01-18 08:00 | 2024-01-31 17:00 | -169 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.2 | OG1-01220 | MLJ | OG1 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-OG1 | Selective Demo (Pumps etc..) - Cellar --> OG1 | 5 | 0 | 2022-07-21 08:00 | 2022-07-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2022-03-28 | 2022-04-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03010 | WELKIN | OG6 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2023-01-05 | 2023-01-09 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03020 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pump Controls - Cellar | 20 | 0 | 2023-01-10 | 2023-02-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03025 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 5 | 2023-03-02 08:00 | 2023-03-08 17:00 | -47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03030 |  | OG6 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-09-26 | 2022-10-20 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03035 | CLOSEOUT | OG6 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-03-09 08:00 | 2023-03-22 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03040 | MEP | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-03-23 08:00 | 2023-04-19 17:00 | -47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2021-04-26 | 2021-04-28 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03007 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 3 | 2022-04-04 | 2023-03-01 17:00 | -87 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2021-10-25 | 2021-12-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03120 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 10 | 2022-08-15 08:00 | 2023-04-05 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03125 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-04-06 08:00 | 2023-04-12 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03130 | NAVILLUS | OG6 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 15 | 2023-03-02 08:00 | 2023-03-22 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03135 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-04-13 08:00 | 2023-04-26 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03140 | MEP | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-04-27 08:00 | 2023-05-24 17:00 | -72 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03115 | WELKIN | OG6 | [6 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-08-22 08:00 | 2022-09-16 08:48 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03110 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 0 | 2023-01-23 08:00 | 2023-02-27 10:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03112 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 0 | 2023-01-25 10:00 | 2023-02-01 10:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.2 | OG6-03107 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-08-08 08:00 | 2023-02-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03220 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-04-06 08:00 | 2023-05-03 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03230 | NAVILLUS | OG6 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 2023-03-02 08:00 | 2023-03-22 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03235 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-05-04 08:00 | 2023-05-17 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03240 | MEP | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-05-18 08:00 | 2023-06-15 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03210 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-03-23 08:00 | 2023-03-29 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.3 | OG6-03215 | WELKIN | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-03-30 08:00 | 2023-04-05 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03305 | CLOSEOUT | OG6 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG6 | 4 | 4 | 2023-06-16 08:00 | 2023-06-21 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03310 | CLOSEOUT | OG6 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - OG6 | 11 | 11 | 2023-12-06 08:00 | 2023-12-20 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03315 | CLOSEOUT | OG6 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Start-Up Testing Mechanical/Plumbing - OG2 | 16 | 16 | 2023-12-21 08:00 | 2024-01-15 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03320 | PUNCH LIST | OG6 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG2 | 5 | 5 | 2024-01-16 08:00 | 2024-01-22 17:00 | -172 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03330 | MEP | OG6 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG2 | 4 | 4 | 2024-01-24 08:00 | 2024-01-29 17:00 | -172 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03325 | CLOSEOUT | OG6 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG2 | 1 | 1 | 2024-01-23 08:00 | 2024-01-23 17:00 | -172 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-03335 | MLJ | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - OG2 | 10 | 10 | 2024-01-16 08:00 | 2024-01-29 17:00 | -200 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2021-09-27 | 2021-12-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03010 | WELKIN | OG1 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-07-27 08:00 | 2022-08-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03020 |  | OG1 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-08-09 08:00 | 2022-09-09 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03025 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 0 | 2023-02-15 08:00 | 2023-02-22 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03030 | VITAL | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Plumbing Equipment - Cellar | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03035 | CLOSEOUT | OG1 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-03-20 08:00 | 2023-03-31 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03040 | MEP | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-04-03 08:00 | 2023-04-28 17:00 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2021-07-26 | 2021-08-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-07-21 | 2021-12-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 15 | 0 | 2021-07-26 08:00 | 2021-12-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03120 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 20 | 2023-02-27 10:00 | 2023-03-27 10:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03125 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 0 | 2023-02-15 10:00 | 2023-02-22 10:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03130 | NAVILLUS | OG1 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2023-02-10 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03135 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-03-27 10:00 | 2023-04-10 10:00 | -43 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03140 | MEP | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-04-10 10:00 | 2023-05-08 10:00 | -43 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03115 | WELKIN | OG1 | [6 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-07-25 08:00 | 2022-09-23 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03110 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 0 | 2022-09-20 08:00 | 2023-02-27 10:00 | -43 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03112 |  | OG1 | [6 empty] | Install HV & EF Units - 1st Floor | 5 | 0 | 2022-09-19 08:00 | 2022-09-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.2 | OG1-03107 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2021-05-17 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03220 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-03-27 08:00 | 2023-04-21 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03230 | NAVILLUS | OG1 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03235 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03240 | MEP | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-05-08 08:00 | 2023-06-05 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03210 | WELKIN | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -63 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.3 | OG1-03215 |  | OG1 | [6 empty] | Install EF Units - 2nd Floor | 5 | 0 | 2023-01-10 | 2023-01-19 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-03305 | CLOSEOUT | OG1 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - OG1 | 4 | 4 | 2023-06-06 08:00 | 2023-06-09 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-03310 | CLOSEOUT | OG1 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - OG1 | 11 | 11 | 2023-12-06 08:00 | 2023-12-20 17:00 | -184 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-03320 | PUNCH LIST | OG1 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG1 | 5 | 5 | 2023-12-21 08:00 | 2023-12-28 17:00 | -156 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-03330 | MEP | OG1 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG1 | 4 | 4 | 2024-01-02 08:00 | 2024-01-05 17:00 | -156 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-03325 | CLOSEOUT | OG1 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG1 | 1 | 1 | 2023-12-29 08:00 | 2023-12-29 17:00 | -156 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-03335 | MLJ | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - OG1 | 10 | 10 | 2023-12-21 08:00 | 2024-01-05 17:00 | -184 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-02005 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-02010 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Install Manholes & Grounding | 8 | 8 | 2023-03-06 08:00 | 2023-03-15 17:00 | -84 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01005 | [8 empty] | Install Site Fencing - Surfside Gardens - South | 10 | 0 | 2021-04-28 | 2021-05-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01015 | [8 empty] | Install Overhead Protection - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01020 | [6 empty] | 31-1900 |  | Install Tree Protection | 10 | 0 | 2020-11-04 | 2020-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01025 | [8 empty] | Remove Trees | 2 | 0 | 2021-01-14 | 2021-01-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01000 | [8 empty] | Remove Curbs And Existing Fencing | 10 | 0 | 2021-07-19 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01035 | [8 empty] | Install Erosion Control | 5 | 0 | 2022-02-10 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01010 | [8 empty] | Set Up Yard and Staging | 10 | 0 | 2020-12-28 | 2021-01-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01045 | [8 empty] | Clear & Grub | 10 | 0 | 2021-05-11 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01050 | [8 empty] | Scrape & Store Topsoil | 10 | 0 | 2021-05-11 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01055 | [8 empty] | Soil Testing | 10 | 0 | 2021-05-14 | 2021-06-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01060 | [6 empty] | 02-2000 |  | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 2021-07-26 08:00 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01065 | [8 empty] | Remove Retaining Walls | 10 | 0 | 2022-01-10 | 2022-04-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01070 | [8 empty] | Install Deep Wells For Dewatering - N/A | 10 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01075 | [8 empty] | Install Piping For Deep Wells - N/A | 5 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01080 | [8 empty] | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01085 | [8 empty] | Run Electric For Dewatering - N/A | 10 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01150 | [8 empty] | Excavate for Electric SG7--> SG1 | 10 | 0 | 2022-05-13 | 2022-05-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01155 | [8 empty] | Install Electrical Conduit SG7--> SG1 | 10 | 0 | 2022-05-13 | 2022-06-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01160 | [8 empty] | Encase conduit in concrete SG7--> SG1 | 5 | 0 | 2022-06-03 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01165 | [8 empty] | Backfill Electrical SG7--> SG1 | 5 | 0 | 2022-06-02 | 2022-06-06 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01405 | NATIONAL GRID | SGS |  | Utilities | SITE |  |  |  | National Gas Install Line from W31st to SG7 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -39 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01205 | [8 empty] | Excavate for Electric SG7--> SG2 | 3 | 0 | 2022-05-13 | 2022-06-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01210 | FIVE STAR | SGS | [6 empty] | Install Electrical Conduit SG7--> SG2 | 2 | 0 | 2022-05-13 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01215 | MLJ | SGS | Concrete |  |  | SITE CONCRETE |  |  | Encase conduit in concrete SG7--> SG2 | 2 | 0 | 2022-06-27 | 2022-06-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01220 | MLJ | SGS | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-SGS | Backfill Electrical SG7--> SG2 | 2 | 0 | 2022-06-30 | 2022-07-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01230 | [8 empty] | Excavate for Electric SG7--> SG3 | 10 | 0 | 2022-05-13 | 2022-06-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01235 | [8 empty] | Install Electrical Conduit & MH SG7--> SG3 | 10 | 0 | 2022-05-13 | 2022-06-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01240 | [8 empty] | Encase conduit in concrete SG7--> SG3 | 3 | 0 | 2022-06-22 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01245 | [8 empty] | Backfill Electrical SG7--> SG3 | 5 | 0 | 2022-06-23 | 2022-06-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01255 | MLJ | SGS | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-SGS | Excavate for Electric SG3--> MH | 3 | 0 | 2022-04-18 | 2022-09-09 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01260 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Install Electrical Conduit SG3--> MH | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01265 | MLJ | SGS | Concrete | Utilities | SITE | SITE CONCRETE |  |  | Encase conduit in concrete SG3--> MH | 2 | 2 | 2023-03-01 08:00 | 2023-03-02 17:00 | -44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01270 | MLJ | SGS | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-SGS | Backfill Electrical SG3--> MH | 2 | 2 | 2023-03-03 08:00 | 2023-03-06 17:00 | -44 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01275 | [8 empty] | Excavate for Steam SG3--> SG2 | 15 | 0 | 2022-03-25 | 2022-04-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01280 | [8 empty] | Install Steam piping SG3--> SG2 | 20 | 0 | 2022-04-07 | 2022-06-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01285 | [8 empty] | Test Steam Piping SG3--> SG2 | 8 | 0 | 2022-06-06 | 2022-06-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01290 | [8 empty] | Backfill Steam Piping SG3--> SG2 | 10 | 0 | 2022-06-17 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01505 | MLJ | SGS | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-SGS | Excavate for water line to drinking fountains SGS --> Water Main W32nd Street | 2 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01510 |  | SGS |  |  |  | PLAYGROUND |  |  | Install water line to drinking fountain SGS --> Water Main W32nd Street | 5 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01515 |  | SGS |  |  |  | PLAYGROUND |  |  | Tap water main for drinking fountain water line SGS --> Water Main W32nd Street | 2 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01520 | MLJ | SGS | BACKFILL |  |  | BACKFILL SITE |  |  | Backfill water line drinking fountain SGS --> Water Main W32nd Street | 2 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01560 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - Yard Drain to Existing+ Piping incl DIP 3 | 10 | 0 | 2022-10-21 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01565 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains Yard Drain to Existing+ Piping incl DIP 3 | 5 | 0 | 2022-10-31 | 2022-11-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01090 | [8 empty] | Activate Dewatering System | 1 | 0 | 2022-01-01 | 2022-01-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01095 |  |  | dewatering | [5 empty] | Maintain Dewatering | 283 | 0 | 2022-01-01 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01287 |  | SGS | [6 empty] | Install Automatic Temperature Control Conduit - SG3--> SG2 | 2 | 0 | 2022-07-25 08:00 | 2022-07-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.Removals1 | SGS-01100 | [8 empty] | De-Activate Dewatering | 1 | 0 | 2022-05-10 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01295 | [8 empty] | Excavate for Steam & HW SG3--> SG7 | 15 | 0 | 2021-12-06 08:00 | 2021-12-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01300 | WELKIN | SGS | UG PIPE | [5 empty] | Install Steam and HW piping SG3--> SG7 | 20 | 0 | 2021-12-17 08:00 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01305 | WELKIN | SGS | UG PIPE | [5 empty] | Test Steam & HW Piping SG3--> SG7 | 8 | 0 | 2022-09-12 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01315 | MLJ | SGS | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-SGS | Backfill Steam & HW Piping SG3--> SG7 | 10 | 0 | 2022-09-19 | 2022-09-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01310 |  | SGS | [6 empty] | Install Automatic Temperature Control Conduit - SG3--> SG7 | 2 | 0 | 2022-09-21 | 2022-09-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01325 | [8 empty] | Excavate for Steam SG3--> SG1 | 15 | 0 | 2021-11-30 08:00 | 2022-01-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01330 | [8 empty] | Install Steam and piping SG3--> SG1 | 20 | 0 | 2022-01-26 | 2022-04-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01335 | WELKIN | [7 empty] | Test Steam & Piping SG3--> SG1 | 8 | 0 | 2022-03-16 | 2022-04-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01345 | [8 empty] | Backfill Steam & Piping SG3--> SG1 | 10 | 0 | 2022-04-15 08:00 | 2022-04-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01340 |  | SGS | [6 empty] | Install Automatic Temperature Control Conduit - SG3--> SG1 | 2 | 0 | 2022-09-21 | 2022-09-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01575 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD8 > AD3 > Existing + Piping incl DIP4 | 10 | 0 | 2022-11-03 | 2022-11-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01580 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD8 > AD3 > Existing + Piping incl DIP4 | 5 | 0 | 2022-11-08 | 2022-11-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01590 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - Yard Drain > AD3 > Existing + Piping | 10 | 0 | 2022-11-03 | 2022-11-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01595 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - Yard Drain > AD3 > Existing + Piping | 5 | 0 | 2022-11-25 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01650 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD16 > AD17 & Piping | 10 | 0 | 2022-11-25 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01655 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD16 > AD17 & Piping | 5 | 0 | 2022-11-30 | 2022-12-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01660 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD21 > Trap to Existing & Piping | 10 | 0 | 2022-12-07 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01665 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD21 > Trap to Existing & Piping | 5 | 0 | 2022-12-19 | 2022-12-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01670 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD1 > AD2 > AD4 > Existing + Piping | 10 | 0 | 2022-12-07 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01675 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD1 > AD2 > AD4 > Existing + Piping | 5 | 0 | 2022-12-19 | 2022-12-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01680 | MLJ | SGS | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD9 > AD4 > Piping | 10 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01685 | MLJ | SGS | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD9 > AD4 > Piping | 5 | 0 | 2022-12-25 | 2022-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01690 | MLJ | SGS | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD20 > Existing + Piping | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01695 | MLJ | SGS | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD20 > Existing + Piping | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -53 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01350 | [8 empty] | Excavate for HW SG7--> SG1 | 15 | 0 | 2022-01-05 | 2022-01-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01355 | [8 empty] | Install HW and piping SG7--> SG1 | 20 | 0 | 2022-02-11 | 2022-03-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01360 | WELKIN | [7 empty] | Test HW & Piping SG7--> SG1 | 8 | 0 | 2022-03-01 | 2022-03-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01370 | [8 empty] | Backfill HW & Piping SG7--> SG1 | 10 | 0 | 2022-05-02 | 2022-05-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01365 | [8 empty] | Install Automatic Temperature Control Conduit - SG7--> SG1 | 2 | 0 | 2022-05-25 | 2022-05-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01375 | [8 empty] | Excavate for HW SG7--> SG2 | 15 | 0 | 2022-02-02 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01380 |  | SGS | [6 empty] | Install HW piping SG7--> SG2 | 20 | 0 | 2022-05-10 | 2022-06-09 08:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01385 | [8 empty] | Test HW Piping SG7--> SG2 | 8 | 0 | 2022-06-09 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01395 | [8 empty] | Backfill HW Piping SG7--> SG2 | 10 | 0 | 2022-06-20 | 2022-06-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01390 | FIVE STAR | SGS |  | Utilities | SITE |  |  |  | Install Automatic Temperature Control Conduit - SG7--> SG2 | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01700 | MLJ | SGS | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - Yard Drain > AD10 > AD11 > Existing + Piping | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01775 | MLJ | SGS | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - Yard Drain > AD10 > AD11 > Existing + Piping | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01780 | MLJ | SGS | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD13 > AD15 > AD14 > AD12 + Piping | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01785 | MLJ | SGS | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD13 > AD15 > AD14 > AD12 + Piping | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01790 | MLJ | SGS | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD19 > AD18 + Piping | 10 | 10 | 2023-04-10 08:00 | 2023-04-21 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01795 | MLJ | SGS | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD19 > AD18 + Piping | 5 | 5 | 2023-04-24 08:00 | 2023-04-28 17:00 | -83 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01800 | MLJ | SGS | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-SGS | Excavate and Install Area Drains - AD5 > AD6 > AD7 > Existing + Piping | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.6 | SGS-01805 | MLJ | SGS | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-SGS | Backfill Area Drains - AD5 > AD6 > AD7 > Existing + Piping | 5 | 5 | 2023-05-08 08:00 | 2023-05-12 17:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01605 | MLJ | SGS | Excavation |  |  | EXC RETAINING |  |  | Excavate for retaining wall --> SGS Phase 5 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01610 | MLJ | SGS | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-SGS | Form Retaining wall footing --> SGS Phase 5 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01615 |  | SGS | REBAR | [5 empty] | Rebar Retaining wall footing --> SGS Phase 5 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01620 | MLJ | SGS | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall footing --> SGS Phase 5 | 1 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01625 |  | SGS | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall footing --> SGS Phase 5 | 1 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01630 | MLJ | SGS | Formwork | Restoration | SITE | SITE FORMWORK | 03-1600 | 03-1600-SGS | Form Retaining wall --> SGS Phase 5 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01635 | TONAGE | SGS | REBAR | Restoration | SITE |  |  |  | Rebar Retaining wall --> SGS Phase 5 | 3 | 3 | 2023-03-02 08:00 | 2023-03-06 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01640 | MLJ | SGS | Concrete | Restoration | SITE | SITE CONCRETE |  |  | Pour Retaining wall --> SGS Phase 5 | 1 | 1 | 2023-03-07 08:00 | 2023-03-07 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01645 | MLJ | SGS | Formwork | Restoration | SITE | SITE FORMWORK |  |  | Strip Retaining wall --> SGS Phase 5 | 1 | 1 | 2023-03-08 08:00 | 2023-03-08 17:00 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01705 | JMC | SGS | CURBS | Restoration | SITE |  |  |  | Install Street Curbs --> SGS Phase 5 | 15 | 15 | 2023-06-06 08:00 | 2023-06-26 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01710 | JMC | SGS | SIDEWALKS | Restoration | SITE |  |  |  | Install sidewalks --> SGS Phase 5 | 10 | 10 | 2023-07-12 08:00 | 2023-07-25 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01715 | MLJ | SGS | CURBS | Restoration | SITE |  |  |  | Install curb around play area --> SGS Phase 5 | 5 | 5 | 2023-07-26 08:00 | 2023-08-01 17:00 | -108 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01720 |  | SGS |  |  |  | PLAYGROUND |  |  | Install Safety Surface --> SGS Phase 5 | 5 | 0 | 2022-12-26 08:00 | 2022-12-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01725 | MLJ | SGS | Concrete | Restoration | SITE | SITE CONCRETE |  |  | Install site furniture concrete foundations --> SGS Phase 5 | 10 | 10 | 2023-06-27 08:00 | 2023-07-11 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01730 | JMC | SGS | COLORED CONCRETE | Restoration | SITE |  |  |  | Install integrally colored concrete walkways --> SGS Phase 5 | 20 | 20 | 2023-08-02 08:00 | 2023-08-29 17:00 | -108 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01735 |  | SGS |  |  |  | PLAYGROUND |  |  | Install Play area items --> SGS Phase 5 | 5 | 0 | 2022-12-26 08:00 | 2022-12-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01740 |  | SGS |  |  |  | PLAYGROUND |  |  | Install fence around play area --> SGS Phase 5 | 10 | 0 | 2022-12-26 08:00 | 2022-12-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01745 | ATLAS | SGS | SITE RESTORATION | Restoration | SITE |  |  |  | Install Fence at building --> SG7 | 5 | 5 | 2023-08-30 08:00 | 2023-09-06 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01750 | MLJ | SGS | SITE RESTORATION | Restoration | SITE |  |  |  | Place Site Furniture --> SGS Phase 5 | 10 | 10 | 2023-09-07 08:00 | 2023-09-20 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01755 | ASPEN | SGS | TOPSOIL | Restoration | SITE |  |  |  | Place topsoil --> SGS Phase 5 | 3 | 3 | 2023-09-21 08:00 | 2023-09-25 17:00 | -33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01760 | ASPEN | SGS |  | Restoration | SITE |  |  |  | Place trees and plantings --> SGS Phase 5 | 5 | 5 | 2023-09-26 08:00 | 2023-10-02 17:00 | -33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01765 | ASPEN | SGS |  | Restoration | SITE |  |  |  | Place lawn --> SGS Phase 5 | 5 | 5 | 2023-10-03 08:00 | 2023-10-09 17:00 | -33 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.5 | SGS-01770 | MLJ | SGS | demob | Closeout | SITE |  |  |  | Demobilize from SGS Phase 5 | 5 | 5 | 2023-10-27 08:00 | 2023-11-02 17:00 | -110 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.7 | SGS-01850 | CLOSEOUT | SGS | INSPECTION | Closeout | SITE |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-10-10 08:00 | 2023-10-17 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.7 | SGS-01855 | PUNCH LIST | SGS |  | Closeout | SITE |  |  |  | Perform Punch List | 10 | 10 | 2023-10-18 08:00 | 2023-10-31 17:00 | -108 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01030 | [8 empty] | Form Plumbing Shafts & Ftgs Below Water Table --> SG7 | 10 | 0 | 2021-09-10 08:00 | 2021-09-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01035 | [8 empty] | Rebar Plumbing Shafts & Ftgs Below Water Table --> SG7 | 5 | 0 | 2021-09-10 08:00 | 2021-09-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01040 | MLJ | SG7 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Pour Plumbing Shafts & Ftgs Below Water Table --> SG7 | 2 | 0 | 2021-09-15 08:00 | 2021-09-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01045 | [8 empty] | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> SG7 | 5 | 0 | 2021-10-11 | 2021-10-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01025 | [8 empty] | Waterproof/Insulation Plumbing Shaft ----> SG7 | 5 | 0 | 2021-10-14 | 2021-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01005 | [8 empty] | Excavate/SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> SG7 | 10 | 0 | 2021-07-30 08:00 | 2021-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01020 | [8 empty] | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> SG7 | 3 | 0 | 2021-09-27 | 2021-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01055 |  |  | SG7 |  |  |  | 31-1400 | 31-1400-SG7 | Backfill Plumbing Shaft & Ftgs/Piers --> SG7 | 5 | 0 | 2021-10-15 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01065 | [8 empty] | Excavate For Remaining Ftgs/Pier/Grade Beams --> SG7 | 10 | 0 | 2021-08-16 08:00 | 2021-09-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01070 |  | SG7 | FORMWORK |  |  | FORMWORK NB | 03-1000 | 03-1000-SG7 | Form Remaining Ftgs/Piers/Grade Beams --> SG7 | 10 | 0 | 2022-01-05 | 2022-05-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01075 | [8 empty] | Rebar Remaining Ftgs/Piers/Grade Beams --> SG7 | 10 | 0 | 2022-01-10 | 2022-05-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01080 | [8 empty] | Pour Remaining Ftgs/Piers/Grade Beams --> SG7 | 5 | 0 | 2022-01-11 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01085 | [8 empty] | Strip Forms Remaining Ftgs/Piers/Grade Beams --> SG7 | 5 | 0 | 2022-01-12 | 2022-05-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01090 | [8 empty] | Install Remaining Steam Into SG7 (5' from the building) | 5 | 0 | 2022-05-25 | 2022-06-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01095 | [8 empty] | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> SG7 | 5 | 0 | 2022-01-14 | 2022-06-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01105 | WEIR | SG7 | STRUCTURAL STEEL | [5 empty] | Install Structural Steel Framing - 1st Floor --> SG7 | 10 | 0 | 2022-07-14 | 2022-08-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01110 |  | SG7 | [6 empty] | Install Metal Deck --> SG7 | 2 | 0 | 2022-08-11 | 2022-08-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01115 | MLJ | SG7 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-SG7 | Form Pour Strip Concrete Stair South Side ---> SG7 | 5 | 0 | 2022-10-25 | 2022-10-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01120 |  | SG7 | [6 empty] | Install Metal Stairs --> SG7 | 2 | 0 | 2022-08-15 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01125 |  | SG7 |  |  |  |  | 07-1100 | 07-1100-SG7 | Place Insulation Below First Floor --> SG7 | 5 | 0 | 2022-06-14 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01130 | [8 empty] | Place WWF First Floor Slab --> SG7 | 2 | 0 | 2022-06-21 | 2022-06-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01135 | MLJ | SG7 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Pour First Floor Slab --> SG7 | 1 | 0 | 2022-06-24 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01150 | [8 empty] | Form First Floor Concrete Walls First Face And Col Encasements--> SG7 | 3 | 0 | 2022-05-25 | 2022-05-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01155 | [8 empty] | Rebar First Floor Concrete Walls --> SG7 | 3 | 0 | 2022-05-29 | 2022-05-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01160 | MLJ | SG7 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-SG7 | Form First Floor Concrete Walls 2Nd Face --> SG7 | 5 | 0 | 2022-09-07 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01165 | [8 empty] | Form, Rebar & Pour Concrete Pads 1st Floor --> SG7 - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01170 |  | SG7 | [6 empty] | Place WWF 2nd Floor Slab --> SG7 | 2 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01175 | MLJ | SG7 | Concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> SG7 | 2 | 0 | 2022-09-14 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01180 | MLJ | SG7 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-SG7 | Strip Forms First Floor Walls & Col Encasements And 1st Floor Pads --> SG7 | 3 | 0 | 2022-09-16 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01185 | MLJ | SG7 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-SG7 | Form Concrete Pads 2nd Floor -->SG7 | 2 | 0 | 2022-09-07 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01205 |  | SG7 | [6 empty] | Place WWF Roof Slab --> SG7 | 2 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01210 | MLJ | SG7 | Concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Pour Roof Slab and 2nd Floor Conc Pads -->SG7 | 1 | 0 | 2022-09-14 | 2022-09-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01215 | MLJ | SG7 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-SG7 | Strip Forms Concrete Pads 2nd Floor -->SG7 | 2 | 0 | 2022-09-16 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01225 | SIG | SG7 | [6 empty] | Install Spray-On Fireproofing on St Stl --> SG7 | 5 | 0 | 2022-09-20 | 2022-09-23 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01230 | FAXA | SG7 | CMU | Structure | NEW BUILDINGS |  |  |  | Place CMU 1st, 2nd Floors and Roof --> SG7 | 20 | 0 | 2022-09-26 08:00 | 2023-01-31 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01240 | CCC | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Stud Framing 1st, 2nd Floors and Roof --> SG7 | 5 | 0 | 2023-01-16 | 2023-02-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01245 | CCC | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Doors --> SG7 | 3 | 3 | 2023-04-10 08:00 | 2023-04-12 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01250 | JMC | SG7 | CAST STONE | Structure | NEW BUILDINGS |  |  |  | Install Cast Stone Panels --> SG7 | 1 | 1 | 2023-04-13 08:00 | 2023-04-13 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01255 | NAVILLUS | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulated Metal Panels/Louvers --> SG7 | 10 | 10 | 2023-04-14 08:00 | 2023-04-27 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01260 | MLJ | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install MEP Roof Penetrations & Drains - SG7 | 1 | 0 | 2023-02-23 | 2023-02-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01265 | TRIANGLE | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Roofing --> SG7 | 15 | 15 | 2023-04-28 08:00 | 2023-05-18 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01270 | E&Y | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Dunnage Gratings --> SG7 | 2 | 0 | 2023-01-30 | 2023-02-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01275 | FAXA | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Brick Façade & Stone --> SG7 | 20 | 0 | 2023-02-01 | 2023-02-20 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01285 | MLJ | SG7 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD VENTS |  |  | Install Flood Vents And Small Louvers --> SG7 | 3 | 3 | 2023-04-28 08:00 | 2023-05-02 17:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01290 | E&Y | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Stair And Roof Platform Railings --> SG7 | 5 | 0 | 2023-02-16 | 2023-02-21 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01295 | E&Y | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Ladders --> SG7 | 3 | 0 | 2023-02-16 | 2023-02-21 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01305 | CCC | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Sheetrock and Stucco --> SG7 | 10 | 10 | 2023-06-05 13:00 | 2023-06-19 12:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01310 | FAXA | SG7 | FLOORING | Interior | NEW BUILDINGS | CERAMIC |  |  | Install Ceramic Tile --> SG7 | 2 | 0 | 2023-02-20 | 2023-02-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01315 | TRIANGLE | SG7 | CEILING | Interior | NEW BUILDINGS |  |  |  | Install Acoustical Ceiling --> SG7 | 2 | 2 | 2023-06-19 13:00 | 2023-06-21 12:00 | -42 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01320 |  | SG7 | WATERPROOFING | [5 empty] | Place Crystaline Waterproofing In Plumbing Shaft --> SG7 | 3 | 0 | 2022-11-17 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01325 | GG PAINT | SG7 | PAINT | Interior | NEW BUILDINGS |  |  |  | Paint All Areas --> SG7 | 15 | 15 | 2023-06-22 08:00 | 2023-07-13 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01330 | MLJ | SG7 | SIGNS | Interior | NEW BUILDINGS |  |  |  | Install Signs --> SG7 | 2 | 2 | 2023-07-14 08:00 | 2023-07-17 17:00 | -49 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01235 | DSTAR | SG7 | WATERPROOFING | Structure | NEW BUILDINGS |  |  |  | Install Waterproofing to Parapet --> SG7 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01280 | CCC | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Stucco Soffit --> SG7 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 28 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01317 | NAVILLUS | SG7 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulated Metal Panels left out for Access --> SG7 | 5 | 5 | 2023-06-15 08:00 | 2023-06-21 17:00 | -49 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01092 | [8 empty] | Install Remaining HW/CW Into SG7 (5' from the building) | 5 | 0 | 2022-04-04 | 2022-04-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01094 | [8 empty] | Install Remaining Electrical POE Into SG7 | 5 | 0 | 2022-06-09 | 2022-06-24 10:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-03005 | WELKIN | SG7 | [6 empty] | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 2023-01-13 13:00 | 2023-01-24 12:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-03010 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Condensate Pump - Foundation Level | 10 | 10 | 2023-03-03 13:00 | 2023-03-17 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03105 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 2023-02-06 | 2023-02-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03110 | [8 empty] | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03125 | VITAL | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 10 | 2023-03-17 13:00 | 2023-03-31 12:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03130 |  | SG7 | [6 empty] | Install FOT Controls - 1st Floor | 20 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03135 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-03-24 13:00 | 2023-03-31 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03140 | VITAL | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Plumbing Equipment - 1st Floor | 15 | 0 | 2023-02-13 | 2023-02-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03145 | [8 empty] | Mechanical Equipment Start-up & Balance - 1st Floor - N/A | 5 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03150 | MEP | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 10 | 10 | 2023-03-22 13:00 | 2023-04-05 12:00 | -32 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03107 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 13 | 2023-01-16 08:00 | 2023-03-15 15:00 | -91 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-03142 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Mechanical Equipment - 1st Floor | 5 | 5 | 2023-03-17 13:00 | 2023-03-24 12:00 | -76 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03225 | VITAL | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 10 | 2023-02-01 13:00 | 2023-04-25 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03235 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 2nd Floor | 5 | 5 | 2023-04-26 08:00 | 2023-05-02 17:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03240 | [8 empty] | Install Plumbing Equipment - 2nd Floor | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03245 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-05-03 08:00 | 2023-05-16 17:00 | -81 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03250 | MEP | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-05-17 08:00 | 2023-06-14 17:00 | -81 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03207 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 8 | 2023-02-01 13:00 | 2023-04-11 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.2 | SG7-03242 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Install Mechanical Equipment - 2nd Floor | 10 | 10 | 2023-04-12 08:00 | 2023-04-25 17:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-03405 | [8 empty] | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-03410 | [8 empty] | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.3 | SG7-03415 | [8 empty] | Install Insulation - Roof - N/A | 15 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-03505 | CLOSEOUT | SG7 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG7 | 4 | 4 | 2023-06-15 08:00 | 2023-06-20 17:00 | -81 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-03510 | MLJ | SG7 | STARTUP | Interior | NEW BUILDINGS |  |  |  | Perform Start-Up Testing - SG7 | 10 | 10 | 2023-08-22 08:00 | 2023-09-05 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-03520 | MEP | SG7 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG7 | 5 | 5 | 2023-09-06 08:00 | 2023-09-12 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-03530 | MEP | SG7 | CLOSEOUT | Interior | NEW BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG7 | 4 | 4 | 2023-09-14 08:00 | 2023-09-19 17:00 | -84 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-03525 | CLOSEOUT | SG7 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG7 | 1 | 1 | 2023-09-13 08:00 | 2023-09-13 17:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.1 | SG1-01005 | ATCO | SG1 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - SG1 | 3 | 3 | 2023-09-21 10:00 | 2023-09-26 10:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.1 | SG1-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> SG1 | 3 | 0 | 2021-07-12 08:00 | 2021-07-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.1 | SG1-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG1 - N/A | 3 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.1 | SG1-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> SG1 | 3 | 0 | 2021-07-12 08:00 | 2021-07-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.1 | SG1-01025 | ATCO | SG1 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> SG1 | 5 | 0 | 2022-09-26 | 2022-09-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.1 | SG1-01030 | ATCO | SG1 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> SG1 | 5 | 0 | 2022-09-27 | 2022-09-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01105 | MLJ | SG1 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-SG1 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> SG1 | 10 | 0 | 2021-04-25 | 2022-09-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01110 | MLJ | SG1 | DEMO |  |  | DEMO DOORS WINDOWS |  |  | Selective Demo (Doors, windows) - 1st Floor --> SG1 | 5 | 0 | 2022-10-03 | 2022-10-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01115 | MLJ | SG1 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> SG1 | 10 | 0 | 2022-08-26 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01205 | MLJ | SG1 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG1 | 5 | 0 | 2022-09-02 | 2022-10-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01210 | MLJ | SG1 | DEMO |  |  | DEMO SLAB OPEN FOR MECH |  |  | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG1 | 5 | 0 | 2022-05-09 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG1 - N/A | 5 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01310 | [8 empty] | Make openings in floor for conduit penetrations - 1st floor apartments --> SG1 - N/A | 5 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01315 | [8 empty] | Install beams below floor - 1st floor apartments --> SG1 - N/A | 5 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01320 |  | SG1 | FRP |  |  |  | 03-6000 | 03-6000-SG1 | Install FRP around floor openings - 1st floor apartments --> SG1 - N/A | 5 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01325 | [8 empty] | Frame walls / install door for electrical room - 1st floor --> SG1 - N/A | 3 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01330 | [8 empty] | Install drywall / tape / spackle - electrical room - 1st floor --> SG1 - N/A | 5 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01335 | [8 empty] | Paint walls and seal floor electrical room - 1st Floor --> SG1 - N/A | 10 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.4 | SG1-01340 | [8 empty] | Install VCT @ electrical room - 1st Floor --> SG1 - N/A | 2 | 0 | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01405 | MLJ | SG1 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG1 | Excavate at Curtain Wall for flood protection (East Side) --> SG1 | 8 | 0 | 2022-07-21 08:00 | 2022-08-04 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01410 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 10 | 0 | 2022-09-26 | 2022-10-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01415 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 5 | 0 | 2022-10-10 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01420 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 0 | 2022-10-18 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01425 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 5 | 0 | 2022-10-19 | 2022-11-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01430 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 8 | 0 | 2022-11-14 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01435 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 6 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01440 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 0 | 2022-11-18 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01445 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 0 | 2022-11-21 | 2022-11-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01450 | FAXA | SG1 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01455 | MLJ | SG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill at Curtain Wall for flood protection (East Side) --> SG1 | 5 | 5 | 2023-03-03 08:00 | 2023-03-09 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01460 | MLJ | SG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form for slab at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 2023-03-10 08:00 | 2023-03-15 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01465 | TONAGE | SG1 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG1 | 6 | 6 | 2023-03-16 08:00 | 2023-03-23 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01470 | MLJ | SG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour slab at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 2023-03-24 08:00 | 2023-03-29 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01475 | MLJ | SG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG1 | 2 | 2 | 2023-03-30 08:00 | 2023-03-31 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01480 | MLJ | SG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | -71 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01505 | MLJ | SG1 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG1 | Excavate at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 2022-10-25 08:00 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01510 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 9 | 0 | 2022-11-14 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01515 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 4 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01520 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 0 | 2022-11-18 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01525 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 4 | 0 | 2022-11-19 08:00 | 2022-11-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01530 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 2022-11-14 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01535 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 5 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01540 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 0 | 2022-11-18 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01545 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 0 | 2022-11-21 | 2022-11-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01550 | FAXA | SG1 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01555 | MLJ | SG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill at Curtain Wall for flood protection (South Side) --> SG1 | 4 | 4 | 2023-03-02 08:00 | 2023-03-07 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01605 | MLJ | SG1 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG1 | Excavate at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 2022-08-25 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01610 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 9 | 0 | 2022-08-28 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01615 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 4 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01620 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01625 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 4 | 0 | 2022-09-08 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01630 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01635 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 5 | 0 | 2022-09-14 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01640 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 2022-09-16 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01645 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 2022-09-26 08:00 | 2022-09-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01650 | FAXA | SG1 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 2022-09-29 08:00 | 2022-10-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01655 | MLJ | SG1 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill at Curtain Wall for flood protection (North Side) --> SG1 | 4 | 0 | 2022-10-04 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01705 | MLJ | SG1 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG1 | Excavate at Curtain Wall for flood protection (West Side) --> SG1 | 8 | 0 | 2022-09-26 08:00 | 2022-10-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01710 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 10 | 0 | 2022-10-06 08:00 | 2022-10-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01715 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 5 | 0 | 2022-10-19 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01720 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 0 | 2022-10-24 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01725 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 5 | 0 | 2022-10-25 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01730 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 8 | 0 | 2022-11-14 | 2022-11-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01735 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 6 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01740 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 0 | 2022-11-18 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01745 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 0 | 2022-11-21 | 2022-11-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01750 | FAXA | SG1 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01755 | MLJ | SG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill at Curtain Wall for flood protection (West Side) --> SG1 | 5 | 5 | 2023-03-03 08:00 | 2023-03-09 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01760 | MLJ | SG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form for slab at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 2023-03-10 08:00 | 2023-03-15 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01765 | TONAGE | SG1 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG1 | 6 | 6 | 2023-03-16 08:00 | 2023-03-23 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01770 | MLJ | SG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour slab at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 2023-03-24 08:00 | 2023-03-29 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01775 | MLJ | SG1 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG1 | 2 | 2 | 2023-03-30 08:00 | 2023-03-31 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01780 | MLJ | SG1 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | -71 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01805 | MLJ | SG1 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG1 | Excavate for concrete shelf around bldg perimeter --> SG1 | 10 | 0 | 2022-08-25 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01810 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Place rebar for concrete shelf around bldg perimeter --> SG1 | 5 | 0 | 2022-08-28 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01815 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour concrete shelf around bldg perimeter --> SG1 | 5 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01820 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Place infill concrete in area ways around bldg perimeter --> SG1 | 5 | 0 | 2022-09-26 08:00 | 2022-09-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01825 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Place waterproofing on concrete shelf around bldg perimeter --> SG1 | 10 | 0 | 2022-09-30 | 2022-10-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01830 | FAXA | SG1 | CMU | [5 empty] | Place CMU around bldg perimeter --SG1 | 15 | 0 | 2022-10-05 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01835 |  | SG1 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> SG1 | 10 | 0 | 2022-10-24 | 2022-11-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01840 | MLJ | SG1 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> SG1 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 42 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01845 | FAXA | SG1 | [6 empty] | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG1 | 20 | 0 | 2022-10-26 | 2022-12-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01850 | MLJ | SG1 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG1 | Backfill around bdg perimeter --> SG1 | 5 | 0 | 2022-12-16 | 2022-12-20 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01855 | CCC | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> SG1 | 4 | 4 | 2023-02-27 08:00 | 2023-03-02 17:00 | 48 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01860 | MLJ | SG1 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> SG1 | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | 42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01865 | MLJ | SG1 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> SG1 | 3 | 3 | 2023-03-20 08:00 | 2023-03-22 17:00 | 42 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.5 | SG1-01350 | MLJ | SG1 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-SG1 | Drill dowels and place rebar for boiler room concrete walls --> SG1 | 5 | 0 | 2022-12-27 | 2023-01-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.5 | SG1-01355 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Form boiler room concrete walls --> SG1 | 5 | 0 | 2023-01-04 | 2023-01-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.5 | SG1-01360 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Pour Concrete boiler room walls --> SG1 | 2 | 0 | 2023-01-11 | 2023-01-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.5 | SG1-01365 | MLJ | SG1 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG1 | Strip Forms boiler room concrete walls --> SG1 | 3 | 0 | 2023-01-13 | 2023-01-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.5 | SG1-01370 |  | SG1 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> SG1 | 10 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.6 | SG1-01385 | [8 empty] | Refurbish Elevator 1 --> SG1 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.6 | SG1-01390 | [8 empty] | Refurbish Elevator 2 --> SG1 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.6 | SG1-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.7 | SG1-09005 | CLOSEOUT | SG1 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-09-26 10:00 | 2023-10-03 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.7 | SG1-09010 | PUNCH LIST | SG1 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-10-03 10:00 | 2023-10-18 10:00 | -98 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.2 | SG1-01220 | MLJ | SG1 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-SG1 | Selective Demo (Pumps etc..) - Cellar --> SG1 | 5 | 0 | 2022-12-27 | 2023-01-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.1 | SG3-01005 | ATCO | SG3 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - SG3 | 3 | 3 | 2023-10-12 08:00 | 2023-10-17 17:00 | -128 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.1 | SG3-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> SG3 | 3 | 0 | 2021-11-08 08:00 | 2021-11-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.1 | SG3-01015 | ATCO | SG3 | ABESTOS | [5 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG3 | 3 | 0 | 2022-06-27 08:00 | 2022-06-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.1 | SG3-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> SG3 | 3 | 0 | 2021-11-08 08:00 | 2021-11-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.1 | SG3-01025 | ATCO | SG3 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> SG3 | 5 | 0 | 2022-10-01 | 2022-10-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.1 | SG3-01030 | ATCO | SG3 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> SG3 | 5 | 0 | 2022-10-02 | 2022-10-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01105 | MLJ | SG3 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-SG3 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> SG3 | 10 | 0 | 2021-05-06 | 2022-08-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01110 | MLJ | SG3 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO DOORS WINDOWS | 02-6015 | 02-6015-SG3 | Selective Demo (Doors, windows) - 1st Floor --> SG3 | 5 | 0 | 2023-02-17 | 2023-02-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01115 | MLJ | SG3 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> SG3 | 10 | 0 | 2022-09-26 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01205 | MLJ | SG3 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG3 | 5 | 0 | 2022-10-17 08:00 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01210 | MLJ | SG3 | DEMO |  |  | DEMO SLAB OPEN FOR MECH | 02-3000 | 02-3000-SG3 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG3 | 5 | 0 | 2022-10-18 08:00 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01215 | MLJ | SG3 | DEMO |  |  | DEMO 2ND FLOOR | 02-6060 | 02-6060-SG3 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG3 | 5 | 0 | 2022-01-27 08:00 | 2022-02-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01310 | MLJ | SG3 | CORE DRILL | [5 empty] | Make openings in floor for conduit penetrations - 2nd floor apartments --> SG3 | 5 | 0 | 2022-10-17 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01315 | WEIR | SG3 | [6 empty] | Install beams below floor - 2nd floor apartments --> SG3 | 5 | 0 | 2022-09-30 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01320 | MLJ | SG3 |  |  |  | FRP | 03-6000 | 03-6000-SG3 | Install FRP around floor openings - 2nd floor apartments --> SG3 | 5 | 0 | 2022-08-15 08:00 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01325 | CCC | SG3 | [6 empty] | Frame walls / install door for electrical room - 2nd floor --> SG3 | 3 | 0 | 2022-05-04 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01330 | CCC | SG3 | [6 empty] | Install drywall / tape / spackle - electrical room - 2nd floor --> SG3 | 5 | 0 | 2022-06-21 | 2022-12-05 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01335 | CCC | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 2nd Floor --> SG3 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 23 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.4 | SG3-01340 | FLOORING | SG3 | FLOORING | Interior | EXISTING BUILDINGS | VCT |  |  | Install VCT @ electrical room - 2nd Floor --> SG3 | 2 | 2 | 2023-03-13 08:00 | 2023-03-14 17:00 | 23 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01405 | MLJ | SG3 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG3 | Excavate at Curtain Wall for flood protection (East Side) --> SG3 | 8 | 0 | 2022-08-25 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01410 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 10 | 0 | 2022-08-28 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01415 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 5 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01420 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01425 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01430 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 8 | 8 | 2023-03-06 08:00 | 2023-03-15 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01435 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 6 | 6 | 2023-03-16 08:00 | 2023-03-23 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01440 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 2023-03-24 08:00 | 2023-03-29 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01445 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 2023-03-30 08:00 | 2023-04-04 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01450 | FAXA | SG3 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01455 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill at Curtain Wall for flood protection (East Side) --> SG3 | 5 | 5 | 2023-04-12 08:00 | 2023-04-18 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01460 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form for slab at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 2023-04-19 08:00 | 2023-04-24 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01465 | TONAGE | SG3 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG3 | 6 | 6 | 2023-04-25 08:00 | 2023-05-02 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01470 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour slab at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 2023-05-03 08:00 | 2023-05-08 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01475 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG3 | 2 | 2 | 2023-05-09 08:00 | 2023-05-10 17:00 | -96 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01480 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 2023-05-16 08:00 | 2023-05-19 17:00 | -99 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01505 | MLJ | SG3 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG3 | Excavate at Curtain Wall for flood protection (South Side) --> SG3 | 8 | 0 | 2023-01-09 08:00 | 2023-01-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01510 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 10 | 0 | 2023-01-16 08:00 | 2023-01-20 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01515 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 5 | 0 | 2023-01-23 08:00 | 2023-02-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01520 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 0 | 2023-02-20 08:00 | 2023-02-20 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01525 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01530 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 8 | 8 | 2023-03-06 08:00 | 2023-03-15 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01535 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 6 | 6 | 2023-03-16 08:00 | 2023-03-23 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01540 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 2023-03-24 08:00 | 2023-03-29 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01545 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 2023-03-30 08:00 | 2023-04-04 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01550 | FAXA | SG3 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01555 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill at Curtain Wall for flood protection (South Side) --> SG3 | 5 | 5 | 2023-04-12 08:00 | 2023-04-18 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01560 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form for slab at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 2023-04-19 08:00 | 2023-04-24 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01565 | TONAGE | SG3 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> SG3 | 6 | 6 | 2023-04-25 08:00 | 2023-05-02 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01570 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour slab at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 2023-05-03 08:00 | 2023-05-08 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01575 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> SG3 | 2 | 2 | 2023-05-09 08:00 | 2023-05-10 17:00 | -96 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01580 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 2023-05-16 08:00 | 2023-05-19 17:00 | -99 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01605 | MLJ | SG3 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG3 | Excavate at Curtain Wall for flood protection (North Side) --> SG3 | 8 | 0 | 2022-09-26 08:00 | 2022-10-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01610 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 10 | 0 | 2022-10-06 08:00 | 2022-10-20 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01615 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 5 | 0 | 2022-10-21 08:00 | 2023-01-30 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01620 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 0 | 2023-01-31 08:00 | 2023-01-31 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01625 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 5 | 0 | 2023-02-01 | 2023-02-02 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01630 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 8 | 0 | 2023-02-02 | 2023-02-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01635 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 6 | 0 | 2023-02-08 | 2023-02-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01640 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 0 | 2023-02-13 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01645 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 0 | 2023-02-14 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01650 | FAXA | SG3 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 4 | 2023-02-16 | 2023-03-02 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01655 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill at Curtain Wall for flood protection (North Side) --> SG3 | 5 | 5 | 2023-03-03 08:00 | 2023-03-09 17:00 | -47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01705 | MLJ | SG3 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG3 | Excavate at Curtain Wall for flood protection (West Side) --> SG3 | 8 | 0 | 2023-01-10 08:00 | 2023-01-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01710 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 10 | 0 | 2023-01-11 08:00 | 2023-01-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01715 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 5 | 0 | 2023-01-16 08:00 | 2023-01-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01720 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 0 | 2023-01-19 08:00 | 2023-01-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01725 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 5 | 0 | 2023-01-23 08:00 | 2023-01-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01730 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 8 | 0 | 2023-01-30 | 2023-02-02 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01735 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 6 | 0 | 2023-02-03 | 2023-02-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01740 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 0 | 2023-02-08 | 2023-02-08 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01745 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 0 | 2023-02-09 | 2023-02-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01750 | FAXA | SG3 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 2023-02-14 | 2023-03-23 17:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01755 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill at Curtain Wall for flood protection (West Side) --> SG3 | 5 | 5 | 2023-03-24 08:00 | 2023-03-30 17:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01760 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form for slab at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 2023-03-31 08:00 | 2023-04-05 17:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01765 | TONAGE | SG3 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG3 | 6 | 6 | 2023-04-06 08:00 | 2023-04-13 17:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01770 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour slab at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 2023-04-14 08:00 | 2023-04-19 17:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01775 | MLJ | SG3 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG3 | 2 | 2 | 2023-04-20 08:00 | 2023-04-21 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01780 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 2023-04-27 08:00 | 2023-05-02 17:00 | -85 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01805 | MLJ | SG3 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG3 | Excavate for concrete shelf around bldg perimeter --> SG3 | 10 | 0 | 2022-08-11 08:00 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01810 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Place rebar for concrete shelf around bldg perimeter --> SG3 | 5 | 0 | 2022-09-09 08:00 | 2022-09-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01815 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour concrete shelf around bldg perimeter --> SG3 | 5 | 0 | 2022-09-26 08:00 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01820 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Place infill concrete in area ways around bldg perimeter --> SG3 | 5 | 0 | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01825 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Place waterproofing on concrete shelf around bldg perimeter --> SG3 | 10 | 0 | 2022-10-10 08:00 | 2022-10-18 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01830 | FAXA | SG3 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU around bldg perimeter --SG3 | 15 | 10 | 2022-10-19 | 2023-03-31 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01835 | DSTAR | SG3 | WATERPROOFING | Exterior | EXISTING BUILDINGS |  |  |  | Place waterproofing on CMU around bldg perimeter --> SG3 | 10 | 10 | 2023-04-03 08:00 | 2023-04-14 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01840 | MLJ | SG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> SG3 | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01845 | FAXA | SG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG3 | 20 | 20 | 2023-05-01 08:00 | 2023-05-26 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01850 | MLJ | SG3 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG3 | Backfill around bdg perimeter --> SG3 | 5 | 5 | 2023-05-30 08:00 | 2023-06-05 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01855 | CCC | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> SG3 | 4 | 4 | 2023-06-06 08:00 | 2023-06-09 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01860 | MLJ | SG3 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> SG3 | 5 | 5 | 2023-06-12 08:00 | 2023-06-16 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01865 | MLJ | SG3 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> SG3 | 3 | 3 | 2023-06-19 08:00 | 2023-06-21 17:00 | -22 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.5 | SG3-01350 | MLJ | SG3 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-SG3 | Drill dowels and place rebar for boiler room concrete walls --> SG3 | 5 | 0 | 2022-11-25 08:00 | 2022-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.5 | SG3-01355 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Form boiler room concrete walls --> SG3 | 5 | 0 | 2022-11-25 08:00 | 2022-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.5 | SG3-01360 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Pour Concrete boiler room walls --> SG3 | 2 | 0 | 2022-11-25 08:00 | 2022-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.5 | SG3-01365 | MLJ | SG3 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG3 | Strip Forms boiler room concrete walls --> SG3 | 3 | 0 | 2022-11-25 08:00 | 2022-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.5 | SG3-01370 |  | SG3 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> SG3 | 10 | 0 | 2022-07-01 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.6 | SG3-01385 | [8 empty] | Refurbish Elevator 1 --> SG3 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.6 | SG3-01390 | [8 empty] | Refurbish Elevator 2 --> SG3 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.6 | SG3-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.7 | SG3-09005 | CLOSEOUT | SG3 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-10-18 08:00 | 2023-10-24 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.7 | SG3-09010 | PUNCH LIST | SG3 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-10-25 08:00 | 2023-11-08 17:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.2 | SG3-01220 | MLJ | SG3 | DEMO |  |  | DEMO PUMPS | 02-6010 | 02-6010-SG3 | Selective Demo (Pumps etc..) - Cellar --> SG3 | 5 | 0 | 2023-01-04 | 2023-01-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.1 | SG2-01005 | ATCO | SG2 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - SG2 | 3 | 3 | 2023-09-20 08:00 | 2023-09-22 17:00 | -112 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.1 | SG2-01010 | [8 empty] | Asbestos Abatement - wire insulation - cellar --> SG2 | 3 | 0 | 2022-02-28 08:00 | 2022-03-04 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.1 | SG2-01015 | [8 empty] | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG2 - N/A | 3 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.1 | SG2-01020 | [8 empty] | Asbestos Abatement - pipe insulation - cellar --> SG2 | 3 | 0 | 2022-02-28 08:00 | 2022-03-04 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.1 | SG2-01025 | ATCO | SG2 | ABESTOS | [5 empty] | Asbestos Abatement - Window Sills - 1st Floor --> SG2 | 5 | 0 | 2022-04-27 08:00 | 2022-04-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.1 | SG2-01030 | ATCO | SG2 | ABESTOS | [5 empty] | Asbestos Abatement - caulk @ windows and areaway vents --> SG2 | 5 | 0 | 2022-04-27 08:00 | 2022-04-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01105 | MLJ | SG2 | DEMO |  |  | DEMO CELLAR WALLS | 02-6005 | 02-6005-SG2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> SG2 | 10 | 0 | 2021-05-18 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01110 | MLJ | SG2 | DEMO |  |  | DEMO DOORS WINDOWS |  |  | Selective Demo (Doors, windows) - 1st Floor --> SG2 | 5 | 0 | 2022-09-26 08:00 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01115 | MLJ | SG2 | DEMO |  |  | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> SG2 | 10 | 0 | 2022-08-01 | 2022-08-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01205 | MLJ | SG2 | DEMO |  |  | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG2 | 5 | 0 | 2022-09-26 08:00 | 2022-09-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01210 | MLJ | SG2 | DEMO |  |  | DEMO SLAB OPEN FOR MECH | 02-3000 | 02-3000-SG2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG2 | 5 | 0 | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG2 - N/A | 5 | 0 | 2022-01-27 | 2022-05-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01310 | [8 empty] | Make openings in floor for conduit penetrations - 1st floor apartments --> SG2 - N/A | 5 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01315 | [8 empty] | Install beams below floor - 1st floor apartments --> SG2 - N/A | 5 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01320 |  | SG2 | FRP |  |  |  | 03-6000 | 03-6000-SG2 | Install FRP around floor openings - 1st floor apartments --> SG2 - N/A | 5 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01325 | [8 empty] | Frame walls / install door for electrical room - 1st floor --> SG2 - N/A | 3 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01330 | [8 empty] | Install drywall / tape / spackle - electrical room - 1st floor --> SG2 - N/A | 5 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01335 | [8 empty] | Paint walls and seal floor electrical room - 1st Floor --> SG2 - N/A | 10 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.4 | SG2-01340 | [8 empty] | Install VCT @ electrical room - 1st Floor --> SG2 - N/A | 2 | 0 | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01405 | MLJ | SG2 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG2 | Excavate at Curtain Wall for flood protection (East Side) --> SG2 | 8 | 0 | 2022-08-05 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01410 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 10 | 0 | 2022-10-03 | 2022-10-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01415 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 5 | 0 | 2022-10-10 08:00 | 2022-10-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01420 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 0 | 2022-10-19 | 2022-10-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01425 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 5 | 0 | 2022-10-25 | 2022-10-31 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01430 | MLJ | SG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 8 | 8 | 2023-02-27 08:00 | 2023-03-08 17:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01435 | MLJ | SG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 6 | 6 | 2023-03-09 08:00 | 2023-03-16 17:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01440 | MLJ | SG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 2023-03-17 08:00 | 2023-03-22 17:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01445 | MLJ | SG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 2023-03-23 08:00 | 2023-03-28 17:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01450 | FAXA | SG2 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 2023-03-30 08:00 | 2023-04-04 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01455 | MLJ | SG2 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill at Curtain Wall for flood protection (East Side) --> SG2 | 5 | 5 | 2023-04-05 08:00 | 2023-04-11 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01460 | MLJ | SG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form for slab at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 2023-04-12 08:00 | 2023-04-17 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01465 | TONAGE | SG2 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG2 | 6 | 6 | 2023-04-18 08:00 | 2023-04-25 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01470 | MLJ | SG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour slab at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 2023-04-26 08:00 | 2023-05-01 17:00 | -93 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01475 | MLJ | SG2 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG2 | 2 | 2 | 2023-05-02 08:00 | 2023-05-03 17:00 | -90 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01480 | MLJ | SG2 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 2023-05-09 08:00 | 2023-05-12 17:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01505 | MLJ | SG2 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG2 | Excavate at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 2022-08-22 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01510 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 9 | 0 | 2022-08-25 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01515 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 4 | 0 | 2022-08-28 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01520 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01525 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 4 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01530 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 2022-09-08 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01535 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 5 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01540 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 0 | 2022-09-14 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01545 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 0 | 2022-09-16 | 2022-09-16 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01550 | FAXA | SG2 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01555 | MLJ | SG2 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill at Curtain Wall for flood protection (South Side) --> SG2 | 4 | 4 | 2023-03-02 08:00 | 2023-03-07 17:00 | -45 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01605 | MLJ | SG2 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG2 | Excavate at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 2022-08-22 | 2022-08-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01610 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 9 | 0 | 2022-08-25 | 2022-08-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01615 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 4 | 0 | 2022-08-28 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01620 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01625 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 4 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01630 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 2022-09-08 | 2022-09-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01635 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 5 | 0 | 2022-09-12 | 2022-09-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01640 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 2022-09-14 | 2022-09-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01645 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 2022-09-16 | 2022-09-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01650 | FAXA | SG2 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 2022-09-26 08:00 | 2022-10-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01655 | MLJ | SG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill at Curtain Wall for flood protection (North Side) --> SG2 | 4 | 0 | 2022-10-04 | 2022-10-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01705 | MLJ | SG2 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG2 | Excavate at Curtain Wall for flood protection (West Side) --> SG2 | 8 | 0 | 2022-10-10 | 2022-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01710 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 10 | 0 | 2022-10-17 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01715 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 5 | 0 | 2022-10-24 | 2022-10-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01720 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-10-27 | 2022-10-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01725 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 5 | 0 | 2022-10-28 | 2022-10-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01730 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 8 | 0 | 2022-10-31 | 2022-11-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01735 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 6 | 0 | 2022-11-02 | 2022-11-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01740 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-11-04 | 2022-11-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01745 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-11-07 | 2022-11-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01750 | FAXA | SG2 | CMU | [5 empty] | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-11-09 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01755 | MLJ | SG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill at Curtain Wall for flood protection (West Side) --> SG2 | 5 | 0 | 2022-11-09 | 2022-11-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01760 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form for slab at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-10-31 | 2022-11-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01765 |  | SG2 | REBAR | [5 empty] | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG2 | 6 | 0 | 2022-11-02 | 2022-11-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01770 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour slab at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-11-04 | 2022-11-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01775 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG2 | 2 | 0 | 2022-11-07 | 2022-11-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01780 | MLJ | SG2 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 2022-11-09 | 2022-11-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01805 | MLJ | SG2 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-SG2 | Excavate for concrete shelf around bldg perimeter --> SG2 | 10 | 0 | 2022-08-03 08:00 | 2022-08-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01810 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Place rebar for concrete shelf around bldg perimeter --> SG2 | 5 | 0 | 2022-05-18 08:00 | 2022-08-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01815 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour concrete shelf around bldg perimeter --> SG2 | 5 | 0 | 2022-08-24 08:00 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01820 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Place infill concrete in area ways around bldg perimeter --> SG2 | 5 | 0 | 2022-08-24 08:00 | 2022-08-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01825 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Place waterproofing on concrete shelf around bldg perimeter --> SG2 | 10 | 0 | 2022-09-26 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01830 | FAXA | SG2 | CMU | [5 empty] | Place CMU around bldg perimeter --SG2 | 15 | 0 | 2022-10-03 | 2022-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01835 |  | SG2 | WATERPROOFING | [5 empty] | Place waterproofing on CMU around bldg perimeter --> SG2 | 10 | 0 | 2022-10-25 | 2022-11-08 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01840 | MLJ | SG2 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place window frames around bldg perimeter --> SG2 | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -55 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01845 | FAXA | SG2 |  | Exterior | EXISTING BUILDINGS |  |  |  | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG2 | 20 | 2 | 2022-11-01 | 2023-03-14 17:00 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01850 | MLJ | SG2 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-SG2 | Backfill around bdg perimeter --> SG2 | 5 | 5 | 2023-03-15 08:00 | 2023-03-21 17:00 | -55 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01855 | CCC | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> SG2 | 4 | 4 | 2023-03-22 08:00 | 2023-03-27 17:00 | 31 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01860 | MLJ | SG2 | FLOOD PROTECTION | Exterior | EXISTING BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> SG2 | 5 | 5 | 2023-03-28 08:00 | 2023-04-03 17:00 | 31 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01865 | MLJ | SG2 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> SG2 | 3 | 3 | 2023-04-04 08:00 | 2023-04-06 17:00 | 31 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.5 | SG2-01350 | MLJ | SG2 |  |  |  | DRILL & DOWEL | 03-1400 | 03-1400-SG2 | Drill dowels and place rebar for boiler room concrete walls --> SG2 | 5 | 0 | 2023-01-04 | 2023-01-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.5 | SG2-01355 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Form boiler room concrete walls --> SG2 | 5 | 0 | 2023-01-11 | 2023-01-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.5 | SG2-01360 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Pour Concrete boiler room walls --> SG2 | 2 | 0 | 2023-01-19 | 2023-01-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.5 | SG2-01365 | MLJ | SG2 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-SG2 | Strip Forms boiler room concrete walls --> SG2 | 3 | 0 | 2023-01-23 | 2023-01-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.5 | SG2-01370 |  | SG2 | WATERPROOFING | [5 empty] | Place crystaline waterproofing on perimeter walls - cellar --> SG2 | 10 | 0 | 2022-07-01 08:00 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.6 | SG2-01385 | [8 empty] | Refurbish Elevator 1 --> SG2 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.6 | SG2-01390 | [8 empty] | Refurbish Elevator 2 --> SG2 (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.6 | SG2-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.7 | SG2-09005 | CLOSEOUT | SG2 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-09-25 08:00 | 2023-09-29 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.7 | SG2-09010 | PUNCH LIST | SG2 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-10-02 08:00 | 2023-10-13 17:00 | -97 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.2 | SG2-01220 | MLJ | SG2 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO PUMPS | 02-6010 | 02-6010-SG2 | Selective Demo (Pumps etc..) - Cellar --> SG2 | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -37 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2022-03-10 | 2022-04-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03010 | WELKIN | SG3 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-07-25 08:00 | 2022-08-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03020 |  | SG3 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-07-27 08:00 | 2023-01-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03025 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 5 | 2023-05-03 08:00 | 2023-05-09 17:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03030 |  | SG3 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-07-27 08:00 | 2022-10-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03035 | CLOSEOUT | SG3 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-05-10 08:00 | 2023-05-23 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03040 | MEP | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-05-24 08:00 | 2023-06-21 17:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03015 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Steam Traps - Cellar | 2 | 2 | 2023-03-27 08:00 | 2023-03-28 17:00 | -68 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03007 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 7 | 2022-09-26 08:00 | 2023-04-04 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-03032 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Mechanical Equipment - Cellar | 20 | 20 | 2023-04-05 08:00 | 2023-05-02 17:00 | -93 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03120 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 20 | 2023-05-03 08:00 | 2023-05-31 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03125 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-06-01 08:00 | 2023-06-07 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03130 | NAVILLUS | SG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 15 | 2023-04-12 08:00 | 2023-05-02 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03135 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-06-08 08:00 | 2023-06-21 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03140 | MEP | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-06-22 08:00 | 2023-07-20 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03115 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Steam Traps - 1st Floor | 1 | 0 | 2023-02-20 08:00 | 2023-02-21 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03110 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 2023-04-05 08:00 | 2023-04-11 17:00 | -108 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03112 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 0 | 2023-02-20 08:00 | 2023-02-21 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.2 | SG3-03107 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 2023-04-05 08:00 | 2023-04-18 17:00 | -112 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 2021-07-26 | 2021-07-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03220 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 2nd Floor | 20 | 20 | 2023-05-24 08:00 | 2023-06-21 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03230 | NAVILLUS | SG3 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 2023-04-19 08:00 | 2023-05-09 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03235 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 2023-06-22 08:00 | 2023-07-06 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03240 | MEP | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-07-07 08:00 | 2023-08-03 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03210 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 2023-05-10 08:00 | 2023-05-16 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.3 | SG3-03215 | WELKIN | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Install EF Units - 2nd Floor | 5 | 5 | 2023-05-17 08:00 | 2023-05-23 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-03305 | CLOSEOUT | SG3 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG3 | 4 | 4 | 2023-08-04 08:00 | 2023-08-09 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-03310 | MLJ | SG3 | STARTUP | Interior | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - SG3 | 10 | 10 | 2023-09-14 08:00 | 2023-09-27 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-03320 | PUNCH LIST | SG3 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG3 | 5 | 5 | 2023-09-28 08:00 | 2023-10-04 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-03330 | MEP | SG3 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG3 | 4 | 4 | 2023-10-06 08:00 | 2023-10-11 17:00 | -100 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-03325 | CLOSEOUT | SG3 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG3 | 1 | 1 | 2023-10-05 08:00 | 2023-10-05 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-03335 | MLJ | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - SG3 | 10 | 10 | 2023-09-28 08:00 | 2023-10-11 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-03305 | CLOSEOUT | SG1 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG1 | 4 | 4 | 2023-08-10 08:00 | 2023-08-15 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-03310 | MLJ | SG1 | STARTUP | Interior | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - SG1 | 10 | 10 | 2023-08-23 10:00 | 2023-09-07 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-03320 | PUNCH LIST | SG1 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG1 | 5 | 5 | 2023-09-07 10:00 | 2023-09-14 10:00 | -88 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-03330 | MEP | SG1 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG1 | 4 | 4 | 2023-10-09 08:00 | 2023-10-12 17:00 | -101 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-03325 | CLOSEOUT | SG1 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG1 | 1 | 1 | 2023-10-06 08:00 | 2023-10-06 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.3 | SG1-03335 | MLJ | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - SG1 | 10 | 10 | 2023-09-07 10:00 | 2023-09-21 10:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03120 | [8 empty] | Install HVAC Controls - 1st Floor | 20 | 0 | 2022-06-10 | 2022-06-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03125 | WELKIN | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-06-20 08:00 | 2023-06-26 17:00 | -111 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03130 | [8 empty] | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2022-06-20 | 2022-06-24 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03135 | WELKIN | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-06-27 08:00 | 2023-07-11 17:00 | -111 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03140 | MEP | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-07-12 08:00 | 2023-08-08 17:00 | -111 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03115 | [8 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-05-27 | 2022-06-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03110 | [8 empty] | Install Ductwork and Appurtenances - 1st Floor | 5 | 0 | 2022-05-25 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03112 | [8 empty] | Install HV & EF Units - 1st Floor | 5 | 0 | 2022-05-19 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.2 | SG1-03107 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-05-25 | 2022-06-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2022-03-10 | 2022-04-11 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03010 | WELKIN | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Condensate Pump - Cellar | 10 | 0 | 2022-12-12 08:00 | 2022-12-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03020 |  | SG1 | [6 empty] | Install Pump Controls - Cellar | 20 | 0 | 2022-10-25 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03025 | WELKIN | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -111 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03030 |  | SG1 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-10-25 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03035 | CLOSEOUT | SG1 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-06-20 08:00 | 2023-07-03 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03040 | MEP | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-07-05 08:00 | 2023-08-01 17:00 | -106 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03015 | WELKIN | SG1 | [6 empty] | Install Steam Traps - Cellar | 2 | 0 | 2022-08-22 08:00 | 2022-09-02 08:48 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-07-26 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2021-07-26 08:00 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03005 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2022-01-31 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03010 | WELKIN | SG2 | [6 empty] | Install Condensate Pump - Cellar | 10 | 0 | 2022-07-27 08:00 | 2022-08-05 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03020 | WELKIN | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Pump Controls - Cellar | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03025 | WELKIN | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03030 |  | SG2 | [6 empty] | Install Plumbing Equipment - Cellar | 15 | 0 | 2022-10-27 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03035 | CLOSEOUT | SG2 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-04-03 08:00 | 2023-04-14 17:00 | -47 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03040 | MEP | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-04-17 08:00 | 2023-05-12 17:00 | -47 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03015 | [8 empty] | Install Steam Traps - Cellar | 2 | 0 | 2021-09-07 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03007 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 2021-09-07 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-03032 | [8 empty] | Install Mechanical Equipment - Cellar | 20 | 0 | 2021-09-07 | 2021-12-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03105 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03120 | WELKIN | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 10 | 2022-08-08 08:00 | 2023-03-10 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03125 | WELKIN | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03130 | NAVILLUS | SG2 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 0 | 2023-02-10 | 2023-02-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03135 | WELKIN | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-03-20 08:00 | 2023-03-31 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03140 | MEP | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 15 | 15 | 2023-04-03 08:00 | 2023-04-21 17:00 | -32 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03115 | WELKIN | SG2 | [6 empty] | Install Steam Traps - 1st Floor | 1 | 0 | 2022-09-20 08:00 | 2022-09-23 08:24 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03110 | WELKIN | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 2022-08-25 08:00 | 2023-02-27 12:00 | -23 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03112 |  | SG2 | [6 empty] | Install HV & EF Units - 1st Floor | 5 | 0 | 2022-08-25 08:00 | 2022-09-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.2 | SG2-03107 | WELKIN | SG2 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 2022-07-25 08:00 | 2022-07-29 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-03305 | CLOSEOUT | SG2 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - SG2 | 4 | 4 | 2023-08-16 08:00 | 2023-08-21 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-03310 | CLOSEOUT | SG2 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - SG2 | 10 | 10 | 2023-08-22 08:00 | 2023-09-05 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-03320 | PUNCH LIST | SG2 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG2 | 5 | 5 | 2023-09-06 08:00 | 2023-09-12 17:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-03330 | MEP | SG2 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG2 | 4 | 4 | 2023-10-10 08:00 | 2023-10-13 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-03325 | CLOSEOUT | SG2 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG2 | 1 | 1 | 2023-10-09 08:00 | 2023-10-09 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.3 | SG2-03335 | MLJ | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Remove Redundant Services - SG2 | 10 | 10 | 2023-09-06 08:00 | 2023-09-19 17:00 | -112 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01005 | [8 empty] | Install Site Fencing - Site 8 | 10 | 0 | 2021-07-12 08:00 | 2021-10-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01015 | [6 empty] | 01-6300 |  | Install Overhead Protection - N/A | 10 | 0 | 2022-02-25 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01020 | [6 empty] | 31-1900 |  | Install Tree Protection | 10 | 0 | 2020-11-06 | 2020-11-11 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01025 | [8 empty] | Remove Trees | 2 | 0 | 2021-05-10 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01000 | [8 empty] | Remove Curbs And Existing Fencing | 10 | 0 | 2021-05-10 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01035 | [8 empty] | Install Erosion Control | 5 | 0 | 2022-03-01 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01010 | [8 empty] | Set Up Yard and Staging | 10 | 0 | 2021-01-10 | 2021-02-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01045 | [8 empty] | Clear & Grub | 10 | 0 | 2021-07-26 08:00 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01050 | [8 empty] | Scrape & Store Topsoil | 10 | 0 | 2021-10-20 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01055 | [8 empty] | Soil Testing | 10 | 0 | 2021-05-14 | 2021-06-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01060 | [6 empty] | 02-2000 |  | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 2021-07-16 08:00 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01065 | [8 empty] | Remove Retaining Walls | 10 | 0 | 2022-04-26 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01070 | [8 empty] | Install Deep Wells For Dewatering | 2 | 0 | 2022-03-25 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01075 | [8 empty] | Install Piping For Deep Wells - N/A | 5 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01080 | [8 empty] | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01085 | [8 empty] | Run Electric For Dewatering - N/A | 10 | 0 | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01150 | MLJ | S8 | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-S8 | Excavate for Electric S8.2--> S8.1 (South) | 10 | 0 | 2022-06-14 | 2022-10-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01155 | FIVE STAR | S8 | [6 empty] | Install Electrical Conduit S8.2--> S8.1 (South) | 5 | 0 | 2022-06-07 | 2022-11-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01160 | MLJ | S8 | Concrete |  |  | SITE CONCRETE |  |  | Encase conduit in concrete S8.2--> S8.1 (South) | 5 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01165 | MLJ | S8 | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-S8 | Backfill Electrical S8.2--> S8.1 (South) | 5 | 0 | 2022-11-03 | 2022-11-04 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01405 | NATIONAL GRID | S8 |  | Utilities | SITE |  |  |  | Gas Line Installation - W36th Street to S8-2 (by National Gas) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -97 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01205 | [8 empty] | Excavate for Electric S8.2--> S8.1 (North) | 3 | 0 | 2022-04-10 | 2022-06-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01210 | [8 empty] | Install Electrical Conduit S8.2--> S8.1 (North) | 5 | 0 | 2022-04-05 08:00 | 2022-06-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01215 | [8 empty] | Encase conduit in concrete S8.2--> S8.1 (North) | 2 | 0 | 2022-06-10 | 2022-06-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01220 | [8 empty] | Backfill Electrical S8.2--> S8.1 (North) | 2 | 0 | 2022-06-13 | 2022-06-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01255 | MLJ | S8 | Excavation |  |  | UTILITY EXC | 33-3100 | 33-3100-S8 | Excavate for Electric S8.2--> MH | 3 | 0 | 2022-06-06 | 2022-08-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01260 | FIVE STAR | S8 | [6 empty] | Install Electrical Conduit S8.2--> MH | 5 | 0 | 2022-06-07 | 2022-08-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01265 | MLJ | S8 | Concrete |  |  | SITE CONCRETE |  |  | Encase conduit in concrete S8.2--> MH | 2 | 0 | 2022-08-10 | 2022-08-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01270 | MLJ | S8 | BACKFILL |  |  | BACKFILL UTILITY | 31-2200 | 31-2200-S8 | Backfill Electric S8.2--> MH | 2 | 0 | 2022-08-11 | 2022-08-11 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01505 | MLJ | S8 | Excavation | Utilities | SITE | PLAYGROUND |  |  | Excavate for water line - S8 Fountain & Playground --> Water Main Surf Avenue | 2 | 0 | 2023-02-13 | 2023-02-14 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01510 | MLJ | S8 |  | Utilities | SITE | PLAYGROUND |  |  | Install water line - S8 Fountain & Playground --> Water Main Surf Avenue | 5 | 0 | 2023-02-15 08:00 | 2023-02-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01515 | MLJ | S8 |  | Utilities | SITE | PLAYGROUND |  |  | Tap water main for S8 Fountain & Playground --> Water Main Surf Avenue | 2 | 2 | 2023-03-14 08:00 | 2023-03-15 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01520 | MLJ | S8 | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-S8 | Backfill water line - S8 Fountain & Playground --> Water Main Surf Avenue | 2 | 2 | 2023-03-16 08:00 | 2023-03-17 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01560 | MLJ | S8 | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-S8 | Excavate and Install Area Drains AD10> Existing+ Piping | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -38 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01565 | MLJ | S8 | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-S8 | Backfill Area Drains AD10> Existing+ Piping | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -38 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01090 | [8 empty] | Activate Dewatering System | 1 | 0 | 2022-05-11 | 2022-05-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01095 |  | S8 | dewatering | [5 empty] | Maintain Dewatering | 255 | 0 | 2022-05-11 | 2022-07-15 15:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.Removals1 | S8-01100 |  | S8 | [6 empty] | De-Activate Dewatering | 1 | 0 | 2022-07-15 15:00 | 2022-07-15 15:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01650 | MLJ | S8 | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-S8 | Excavate and Install Area Drains - AD6 > AD8 > AD9 to Existing & Piping | 15 | 0 | 2022-11-29 08:00 | 2022-12-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01655 | MLJ | S8 | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-S8 | Backfill Area Drains - AD6 > AD8 > AD9 to Existing & Piping | 5 | 0 | 2022-12-05 | 2022-12-09 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01660 | MLJ | S8 | Excavation |  |  | AREA DRAIN | 33-2600 | 33-2600-S8 | Excavate and Install Area Drains - AD5 > Existing + Piping | 15 | 0 | 2022-12-01 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01665 | MLJ | S8 | BACKFILL |  |  | BACKFILL AD | 33-2600 | 33-2600-S8 | Backfill Area Drains - AD5 > Existing + Piping | 5 | 0 | 2022-12-06 | 2022-12-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01670 | MLJ | S8 | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-S8 | Excavate and Install Area Drains - Yard Drain > Existing + Piping | 15 | 0 | 2023-02-01 | 2023-02-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01675 | MLJ | S8 | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-S8 | Backfill Area Drains - Yard Drain > Existing + Piping | 5 | 0 | 2023-02-02 08:00 | 2023-02-03 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01680 | MLJ | S8 | Excavation | Utilities | SITE | AREA DRAIN | 33-2600 | 33-2600-S8 | Excavate and Install Area Drains - AD1 > AD2 > Existing + Piping | 15 | 0 | 2023-02-03 08:00 | 2023-02-06 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01685 | MLJ | S8 | BACKFILL | Utilities | SITE | BACKFILL AD | 33-2600 | 33-2600-S8 | Backfill Area Drains - AD1 > AD2 > Existing + Piping | 5 | 0 | 2023-02-06 08:00 | 2023-02-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01605 | MLJ | S8 | Excavation |  |  | EXC RETAINING |  |  | Excavate for retaining wall --> S8 Phase 6 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01610 | MLJ | S8 | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-S8 | Form Retaining wall footing --> S8 Phase 6 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01615 |  | S8 | REBAR | [5 empty] | Rebar Retaining wall footing --> S8 Phase 6 | 2 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01620 | MLJ | S8 | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall footing --> S8 Phase 6 | 1 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01625 |  | S8 | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall footing --> S8 Phase 6 | 1 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01630 | MLJ | S8 | Formwork |  |  | SITE FORMWORK | 03-1600 | 03-1600-S8 | Form Retaining wall -->S8 Phase 6 | 3 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01635 |  | S8 | REBAR | [5 empty] | Rebar Retaining wall --> S8 Phase 6 | 3 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01640 | MLJ | S8 | Concrete |  |  | SITE CONCRETE |  |  | Pour Retaining wall --> S8 Phase 6 | 1 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01645 |  | S8 | Formwork |  |  | SITE FORMWORK |  |  | Strip Retaining wall --> S8 Phase 6 | 1 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01705 | JMC | S8 | CURBS | Restoration | SITE |  |  |  | Install Street Curbs --> S8 Phase 6 | 15 | 15 | 2023-09-07 08:00 | 2023-09-27 17:00 | -133 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01710 | JMC | S8 | SIDEWALKS | Restoration | SITE |  |  |  | Install sidewalks --> S8 Phase 6 | 10 | 10 | 2023-09-28 08:00 | 2023-10-11 17:00 | -133 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01715 | MLJ | S8 | CURBS | Restoration | SITE |  |  |  | Install curb around play area --> S8 Phase 6 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01720 | MLJ | S8 |  | Restoration | SITE | PLAYGROUND |  |  | Install Safety Surface --> S8 Phase 6 | 5 | 5 | 2023-07-05 08:00 | 2023-07-11 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01725 | MLJ | S8 | Concrete | Restoration | SITE | SITE CONCRETE |  |  | Install site furniture concrete foundations --> S8 Phase 6 | 10 | 10 | 2023-06-20 08:00 | 2023-07-03 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01730 | JMC | S8 | COLORED CONCRETE | Restoration | SITE |  |  |  | Install integrally colored concrete walkways --> S8 Phase 6 | 15 | 15 | 2023-07-12 08:00 | 2023-08-01 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01735 | MLJ | S8 |  | Restoration | SITE | PLAYGROUND |  |  | Install Play area items --> S8 Phase 6 | 5 | 5 | 2023-08-02 08:00 | 2023-08-08 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01740 | MLJ | S8 |  | Restoration | SITE | PLAYGROUND |  |  | Install fence around play area --> S8 Phase 6 | 10 | 10 | 2023-08-09 08:00 | 2023-08-22 17:00 | -98 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01745 | ATLAS | S8 | SITE RESTORATION | [5 empty] | Install Fence at building --> S8 | 5 | 0 | 2023-01-02 08:00 | 2023-01-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01750 | MLJ | S8 | SITE RESTORATION | Restoration | SITE |  |  |  | Place Site Furniture --> S8 Phase 6 | 10 | 10 | 2023-08-23 08:00 | 2023-09-06 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01755 | ASPEN | S8 | TOPSOIL | Restoration | SITE |  |  |  | Place topsoil --> S8 Phase 6 | 3 | 3 | 2023-10-27 08:00 | 2023-10-31 17:00 | -59 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01760 | ASPEN | S8 |  | Restoration | SITE |  |  |  | Place trees and plantings --> S8 Phase 6 | 5 | 5 | 2023-11-01 08:00 | 2023-11-07 17:00 | -59 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01765 | ASPEN | S8 |  | Restoration | SITE |  |  |  | Place lawn --> SGS Phase 5 | 5 | 5 | 2023-11-08 08:00 | 2023-11-14 17:00 | -59 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01770 | MLJ | S8 |  | Closeout | SITE |  |  |  | Demobilize from SGS Phase 6 | 5 | 5 | 2023-11-15 08:00 | 2023-11-21 17:00 | -121 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.7 | S8-01850 | CLOSEOUT | S8 | INSPECTION | Closeout | SITE |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-11-15 08:00 | 2023-11-21 17:00 | -131 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.7 | S8-01855 | PUNCH LIST | S8 |  | Closeout | SITE |  |  |  | Perform Punch List | 10 | 10 | 2023-11-22 08:00 | 2023-12-06 17:00 | -131 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01030 | [8 empty] | Form Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 10 | 0 | 2022-05-16 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01035 | [8 empty] | Rebar Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 5 | 0 | 2022-05-16 | 2022-05-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01040 | MLJ | S82 | concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Pour Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 2 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01045 | [8 empty] | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 5 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01025 | [8 empty] | Waterproof/Insulation Plumbing Shaft ----> S8 (Addition) | 5 | 0 | 2022-05-18 | 2022-05-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01005 | [8 empty] | Excavate/SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> S8 (Addition) | 10 | 0 | 2022-04-29 | 2022-05-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01020 | [8 empty] | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> S8 (Addition) | 3 | 0 | 2022-05-12 | 2022-05-13 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01055 |  |  | S82 |  |  |  | 31-1400 | 31-1400-S82 | Backfill Plumbing Shaft & Ftgs/Piers --> S8 (Addition) | 5 | 0 | 2022-05-16 | 2022-05-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01065 | [8 empty] | Excavate For Remaining Ftgs/Pier/Grade Beams --> S8 (Addition) | 10 | 0 | 2022-05-16 | 2022-05-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01070 |  | S82 | FORMWORK |  |  | FORMWORK NB | 03-1000 | 03-1000-S82 | Form Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 10 | 0 | 2022-06-01 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01075 | [8 empty] | Rebar Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 10 | 0 | 2022-05-25 | 2022-06-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01080 | [8 empty] | Pour Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 5 | 0 | 2022-06-02 | 2022-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01085 | MLJ | S82 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-S82 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 5 | 0 | 2022-07-18 | 2022-07-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01090 |  | S81 | [6 empty] | Install Remaining Steam Into S8 (Addition) (5' from the building) | 5 | 0 | 2022-09-01 | 2022-09-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01095 | MLJ | S81 | BACKFILL |  |  | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> S8 (Addition) | 5 | 0 | 2022-06-28 | 2022-07-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01105 | WEIR | S81 | STRUCTURAL STEEL | [5 empty] | Install Structural Steel Framing - 1st Floor --> S8 (Addition) | 10 | 0 | 2022-07-26 08:00 | 2022-08-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01110 |  | S81 | [6 empty] | Install Metal Deck --> S8 (Addition) | 2 | 0 | 2022-08-22 08:00 | 2022-08-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01115 | MLJ | S82 | Formwork | Structure | NEW BUILDINGS | NB FORMWORK | 03-1000 | 03-1000-S82 | Form Pour Strip Concrete Stair South Side ---> S8 (Addition) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01120 | E&Y | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Metal Stairs --> S8 (Addition) | 2 | 0 | 2023-02-13 08:00 | 2023-02-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01125 |  | S81 | [6 empty] | Place Insulation Below First Floor --> S8 (Addition) | 5 | 0 | 2022-07-07 | 2022-08-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01130 |  | S81 | [6 empty] | Place WWF First Floor Slab --> S8 (Addition) | 2 | 0 | 2022-07-11 08:00 | 2022-07-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01135 | MLJ | S82 | Concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Pour First Floor Slab --> S8 (Addition) | 1 | 0 | 2022-07-15 08:00 | 2022-07-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01150 | MLJ | S82 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-S82 | Form First Floor Concrete Walls First Face And Col Encasements--> S8 (Addition) | 3 | 0 | 2022-09-05 | 2022-09-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01155 | MLJ | S82 | Concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Rebar First Floor Concrete Walls --> S8 (Addition) | 3 | 0 | 2022-09-01 | 2022-09-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01160 | MLJ | S82 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-S82 | Form First Floor Concrete Walls 2Nd Face --> S8 (Addition) | 5 | 0 | 2022-09-21 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01165 | [8 empty] | Form, Rebar & Pour Concrete Pads 1st Floor --> S8 (Addition) - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01170 |  | S81 | [6 empty] | Place WWF 2nd Floor Slab --> S8 (Addition) | 2 | 0 | 2022-09-21 | 2022-09-22 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01175 | MLJ | S82 | Concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> S8 (Addition) | 2 | 0 | 2022-09-27 | 2022-09-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01180 | MLJ | S82 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-S82 | Strip Forms First Floor Walls & Col Encasements And 1st Floor Pads --> S8 (Addition) | 3 | 0 | 2022-09-29 | 2022-10-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01185 | MLJ | S82 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-S82 | Form Concrete Pads 2nd Floor -->S8 (Addition) | 2 | 0 | 2022-09-26 | 2022-09-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01205 |  | S81 | [6 empty] | Place WWF Roof Slab --> S8 (Addition) | 2 | 0 | 2022-09-19 | 2022-09-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01210 | MLJ | S82 | Concrete |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Pour Roof Slab and 2nd Floor Conc Pads -->S8 (Addition) | 1 | 0 | 2022-09-27 | 2022-09-27 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01215 | MLJ | S82 | Formwork |  |  | NB FORMWORK | 03-1000 | 03-1000-S82 | Strip Forms Concrete Pads 2nd Floor -->S8 (Addition) | 2 | 0 | 2022-10-03 | 2022-10-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01225 | SIG | S82 | [6 empty] | Install Spray-On Fireproofing on St Stl --> S8 (Addition) | 5 | 0 | 2022-10-10 | 2022-11-02 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01230 | FAXA | S82 | CMU | Structure | NEW BUILDINGS |  |  |  | Place CMU 1st, 2nd Floors and Roof --> S8 (Addition) | 20 | 10 | 2022-11-01 | 2023-03-10 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01240 | CCC | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Stud Framing 1st, 2nd Floors and Roof --> S8 (Addition) | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -69 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01245 | CCC | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Doors --> S8 (Addition) | 3 | 3 | 2023-04-10 08:00 | 2023-04-12 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01250 | JMC | S81 | CAST STONE | Exterior | EXISTING BUILDINGS |  |  |  | Install Cast Stone Panels --> S8 (Addition) | 1 | 1 | 2023-04-13 08:00 | 2023-04-13 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01255 | NAVILLUS | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Insulated Metal Panels/Louvers --> S8 (Addition) | 10 | 10 | 2023-04-14 08:00 | 2023-04-27 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01260 | MLJ | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install MEP Roof Penetrations & Drains - S8 (Addition) | 1 | 0 | 2023-02-13 08:00 | 2023-02-14 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01265 | TRIANGLE | S82 |  | Structure | NEW BUILDINGS |  |  |  | Install Roofing --> S8 (Addition) | 15 | 5 | 2023-02-15 08:00 | 2023-05-04 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01270 | E&Y | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Dunnage Gratings --> S8 (Addition) | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 6 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01275 | FAXA | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Brick Façade & Stone --> S8 (Addition) | 20 | 20 | 2023-03-01 08:00 | 2023-03-28 17:00 | 6 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01285 | MLJ | S82 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD VENTS |  |  | Install Flood Vents And Small Louvers --> S8 (Addition) | 3 | 3 | 2023-04-28 08:00 | 2023-05-02 17:00 | -11 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01290 | E&Y | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Stair And Roof Platform Railings --> S8 (Addition) | 5 | 5 | 2023-03-29 08:00 | 2023-04-04 17:00 | 13 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01295 | E&Y | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Ladders --> S8 (Addition) | 3 | 3 | 2023-04-05 08:00 | 2023-04-07 17:00 | 20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01305 | CCC | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Sheetrock and Stucco --> S8 (Addition) | 10 | 10 | 2023-07-03 13:00 | 2023-07-18 12:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01310 | FAXA | S82 | FLOORING | Structure | NEW BUILDINGS | CERAMIC |  |  | Install Ceramic Tile --> S8 (Addition) | 2 | 2 | 2023-07-18 13:00 | 2023-07-20 12:00 | -54 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01315 | TRIANGLE | S82 | CEILING | Structure | NEW BUILDINGS |  |  |  | Install Acoustical Ceiling --> S8 (Addition) | 2 | 2 | 2023-07-20 13:00 | 2023-07-24 12:00 | -54 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01320 |  | S81 | WATERPROOFING | [5 empty] | Place Crystaline Waterproofing In Plumbing Shaft --> S8 (Addition) | 3 | 0 | 2022-11-25 08:00 | 2022-11-29 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01325 | GG PAINT | S81 | PAINT | Interior | EXISTING BUILDINGS |  |  |  | Paint All Areas --> S8 (Addition) | 15 | 15 | 2023-08-17 13:00 | 2023-09-08 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01330 | MLJ | S82 | SIGNS | Interior | NEW BUILDINGS |  |  |  | Install Signs --> S8 (Addition) | 2 | 2 | 2023-09-08 13:00 | 2023-09-12 12:00 | -89 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01235 | DSTAR | S81 | WATERPROOFING | Exterior | EXISTING BUILDINGS |  |  |  | Install Waterproofing to Parapet --> S8 (Addition) | 3 | 0 | 2023-02-16 08:00 | 2023-02-20 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01280 | CCC | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Stucco Soffit --> S8 (Addition) | 5 | 5 | 2023-03-29 08:00 | 2023-04-04 17:00 | 6 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01317 | NAVILLUS | S81 |  | Exterior | EXISTING BUILDINGS |  |  |  | Install Insulated Metal Panels left out for Access --> S8 (Addition) | 5 | 5 | 2023-08-10 13:00 | 2023-08-17 12:00 | -89 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01092 |  | S81 | [6 empty] | Install Remaining HW/CW Into S8 (Addition) (5' from the building) | 5 | 0 | 2022-08-25 08:00 | 2022-08-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01094 |  | S81 | [6 empty] | Install Remaining Electrical POE Into S8 (Addition) | 5 | 0 | 2022-06-01 | 2022-06-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.1 | S8E-01005 | ATCO | S81 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - gaskets - cellar - S8 (Existing) | 3 | 3 | 2023-09-20 13:00 | 2023-09-25 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.1 | S8E-01010 | ATCO | S81 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - wire insulation - cellar --> S8 (Existing) | 3 | 3 | 2023-02-27 08:00 | 2023-03-01 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.1 | S8E-01015 | ATCO | S81 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - flooring materials at slab penetrations - cellar --> S8 (Existing) | 3 | 3 | 2023-03-02 08:00 | 2023-03-06 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.1 | S8E-01020 | ATCO | S81 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - pipe insulation - cellar --> S8 (Existing) | 3 | 3 | 2023-03-07 08:00 | 2023-03-09 17:00 | -72 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.1 | S8E-01025 | [8 empty] | Asbestos Abatement - Window Sills - 1st Floor --> S8 (Existing) | 5 | 0 | 2022-04-20 | 2022-04-22 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.1 | S8E-01030 | ATCO | S81 | ABESTOS | Building Demo | EXISTING BUILDINGS |  |  |  | Asbestos Abatement - caulk @ windows and areaway vents --> S8 (Existing) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01105 | MLJ | S81 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO CELLAR WALLS | 02-6005 | 02-6005-S81 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> S8 (Existing) | 10 | 10 | 2023-03-10 08:00 | 2023-03-23 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01110 | MLJ | S81 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO DOORS WINDOWS |  |  | Selective Demo (Doors, windows) - 1st Floor --> S8 (Existing) | 5 | 5 | 2023-03-24 08:00 | 2023-03-30 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01115 | MLJ | S81 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO AREAWAY |  |  | Selective Demo (Areaway drain, slab, wall) --> S8 (Existing) | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -64 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01205 | MLJ | S81 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO RAMP |  |  | Selective Demo (Existing Ramp, railing) - 1st Floor --> S8 (Existing) | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -64 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01210 | MLJ | S81 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO SLAB OPEN FOR MECH |  |  | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> S8 (Existing) | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -64 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01215 | [8 empty] | Selective Demo - 2nd Floor Apartment for Electrical Room --> S8 (Existing) - N/A | 5 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01310 | MLJ | S82 | CORE DRILL | Interior | NEW BUILDINGS |  |  |  | Make openings in floor for conduit penetrations - 1st floor apartments --> S8 (Existing) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -50 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01315 | WEIR | S82 | [6 empty] | Install beams below floor - 1st floor apartments --> S8 (Existing) | 5 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01320 | MLJ | S81 |  | Interior | EXISTING BUILDINGS | FRP | 03-6000 | 03-6000-S81 | Install FRP around floor openings - 1st floor apartments --> S8 (Existing) | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | -50 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01325 | CCC | S82 |  | Interior | NEW BUILDINGS |  |  |  | Frame walls / install door for electrical room - 1st floor --> S8 (Existing) | 3 | 3 | 2023-03-13 08:00 | 2023-03-15 17:00 | -50 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01330 | CCC | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install drywall / tape / spackle - electrical room - 1st floor --> S8 (Existing) | 5 | 5 | 2023-06-29 08:00 | 2023-07-06 17:00 | -72 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01335 | CCC | S82 |  | Interior | NEW BUILDINGS |  |  |  | Paint walls and seal floor electrical room - 1st Floor --> S8 (Existing) | 10 | 10 | 2023-07-14 08:00 | 2023-07-27 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.4 | S8E-01340 | FLOORING | S82 | FLOORING | Interior | NEW BUILDINGS | VCT |  |  | Install VCT @ electrical room - 1st Floor --> S8 (Existing) | 2 | 2 | 2023-07-28 08:00 | 2023-07-31 17:00 | -74 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01405 | MLJ | S81 | Excavation | Exterior | EXISTING BUILDINGS | EB EXC | 31-1000 | 31-1000-S81 | Excavate at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 9 | 9 | 2023-02-27 08:00 | 2023-03-09 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01410 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 12 | 12 | 2023-03-16 08:00 | 2023-03-31 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01415 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 2023-04-03 08:00 | 2023-04-11 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01420 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-04-12 08:00 | 2023-04-19 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01425 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 2023-04-20 08:00 | 2023-04-28 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01430 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01435 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 8 | 8 | 2023-05-15 08:00 | 2023-05-24 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01440 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-05-25 08:00 | 2023-06-02 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01445 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-06-05 08:00 | 2023-06-12 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01450 | FAXA | S81 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-06-13 08:00 | 2023-06-20 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01455 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 2023-06-21 08:00 | 2023-06-29 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01460 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form for slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-06-30 08:00 | 2023-07-10 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01465 | TONAGE | S82 | REBAR | Structure | NEW BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 8 | 8 | 2023-07-11 08:00 | 2023-07-20 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01470 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-07-21 08:00 | 2023-07-28 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01475 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms for slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 4 | 4 | 2023-07-31 08:00 | 2023-08-03 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01480 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill surounding area at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 2023-08-04 08:00 | 2023-08-11 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01505 | MLJ | S81 | Excavation | Exterior | EXISTING BUILDINGS | EB EXC | 31-1000 | 31-1000-S81 | Excavate at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 9 | 0 | 2023-01-25 08:00 | 2023-02-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01510 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 12 | 12 | 2023-03-16 08:00 | 2023-03-31 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01515 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 2023-04-03 08:00 | 2023-04-11 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01520 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-04-12 08:00 | 2023-04-19 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01525 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 2023-04-20 08:00 | 2023-04-28 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01530 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01535 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 8 | 8 | 2023-05-15 08:00 | 2023-05-24 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01540 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-05-25 08:00 | 2023-06-02 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01545 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-06-05 08:00 | 2023-06-12 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01550 | FAXA | S81 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-06-13 08:00 | 2023-06-20 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01555 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 2023-06-21 08:00 | 2023-06-29 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01560 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form for slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-06-30 08:00 | 2023-07-10 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01565 | TONAGE | S82 | REBAR | Structure | NEW BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 8 | 8 | 2023-07-11 08:00 | 2023-07-20 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01570 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-07-21 08:00 | 2023-07-28 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01575 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms for slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 4 | 4 | 2023-07-31 08:00 | 2023-08-03 17:00 | -116 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01580 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill surounding area at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 2023-08-07 08:00 | 2023-08-14 17:00 | -117 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01605 | MLJ | S81 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-S81 | Excavate at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 9 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01610 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 12 | 0 | 2022-11-16 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01615 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 0 | 2022-11-16 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01620 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 0 | 2022-11-29 | 2022-11-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01625 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 0 | 2022-11-30 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01630 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 10 | 0 | 2022-11-01 | 2022-12-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01635 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 8 | 0 | 2022-12-02 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01640 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 0 | 2022-12-07 | 2022-12-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01645 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 0 | 2022-12-08 | 2022-12-09 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01650 | FAXA | S81 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 6 | 2023-02-27 08:00 | 2023-03-06 17:00 | -24 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01655 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 0 | 2023-02-21 08:00 | 2023-02-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01705 | MLJ | S81 | Excavation |  |  | EB EXC | 31-1000 | 31-1000-S81 | Excavate at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 9 | 0 | 2022-11-14 | 2022-11-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01710 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 11 | 0 | 2022-11-16 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01715 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 6 | 0 | 2022-11-16 | 2022-11-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01720 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 0 | 2022-11-23 08:00 | 2022-11-29 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01725 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 6 | 0 | 2022-11-30 | 2022-11-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01730 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Form concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 9 | 0 | 2022-11-01 | 2022-12-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01735 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 7 | 0 | 2022-12-02 | 2022-12-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01740 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 0 | 2022-12-07 | 2022-12-07 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01745 | MLJ | S81 | Formwork |  |  | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 0 | 2022-12-08 | 2022-12-09 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01750 | FAXA | S81 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU wall and grout fill at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -97 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01755 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 6 | 0 | 2023-02-21 08:00 | 2023-02-23 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01805 | MLJ | S81 | Excavation | Exterior | EXISTING BUILDINGS | EB EXC | 31-1000 | 31-1000-S81 | Excavate for concrete shelf around bldg perimeter --> S8 (Existing) | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01810 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Place rebar for concrete shelf around bldg perimeter --> S8 (Existing) | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01815 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour concrete shelf around bldg perimeter --> S8 (Existing) | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01820 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Place infill concrete in area ways around bldg perimeter --> S8 (Existing) | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01825 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Place waterproofing on concrete shelf around bldg perimeter --> S8 (Existing) | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -83 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01830 | FAXA | S81 | CMU | Exterior | EXISTING BUILDINGS |  |  |  | Place CMU around bldg perimeter --S8 (Existing) | 15 | 15 | 2023-04-03 08:00 | 2023-04-21 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01835 | DSTAR | S82 | WATERPROOFING | Structure | NEW BUILDINGS |  |  |  | Place waterproofing on CMU around bldg perimeter --> S8 (Existing) | 10 | 10 | 2023-04-24 08:00 | 2023-05-05 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01840 | MLJ | S82 |  | Exterior | NEW BUILDINGS |  |  |  | Place window frames around bldg perimeter --> S8 (Existing) | 10 | 10 | 2023-05-08 08:00 | 2023-05-19 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01845 | FAXA | S82 |  | Structure | NEW BUILDINGS |  |  |  | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> S8 (Existing) | 15 | 15 | 2023-05-22 08:00 | 2023-06-12 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01850 | MLJ | S81 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-S81 | Backfill around bdg perimeter --> S8 (Existing) | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01855 | CCC | S82 |  | Interior | NEW BUILDINGS |  |  |  | Place frame / stucco / and signs at entrances --> S8 (Existing) | 4 | 4 | 2023-06-20 08:00 | 2023-06-23 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01860 | MLJ | S82 | FLOOD PROTECTION | Structure | NEW BUILDINGS | FLOOD WINDOWS |  |  | Place window floodgates at windows --> S8 (Existing) | 5 | 5 | 2023-06-26 08:00 | 2023-06-30 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01865 | MLJ | S81 | SIGNS | Interior | EXISTING BUILDINGS |  |  |  | Install signs --> S8 (Existing) | 3 | 3 | 2023-07-03 08:00 | 2023-07-06 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.5 | S8E-01350 | MLJ | S81 |  | Interior | EXISTING BUILDINGS | DRILL & DOWEL | 03-1400 | 03-1400-S81 | Drill dowels and place rebar for boiler room concrete walls --> S8 (Existing) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.5 | S8E-01355 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Form boiler room concrete walls --> S8 (Existing) | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.5 | S8E-01360 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Pour Concrete boiler room walls --> S8 (Existing) | 2 | 2 | 2023-03-13 08:00 | 2023-03-14 17:00 | 18 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.5 | S8E-01365 | MLJ | S81 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-S81 | Strip Forms boiler room concrete walls --> S8 (Existing) | 3 | 3 | 2023-03-15 08:00 | 2023-03-17 17:00 | 20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.5 | S8E-01370 | DSTAR | S82 | WATERPROOFING | Structure | NEW BUILDINGS |  |  |  | Place crystaline waterproofing on perimeter walls - cellar --> S8 (Existing) | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -102 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.6 | S8E-01385 | [8 empty] | Refurbish Elevator 1 --> S8 (Existing) (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.6 | S8E-01390 | [8 empty] | Refurbish Elevator 2 --> S8 (Existing) (Omitted PCOCO 69) | 20 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.6 | S8E-01380 | [8 empty] | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.7 | S8E-09005 | CLOSEOUT | S82 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Perform Inspections & Issue Punch List | 5 | 5 | 2023-09-25 13:00 | 2023-10-02 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.7 | S8E-09010 | PUNCH LIST | S82 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List | 10 | 10 | 2023-10-02 13:00 | 2023-10-17 12:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.2 | S8E-01220 | MLJ | S81 | DEMO | Building Demo | EXISTING BUILDINGS | DEMO PUMPS | 02-6010 | 02-6010-S81 | Selective Demo (Pumps etc..) - Cellar --> S8 (Existing) | 5 | 5 | 2023-05-08 08:00 | 2023-05-12 17:00 | -94 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03005 | WELKIN | S82 | [6 empty] | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 2022-11-01 | 2022-11-18 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03010 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Condensate Pump - Cellar | 10 | 10 | 2023-05-15 08:00 | 2023-05-26 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03020 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Pump Controls - Cellar | 20 | 20 | 2023-04-10 08:00 | 2023-05-05 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03025 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - Cellar | 5 | 5 | 2023-06-01 08:00 | 2023-06-07 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03030 | VITAL | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Plumbing Equipment - Cellar | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03035 | CLOSEOUT | S82 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 2023-06-08 08:00 | 2023-06-21 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03040 | MEP | S82 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 2023-06-22 08:00 | 2023-07-20 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03015 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Steam Traps - Cellar | 2 | 2 | 2023-05-30 08:00 | 2023-05-31 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03007 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 20 | 2023-03-13 08:00 | 2023-04-07 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-03032 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Mechanical Equipment - Cellar | 20 | 20 | 2023-04-10 08:00 | 2023-05-05 17:00 | -77 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03105 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 10 | 10 | 2023-04-10 08:00 | 2023-04-21 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03120 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install HVAC Controls - 1st Floor | 20 | 20 | 2023-05-15 08:00 | 2023-06-12 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03125 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-06-13 08:00 | 2023-06-19 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03130 | NAVILLUS | S82 |  | Structure | NEW BUILDINGS |  |  |  | Install Mechanical Louvers - 1st Floor | 15 | 15 | 2023-04-24 08:00 | 2023-05-12 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03135 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 2023-06-20 08:00 | 2023-07-03 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03140 | MEP | S82 |  | Interior | NEW BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-07-05 08:00 | 2023-08-01 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03115 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Steam Traps - 1st Floor | 1 | 1 | 2023-04-24 08:00 | 2023-04-24 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03110 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03112 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Install HV & EF Units - 1st Floor | 5 | 5 | 2023-04-17 08:00 | 2023-04-21 17:00 | -102 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.2 | S8E-03107 | WELKIN | S82 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 2023-04-10 08:00 | 2023-04-21 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03105 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 15 | 2023-03-17 13:00 | 2023-04-07 12:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03110 | [8 empty] | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03125 | VITAL | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 10 | 2023-04-28 13:00 | 2023-05-12 12:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03130 |  | S81 | [6 empty] | Install FOT Controls - 1st Floor | 20 | 0 | 2022-12-25 08:00 | 2022-12-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03135 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 2023-05-19 13:00 | 2023-05-26 12:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03140 | VITAL | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Plumbing Equipment - 1st Floor | 15 | 15 | 2023-04-28 13:00 | 2023-05-19 12:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03145 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 5 | 2023-05-26 13:00 | 2023-06-05 12:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03150 | MEP | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 2023-06-05 13:00 | 2023-07-03 12:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03107 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 15 | 2023-04-07 13:00 | 2023-04-28 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-03142 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Mechanical Equipment - 1st Floor | 15 | 3 | 2023-02-13 13:00 | 2023-05-03 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-03005 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 5 | 5 | 2023-03-20 08:00 | 2023-03-24 17:00 | -98 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-03010 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Condensate Pump - Foundation Level | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | -98 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03205 | [8 empty] | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03225 | VITAL | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 20 | 2023-06-05 13:00 | 2023-07-03 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03235 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Perform Hydrostatic Testing - 2nd Floor | 5 | 5 | 2023-07-03 13:00 | 2023-07-11 12:00 | -113 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03240 | [8 empty] | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03245 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 2 | 2023-02-12 13:00 | 2023-07-13 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03250 | MEP | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 2023-07-13 13:00 | 2023-08-10 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03207 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 15 | 2023-05-12 13:00 | 2023-06-05 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.2 | S8A-03242 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Install Mechanical Equipment - 2nd Floor | 5 | 5 | 2023-06-05 13:00 | 2023-06-12 12:00 | -98 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-03405 | [8 empty] | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-03410 | [8 empty] | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.3 | S8A-03415 | TRIANGLE | S82 |  | Structure | NEW BUILDINGS |  |  |  | Install Insulation - Roof | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | -11 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-03505 | CLOSEOUT | S81 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - S8A | 4 | 4 | 2023-08-10 13:00 | 2023-08-16 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-03510 | CLOSEOUT | S81 | STARTUP | Closeout | EXISTING BUILDINGS |  |  |  | Perform Start-Up Testing - S8A | 10 | 10 | 2023-08-22 13:00 | 2023-09-06 12:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-03520 | PUNCH LIST | S81 |  | Closeout | EXISTING BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - S8A | 5 | 5 | 2023-09-06 13:00 | 2023-09-13 12:00 | -86 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-03530 | MEP | S81 | CLOSEOUT | Interior | EXISTING BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - S8A | 4 | 4 | 2023-10-11 08:00 | 2023-10-17 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-03525 | CLOSEOUT | S81 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - S8A | 1 | 1 | 2023-10-10 08:00 | 2023-10-10 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-03305 | CLOSEOUT | S82 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Mechanical/Plumbing Inspection - S8E | 4 | 4 | 2023-08-16 13:00 | 2023-08-22 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-03310 | CLOSEOUT | S82 | STARTUP | Closeout | NEW BUILDINGS |  |  |  | Perform Start-Up Testing - S8E | 10 | 10 | 2023-08-22 13:00 | 2023-09-06 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-03320 | PUNCH LIST | S82 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Punch List - Electrical/Mechanical/Plumbing Work - S8E | 5 | 5 | 2023-09-06 13:00 | 2023-09-13 12:00 | -85 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-03330 | MEP | S82 |  | Closeout | NEW BUILDINGS |  |  |  | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - S8E | 4 | 4 | 2023-10-12 08:00 | 2023-10-18 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-03325 | CLOSEOUT | S82 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - S8E | 1 | 1 | 2023-10-11 08:00 | 2023-10-11 17:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.3 | S8E-03335 | MLJ | S82 |  | Closeout | NEW BUILDINGS |  |  |  | Remove Redundant Services - S8E | 10 | 10 | 2023-09-06 13:00 | 2023-09-20 12:00 | -113 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05010 | [8 empty] | DOB Issue Demolition Permit | 20 | 0 | 2021-03-17 | 2021-10-06 |  | 0
Not Started |  | CI NYCHA Update #20.Milestones | M905 | [8 empty] | Project Close-out (Including obtaining COC) | 90 | 90 | 2024-04-25 08:00 | 2024-07-23 17:00 | -334 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01013 | [8 empty] | Asbestos Abatement at OG-7 (Garden Shed) | 5 | 0 | 2021-03-05 | 2021-03-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01015 | [8 empty] | Demo OG-7 (Garden Shed) Structure | 3 | 0 | 2021-12-02 08:00 | 2021-12-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01018 | [8 empty] | Demo OG-7 Footings | 2 | 0 | 2021-12-03 | 2021-12-04 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01410 | NATIONAL GRID | OGE |  | Utilities | SITE |  |  |  | National Gas to Install Line - OG8 --> W33rd Street | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.4 | OGP1-01415 | MLJ | OGW | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-OGW | Backfill Gas line - OG8 --> W33rd Street | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -24 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.2 | SG4-01220 |  | SG4 |  |  |  |  | 02-6010 | 02-6010-SG4 | Selective Demo (pumps etc..) - Cellar --> SG4 | 5 | 0 | 2022-06-06 | 2022-06-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01575 | [8 empty] | Prepare & Submit Construction Work Plan | 20 | 0 | 2020-10-01 | 2020-11-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01580 | [8 empty] | Review & Approve Construction Work Plan | 10 | 0 | 2020-11-12 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01850 | [8 empty] | Prepare & Submit Arborist Subcontractor | 5 | 0 | 2020-09-01 | 2020-09-23 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01855 | [8 empty] | Review & Approve Arborist Subcontractor | 10 | 0 | 2020-09-24 | 2020-10-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01521 | MLJ | SGN | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall footing --> SGN | 7 | 0 | 2022-08-17 08:00 | 2022-08-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.5.4 | SGN-01541 | MLJ | SGN | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall --> SGN | 7 | 0 | 2022-08-26 08:00 | 2022-09-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01041 | [8 empty] | Cure Plumbing Shafts & Ftgs Below Water Table --> SG6 | 7 | 0 | 2021-04-30 | 2021-05-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01081 | [8 empty] | Cure Remaining Ftgs/Piers/Grade Beams --> SG6 | 7 | 0 | 2021-07-13 | 2021-07-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01116 | [8 empty] | Cure Concrete Stair South Side ---> SG6 | 7 | 0 | 2021-12-11 08:00 | 2021-12-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01140 | [8 empty] | Cure First Floor Slab --> SG6 | 7 | 0 | 2021-07-13 08:00 | 2021-07-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01176 | [8 empty] | Cure 2nd Floor Slab / First Floor Walls & Col Encasements --> SG6 | 7 | 0 | 2021-10-13 | 2021-10-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01211 | [8 empty] | Cure Roof Slab and 2nd Floor Conc Pads -->SG6 | 7 | 0 | 2021-12-04 08:00 | 2021-12-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.5 | SG4-01361 | [8 empty] | Cure Concrete boiler room walls --> SG4 | 7 | 0 | 2021-05-14 | 2021-05-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01421 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 7 | 0 | 2022-02-25 08:00 | 2022-03-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01441 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 7 | 0 | 2022-03-22 08:00 | 2022-03-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01471 | MLJ | SG4 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure slab at Curtain Wall for flood protection (East Side) --> SG4 | 7 | 0 | 2022-08-12 08:00 | 2022-08-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01521 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 7 | 0 | 2022-02-25 08:00 | 2022-03-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01541 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 7 | 0 | 2022-03-22 08:00 | 2022-03-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01571 | MLJ | SG4 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure slab at Curtain Wall for flood protection (South Side) --> SG4 | 7 | 0 | 2022-03-22 08:00 | 2022-03-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01621 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 7 | 0 | 2022-04-16 08:00 | 2022-04-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01641 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 7 | 0 | 2022-05-02 08:00 | 2022-05-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01671 | MLJ | SG4 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure slab at Curtain Wall for flood protection (North Side) --> SG4 | 7 | 0 | 2022-12-13 08:00 | 2022-12-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01721 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 7 | 0 | 2022-02-25 08:00 | 2022-03-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01741 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 7 | 0 | 2022-03-22 08:00 | 2022-03-28 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01771 | MLJ | SG4 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure slab at Curtain Wall for flood protection (West Side) --> SG4 | 7 | 7 | 2023-04-12 08:00 | 2023-04-18 17:00 | 12 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.5 | SG4-01816 | MLJ | SG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG4 | Cure concrete shelf around bldg perimeter --> SG4 | 7 | 0 | 2022-03-22 08:00 | 2022-03-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01421 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 7 | 0 | 2022-02-22 08:00 | 2022-03-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01441 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 7 | 0 | 2022-08-12 | 2022-08-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01471 | MLJ | SG5 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure slab at Curtain Wall for flood protection (East Side) --> SG5 | 7 | 0 | 2022-09-10 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01521 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 7 | 0 | 2022-08-01 08:00 | 2022-08-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01541 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 7 | 0 | 2022-08-02 08:00 | 2022-08-08 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01571 | MLJ | SG5 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure slab at Curtain Wall for flood protection (South Side) --> SG5 | 7 | 0 | 2022-12-13 08:00 | 2022-12-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01621 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 7 | 0 | 2022-02-22 08:00 | 2022-02-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01641 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 7 | 0 | 2022-10-29 08:00 | 2022-11-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01671 | MLJ | SG5 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure slab at Curtain Wall for flood protection (North Side) --> SG5 | 7 | 0 | 2022-12-13 08:00 | 2022-12-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01721 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 7 | 0 | 2022-03-22 08:00 | 2022-03-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01741 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 7 | 0 | 2022-08-12 08:00 | 2022-08-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01771 | MLJ | SG5 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure slab at Curtain Wall for flood protection (West Side) --> SG5 | 7 | 0 | 2022-09-10 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.5 | SG5-01817 | MLJ | SG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG5 | Cure concrete shelf around bldg perimeter --> SG5 | 7 | 0 | 2022-03-22 08:00 | 2022-03-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01176 | MLJ | S82 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> S8 (Addition) | 7 | 0 | 2022-09-28 08:00 | 2022-10-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01136 | MLJ | S82 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Cure First Floor Slab --> S8 (Addition) | 7 | 0 | 2022-07-16 08:00 | 2022-07-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01041 | [8 empty] | Cure Plumbing Shafts & Ftgs Below Water Table --> OG8 | 7 | 0 | 2021-08-10 | 2021-08-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01081 | [8 empty] | Cure Remaining Ftgs/Piers/Grade Beams --> OG8 | 7 | 0 | 2021-12-08 08:00 | 2021-12-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01116 | [8 empty] | Cure Concrete Stair South Side ---> OG8 | 7 | 0 | 2022-03-05 08:00 | 2022-03-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01136 | [8 empty] | Cure First Floor Slab --> OG8 | 7 | 0 | 2022-03-08 08:00 | 2022-03-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01176 | MLJ | OG8 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-OG8 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements --> OG8 | 7 | 0 | 2022-04-06 08:00 | 2022-04-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01211 | [8 empty] | Cure Roof Slab and 2nd Floor Conc Pads -->OG8 | 7 | 0 | 2022-05-10 | 2022-05-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.5 | OG4-01361 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure Concrete boiler room walls --> OG4 | 7 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01421 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 2022-06-22 08:00 | 2022-06-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.1 | OG4-01441 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 2022-06-22 08:00 | 2022-06-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01521 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 7 | 0 | 2022-06-22 08:00 | 2022-06-28 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01541 | MLJ | OG4 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 7 | 7 | 2023-03-03 08:00 | 2023-03-09 17:00 | 3 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01621 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 7 | 0 | 2022-06-22 08:00 | 2022-06-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.3 | OG4-01641 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 7 | 0 | 2022-10-15 08:00 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01721 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 2022-06-22 08:00 | 2022-06-28 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.4 | OG4-01741 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 2022-10-15 08:00 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.5 | OG4-01816 | MLJ | OG4 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure concrete shelf around bldg perimeter --> OG4 | 7 | 0 | 2022-06-22 08:00 | 2022-06-29 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.5 | OG5-01361 | MLJ | OG5 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure Concrete boiler room walls --> OG5 | 7 | 0 | 2022-11-11 08:00 | 2022-11-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01421 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.1 | OG5-01441 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 2022-10-11 08:00 | 2022-10-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01521 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01541 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 7 | 0 | 2022-06-25 08:00 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01571 | MLJ | OG5 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure slab at Curtain Wall for flood protection (South Side) --> OG5 | 7 | 0 | 2022-08-23 08:00 | 2022-08-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01621 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 7 | 0 | 2022-06-09 08:00 | 2022-06-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.3 | OG5-01641 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 7 | 0 | 2022-08-09 08:00 | 2022-08-15 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01721 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 2022-06-09 08:00 | 2022-06-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.4 | OG5-01741 | MLJ | OG5 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 2022-12-24 08:00 | 2022-12-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.5 | OG5-01816 | MLJ | OG5 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG5 | Cure concrete shelf around bldg perimeter --> OG5 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01041 | MLJ | S82 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Cure Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 7 | 0 | 2022-05-19 08:00 | 2022-05-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01641 | MLJ | OGW | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall --> OG Phase 2A | 7 | 0 | 2022-07-26 08:00 | 2022-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01041 | [8 empty] | Cure Plumbing Shafts & Ftgs Below Water Table --> OG9 | 7 | 0 | 2021-09-17 08:00 | 2021-09-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01081 | [8 empty] | Cure Remaining Ftgs/Piers/Grade Beams --> OG9 | 7 | 0 | 2021-11-03 08:00 | 2021-11-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01116 | [8 empty] | Cure Concrete Stair South Side ---> OG9 | 7 | 0 | 2021-12-20 08:00 | 2021-12-27 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01136 | [8 empty] | Cure First Floor Slab --> OG9 | 7 | 0 | 2021-12-27 08:00 | 2022-01-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01176 | [8 empty] | Cure 2nd Floor Slab / First Floor Walls & Col Encasements --> OG9 | 7 | 0 | 2022-02-07 08:00 | 2022-02-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01211 | [8 empty] | Cure Roof Slab and 2nd Floor Conc Pads -->OG9 | 7 | 0 | 2022-02-02 08:00 | 2022-02-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.5 | OG3-01361 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure Concrete boiler room walls --> OG3 | 7 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01421 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.1 | OG3-01441 | MLJ | OG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 7 | 7 | 2023-03-23 08:00 | 2023-03-29 17:00 | 5 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01521 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.2 | OG3-01541 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 2022-09-10 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01621 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.3 | OG3-01641 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 2022-09-10 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01721 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01741 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 7 | 0 | 2022-09-10 08:00 | 2022-09-16 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01771 | MLJ | OG3 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure slab at Curtain Wall for flood protection (West Side) --> OG3 | 7 | 0 | 2022-10-14 08:00 | 2022-10-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.5 | OG3-01816 | MLJ | OG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG3 | Cure concrete shelf around bldg perimeter --> OG3 | 7 | 0 | 2022-06-11 08:00 | 2022-06-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.5 | OG2-01361 | MLJ | OG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure Concrete boiler room walls --> OG2 | 7 | 0 | 2023-02-14 | 2023-02-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01421 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 2022-05-20 08:00 | 2022-05-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.1 | OG2-01441 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 2022-08-12 08:00 | 2022-08-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01521 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 7 | 0 | 2022-05-20 08:00 | 2022-05-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.2 | OG2-01541 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 7 | 0 | 2022-08-12 08:00 | 2022-08-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01621 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 2022-05-20 08:00 | 2022-05-26 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.3 | OG2-01641 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 2022-08-12 08:00 | 2022-08-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01721 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 7 | 0 | 2022-05-20 08:00 | 2022-05-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01741 | MLJ | OG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 7 | 0 | 2022-12-10 08:00 | 2022-12-16 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01771 | MLJ | OG2 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure slab at Curtain Wall for flood protection (West Side) --> OG2 | 7 | 7 | 2023-03-30 08:00 | 2023-04-05 17:00 | 14 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.5 | OG2-01816 | MLJ | OG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG2 | Cure concrete shelf around bldg perimeter --> OG2 | 7 | 0 | 2022-05-20 08:00 | 2022-05-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01641 | MLJ | OGW | CONCRETE | Restoration | SITE | SITE CONCRETE |  |  | Cure Retaining wall --> OG Phase 3A | 7 | 0 | 2022-10-19 08:00 | 2022-10-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01641 | MLJ | OGE | CONCRETE | Restoration | SITE | SITE CONCRETE |  |  | Cure Retaining wall --> OG Phase 4 | 7 | 0 | 2022-11-23 08:00 | 2022-11-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01041 | [8 empty] | Cure Plumbing Shafts & Ftgs Below Water Table --> OG10 | 7 | 0 | 2021-08-28 08:00 | 2021-09-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01081 | [8 empty] | Cure Remaining Ftgs/Piers/Grade Beams --> OG10 | 7 | 0 | 2021-09-28 08:00 | 2021-10-05 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01116 | [8 empty] | Cure Concrete Stair South Side ---> OG10 | 7 | 0 | 2021-11-15 08:00 | 2021-11-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01136 | [8 empty] | Cure First Floor Slab --> OG10 | 7 | 0 | 2021-11-16 08:00 | 2021-11-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01176 | [8 empty] | Cure 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> OG10 | 7 | 0 | 2022-02-11 08:00 | 2022-02-18 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01211 | [8 empty] | Cure Roof Slab and 2nd Floor Conc Pads -->OG10 | 7 | 0 | 2022-02-11 08:00 | 2022-02-18 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.5 | OG6-01361 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure Concrete boiler room walls --> OG6 | 7 | 7 | 2023-02-28 08:00 | 2023-03-06 17:00 | 41 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01421 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 7 | 7 | 2023-04-05 08:00 | 2023-04-11 17:00 | -21 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.1 | OG6-01441 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 7 | 7 | 2023-05-06 08:00 | 2023-05-12 17:00 | -39 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01521 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 0 | 2022-12-03 08:00 | 2022-12-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.2 | OG6-01541 | MLJ | OG6 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 0 | 2022-12-12 08:00 | 2022-12-19 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01621 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 0 | 2023-01-06 08:00 | 2023-01-12 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.3 | OG6-01641 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 0 | 2023-02-10 08:00 | 2023-02-16 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01721 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 7 | 7 | 2023-04-29 08:00 | 2023-05-05 17:00 | -66 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01741 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 7 | 7 | 2023-06-02 08:00 | 2023-06-08 17:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.4 | OG6-01771 | MLJ | OG6 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure slab at Curtain Wall for flood protection (West Side) --> OG6 | 7 | 7 | 2023-07-13 08:00 | 2023-07-19 17:00 | -90 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.1.EFPC.5 | OG6-01816 | MLJ | OG6 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG6 | Cure concrete shelf around bldg perimeter --> OG6 | 7 | 0 | 2022-11-16 08:00 | 2022-11-22 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.5 | OG1-01361 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure Concrete boiler room walls --> OG1 | 7 | 0 | 2023-02-14 08:00 | 2023-02-20 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01421 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 7 | 0 | 2022-05-25 13:00 | 2022-05-31 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.1 | OG1-01441 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 7 | 0 | 2022-10-18 08:00 | 2022-10-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01521 | [8 empty] | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 2022-03-11 | 2022-03-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.2 | OG1-01541 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 2022-09-08 08:00 | 2022-09-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01621 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 2022-05-25 08:00 | 2022-05-31 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.3 | OG1-01641 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 2022-09-08 08:00 | 2022-09-14 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01721 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 7 | 7 | 2023-03-24 08:00 | 2023-03-30 17:00 | 25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01741 | MLJ | OG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 7 | 7 | 2023-04-26 08:00 | 2023-05-02 17:00 | 5 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01771 | MLJ | OG1 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure slab at Curtain Wall for flood protection (West Side) --> OG1 | 7 | 7 | 2023-05-09 08:00 | 2023-05-15 17:00 | 3 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.5 | OG1-01816 | MLJ | OG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-OG1 | Cure concrete shelf around bldg perimeter --> OG1 | 7 | 0 | 2022-05-27 08:00 | 2022-06-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01641 | MLJ | S8 | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall --> S8 Phase 6 | 7 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01641 | MLJ | SGS | CONCRETE | Restoration | SITE | SITE CONCRETE |  |  | Cure Retaining wall --> SGS Phase 5 | 7 | 7 | 2023-03-08 08:00 | 2023-03-14 17:00 | -75 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01041 | [8 empty] | Cure Plumbing Shafts & Ftgs Below Water Table --> SG7 | 7 | 0 | 2021-10-10 | 2021-10-17 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01081 | [8 empty] | Cure Remaining Ftgs/Piers/Grade Beams --> SG7 | 7 | 0 | 2022-05-11 08:00 | 2022-05-17 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01116 | MLJ | SG7 | Concrete | Structure | NEW BUILDINGS | NB CONCRETE | 03-1900 | 03-1900-SG7 | Cure Concrete Stair South Side ---> SG7 | 7 | 0 | 2022-11-01 08:00 | 2022-11-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01136 | MLJ | SG7 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Cure First Floor Slab --> SG7 | 7 | 0 | 2022-06-25 08:00 | 2022-07-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01176 | MLJ | SG7 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> SG7 | 7 | 0 | 2022-09-15 08:00 | 2022-09-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01211 | MLJ | SG7 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-SG7 | Cure Roof Slab and 2nd Floor Conc Pads -->SG7 | 7 | 0 | 2022-09-15 08:00 | 2022-09-21 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.5 | SG3-01361 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure Concrete boiler room walls --> SG3 | 7 | 0 | 2022-11-25 08:00 | 2022-11-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01421 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 7 | 0 | 2022-09-08 08:00 | 2022-09-14 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01441 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 7 | 7 | 2023-03-30 08:00 | 2023-04-05 17:00 | -147 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01471 | MLJ | SG3 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure slab at Curtain Wall for flood protection (East Side) --> SG3 | 7 | 7 | 2023-05-09 08:00 | 2023-05-15 17:00 | -145 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01521 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 7 | 0 | 2023-02-20 08:00 | 2023-02-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01541 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 7 | 7 | 2023-03-30 08:00 | 2023-04-05 17:00 | -147 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01571 | MLJ | SG3 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure slab at Curtain Wall for flood protection (South Side) --> SG3 | 7 | 7 | 2023-05-09 08:00 | 2023-05-15 17:00 | -145 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01621 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 7 | 0 | 2023-02-01 08:00 | 2023-02-07 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.3 | SG3-01641 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 7 | 0 | 2023-02-13 08:00 | 2023-02-20 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01721 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 7 | 0 | 2023-01-21 08:00 | 2023-01-27 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01741 | MLJ | SG3 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 7 | 0 | 2023-02-09 08:00 | 2023-02-15 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.4 | SG3-01771 | MLJ | SG3 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure slab at Curtain Wall for flood protection (West Side) --> SG3 | 7 | 7 | 2023-04-20 08:00 | 2023-04-26 17:00 | -125 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.5 | SG3-01816 | MLJ | SG3 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG3 | Cure concrete shelf around bldg perimeter --> SG3 | 7 | 0 | 2022-10-01 08:00 | 2022-10-07 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.5 | SG1-01361 | MLJ | SG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure Concrete boiler room walls --> SG1 | 7 | 0 | 2023-01-13 08:00 | 2023-01-19 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01421 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 7 | 0 | 2022-10-18 08:00 | 2022-10-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01441 | MLJ | SG1 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 7 | 0 | 2022-11-19 08:00 | 2022-11-25 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01471 | MLJ | SG1 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure slab at Curtain Wall for flood protection (East Side) --> SG1 | 7 | 7 | 2023-03-30 08:00 | 2023-04-05 17:00 | -105 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01521 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 2022-11-19 08:00 | 2022-11-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.2 | SG1-01541 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 2022-11-18 08:00 | 2022-11-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01621 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 2022-09-08 08:00 | 2022-09-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.3 | SG1-01641 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 2022-09-17 08:00 | 2022-09-23 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01721 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 7 | 0 | 2022-10-25 08:00 | 2022-10-31 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01741 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 7 | 0 | 2022-11-18 08:00 | 2022-11-24 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01771 | MLJ | SG1 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure slab at Curtain Wall for flood protection (West Side) --> SG1 | 7 | 7 | 2023-03-30 08:00 | 2023-04-05 17:00 | -105 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.5 | SG1-01816 | MLJ | SG1 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG1 | Cure concrete shelf around bldg perimeter --> SG1 | 7 | 0 | 2022-09-07 | 2022-09-07 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.5 | SG2-01361 | MLJ | SG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure Concrete boiler room walls --> SG2 | 7 | 0 | 2023-01-21 08:00 | 2023-01-27 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01421 | MLJ | SG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 7 | 0 | 2022-10-20 08:00 | 2022-10-26 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01441 | MLJ | SG2 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 7 | 7 | 2023-03-23 08:00 | 2023-03-29 17:00 | -136 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.1 | SG2-01471 | MLJ | SG2 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure slab at Curtain Wall for flood protection (East Side) --> SG2 | 7 | 7 | 2023-05-02 08:00 | 2023-05-08 17:00 | -137 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01521 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 2022-09-07 08:00 | 2022-09-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.2 | SG2-01541 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 2022-09-16 08:00 | 2022-09-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01621 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 2022-09-07 08:00 | 2022-09-13 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.3 | SG2-01641 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 2022-09-16 08:00 | 2022-09-22 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01721 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 7 | 0 | 2022-10-28 08:00 | 2022-11-03 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01741 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 7 | 0 | 2022-11-04 08:00 | 2022-11-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01771 | MLJ | SG2 | CONCRETE |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure slab at Curtain Wall for flood protection (West Side) --> SG2 | 7 | 0 | 2022-11-04 08:00 | 2022-11-10 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.5 | SG2-01816 | MLJ | SG2 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-SG2 | Cure concrete shelf around bldg perimeter --> SG2 | 7 | 0 | 2022-08-24 08:00 | 2022-08-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.5.1 | OGP1-01621 | MLJ | OGW | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall footing --> OG Phase 2A | 7 | 0 | 2022-07-26 08:00 | 2022-08-02 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.1 | OGW-01621 | MLJ | OGW | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall footing --> OG Phase 3A | 7 | 0 | 2022-09-22 08:00 | 2022-09-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.4 | OGE-01621 | MLJ | OGE | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall footing --> OG Phase 4 | 7 | 0 | 2022-10-21 08:00 | 2022-10-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01081 | [8 empty] | Cure Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 7 | 0 | 2022-05-27 | 2022-06-03 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01116 | MLJ | S82 | Concrete | Structure | NEW BUILDINGS | NB CONCRETE | 03-1900 | 03-1900-S82 | Cure Concrete Stair South Side ---> S8 (Addition) | 7 | 7 | 2023-03-04 08:00 | 2023-03-10 17:00 | 37 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.4 | S8-01621 | MLJ | S8 | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall footing --> S8 Phase 6 | 7 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.5.4 | SGS-01621 | MLJ | SGS | CONCRETE |  |  | SITE CONCRETE |  |  | Cure Retaining wall footing --> SGS Phase 5 | 7 | 0 | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01211 | MLJ | S82 | CONCRETE |  |  | NB CONCRETE | 03-1900 | 03-1900-S82 | Cure Roof Slab and 2nd Floor Conc Pads -->S8 (Addition) | 7 | 0 | 2022-09-27 08:00 | 2022-10-04 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.5 | S8E-01361 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure Concrete boiler room walls --> S8 (Existing) | 7 | 7 | 2023-03-15 08:00 | 2023-03-21 17:00 | 26 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01421 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 2023-04-20 08:00 | 2023-04-26 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01441 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 2023-06-03 08:00 | 2023-06-09 17:00 | -165 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.1 | S8E-01471 | MLJ | S81 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 2023-07-29 08:00 | 2023-08-04 17:00 | -157 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01521 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 2023-04-20 08:00 | 2023-04-26 17:00 | -140 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01541 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 2023-06-03 08:00 | 2023-06-09 17:00 | -165 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.2 | S8E-01571 | MLJ | S81 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 2023-07-29 08:00 | 2023-08-04 17:00 | -165 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01621 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 0 | 2022-11-30 08:00 | 2022-12-07 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.3 | S8E-01641 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 0 | 2022-12-08 08:00 | 2022-12-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01721 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 7 | 0 | 2022-11-30 08:00 | 2022-12-06 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.4 | S8E-01741 | MLJ | S81 | Concrete |  |  | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 7 | 0 | 2022-12-08 08:00 | 2022-12-14 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.5.EFPC.5 | S8E-01816 | MLJ | S81 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-S81 | Cure concrete shelf around bldg perimeter --> S8 (Existing) | 7 | 7 | 2023-03-25 08:00 | 2023-03-31 17:00 | -121 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01107 | [8 empty] | Install Structural Steel Framing - 2nd Floor --> SG6 | 10 | 0 | 2021-08-11 08:00 | 2021-08-17 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01107 | [8 empty] | Install Structural Steel Framing - 2nd Floor --> OG8 | 7 | 0 | 2022-01-10 | 2022-01-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01109 | [8 empty] | Install Structural Steel Framing - 3rd Foor --> OG8 | 7 | 0 | 2022-01-17 | 2022-01-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01107 | [8 empty] | Install Structural Steel Framing - 2nd Floor --> OG9 | 10 | 0 | 2021-11-14 | 2021-11-24 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01107 | [8 empty] | Install Structural Steel Framing - 2nd Floor --> OG10 | 10 | 0 | 2022-01-14 | 2022-01-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01107 | WEIR | SG7 | STRUCTURAL STEEL | [5 empty] | Install Structural Steel Framing - 2nd Floor --> SG7 | 10 | 0 | 2022-08-08 08:00 | 2022-08-12 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01107 | WEIR | S81 | STRUCTURAL STEEL | [5 empty] | Install Structural Steel Framing - 2nd Floor --> S8 (Addition) | 10 | 0 | 2022-09-01 08:00 | 2022-09-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03015 | [8 empty] | File for Alt 2 Permit - SG-4 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03020 | [8 empty] | DOB Issue Alt 2 Permit - SG-4 | 20 | 0 | 2020-12-01 | 2020-12-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03025 | [8 empty] | File for Alt 2 Permit - SG-5 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03030 | [8 empty] | DOB Issue Alt 2 Permit - SG-5 | 20 | 0 | 2020-12-01 | 2020-12-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03035 | [8 empty] | File for Alt 2 Permit - OG-2 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03040 | [8 empty] | DOB Issue Alt 2 Permit - OG-2 | 20 | 0 | 2020-12-01 | 2020-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03045 | [8 empty] | File for Alt 2 Permit - OG-3 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03050 | [8 empty] | DOB Issue Alt 2 Permit - OG-3 | 20 | 0 | 2020-12-01 | 2021-02-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03055 | [8 empty] | File for Alt 2 Permit - OG-4 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03060 | [8 empty] | DOB Issue Alt 2 Permit - OG-4 | 20 | 0 | 2020-12-01 | 2020-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03065 | [8 empty] | File for New building Permit - OG-8 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03070 | [8 empty] | DOB Issue New building Permit - OG-8 | 20 | 0 | 2020-12-01 | 2021-02-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03075 | [8 empty] | File for New building Permit - OG-9 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03080 | [8 empty] | DOB Issue New building Permit - OG-9 | 20 | 0 | 2020-12-01 | 2021-06-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03105 | [8 empty] | File for Alt 2 Permit - OG-1 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03110 | [8 empty] | DOB Issue Alt 2 Permit - OG-1 | 20 | 0 | 2020-12-01 | 2021-02-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03115 | [8 empty] | File for Alt 2 Permit - OG-5 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03120 | [8 empty] | DOB Issue Alt 2 Permit - OG-5 | 20 | 0 | 2020-12-01 | 2021-05-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03125 | [8 empty] | File for Alt 2 Permit - OG-6 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03130 | [8 empty] | DOB Issue Alt 2 Permit - OG-6 | 20 | 0 | 2020-12-01 | 2021-06-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03135 | [8 empty] | File for New building Permit - OG-10 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03140 | [8 empty] | DOB Issue New building Permit - OG-10 | 20 | 0 | 2020-12-01 | 2021-02-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03205 | [8 empty] | File for Alt 2 Permit - SG-1 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03210 | [8 empty] | DOB Issue Alt 2 Permit - SG-1 | 20 | 0 | 2020-12-01 | 2020-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03215 | [8 empty] | File for Alt 2 Permit - SG-2 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03220 | [8 empty] | DOB Issue Alt 2 Permit - SG-2 | 20 | 0 | 2020-12-01 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03225 | [8 empty] | File for Alt 2 Permit - SG-3 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03230 | [8 empty] | DOB Issue Alt 2 Permit - SG-3 | 20 | 0 | 2020-12-01 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03235 | [8 empty] | File for New building Permit - SG-7 | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03240 | [8 empty] | DOB Issue New building Permit - SG-7 | 20 | 0 | 2020-12-01 | 2020-12-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03305 | [8 empty] | File for Alt 2 Permit - S8E | 10 | 0 | 2020-11-01 | 2020-12-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03310 | [8 empty] | DOB Issue Alt 2 Permit - S8E | 20 | 0 | 2020-12-01 | 2021-06-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03315 | [8 empty] | File for Alt 1 Permit - S8A | 10 | 0 | 2020-11-01 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03320 | [8 empty] | DOB Issue Alt 1 Permit - S8a | 20 | 0 | 2020-12-15 | 2021-05-06 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02522 |  | SG6 | [6 empty] | Notifcation to 3rd Party for Testing at SG6 | 3 | 0 | 2022-08-01 15:00 | 2022-08-23 15:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.4 | SG4-02512 |  | SG4 | [6 empty] | Notifcation to 3rd Party for Testing at SG4 | 3 | 0 | 2022-06-01 08:00 | 2022-06-01 17:00 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.4 | SG5-02512 | MLJ | SG5 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at SG5 | 3 | 3 | 2023-03-28 10:00 | 2023-03-31 10:00 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02707 | MLJ | OG8 |  | Closeout | NEW BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG8 | 3 | 3 | 2023-07-03 08:00 | 2023-07-06 17:00 | -138 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.4 | OG4-02507 | MLJ | OG4 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG4 | 3 | 3 | 2023-04-14 13:00 | 2023-04-19 12:00 | -87 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.4 | OG5-02507 |  | OG5 | [6 empty] | Notifcation to 3rd Party for Testing at OG5 | 3 | 0 | 2022-09-10 | 2022-09-10 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02507 | MLJ | OG9 |  | Closeout | NEW BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG9 | 3 | 3 | 2023-04-06 13:00 | 2023-04-11 12:00 | -90 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.4 | OG3-02507 | MLJ | OG3 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG3 | 3 | 3 | 2023-04-11 08:00 | 2023-04-13 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.4 | OG2-02507 | MLJ | OG2 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG2 | 3 | 3 | 2023-03-23 09:36 | 2023-03-28 09:36 | -87 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02507 | MLJ | OG10 |  | Closeout | NEW BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG10 | 3 | 3 | 2023-05-11 13:00 | 2023-05-16 12:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.4 | OG6-02507 | MLJ | OG6 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG6 | 3 | 3 | 2023-07-17 08:00 | 2023-07-19 17:00 | -121 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.4 | OG1-02507 | MLJ | OG1 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at OG1 | 3 | 3 | 2023-03-27 08:00 | 2023-03-29 17:00 | -26 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02607 | MLJ | SG7 |  | Closeout | NEW BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at SG7 | 3 | 3 | 2023-07-21 13:00 | 2023-07-26 12:00 | -105 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.4 | SG3-02507 | MLJ | SG3 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at SG3 | 3 | 3 | 2023-08-15 08:00 | 2023-08-17 17:00 | -126 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02517 | MLJ | S81 |  | Closeout | EXISTING BUILDINGS |  |  |  | Notifcation to 3rd Party for Testing at S8A | 3 | 3 | 2023-07-03 13:00 | 2023-07-07 12:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.1 | ABLT-SG6-01005 | ENGINEERING | SG6 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG6 | 15 | 0 | 2023-01-25 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.1 | ABLT-SG6-01010 | ENGINEERING | SG6 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG6 | 10 | 3 | 2023-02-16 | 2023-03-01 17:00 | 62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.1 | ABLT-SG6-01015 | ENGINEERING | SG6 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG6 | 15 | 15 | 2023-07-20 08:00 | 2023-08-09 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.1 | ABLT-SG6-01020 | ENGINEERING | SG6 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG6 | 10 | 10 | 2023-08-10 08:00 | 2023-08-23 17:00 | -71 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.1 | ABLT-SG6-01025 | ENGINEERING | SG6 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG6 | 15 | 0 | 2023-01-09 08:00 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.1 | ABLT-SG6-01030 | ENGINEERING | SG6 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG6 | 10 | 3 | 2023-02-16 | 2023-04-06 17:00 | 26 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.2 | ABLT-SGN-01005 | ENGINEERING | SGN |  | Engineering | SITE | ENG |  |  | Prep/Submit Site Utility As-Built Drawings - Surfside Gardens North | 15 | 0 | 2023-02-10 | 2023-02-17 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.2 | ABLT-SGN-01010 | ENGINEERING | SGN |  | Engineering | SITE | ENG |  |  | Review/Approve Site Utility As-Built Drawings - Surfside Gardens North | 10 | 3 | 2023-02-18 | 2023-03-01 17:00 | 62 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.3 | ABLT-SG4-01005 | ENGINEERING | SG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG4 | 15 | 0 | 2023-01-25 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.3 | ABLT-SG4-01010 | ENGINEERING | SG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG4 | 10 | 3 | 2023-02-16 | 2023-08-02 17:00 | -46 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.3 | ABLT-SG4-01015 | ENGINEERING | SG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG4 | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.3 | ABLT-SG4-01020 | ENGINEERING | SG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG4 | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | 10 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.3 | ABLT-SG4-01025 | ENGINEERING | SG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG4 | 15 | 0 | 2023-01-09 08:00 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.3 | ABLT-SG4-01030 | ENGINEERING | SG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG4 | 10 | 3 | 2023-02-16 | 2023-06-07 17:00 | -17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.4 | ABLT-SG5-01005 | ENGINEERING | SG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG5 | 15 | 0 | 2023-01-25 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.4 | ABLT-SG5-01010 | ENGINEERING | SG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG5 | 10 | 3 | 2023-02-16 | 2023-04-21 17:00 | 25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.4 | ABLT-SG5-01015 | ENGINEERING | SG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG5 | 15 | 15 | 2023-04-24 08:00 | 2023-05-12 17:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.4 | ABLT-SG5-01020 | ENGINEERING | SG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG5 | 10 | 10 | 2023-05-15 08:00 | 2023-05-26 17:00 | -10 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.4 | ABLT-SG5-01025 | ENGINEERING | SG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG5 | 15 | 0 | 2023-01-09 08:00 | 2023-02-15 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.1.4 | ABLT-SG5-01030 | ENGINEERING | SG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG5 | 10 | 3 | 2023-02-16 | 2023-05-16 17:00 | -2 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.2 | ABLT-OGP1-01005 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Site Utility As-Built Drawings - O'Dwyer Gardens Part 1 | 15 | 15 | 2023-12-06 08:00 | 2023-12-27 17:00 | -155 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.2 | ABLT-OGP1-01010 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Site Utility As-Built Drawings - O'Dwyer Gardens Part 1 | 10 | 10 | 2023-12-28 08:00 | 2024-01-11 17:00 | -155 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.1 | ABLT-OG8-01005 | ENGINEERING | OG8 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG8 | 15 | 15 | 2023-06-08 08:00 | 2023-06-28 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.1 | ABLT-OG8-01010 | ENGINEERING | OG8 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG8 | 10 | 10 | 2023-06-29 08:00 | 2023-07-13 17:00 | -32 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.1 | ABLT-OG8-01015 | ENGINEERING | OG8 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG8 | 15 | 15 | 2023-07-11 08:00 | 2023-07-31 17:00 | -64 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.1 | ABLT-OG8-01020 | ENGINEERING | OG8 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG8 | 10 | 10 | 2023-08-01 08:00 | 2023-08-14 17:00 | -64 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.1 | ABLT-OG8-01025 | ENGINEERING | OG8 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG8 | 15 | 15 | 2023-06-07 08:00 | 2023-06-27 17:00 | -41 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.1 | ABLT-OG8-01030 | ENGINEERING | OG8 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG8 | 10 | 10 | 2023-06-28 08:00 | 2023-07-12 17:00 | -41 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.3 | ABLT-OG4-01005 | ENGINEERING | OG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG4 | 15 | 15 | 2023-10-04 08:00 | 2023-10-25 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.3 | ABLT-OG4-01010 | ENGINEERING | OG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG4 | 10 | 10 | 2023-10-26 08:00 | 2023-11-09 17:00 | -114 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.3 | ABLT-OG4-01015 | ENGINEERING | OG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG4 | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.3 | ABLT-OG4-01020 | ENGINEERING | OG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG4 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.3 | ABLT-OG4-01025 | ENGINEERING | OG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG4 | 15 | 7 | 2023-01-09 08:00 | 2023-06-16 17:00 | -34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.3 | ABLT-OG4-01030 | ENGINEERING | OG4 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG4 | 10 | 10 | 2023-06-19 08:00 | 2023-06-30 17:00 | -34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.4 | ABLT-OG5-01005 | ENGINEERING | OG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG5 | 15 | 15 | 2024-01-25 08:00 | 2024-02-14 17:00 | -189 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.4 | ABLT-OG5-01010 | ENGINEERING | OG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG5 | 10 | 10 | 2024-02-15 08:00 | 2024-02-29 17:00 | -189 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.4 | ABLT-OG5-01015 | ENGINEERING | OG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG5 | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.4 | ABLT-OG5-01020 | ENGINEERING | OG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG5 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.4 | ABLT-OG5-01025 | ENGINEERING | OG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG5 | 15 | 7 | 2023-01-09 08:00 | 2023-11-01 17:00 | -129 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.5.4 | ABLT-OG5-01030 | ENGINEERING | OG5 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG5 | 10 | 10 | 2023-11-02 08:00 | 2023-11-17 17:00 | -129 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.2 | ABLT-OGW-01005 | ENGINEERING | OGW |  | Engineering | SITE | ENG |  |  | Prep/Submit Site Utility As-Built Drawings - O'Dwyer Gardens West | 15 | 15 | 2023-04-12 08:00 | 2023-05-02 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.2 | ABLT-OGW-01010 | ENGINEERING | OGW |  | Engineering | SITE | ENG |  |  | Review/Approve Site Utility As-Built Drawings - O'Dwyer Gardens West | 10 | 10 | 2023-05-03 08:00 | 2023-05-16 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.1 | ABLT-OG9-01005 | ENGINEERING | OG9 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG9 | 15 | 15 | 2023-03-06 08:00 | 2023-03-24 17:00 | 35 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.1 | ABLT-OG9-01010 | ENGINEERING | OG9 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG9 | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | 35 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.1 | ABLT-OG9-01015 | ENGINEERING | OG9 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG9 | 15 | 15 | 2023-04-24 08:00 | 2023-05-12 17:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.1 | ABLT-OG9-01020 | ENGINEERING | OG9 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG9 | 10 | 10 | 2023-05-15 08:00 | 2023-05-26 17:00 | -10 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.1 | ABLT-OG9-01025 | ENGINEERING | OG9 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG9 | 15 | 7 | 2023-01-09 08:00 | 2023-03-29 17:00 | 22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.1 | ABLT-OG9-01030 | ENGINEERING | OG9 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG9 | 10 | 10 | 2023-03-30 08:00 | 2023-04-12 17:00 | 22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.3 | ABLT-OG2-01005 | ENGINEERING | OG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG2 | 15 | 15 | 2023-07-31 08:00 | 2023-08-18 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.3 | ABLT-OG2-01010 | ENGINEERING | OG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG2 | 10 | 10 | 2023-08-21 08:00 | 2023-09-01 17:00 | -68 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.3 | ABLT-OG2-01015 | ENGINEERING | OG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG2 | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.3 | ABLT-OG2-01020 | ENGINEERING | OG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG2 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.3 | ABLT-OG2-01025 | ENGINEERING | OG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG2 | 15 | 7 | 2023-01-09 08:00 | 2023-05-18 17:00 | -14 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.3 | ABLT-OG2-01030 | ENGINEERING | OG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG2 | 10 | 10 | 2023-05-19 08:00 | 2023-06-02 17:00 | -14 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.4 | ABLT-OG3-01005 | ENGINEERING | OG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG3 | 15 | 15 | 2023-10-11 08:00 | 2023-11-01 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.4 | ABLT-OG3-01010 | ENGINEERING | OG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG3 | 10 | 10 | 2023-11-02 08:00 | 2023-11-17 17:00 | -119 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.4 | ABLT-OG3-01015 | ENGINEERING | OG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG3 | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.4 | ABLT-OG3-01020 | ENGINEERING | OG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG3 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.4 | ABLT-OG3-01025 | ENGINEERING | OG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG3 | 15 | 7 | 2023-01-09 08:00 | 2023-06-19 17:00 | -35 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.2.4 | ABLT-OG3-01030 | ENGINEERING | OG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG3 | 10 | 10 | 2023-06-20 08:00 | 2023-07-03 17:00 | -35 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.1 | ABLT-OG10-01005 | ENGINEERING | OG10 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG10 | 15 | 15 | 2023-02-27 08:00 | 2023-03-17 17:00 | 40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.1 | ABLT-OG10-01010 | ENGINEERING | OG10 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG10 | 10 | 10 | 2023-03-20 08:00 | 2023-03-31 17:00 | 40 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.1 | ABLT-OG10-01015 | ENGINEERING | OG10 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG10 | 15 | 15 | 2023-05-18 13:00 | 2023-06-09 12:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.1 | ABLT-OG10-01020 | ENGINEERING | OG10 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG10 | 10 | 10 | 2023-06-09 13:00 | 2023-06-23 12:00 | -29 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.1 | ABLT-OG10-01025 | ENGINEERING | OG10 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG10 | 15 | 7 | 2023-01-09 08:00 | 2023-03-23 17:00 | 26 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.1 | ABLT-OG10-01030 | ENGINEERING | OG10 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG10 | 10 | 10 | 2023-03-24 08:00 | 2023-04-06 17:00 | 26 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.2 | ABLT-OG1-01005 | ENGINEERING | OG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG1 | 15 | 15 | 2024-01-18 08:00 | 2024-02-07 17:00 | -184 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.2 | ABLT-OG1-01010 | ENGINEERING | OG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG1 | 10 | 10 | 2024-02-08 08:00 | 2024-02-22 17:00 | -184 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.2 | ABLT-OG1-01015 | ENGINEERING | OG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG1 | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.2 | ABLT-OG1-01020 | ENGINEERING | OG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG1 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.2 | ABLT-OG1-01025 | ENGINEERING | OG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG1 | 15 | 7 | 2023-01-09 08:00 | 2023-06-09 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.2 | ABLT-OG1-01030 | ENGINEERING | OG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG1 | 10 | 10 | 2023-06-12 08:00 | 2023-06-23 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.3 | ABLT-OG6-01005 | ENGINEERING | OG6 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - OG6 | 15 | 15 | 2024-02-09 08:00 | 2024-03-01 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.3 | ABLT-OG6-01010 | ENGINEERING | OG6 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - OG6 | 10 | 10 | 2024-03-04 08:00 | 2024-03-15 17:00 | -200 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.3 | ABLT-OG6-01015 | ENGINEERING | OG6 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - OG6 | 15 | 15 | 2023-07-24 08:00 | 2023-08-11 17:00 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.3 | ABLT-OG6-01020 | ENGINEERING | OG6 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - OG6 | 10 | 10 | 2023-08-14 08:00 | 2023-08-25 17:00 | -73 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.3 | ABLT-OG6-01025 | ENGINEERING | OG6 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - OG6 | 15 | 7 | 2023-01-09 08:00 | 2023-06-21 17:00 | -37 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.3 | ABLT-OG6-01030 | ENGINEERING | OG6 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - OG6 | 10 | 10 | 2023-06-22 08:00 | 2023-07-06 17:00 | -37 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.1 | ABLT-SG7-01005 | ENGINEERING | SG7 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG7 | 15 | 15 | 2023-06-21 13:00 | 2023-07-13 12:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.1 | ABLT-SG7-01010 | ENGINEERING | SG7 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG7 | 10 | 10 | 2023-07-13 13:00 | 2023-07-27 12:00 | -42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.1 | ABLT-SG7-01015 | ENGINEERING | SG7 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG7 | 15 | 15 | 2023-07-28 13:00 | 2023-08-18 12:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.1 | ABLT-SG7-01020 | ENGINEERING | SG7 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG7 | 10 | 10 | 2023-08-18 13:00 | 2023-09-01 12:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.1 | ABLT-SG7-01025 | ENGINEERING | SG7 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG7 | 15 | 15 | 2023-06-21 08:00 | 2023-07-12 17:00 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.1 | ABLT-SG7-01030 | ENGINEERING | SG7 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG7 | 10 | 10 | 2023-07-13 08:00 | 2023-07-26 17:00 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.2 | ABLT-SG1-01005 | ENGINEERING | SG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG1 | 15 | 15 | 2023-10-03 10:00 | 2023-10-25 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.2 | ABLT-SG1-01010 | ENGINEERING | SG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG1 | 10 | 10 | 2023-10-25 10:00 | 2023-11-09 10:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.2 | ABLT-SG1-01015 | ENGINEERING | SG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG1 | 15 | 15 | 2023-08-16 10:00 | 2023-09-07 10:00 | -90 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.2 | ABLT-SG1-01020 | ENGINEERING | SG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG1 | 10 | 10 | 2023-09-07 10:00 | 2023-09-21 10:00 | -90 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.2 | ABLT-SG1-01025 | ENGINEERING | SG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG1 | 15 | 7 | 2023-01-09 08:00 | 2023-08-15 17:00 | -75 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.2 | ABLT-SG1-01030 | ENGINEERING | SG1 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG1 | 10 | 10 | 2023-08-16 08:00 | 2023-08-29 17:00 | -75 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.3 | ABLT-SG2-01005 | ENGINEERING | SG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG2 | 15 | 15 | 2023-10-02 08:00 | 2023-10-23 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.3 | ABLT-SG2-01010 | ENGINEERING | SG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG2 | 10 | 10 | 2023-10-24 08:00 | 2023-11-06 17:00 | -112 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.3 | ABLT-SG2-01015 | ENGINEERING | SG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG2 | 15 | 15 | 2023-05-08 08:00 | 2023-05-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.3 | ABLT-SG2-01020 | ENGINEERING | SG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG2 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -20 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.3 | ABLT-SG2-01025 | ENGINEERING | SG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG2 | 15 | 7 | 2023-01-09 08:00 | 2023-08-21 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.3 | ABLT-SG2-01030 | ENGINEERING | SG2 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG2 | 10 | 10 | 2023-08-22 08:00 | 2023-09-05 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.4 | ABLT-SG3-01005 | ENGINEERING | SG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - SG3 | 15 | 15 | 2023-10-25 08:00 | 2023-11-16 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.4 | ABLT-SG3-01010 | ENGINEERING | SG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - SG3 | 10 | 10 | 2023-11-17 08:00 | 2023-12-01 17:00 | -128 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.4 | ABLT-SG3-01015 | ENGINEERING | SG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - SG3 | 15 | 15 | 2023-08-22 08:00 | 2023-09-12 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.4 | ABLT-SG3-01020 | ENGINEERING | SG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - SG3 | 10 | 10 | 2023-09-13 08:00 | 2023-09-26 17:00 | -94 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.4 | ABLT-SG3-01025 | ENGINEERING | SG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - SG3 | 15 | 7 | 2023-01-09 08:00 | 2023-08-09 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.4 | ABLT-SG3-01030 | ENGINEERING | SG3 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - SG3 | 10 | 10 | 2023-08-10 08:00 | 2023-08-23 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.1 | ABLT-S8A-01005 | ENGINEERING | S81 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - S8A | 15 | 15 | 2023-08-17 13:00 | 2023-09-08 12:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.1 | ABLT-S8A-01010 | ENGINEERING | S81 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - S8A | 10 | 10 | 2023-09-08 13:00 | 2023-09-22 12:00 | -82 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.1 | ABLT-S8A-01015 | ENGINEERING | S81 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - S8A | 15 | 15 | 2023-07-11 13:00 | 2023-08-01 12:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.1 | ABLT-S8A-01020 | ENGINEERING | S81 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - S8A | 10 | 10 | 2023-08-01 13:00 | 2023-08-15 12:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.1 | ABLT-S8A-01025 | ENGINEERING | S81 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - S8A | 15 | 15 | 2023-08-16 13:00 | 2023-09-07 12:00 | -91 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.1 | ABLT-S8A-01030 | ENGINEERING | S81 |  | Overhead | EXISTING BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - S8A | 10 | 10 | 2023-09-07 13:00 | 2023-09-21 12:00 | -91 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.3 | ABLT-S8E-01005 | ENGINEERING | S82 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Architectural/Civil As-Built Drawings - S8E | 15 | 15 | 2023-10-02 13:00 | 2023-10-24 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.3 | ABLT-S8E-01010 | ENGINEERING | S82 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Architectural/Civil As-Built Drawings - S8E | 10 | 10 | 2023-10-24 13:00 | 2023-11-08 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.3 | ABLT-S8E-01015 | ENGINEERING | S82 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Electrical As-Built Drawings - S8E | 15 | 15 | 2023-07-26 13:00 | 2023-08-16 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.3 | ABLT-S8E-01020 | ENGINEERING | S82 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Electrical As-Built Drawings - S8E | 10 | 10 | 2023-08-16 13:00 | 2023-08-30 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.3 | ABLT-S8E-01025 | ENGINEERING | S82 |  | Engineering | NEW BUILDINGS | ENG |  |  | Prep/Submit Mechanical As-Built Drawings - S8E | 15 | 15 | 2023-08-22 13:00 | 2023-09-13 12:00 | -95 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.3 | ABLT-S8E-01030 | ENGINEERING | S82 |  | Engineering | NEW BUILDINGS | ENG |  |  | Review/Approve Mechanical As-Built Drawings - S8E | 10 | 10 | 2023-09-13 13:00 | 2023-09-27 12:00 | -95 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.4 | ABLT-OGE-01005 | ENGINEERING | OGE |  | Engineering | SITE | ENG |  |  | Prep/Submit Site Utility As-Built Drawings - O'Dwyer Gardens East | 15 | 15 | 2023-05-24 08:00 | 2023-06-14 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.3.4 | ABLT-OGE-01010 | ENGINEERING | OGE |  | Engineering | SITE | ENG |  |  | Review/Approve Site Utility As-Built Drawings - O'Dwyer Gardens East | 10 | 10 | 2023-06-15 08:00 | 2023-06-28 17:00 | -22 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.5 | ABLT-SGS-01005 | ENGINEERING | SGS |  | Engineering | SITE | ENG |  |  | Prep/Submit Site Utility As-Built Drawings - Surfside Gardens South | 15 | 15 | 2023-09-07 08:00 | 2023-09-27 17:00 | -95 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.4.5 | ABLT-SGS-01010 | ENGINEERING | SGS |  | Engineering | SITE | ENG |  |  | Review/Approve Site Utility As-Built Drawings - Surfside Gardens South | 10 | 10 | 2023-09-28 08:00 | 2023-10-11 17:00 | -95 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.2 | ABLT-S8-01005 | ENGINEERING | S8 |  | Engineering | SITE | ENG |  |  | Prep/Submit Site Utility As-Built Drawings - Site 8 | 15 | 15 | 2023-10-12 08:00 | 2023-11-02 17:00 | -120 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.1.6.2 | ABLT-S8-01010 | ENGINEERING | S8 |  | Engineering | SITE | ENG |  |  | Review/Approve Site Utility As-Built Drawings - Site 8 | 10 | 10 | 2023-11-03 08:00 | 2023-11-20 17:00 | -120 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01005 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Spray Shower Equipment O&M Manual/Guarantees/Warranties | 30 | 30 | 2023-02-27 08:00 | 2023-04-07 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01010 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Spray Shower Equipment O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-04-10 08:00 | 2023-04-28 17:00 | -39 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02035 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Switchboards O&M Manual/Guarantees/Warranties | 80 | 20 | 2022-12-05 08:00 | 2023-03-24 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02040 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Switchboards O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02050 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Smoke/Fire Alarm System O&M Manual/Guarantees/Warranties | 80 | 80 | 2023-02-27 08:00 | 2023-06-19 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02055 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Smoke/Fire Alarm System O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-06-20 08:00 | 2023-07-11 17:00 | -71 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02070 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Power & Distribution Panels O&M Manual/Guarantees/Warranties | 80 | 20 | 2022-12-25 | 2023-03-24 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02075 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Power & Distribution Panels O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -103 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02090 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Automatic Transfer Switch O&M Manual/Guarantees/Warranties | 80 | 20 | 2022-12-26 08:00 | 2023-03-24 17:00 | -103 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02095 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Automatic Transfer Switch O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -103 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02105 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Emergency Lighting O&M Manual/Guarantees/Warranties | 80 | 20 | 2022-05-02 08:00 | 2023-03-24 17:00 | -106 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02110 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Emergency lighting O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -106 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02125 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Prep/Submit Emergency & Optional Standby Power System (incl Emer Generator) O&M Manual/Guarantees/Warranties | 80 | 20 | 2021-12-13 | 2023-03-24 17:00 | -107 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02130 | ENGINEERING | ENG |  |  | Overhead | ENG |  |  | Review/Approve Emergency & Optional Standby Power System (incl Emer Generator) O&M Manual/Guarantees/Warranties | 15 | 15 | 2023-03-27 08:00 | 2023-04-14 17:00 | -107 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06005 | [8 empty] | File for Electrical Permits - SG6 | 10 | 0 | 2020-11-18 | 2020-11-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06010 | [8 empty] | DOB Issue Electrical Permits - SG6 | 20 | 0 | 2020-11-23 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01512 | [8 empty] | Revise & Re-Submit Safety Plan | 10 | 0 | 2020-09-16 | 2020-09-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.GENRAL | 01514 | [8 empty] | Review & Approve Safety Plan | 5 | 0 | 2020-09-17 | 2020-10-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07005 | [8 empty] | File for DEP Asbestos Control Program (ACP) - SG4 | 10 | 0 | 2020-09-04 | 2020-10-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07010 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - SG4 | 20 | 0 | 2020-10-08 | 2020-10-22 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03205 | [5 empty] | ENG |  |  | Prepare Smooth Concrete Finish Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 60 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03210 | [5 empty] | ENG |  |  | Review & Approve Smooth Concrete Finish Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 60 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01000 | [8 empty] | Request CSC to Sign off Demolition Plan at OG-7 | 5 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01003 | [8 empty] | CSC Sign off Demolition Plan at OG-7 | 3 | 0 | 2021-05-25 | 2021-05-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01008 | [8 empty] | Request CSC for Pre-Demolition Inspection at OG-7 | 5 | 0 | 2021-06-14 | 2021-06-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01010 | [8 empty] | CSC Pre-Demolition Inspection at OG-7 | 3 | 0 | 2021-06-17 | 2021-06-18 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03220 | [5 empty] | ENG |  |  | Prepare Architectural Concrete Finish Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 60 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03225 | [5 empty] | ENG |  |  | Review & Approve Architectural Concrete Finish Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 60 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03230 | [5 empty] | ENG |  |  | Prepare Textured Concrete for Exterior Pavements Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | -7 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03235 | [5 empty] | ENG |  |  | Review & Approve Textured Concrete for Exterior Pavements Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | -7 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03240 | [5 empty] | ENG |  |  | Prepare Self Consolidating Concrete Mock-up | 2 | 0 | 2022-03-15 | 2022-03-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03245 | [5 empty] | ENG |  |  | Review & Approve Self Consolidating Concrete Mock-up | 3 | 0 | 2022-03-16 | 2022-03-16 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03250 | [5 empty] | ENG |  |  | Prepare Floor Concrete Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 45 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 3 | 03255 | [5 empty] | ENG |  |  | Review & Approve Floor Concrete Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 45 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03260 | [5 empty] | ENG |  |  | Prepare Surface Preparation and Repair Work Mock-up | 2 | 0 | 2022-08-01 | 2022-08-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 3 | 03265 | [5 empty] | ENG |  |  | Review & Approve Surface Preparation and Repair Work Mock-up | 3 | 0 | 2022-08-02 | 2022-08-02 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04205 | [8 empty] | Prepare Masonry Sample Panels (A) Mock-up | 2 | 0 | 2022-03-25 08:00 | 2022-03-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04210 | [8 empty] | Review & Approve Masonry Sample Panels (A) Mock-up | 3 | 0 | 2022-04-01 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04220 | [8 empty] | Prepare Masonry Sample Panels (B) Mock-up | 2 | 0 | 2022-03-25 | 2022-03-28 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04225 | [8 empty] | Review & Approve Masonry Sample Panels (B) Mock-up | 3 | 0 | 2022-04-01 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04230 | [5 empty] | ENG |  |  | Prepare Masonry Sample Cleaning Procedure Mock-up | 2 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 4 | 04235 | [5 empty] | ENG |  |  | Review & Approve Masonry Sample Cleaning Procedure Mock-up | 3 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05805 | [5 empty] | ENG |  |  | Prepare Railing Form and Finish Mock-ups | 2 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.div. 5 | 05810 | [5 empty] | ENG |  |  | Review & Approve Railing Form and Finish Mock-ups | 3 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07405 | [8 empty] | Prepare Typical Waterproofing Mock-up | 2 | 0 | 2022-02-16 | 2022-02-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07410 | [8 empty] | Review & Approve Typical Waterproofing Mock-up | 3 | 0 | 2022-02-18 | 2022-02-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07420 | [8 empty] | Prepare Crystalline Waterproofing Mock-up | 2 | 0 | 2022-02-16 | 2022-02-16 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07425 | [8 empty] | Review & Approve Crystalline Waterproofing Mock-up | 3 | 0 | 2022-02-18 | 2022-02-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07430 | [5 empty] | ENG |  |  | Prepare Air Barrier Mock-up | 2 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07435 | [5 empty] | ENG |  |  | Review & Approve Air Barrier Mock-up | 3 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07440 | [5 empty] | ENG |  |  | Prepare Roof Mock-up | 2 | 0 | 2022-07-26 08:00 | 2022-08-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 7 | 07445 | [5 empty] | ENG |  |  | Review & Approve Roof Mock-up | 3 | 0 | 2022-08-02 | 2022-09-22 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 7 | 07450 | [5 empty] | ENG |  |  | Prepare Sealant Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 16 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 7 | 07455 | [5 empty] | ENG |  |  | Review & Approve Sealant Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 16 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 9 | 09305 | [5 empty] | ENG |  |  | Prepare Cement Plastering Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 33 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 9 | 09310 | [5 empty] | ENG |  |  | Review & Approve Cement Plastering Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 33 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09320 | [5 empty] | ENG |  |  | Prepare Gypsum Board Mock-up | 2 | 0 | 2022-07-13 | 2022-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09325 | [5 empty] | ENG |  |  | Review & Approve Gypsum Board Mock-up | 3 | 0 | 2022-07-18 | 2022-09-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09330 | [5 empty] | ENG |  |  | Prepare Tiling Mock-up | 2 | 0 | 2022-11-21 | 2022-12-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09335 | [5 empty] | ENG |  |  | Review & Approve Tiling Mock-up | 3 | 0 | 2022-12-06 | 2022-12-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09340 | [5 empty] | ENG |  |  | Prepare Painting Mock-up | 2 | 0 | 2022-07-01 | 2022-07-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 9 | 09345 | [5 empty] | ENG |  |  | Review & Approve Painting Mock-up | 3 | 0 | 2022-07-16 | 2022-11-07 |  | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32805 | [5 empty] | ENG |  |  | Prepare Porous Concrete Pavement Test Panel Mock-up | 2 | 2 | 2022-09-26 | 2023-02-28 17:00 | 8 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 32 | 32810 | [5 empty] | ENG |  |  | Review & Approve Porous Concrete Pavement Test Panel Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 8 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32820 | [5 empty] | ENG |  |  | Prepare Integrally Colored Concrete Mock-up/Field Samples | 2 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 32 | 32825 | [5 empty] | ENG |  |  | Review & Approve Integrally Colored Concrete Mock-up/Field Samples | 3 | 0 | 2022-03-25 | 2022-03-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01072 | [8 empty] | Waterproof/Insulation Below Slab ----> OG8 | 5 | 0 | 2021-09-20 | 2022-02-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01072 | [8 empty] | Waterproof/Insulation Below Slab ----> SG6 | 5 | 0 | 2021-06-28 | 2021-07-02 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01072 | [8 empty] | Waterproof/Insulation Below Slab ----> OG9 | 5 | 0 | 2021-10-22 08:00 | 2021-12-14 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01072 | [8 empty] | Waterproof/Insulation Below Slab ----> OG10 | 5 | 0 | 2021-11-12 08:00 | 2021-11-14 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01072 | [8 empty] | Waterproof/Insulation Below Slab ----> SG7 | 5 | 0 | 2022-06-14 | 2022-06-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01072 |  | S82 | WATERPROOFING | [5 empty] | Waterproof/Insulation Below Slab ----> S8 (Addition) | 5 | 0 | 2022-07-07 | 2022-07-08 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.1 | SG1-01485 | MLJ | SG1 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (East Side) --> SG1 | 1 | 1 | 2023-04-12 08:00 | 2023-04-12 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.4.EFPC.4 | SG1-01785 | MLJ | SG1 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> SG1 | 1 | 1 | 2023-04-12 08:00 | 2023-04-12 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.1.EFPC.4 | SG2-01785 | MLJ | SG2 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> SG2 | 1 | 1 | 2023-02-27 08:00 | 2023-02-27 17:00 | -39 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.2 | SG3-01585 | MLJ | SG3 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (South Side) --> SG3 | 1 | 1 | 2023-05-22 08:00 | 2023-05-22 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.5.EFPC.1 | SG3-01485 | MLJ | SG3 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (East Side) --> SG3 | 1 | 1 | 2023-05-22 08:00 | 2023-05-22 17:00 | -99 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.1.EFPC.4 | OG1-01785 | MLJ | OG1 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> OG1 | 1 | 1 | 2023-05-16 08:00 | 2023-05-16 17:00 | 3 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.5.EFPC.4 | OG2-01785 | MLJ | OG2 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> OG2 | 1 | 1 | 2023-04-12 08:00 | 2023-04-12 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.5.EFPC.4 | OG3-01785 | MLJ | OG3 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> OG3 | 1 | 1 | 2023-02-27 08:00 | 2023-02-27 17:00 | 42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.5.EFPC.2 | OG5-01585 | MLJ | OG5 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (South Side) --> OG5 | 1 | 1 | 2023-02-27 08:00 | 2023-02-27 17:00 | 42 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01585 | MLJ | OG4 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (South Side) --> OG4 | 1 | 1 | 2023-04-25 08:00 | 2023-04-25 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.1 | SG4-01485 | MLJ | SG4 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (East Side) --> SG4 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.2 | SG4-01585 | MLJ | SG4 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (South Side) --> SG4 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.3 | SG4-01685 | MLJ | SG4 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (North Side) --> SG4 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.5.EFPC.4 | SG4-01785 | MLJ | SG4 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> SG4 | 1 | 1 | 2023-04-25 08:00 | 2023-04-25 17:00 | 8 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.1 | SG5-01485 | MLJ | SG5 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (East Side) --> SG5 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.2 | SG5-01585 | MLJ | SG5 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (South Side) --> SG5 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.3 | SG5-01685 | MLJ | SG5 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (North Side) --> SG5 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.EFPC.4 | SG5-01785 | MLJ | SG5 | Aquafence | Exterior | EXISTING BUILDINGS | AQUAFENCE |  |  | Install Aquafence (West Side) --> SG5 | 1 | 1 | 2023-03-06 08:00 | 2023-03-06 17:00 | 44 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 10 | 10045 | [5 empty] | ENG |  |  | Prepare Aquafence/Floodbreak Mock-up | 2 | 2 | 2023-02-27 08:00 | 2023-02-28 17:00 | 44 | 0
Not Started |  | CI NYCHA Update #20.Procurement.Div. 10 | 10050 | [5 empty] | ENG |  |  | Review & Approve Aquafence/Floodbreak Mock-up | 3 | 3 | 2023-03-01 08:00 | 2023-03-03 17:00 | 44 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01560 | MLJ | OG4 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG4 | Form for slab at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 2023-03-23 08:00 | 2023-03-28 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01565 | TONAGE | OG4 | REBAR | Exterior | EXISTING BUILDINGS |  |  |  | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> OG4 | 6 | 6 | 2023-03-29 08:00 | 2023-04-05 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01570 | MLJ | OG4 | Concrete | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG4 | Pour slab at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 2023-04-06 08:00 | 2023-04-11 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01575 | MLJ | OG4 | Formwork | Exterior | EXISTING BUILDINGS | EB FORMWORK | 03-1100 | 03-1100-OG4 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> OG4 | 2 | 2 | 2023-04-12 08:00 | 2023-04-13 17:00 | 4 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01580 | MLJ | OG4 | BACKFILL | Exterior | EXISTING BUILDINGS | BACKFILL EB | 31-1100 | 31-1100-OG4 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 2023-04-19 08:00 | 2023-04-24 17:00 | 1 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.5.EFPC.2 | OG4-01571 | MLJ | OG4 | CONCRETE | Exterior | EXISTING BUILDINGS | EB CONCRETE | 03-2100 | 03-2100-OG4 | Cure slab at Curtain Wall for flood protection (South Side) --> OG4 | 7 | 7 | 2023-04-12 08:00 | 2023-04-18 17:00 | 1 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.1 | SURV-SGN-P-01005 | [8 empty] | Conduct Plumbing Site Survey - Surfside Gardens North (SG-4, SG-5, SG-6) - N/A | 20 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.1 | SURV-SGN-M-01005 | [8 empty] | Conduct Mechanical Site Survey - Surfside Gardens North (SG-4, SG-5, SG-6) | 20 | 0 | 2020-12-21 | 2021-01-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.2 | SURV-OGP1-P-01005 | [8 empty] | Conduct Plumbing Site Survey - Odwyer Gardens - Part 1 (OG-4 & OG-5) - N/A | 20 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.2 | SURV-OGP1-M-01005 | [8 empty] | Conduct Mechanical Site Survey - Odwyer Gardens - Part 1 (OG-4 & OG-5) | 20 | 0 | 2021-01-22 | 2021-01-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.1 | SURV-OGW-P-01005 | [8 empty] | Conduct Plumbing Site Survey - O'Dwyer Garden - West (OG-2, OG-3 & OG-9) - N/A | 20 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.1 | SURV-OGW-M-01005 | [8 empty] | Conduct Mechanical Site Survey - O'Dwyer Garden - West (OG-2, OG-3 & OG-9) | 20 | 0 | 2021-01-22 | 2021-01-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.1 | SURV-OGE-P-01005 | [8 empty] | Conduct Plumbing Site Survey - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) - N/A | 20 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.1 | SURV-OGE-M-01005 | [8 empty] | Conduct Mechanical Site Survey - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) | 20 | 0 | 2021-01-22 | 2021-01-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.1 | SURV-SGS-P-01005 | [8 empty] | Conduct Plumbing Site Survey - Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) - N/A | 20 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.1 | SURV-SGS-M-01005 | [8 empty] | Conduct Mechanical Site Survey - Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | 20 | 0 | 2021-01-22 | 2021-01-29 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.4 | SURV-S8-P-01005 | [8 empty] | Conduct Plumbing Site Survey - Site 8 (S8 & S8-1) - N/A | 20 | 0 | 2021-01-04 | 2021-01-04 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.4 | SURV-S8-M-01005 | [8 empty] | Conduct Mechanical Site Survey - Site 8 (S8 & S8-1) | 20 | 0 | 2021-01-22 | 2021-01-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24335 | [8 empty] | Release Fin Tube Boilers | 1 | 0 | 2022-01-03 | 2022-01-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 10 | 10085 | [8 empty] | Release Flood Control System - Aquafence/Floodbreak | 0 | 0 | 2021-09-30 |  |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01706 | MLJ | OGW | BACKFILL | Restoration | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-OGW | Backfill Trench for ashpalt repairs (Lot near OG5) --> OG Phase 4 | 5 | 5 | 2023-05-08 08:00 | 2023-05-12 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01707 | CITYWIDE | OGE | ASPHALT | Restoration | SITE |  |  |  | Asphalt Repairs (Lot near OG5) --> OG Phase 4 | 5 | 5 | 2023-05-15 08:00 | 2023-05-19 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01708 | MLJ | OGE | Excavation | Restoration | SITE | ASHPALT |  |  | Excavate & Backfill for Ashpalt (Lot near OG10) --> OG Phase 4 | 15 | 15 | 2023-05-22 08:00 | 2023-06-12 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.5 | OGE-01709 | CITYWIDE | OGE | ASPHALT | Restoration | SITE |  |  |  | Asphalt and Linemarking (Lot near OG10) --> OG Phase 4 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -25 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01708 | MLJ | OGW | Excavation | Restoration | SITE | ASHPALT |  |  | Excavate & Backfill for Ashpalt --> OG Phase 3A | 15 | 15 | 2023-12-06 08:00 | 2023-12-27 17:00 | -160 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.5 | OGW-01709 | CITYWIDE | OGW | ASPHALT | Restoration | SITE |  |  |  | Asphalt and Linemarking --> OG Phase 3A | 10 | 10 | 2023-12-28 08:00 | 2024-01-11 17:00 | -160 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01708 | MLJ | S8 | Excavation | Restoration | SITE | ASHPALT |  |  | Excavate & Backfill for Ashpalt --> S8 Phase 6 | 15 | 15 | 2023-08-15 08:00 | 2023-09-05 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.5 | S8-01709 | CITYWIDE | S8 | ASPHALT | Restoration | SITE |  |  |  | Asphalt and Linemarking --> S8 Phase 6 | 10 | 10 | 2023-09-06 08:00 | 2023-09-19 17:00 | -94 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01005 | MLJ | OH |  |  | Overhead |  |  |  | Project Management | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01166 | [8 empty] | Cure Concrete Pads 1st Floor --> SG6 | 7 | 0 | 2021-10-17 | 2021-10-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01166 | [8 empty] | Cure Concrete Pads 1st Floor --> OG8 | 7 | 0 | 2022-04-02 08:00 | 2022-04-09 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01166 | [8 empty] | Cure Concrete Pads 1st Floor --> OG9 - N/A | 7 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01166 | [8 empty] | Cure Concrete Pads 1st Floor --> OG10 - N/A | 7 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01166 | [8 empty] | Cure Concrete Pads 1st Floor --> SG7 - N/A | 7 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.7 | S8A-01166 | [8 empty] | Cure Concrete Pads 1st Floor --> S8 (Addition) - N/A | 7 | 0 | 2020-12-25 | 2020-12-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.Mob | MOBE-01010 | MLJ | OH | [6 empty] | Project Surveying | 333 | 0 | 2020-07-13 17:00 | 2022-11-01 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.Mob | MOBE-01015 | MLJ | OH |  |  | Overhead |  |  |  | Project Engineering | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01010 | MLJ | OH |  |  | Overhead |  |  |  | CPM - Monthly Updates | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01015 | MLJ | OH |  |  | Overhead |  |  |  | Field Office - Rent, Maintenance and Supplies | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01020 | MLJ | OH |  |  | Overhead |  |  |  | Yard - Maintenance | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01025 | MLJ | OH |  |  | Overhead |  |  |  | Progress Photos | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01030 | [8 empty] | Equipment Support for Site - SGN | 0 | 0 | 2021-05-25 | 2022-01-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01035 | MLJ | SGS | [6 empty] | Equipment Support for Site - SGS | 60 | 0 | 2022-01-01 | 2022-08-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01040 | MLJ | OGE | [6 empty] | Equipment Support for Site - OGE | 209 | 0 | 2022-03-02 | 2023-01-10 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01045 | [8 empty] | Equipment Support for Site - OGW | 1 | 0 | 2021-08-02 17:00 | 2022-03-16 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01050 | MLJ | S8 |  | Utilities | SITE |  |  |  | Equipment Support for Site - S8 | 74 | 0 | 2022-05-11 | 2023-02-27 08:00 | -112 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01060 | WELKIN | OH |  |  | Overhead |  |  |  | HVAC Project Management/Site Supervision | 718 | 293 | 2020-07-13 17:00 | 2024-04-24 17:00 | -228 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.6 | PAY-01065 | WELKIN | OH |  |  | Overhead |  |  |  | HVAC Scheduling | 639 | 97 | 2020-07-13 17:00 | 2023-07-13 12:00 | -104 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02501 | NATIONAL GRID | SG6 |  | Utilities | NEW BUILDINGS |  |  |  | National Grid to Install Meter - SG6 | 1 | 1 | 2023-03-02 08:00 | 2023-03-02 17:00 | 15 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02701 | NATIONAL GRID | OG8 |  | Utilities | NEW BUILDINGS |  |  |  | National Grid to Install Meter - OG8 | 1 | 1 | 2023-07-03 08:00 | 2023-07-03 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02501 | NATIONAL GRID | OG9 |  | Utilities | NEW BUILDINGS |  |  |  | National Grid to Install Meter - OG9 | 1 | 1 | 2023-04-06 13:00 | 2023-04-07 12:00 | 16 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02501 | NATIONAL GRID | OG10 |  | Utilities | NEW BUILDINGS |  |  |  | National Grid to Install Meter - OG10 | 1 | 1 | 2023-05-11 13:00 | 2023-05-12 12:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02601 | NATIONAL GRID | SG7 |  | Utilities | NEW BUILDINGS |  |  |  | National Grid to Install Meter - SG7 | 1 | 1 | 2023-07-20 13:00 | 2023-07-21 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02501 | NATIONAL GRID | S82 |  | Utilities | NEW BUILDINGS |  |  |  | National Grid to Install Meter - S8A | 1 | 1 | 2023-08-01 13:00 | 2023-08-02 12:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01105 | MLJ | SG6 |  | Closeout | NEW BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG6 | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01110 | MLJ | SG4 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG4 | 10 | 10 | 2023-06-08 08:00 | 2023-06-21 17:00 | -17 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01115 | MLJ | SG5 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG5 | 10 | 10 | 2023-05-17 08:00 | 2023-05-31 17:00 | -2 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01120 | MLJ | OGE |  | Closeout | SITE | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG8 | 10 | 10 | 2023-07-13 08:00 | 2023-07-26 17:00 | -41 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01125 | MLJ | OG4 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG4 | 10 | 10 | 2023-07-03 08:00 | 2023-07-17 17:00 | -34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01130 | MLJ | OG5 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG5 | 10 | 10 | 2023-11-20 08:00 | 2023-12-04 17:00 | -129 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01135 | MLJ | OG9 |  | Closeout | NEW BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG9 | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01140 | MLJ | OG2 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG2 | 10 | 10 | 2023-06-05 08:00 | 2023-06-16 17:00 | -14 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01145 | MLJ | OG3 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG3 | 10 | 10 | 2023-07-05 08:00 | 2023-07-18 17:00 | -35 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01150 | MLJ | OG10 |  | Closeout | NEW BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG10 | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01155 | MLJ | OG1 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG1 | 10 | 10 | 2023-06-26 08:00 | 2023-07-10 17:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01160 | MLJ | OG6 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG6 | 10 | 10 | 2023-07-07 08:00 | 2023-07-20 17:00 | -37 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01165 | MLJ | SG7 |  | Closeout | NEW BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG7 | 10 | 10 | 2023-07-27 08:00 | 2023-08-09 17:00 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01170 | MLJ | SG1 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG1 | 10 | 10 | 2023-08-30 08:00 | 2023-09-13 17:00 | -75 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01175 | MLJ | SG2 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG2 | 10 | 10 | 2023-09-06 08:00 | 2023-09-19 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01180 | MLJ | SG3 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG3 | 10 | 10 | 2023-08-24 08:00 | 2023-09-07 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01185 | MLJ | S81 |  | Engineering | EXISTING BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - S8A | 10 | 10 | 2023-09-21 13:00 | 2023-10-05 12:00 | -91 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.1 | O&M-01190 | MLJ | S82 |  | Closeout | NEW BUILDINGS | PLAYGROUND |  |  | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - S8E | 10 | 10 | 2023-09-27 13:00 | 2023-10-11 12:00 | -95 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02205 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG6 | 10 | 10 | 2023-08-24 08:00 | 2023-09-07 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02210 | FIVE STAR | SG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG4 | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | 10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02215 | FIVE STAR | SG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG5 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02220 | FIVE STAR | OGE |  | Utilities | SITE |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG8 | 10 | 10 | 2023-08-15 08:00 | 2023-08-28 17:00 | -64 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02225 | FIVE STAR | OG4 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG4 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02230 | FIVE STAR | OG5 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG5 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02235 | FIVE STAR | OG9 |  | Interior | NEW BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG9 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02240 | FIVE STAR | OG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG2 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02245 | FIVE STAR | OG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG3 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02250 | FIVE STAR | OG10 |  | Interior | NEW BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG10 | 10 | 10 | 2023-06-23 13:00 | 2023-07-10 12:00 | -29 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02255 | FIVE STAR | OG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG1 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02260 | FIVE STAR | OG6 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG6 | 10 | 10 | 2023-08-28 08:00 | 2023-09-11 17:00 | -73 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02265 | FIVE STAR | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG7 | 10 | 10 | 2023-09-01 13:00 | 2023-09-18 12:00 | -78 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02270 | FIVE STAR | SG1 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG1 | 10 | 10 | 2023-09-21 10:00 | 2023-10-05 10:00 | -90 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02275 | FIVE STAR | SG2 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG2 | 10 | 10 | 2023-06-13 08:00 | 2023-06-26 17:00 | -20 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02280 | FIVE STAR | SG3 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG3 | 10 | 10 | 2023-09-27 08:00 | 2023-10-10 17:00 | -94 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02285 | FIVE STAR | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - S8A | 10 | 10 | 2023-08-15 13:00 | 2023-08-29 12:00 | -65 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.7.2.2 | O&M-02290 | FIVE STAR | S82 |  | Interior | NEW BUILDINGS |  |  |  | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - S8E | 10 | 10 | 2023-08-30 13:00 | 2023-09-14 12:00 | -76 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-04000 | [8 empty] | NYCHA Provide Information for Dewatering Permit (Indemnity Letter) | 42 | 0 | 2020-09-23 | 2020-11-25 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06015 | [8 empty] | File for Electrical Permits - SG4 | 10 | 0 | 2021-01-26 | 2021-02-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06020 | [8 empty] | DOB Issue Electrical Permits - SG4 | 20 | 0 | 2021-02-01 | 2021-02-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06025 | [8 empty] | File for Electrical Permits - SG-5 | 10 | 0 | 2021-01-26 | 2021-02-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06030 | [8 empty] | DOB Issue Electrical Permits - SG-5 | 20 | 0 | 2021-02-01 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06050 | [8 empty] | File for Electrical Permits - OG-2 | 10 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06055 | [8 empty] | DOB Issue Electrical Permits - OG-2 | 20 | 0 | 2021-02-01 | 2021-02-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06060 | [8 empty] | File for Electrical Permits - OG-3 | 10 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06065 | [8 empty] | DOB Issue Electrical Permits - OG-3 | 20 | 0 | 2021-02-01 | 2021-02-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06075 | [8 empty] | File for Electrical Permits - OG-4 | 10 | 0 | 2021-01-25 | 2021-02-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06080 | [8 empty] | DOB Issue Electrical Permits - OG-4 | 20 | 0 | 2021-02-01 | 2021-02-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06085 | [8 empty] | File for Electrical Permits - OG-8 | 10 | 0 | 2021-01-25 | 2021-02-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06090 | [8 empty] | DOB Issue Electrical Permits - OG-8 | 20 | 0 | 2021-02-03 | 2021-02-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06095 | [8 empty] | File for Electrical Permits - OG-9 | 10 | 0 | 2021-02-01 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06100 | [8 empty] | DOB Issue Electrical Permits - OG-9 | 20 | 0 | 2021-02-08 | 2021-02-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06105 | [8 empty] | File for Electrical Permits - OG-1 | 10 | 0 | 2021-02-01 | 2021-02-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06110 | [8 empty] | DOB Issue Electrical Permits - OG-1 | 20 | 0 | 2021-02-08 | 2021-02-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06120 | [8 empty] | File for Electrical Permits - OG-5 | 10 | 0 | 2021-02-01 | 2021-02-03 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06125 | [8 empty] | DOB Issue Electrical Permits - OG-5 | 20 | 0 | 2021-02-03 | 2021-02-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06130 | [8 empty] | File for Electrical Permits - OG-6 | 10 | 0 | 2021-03-01 | 2021-03-05 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06135 | [8 empty] | DOB Issue Electrical Permits - OG-6 | 20 | 0 | 2021-03-05 | 2021-03-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06140 | [8 empty] | File for Electrical Permits - OG-10 | 10 | 0 | 2021-03-15 | 2021-03-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06145 | [8 empty] | DOB Issue Electrical Permits - OG-10 | 20 | 0 | 2021-03-22 | 2021-03-29 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06150 | [8 empty] | File for Electrical Permits - SG-1 | 10 | 0 | 2021-04-05 | 2021-04-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06155 | [8 empty] | DOB Issue Electrical Permits - SG-1 | 20 | 0 | 2021-04-09 | 2021-04-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06160 | [8 empty] | File for Electrical Permits - SG-2 | 10 | 0 | 2021-04-05 | 2021-04-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06165 | [8 empty] | DOB Issue Electrical Permits - SG-2 | 20 | 0 | 2021-04-08 08:00 | 2021-04-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06170 | [8 empty] | File for Electrical Permits - SG-3 | 10 | 0 | 2021-04-05 | 2021-04-09 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06175 | [8 empty] | DOB Issue Electrical Permits - SG-3 | 20 | 0 | 2021-04-12 | 2021-04-12 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06180 | [8 empty] | File for Electrical Permits - SG-7 | 10 | 0 | 2021-04-12 | 2021-04-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06185 | [8 empty] | DOB Issue Electrical Permits - SG-7 | 20 | 0 | 2021-04-08 08:00 | 2021-04-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06190 | [8 empty] | File for Electrical Permits - S8E | 10 | 0 | 2021-05-25 08:00 | 2021-06-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06195 | [8 empty] | DOB Issue Electrical Permits - S8E | 20 | 0 | 2021-06-17 | 2021-06-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06205 | [8 empty] | File for Electrical Permits - S8A | 10 | 0 | 2021-05-25 08:00 | 2021-06-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-06210 | [8 empty] | DOB Issue Electrical Permits - S8A | 20 | 0 | 2021-06-17 | 2021-07-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05505 | [8 empty] | File for Temporary Power Permits - Phase 1 | 10 | 0 | 2020-11-18 | 2020-11-20 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05510 | [8 empty] | DOB Issue Temporary Power Permits - Phase 1 | 20 | 0 | 2020-11-23 | 2020-12-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05550 | [8 empty] | File for Temporary Power Permits - Remaining Phases | 10 | 0 | 2021-02-01 | 2021-02-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05555 | [8 empty] | DOB Issue Temporary Power Permits - Remaining Phases | 5 | 0 | 2021-02-26 | 2021-02-26 |  | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.1 | SG6-BOILER |  | SG6 | [6 empty] | Boiler Commissioned - SG6 | 0 | 0 |  | 2023-05-11 17:00 | -25 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.1 | SG6-GENERATOR |  | SG6 | [6 empty] | Generator/Switch Gear Commissioned - SG6 | 0 | 0 |  | 2023-04-20 17:00 | -10 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.1 | SG6-HVAC |  | SG6 | [6 empty] | HVAC Commissioned - SG6 | 0 | 0 |  | 2023-03-14 17:00 | 17 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.1 | SG6-FA |  | SG6 | [6 empty] | Fire Alarm System Commissioned - SG6 | 0 | 0 |  | 2023-07-18 17:00 | -71 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.1 | SG6-GAS |  | SG6 | [6 empty] | DOB Sign-off for Gas Work - SG6 | 0 | 0 |  | 2023-03-16 17:00 | 15 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.2 | SG4-GENERATOR |  | SG4 | [6 empty] | Generator/Switch Gear Commissioned - SG4 | 0 | 0 |  | 2023-04-27 17:00 | 11 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.2 | SG4-HVAC |  | SG4 | [6 empty] | HVAC Commissioned - SG4 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.2 | SG4-FA |  | SG4 | [6 empty] | Fire Alarm System Commissioned - SG4 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.3 | SG5-GENERATOR |  | SG5 | [6 empty] | Generator/Switch Gear Commissioned - SG5 | 0 | 0 |  | 2023-05-16 17:00 | -2 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.3 | SG5-HVAC |  | SG5 | [6 empty] | HVAC Commissioned - SG5 | 0 | 0 |  | 2023-06-29 17:00 | -33 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.3 | SG5-FA |  | SG5 | [6 empty] | Fire Alarm System Commissioned - SG5 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.4 | OG8-BOILER |  | OG8 | [6 empty] | Boiler Commissioned - OG8 | 0 | 0 |  | 2023-08-11 17:00 | -63 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.4 | OG8-GENERATOR |  | OG8 | [6 empty] | Generator/Switch Gear Commissioned - OG8 | 0 | 0 |  | 2023-09-05 17:00 | -79 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.4 | OG8-HVAC |  | OG8 | [6 empty] | HVAC Commissioned - OG8 | 0 | 0 |  | 2023-09-05 17:00 | -79 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.4 | OG8-FA |  | OG8 | [6 empty] | Fire Alarm System Commissioned - OG8 | 0 | 0 |  | 2023-07-25 17:00 | -50 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.4 | OG8-GAS |  | OG8 | [6 empty] | DOB Sign-off for Gas Work - OG8 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.5 | OG4-GENERATOR |  | OG4 | [6 empty] | Generator/Switch Gear Commissioned - OG4 | 0 | 0 |  | 2023-07-25 17:00 | -50 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.5 | OG4-HVAC |  | OG4 | [6 empty] | HVAC Commissioned - OG4 | 0 | 0 |  | 2023-09-07 17:00 | -81 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.5 | OG4-FA |  | OG4 | [6 empty] | Fire Alarm System Commissioned - OG4 | 0 | 0 |  | 2023-08-01 17:00 | -55 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.6 | OG5-GENERATOR |  | OG5 | [6 empty] | Generator/Switch Gear Commissioned - OG5 | 0 | 0 |  | 2023-07-31 17:00 | -54 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.6 | OG5-HVAC |  | OG5 | [6 empty] | HVAC Commissioned - OG5 | 0 | 0 |  | 2023-12-28 17:00 | -156 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.6 | OG5-FA |  | OG5 | [6 empty] | Fire Alarm System Commissioned - OG5 | 0 | 0 |  | 2023-08-07 17:00 | -59 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.7 | OG9-GENERATOR |  | OG9 | [6 empty] | Generator/Switch Gear Commissioned - OG9 | 0 | 0 |  | 2023-10-20 17:00 | -111 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.7 | OG9-HVAC |  | OG9 | [6 empty] | HVAC Commissioned - OG9 | 0 | 0 |  | 2023-10-20 17:00 | -111 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.7 | OG9-FA |  | OG9 | [6 empty] | Fire Alarm System Commissioned - OG9 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.7 | OG9-GAS |  | OG9 | [6 empty] | DOB Sign-off for Gas Work - OG9 | 0 | 0 |  | 2023-04-21 12:00 | 16 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.8 | OG3-GENERATOR |  | OG3 | [6 empty] | Generator/Switch Gear Commissioned - OG3 | 0 | 0 |  | 2023-05-05 17:00 | 5 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.8 | OG3-HVAC |  | OG3 | [6 empty] | HVAC Commissioned - OG3 | 0 | 0 |  | 2023-09-28 17:00 | -96 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.8 | OG3-FA |  | OG3 | [6 empty] | Fire Alarm System Commissioned - OG3 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.9 | OG2-GENERATOR |  | OG2 | [6 empty] | Generator/Switch Gear Commissioned - OG2 | 0 | 0 |  | 2023-05-15 17:00 | -1 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.9 | OG2-HVAC |  | OG2 | [6 empty] | HVAC Commissioned - OG2 | 0 | 0 |  | 2023-07-03 17:00 | -35 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.9 | OG2-FA |  | OG2 | [6 empty] | Fire Alarm System Commissioned - OG2 | 0 | 0 |  | 2023-07-18 17:00 | -45 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.10 | OG10-GENERATOR |  | OG10 | [6 empty] | Generator/Switch Gear Commissioned - OG10 | 0 | 0 |  | 2023-05-24 12:00 | -8 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.10 | OG10-HVAC |  | OG10 | [6 empty] | HVAC Commissioned - OG10 | 0 | 0 |  | 2024-01-19 17:00 | -171 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.10 | OG10-FA |  | OG10 | [6 empty] | Fire Alarm System Commissioned - OG10 | 0 | 0 |  | 2023-07-17 17:00 | -44 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.10 | OG10-GAS |  | OG10 | [6 empty] | DOB Sign-off for Gas Work - OG10 | 0 | 0 |  | 2023-05-26 12:00 | -10 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.11 | OG6-GENERATOR |  | OG6 | [6 empty] | Generator/Switch Gear Commissioned - OG6 | 0 | 0 |  | 2023-08-11 17:00 | -63 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.11 | OG6-HVAC |  | OG6 | [6 empty] | HVAC Commissioned - OG6 | 0 | 0 |  | 2024-01-15 17:00 | -167 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.11 | OG6-FA |  | OG6 | [6 empty] | Fire Alarm System Commissioned - OG6 | 0 | 0 |  | 2023-08-18 17:00 | -68 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.12 | OG1-GENERATOR |  | OG1 | [6 empty] | Generator/Switch Gear Commissioned - OG1 | 0 | 0 |  | 2023-08-17 17:00 | -67 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.12 | OG1-HVAC |  | OG1 | [6 empty] | HVAC Commissioned - OG1 | 0 | 0 |  | 2023-12-20 17:00 | -151 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.12 | OG1-FA |  | OG1 | [6 empty] | Fire Alarm System Commissioned - OG1 | 0 | 0 |  | 2023-08-24 17:00 | -72 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.13 | SG7-GENERATOR |  | SG7 | [6 empty] | Generator/Switch Gear Commissioned - SG7 | 0 | 0 |  | 2023-08-29 10:00 | -79 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.13 | SG7-HVAC |  | SG7 | [6 empty] | HVAC Commissioned - SG7 | 0 | 0 |  | 2023-09-05 17:00 | -84 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.13 | SG7-FA |  | SG7 | [6 empty] | Fire Alarm System Commissioned - SG7 | 0 | 0 |  | 2023-09-06 10:00 | -84 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.13 | SG7-GAS |  | SG7 | [6 empty] | DOB Sign-off for Gas Work - SG7 | 0 | 0 |  | 2023-08-04 12:00 | -63 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.14 | SG3-GENERATOR |  | SG3 | [6 empty] | Generator/Switch Gear Commissioned - SG3 | 0 | 0 |  | 2023-09-13 17:00 | -89 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.14 | SG3-HVAC |  | SG3 | [6 empty] | HVAC Commissioned - SG3 | 0 | 0 |  | 2023-09-27 17:00 | -99 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.14 | SG3-FA |  | SG3 | [6 empty] | Fire Alarm System Commissioned - SG3 | 0 | 0 |  | 2023-09-20 17:00 | -94 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.15 | SG1-GENERATOR |  | SG1 | [6 empty] | Generator/Switch Gear Commissioned - SG1 | 0 | 0 |  | 2023-08-23 10:00 | -73 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.15 | SG1-HVAC |  | SG1 | [6 empty] | HVAC Commissioned - SG1 | 0 | 0 |  | 2023-09-07 10:00 | -83 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.16 | SG2-GENERATOR |  | SG2 | [6 empty] | Generator/Switch Gear Commissioned - SG2 | 0 | 0 |  | 2023-08-14 12:00 | -66 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.16 | SG2-HVAC |  | SG2 | [6 empty] | HVAC Commissioned - SG2 | 0 | 0 |  | 2023-09-05 17:00 | -81 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.17 | S8A-GENERATOR |  | S81 | [6 empty] | Generator/Switch Gear Commissioned - S8A | 0 | 0 |  | 2023-08-01 12:00 | -56 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.17 | S8A-HVAC |  | S81 | [6 empty] | HVAC Commissioned - S8A | 0 | 0 |  | 2023-09-06 12:00 | -81 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.17 | S8A-FA |  | S81 | [6 empty] | Fire Alarm System Commissioned - S8A | 0 | 0 |  | 2023-08-08 12:00 | -61 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.17 | S8A-GAS |  | S81 | [6 empty] | DOB Sign-off for Gas Work - S8A | 0 | 0 |  | 2023-08-16 12:00 | -67 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.18 | S8E-GENERATOR |  | S82 | [6 empty] | Generator/Switch Gear Commissioned - S8E | 0 | 0 |  | 2023-07-26 12:00 | -51 | 0
Not Started |  | CI NYCHA Update #20.Interim Milestones.18 | S8E-HVAC |  | S82 | [6 empty] | HVAC Commissioned - S8E | 0 | 0 |  | 2023-09-06 12:00 | -80 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02502 | CLOSEOUT | SG6 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Inspection and issue permit - SG6 | 10 | 10 | 2023-03-03 08:00 | 2023-03-16 17:00 | 15 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.6 | SG6-02503 | NATIONAL GRID | SG6 |  | Engineering | NEW BUILDINGS |  |  |  | National Grid Approval - SG6 | 10 | 10 | 2023-03-03 08:00 | 2023-03-16 17:00 | 15 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02702 | CLOSEOUT | OG8 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Inspection and issue permit - OG8 | 10 | 10 | 2023-07-05 08:00 | 2023-07-18 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.6 | OG8-02703 | NATIONAL GRID | OG8 |  | Engineering | NEW BUILDINGS |  |  |  | National Grid Approval - OG8 | 10 | 10 | 2023-07-05 08:00 | 2023-07-18 17:00 | -45 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02502 | CLOSEOUT | OG9 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Inspection and issue permit - OG9 | 10 | 10 | 2023-04-07 13:00 | 2023-04-21 12:00 | 16 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.6 | OG9-02503 | NATIONAL GRID | OG9 |  | Engineering | NEW BUILDINGS |  |  |  | National Grid Approval - OG9 | 10 | 10 | 2023-04-07 13:00 | 2023-04-21 12:00 | 16 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02502 | CLOSEOUT | OG10 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Inspection and issue permit - OG10 | 10 | 10 | 2023-05-12 13:00 | 2023-05-26 12:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.6 | OG10-02503 | NATIONAL GRID | OG10 |  | Engineering | NEW BUILDINGS |  |  |  | National Grid Approval - OG10 | 10 | 10 | 2023-05-12 13:00 | 2023-05-26 12:00 | -10 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02602 | CLOSEOUT | SG7 | INSPECTION | Closeout | NEW BUILDINGS |  |  |  | DOB Inspection and issue permit - SG7 | 10 | 10 | 2023-07-21 13:00 | 2023-08-04 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.6 | SG7-02603 | NATIONAL GRID | SG7 |  | Engineering | NEW BUILDINGS |  |  |  | National Grid Approval - SG7 | 10 | 10 | 2023-07-21 13:00 | 2023-08-04 12:00 | -63 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02502 | CLOSEOUT | S81 | INSPECTION | Closeout | EXISTING BUILDINGS |  |  |  | DOB Inspection and issue permit - S8A | 10 | 10 | 2023-08-02 13:00 | 2023-08-16 12:00 | -67 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.6 | S8A-02503 | NATIONAL GRID | S82 |  | Engineering | NEW BUILDINGS |  |  |  | National Grid Approval - S8A | 10 | 10 | 2023-08-02 13:00 | 2023-08-16 12:00 | -67 | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02000 | [8 empty] | Await Receipt of DPL1, CCD1 and TPP1 from NYCHA to Pull Fence Permit (Should have been at NTP) | 53 | 0 | 2020-07-13 | 2020-09-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02015 | [8 empty] | DOB Issue Fence Permit - SG-4 | 20 | 0 | 2020-09-28 | 2020-12-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02020 | [8 empty] | DOB Issue Fence Permit - SG-5 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02025 | [8 empty] | DOB Issue Fence Permit - OG-2 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02030 | [8 empty] | DOB Issue Fence Permit - OG-3 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02035 | [8 empty] | DOB Issue Fence Permit - OG-4 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02040 | [8 empty] | DOB Issue Fence Permit - OG-8 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02045 | [8 empty] | DOB Issue Fence Permit - OG-9 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02050 | [8 empty] | DOB Issue Fence Permit - OG-1 | 20 | 0 | 2020-09-28 | 2020-12-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02055 | [8 empty] | DOB Issue Fence Permit - OG-5 | 20 | 0 | 2020-09-28 | 2021-01-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02060 | [8 empty] | DOB Issue Fence Permit - OG-6 | 20 | 0 | 2020-09-28 | 2021-01-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02065 | [8 empty] | DOB Issue Fence Permit - OG-10 | 20 | 0 | 2020-09-28 | 2021-01-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02070 | [8 empty] | DOB Issue Fence Permit - SG-1 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02075 | [8 empty] | DOB Issue Fence Permit - SG-2 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02080 | [8 empty] | DOB Issue Fence Permit - SG-3 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02085 | [8 empty] | DOB Issue Fence Permit - SG-7 | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02090 | [8 empty] | DOB Issue Fence Permit - S8E | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02095 | [8 empty] | DOB Issue Fence Permit - S8A | 20 | 0 | 2020-09-28 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02002 | [8 empty] | DOB Notifies MLJ of need for L2 Forms for OG5 & OG6 due to Previous Fine | 1 | 0 | 2020-12-11 | 2020-12-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-02003 | [8 empty] | NYCHA Provide L2 Forms for OG5 and OG6 | 5 | 0 | 2020-12-14 | 2020-12-31 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01860 | [8 empty] | Prepare & Submit Fence Subcontractor | 1 | 0 | 2020-07-13 | 2020-07-13 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Subcont | 01865 | [8 empty] | Review & Approve Fence Subcontractor | 10 | 0 | 2020-07-14 | 2021-08-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05000 | [8 empty] | Request NYCHA for Documentation for Demolition Permit Filing | 1 | 0 | 2020-09-16 08:00 | 2020-09-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001 | [8 empty] | NYCHA Provide Notarized Letters, Notifications and Forms to MLJ for Demo Permit Application | 20 | 0 | 2020-11-25 08:00 | 2021-03-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05005 | [8 empty] | File for Demolition Permit (Requires forms from NYCHA) | 10 | 0 | 2021-03-16 | 2021-03-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01002 | [8 empty] | Install SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> SG6 | 4 | 0 | 2021-03-26 | 2021-04-01 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31205 | [8 empty] | Prepare & Submit Methods of Excavation | 20 | 0 | 2020-12-01 | 2020-12-18 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 31 | 31210 | [8 empty] | Review & Approve Methods of Excavation | 10 | 0 | 2020-12-21 | 2021-02-12 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.7 | OG8-01002 | [8 empty] | Install SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG8 | 5 | 0 | 2021-04-02 | 2021-04-06 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.7 | OG9-01002 | [8 empty] | Install SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG9 | 5 | 0 | 2021-07-07 | 2021-07-09 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01005 | [8 empty] | Site closure due to shooting - January 8, 2021 | 1 | 0 | 2021-01-08 | 2021-01-08 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01010 | [8 empty] | Site closure due to shooting - January 19 - 22, 2021 | 4 | 0 | 2021-01-19 | 2021-01-22 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01050 | [8 empty] | Basement not in a suitable condition to commence work - SG4 | 0 | 0 | 2020-07-13 | 2021-01-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01055 | [8 empty] | Basement not in a suitable condition to commence work - SG5 | 0 | 0 | 2020-07-13 08:00 | 2021-04-02 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01060 | [8 empty] | Basement not in a suitable condition to commence work - OG4 | 160 | 0 | 2020-07-13 08:00 | 2021-05-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01065 | [8 empty] | Basement not in a suitable condition to commence work - OG5 | 160 | 0 | 2020-07-13 08:00 | 2021-10-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01070 | [8 empty] | Basement not in a suitable condition to commence work - OG3 | 160 | 0 | 2020-07-13 08:00 | 2022-02-28 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01075 | [8 empty] | Basement not in a suitable condition to commence work - OG2 | 0 | 0 | 2020-07-13 08:00 | 2021-05-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01080 | [8 empty] | Basement not in a suitable condition to commence work - OG6 | 146 | 0 | 2020-07-13 08:00 | 2021-02-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01085 | [8 empty] | Basement not in a suitable condition to commence work - OG1 | 146 | 0 | 2020-07-13 08:00 | 2021-02-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01090 |  | SG3 | [6 empty] | Basement not in a suitable condition to commence work - SG3 | 0 | 0 | 2020-07-13 08:00 | 2022-09-30 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01095 | [8 empty] | Basement not in a suitable condition to commence work - SG1 | 150 | 0 | 2020-07-13 08:00 | 2021-02-19 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01100 | [8 empty] | Basement not in a suitable condition to commence work - SG2 | 0 | 0 | 2020-07-13 08:00 | 2021-05-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01105 | [8 empty] | Basement not in a suitable condition to commence work - S8E | 0 | 0 | 2020-07-13 08:00 | 2021-03-25 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01215 | [8 empty] | Redesign Site Fencing due to Conflict with Specifications | 50 | 0 | 2020-11-11 | 2021-02-08 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01205 | [8 empty] | RFI #152 - Temp Site Fencing Design Discrepency - Submit | 1 | 0 | 2020-11-03 | 2020-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01210 | [8 empty] | RFI #152 - Temp Site Fencing Design Discrepency - Response | 5 | 0 | 2020-11-04 | 2020-11-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07015 | [8 empty] | File for DEP Asbestos Control Program (ACP) - SG5 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07020 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - SG5 | 20 | 0 | 2020-10-07 | 2020-10-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07025 | [8 empty] | File for DEP Asbestos Control Program (ACP) - OG2 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07030 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - OG2 | 20 | 0 | 2020-10-07 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07035 | [8 empty] | File for DEP Asbestos Control Program (ACP) - OG3 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07040 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - OG3 | 20 | 0 | 2020-10-07 | 2020-10-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07045 | [8 empty] | File for DEP Asbestos Control Program (ACP) - OG4 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07050 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - OG4 | 20 | 0 | 2020-10-07 | 2020-11-19 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07055 | [8 empty] | File for DEP Asbestos Control Program (ACP) - OG5 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07060 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - OG5 | 20 | 0 | 2020-10-07 | 2020-11-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07065 | [8 empty] | File for DEP Asbestos Control Program (ACP) - OG6 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07070 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - OG6 | 20 | 0 | 2020-10-07 | 2020-11-10 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07075 | [8 empty] | File for DEP Asbestos Control Program (ACP) - OG1 | 10 | 0 | 2020-09-04 | 2020-10-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07080 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - OG1 | 20 | 0 | 2020-10-07 | 2020-11-06 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07085 | [8 empty] | File for DEP Asbestos Control Program (ACP) - SG3 | 10 | 0 | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07090 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - SG3 | 20 | 0 | 2021-04-30 | 2021-05-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07095 | [8 empty] | File for DEP Asbestos Control Program (ACP) - SG1 | 10 | 0 | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07100 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - SG1 | 20 | 0 | 2021-04-30 | 2021-05-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07105 | [8 empty] | File for DEP Asbestos Control Program (ACP) - SG2 | 10 | 0 | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07110 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - SG2 | 20 | 0 | 2021-04-30 | 2021-05-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07115 | [8 empty] | File for DEP Asbestos Control Program (ACP) - S8E | 10 | 0 | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-07120 | [8 empty] | DEP Issue Asbestos Control Program (ACP) Permit - S8E | 20 | 0 | 2022-02-16 08:00 | 2022-04-20 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.5.Removals1 | OGE-01007 | [8 empty] | Install Site Fencing - O'Dwyer Gardens - East - @ OG10 & OG7 Only | 10 | 0 | 2021-02-24 | 2021-02-26 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01006 | [8 empty] | Install Site Fencing - O'Dwyer Gardens - West (Central) | 5 | 0 | 2022-02-10 | 2022-02-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.Removals1 | OGW-01007 | [8 empty] | Clear & Grub and Demo Playground (Central) | 5 | 0 | 2022-02-16 | 2022-02-21 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-03999 | [8 empty] | Request Indemnity Letter from NYCHA for Dewatering Permit | 1 | 0 | 2020-09-23 | 2020-09-23 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.5 | SG6-03000 | [8 empty] | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 2022-03-23 | 2022-05-31 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.4 | OG8-03000 | WELKIN | OG8 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 2022-08-01 08:00 | 2022-09-26 12:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.4 | OG9-03000 | WELKIN | OG9 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 2022-08-01 08:00 | 2022-10-25 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.4 | OG10-03000 | WELKIN | OG10 | [6 empty] | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 2022-07-25 08:00 | 2022-09-24 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.4 | SG7-03000 | WELKIN | SG7 |  | Interior | NEW BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 5 | 2023-01-23 08:00 | 2023-03-03 12:00 | -113 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.4 | S8A-03000 | WELKIN | S81 |  | Interior | EXISTING BUILDINGS |  |  |  | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 5 | 2023-03-13 08:00 | 2023-03-17 17:00 | -98 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03132 |  | SG6 | [6 empty] | Install and terminate wires - FOT Controls - 1st Floor | 10 | 0 | 2022-08-08 08:00 | 2022-09-23 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03232 | FIVE STAR | SG6 |  | Interior | NEW BUILDINGS |  |  |  | Install & Terminate Wires for Boiler Controls - 2nd Floor | 10 | 2 | 2022-08-22 08:00 | 2023-02-28 12:00 | -76 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-03132 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Wire & Terminate FOT Controls - 1st Floor | 20 | 10 | 2023-02-16 08:00 | 2023-03-24 17:00 | -79 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.2 | OG8-03232 | FIVE STAR | OG8 |  | Interior | NEW BUILDINGS |  |  |  | Install Wire & Terminate for Boiler Controls - 2nd Floor | 20 | 20 | 2023-04-03 08:00 | 2023-04-28 17:00 | -106 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-03108 | [8 empty] | Install Ductwork - 1st Floor | 5 | 0 | 2022-01-19 | 2022-01-28 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.2 | SG6-03208 | [8 empty] | Install Ductwork - 2nd Floor | 5 | 0 | 2022-02-04 | 2022-02-18 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-03305 | [8 empty] | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.3 | SG6-03310 | [8 empty] | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 2021-02-01 | 2021-02-01 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01002a | [8 empty] | Excavate High Level & Lagging | 5 | 0 | 2021-02-25 | 2021-03-11 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.4 | SG6-01002b | [8 empty] | Install Sheet Piles | 3 | 0 | 2021-03-11 | 2021-03-30 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.2 | SURV-OGP1-E-01001 |  | OGE | [6 empty] | Cleaning & Pipe Repairs (Disputed Work) | 5 | 0 | 2022-09-01 | 2022-09-03 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.1 | SURV-OGW-E-01001 |  | OGW | [6 empty] | Cleaning & Pipe Repairs (Disputed Work) - OG-3 | 5 | 0 | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.1 | SURV-OGW-E-01016 | [8 empty] | Conduct Electrical Site Survey - O'Dwyer Garden - Part 2 (OG-2) | 15 | 0 | 2020-09-08 | 2021-06-08 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.1 | SURV-SGS-E-01031 | [8 empty] | Conduct Electrical Site Survey - Surfside Gardens South (SG-2) | 10 | 0 | 2021-06-01 | 2021-07-21 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.1 | SURV-SGS-E-01032 | [8 empty] | Conduct Electrical Site Survey - Surfside Gardens South (SG-3) | 10 | 0 | 2021-06-01 | 2021-09-17 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01305 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - SG6 (RFI #135) | 128 | 0 | 2020-09-01 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01310 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - SG4 | 128 | 0 | 2020-09-01 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01315 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - SG5 | 128 | 0 | 2020-09-01 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01320 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG8 (RFI 92, 111) | 22 | 0 | 2021-02-23 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01325 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG5 (RFI 92, 111) | 22 | 0 | 2021-02-23 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01330 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG4 | 22 | 0 | 2021-02-23 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01335 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG9 (RFI 92) | 32 | 0 | 2021-02-23 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01340 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG3 | 32 | 0 | 2021-02-23 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01345 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG2 (RFI 92) | 32 | 0 | 2021-02-23 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01350 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG10 | 37 | 0 | 2021-02-16 | 2021-09-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01355 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG6 | 37 | 0 | 2021-02-16 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01360 | [8 empty] | DELAY - Discrepancies between Internal and External MEP Drawings - OG1 | 37 | 0 | 2021-02-16 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01365 | [8 empty] | DELAY - MEP Discrepancies - SG7 | 37 | 0 | 2021-02-23 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01370 | [8 empty] | DELAY - MEP Discrepancies - SG3 | 32 | 0 | 2021-02-23 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01375 | [8 empty] | DELAY - MEP Discrepancies - SG1 | 32 | 0 | 2021-02-23 | 2022-03-24 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01380 | [8 empty] | DELAY - MEP Discrepancies - SG2 | 32 | 0 | 2021-02-23 | 2022-03-24 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.7 | OG10-01019 | [8 empty] | Install Sheeting/SOE --> OG10 | 10 | 0 | 2021-06-30 | 2021-07-06 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01405 | [8 empty] | DELAY - OG8 Obstructions in Ground | 35 | 0 | 2021-04-07 | 2021-06-11 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01410 | [8 empty] | DELAY - Asbestos Abatement Additional Review and Property Management Coordination | 20 | 0 | 2021-05-07 | 2021-06-11 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01415 | [8 empty] | DELAY - Paint Removal Additional Review and Property Management Coordination (Notified by E-Mail) | 22 | 0 | 2021-05-07 | 2021-06-11 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01005 |  |  | CO007 | [5 empty] | Submit RFI 116 - Boiler Accessories | 1 | 0 | 2020-09-25 | 2020-09-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01010 |  |  | CO007 | [5 empty] | Response RFI 116 - Boiler Accessories | 5 | 0 | 2020-09-28 | 2020-10-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01015 |  |  | CO007 | [5 empty] | MLJ Await Receipt of Change Order #7 | 150 | 0 | 2020-10-13 08:00 | 2022-03-15 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01020 |  |  | CO007 | [5 empty] | Prep/Submit Boiler Accessories | 20 | 0 | 2022-03-16 | 2022-03-25 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01025 |  |  | CO007 | [5 empty] | Review/Approve Boiler Accessories | 10 | 0 | 2022-03-26 | 2022-04-12 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01030 |  |  | CO007 | [5 empty] | Fab/Deliver Boiler Accessories | 60 | 0 | 2022-04-01 | 2022-09-09 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO003-01005 |  |  | CO003 | [5 empty] | National Grid Revised Allowance | 120 | 0 | 2020-12-01 | 2021-10-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01420 | [8 empty] | Delay - Removal of Cars in OG Parking Lot 3 (OG10 and OG7) | 20 | 0 | 2021-04-25 | 2021-05-11 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01425 | [8 empty] | DELAY - Waiting on Revised TR From DOB for OG9 Permit | 5 | 0 | 2021-06-09 08:00 | 2021-06-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001a | [8 empty] | MLJ Provide Rodent Control Plan | 10 | 0 | 2021-02-01 | 2021-02-17 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001b | [8 empty] | MLJ/FSE Provide Electric Cut-Off Letter | 10 | 0 | 2021-02-01 | 2021-02-07 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001c | [8 empty] | MLJ Provide SRO Intake Form | 10 | 0 | 2021-02-01 | 2021-02-11 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001d | [8 empty] | MLJ Provide Photographs | 10 | 0 | 2020-08-03 | 2020-08-24 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001e | [8 empty] | MLJ Provide Separate Fence Application | 10 | 0 | 2020-12-01 | 2020-12-14 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001f | [8 empty] | MLJ Request Gas Cut-off Letter | 10 | 0 | 2020-10-19 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001f5 | [8 empty] | NYCHA Provide Gas Cut-Off Letter | 90 | 0 | 2020-10-30 | 2021-03-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001g | [8 empty] | MLJ Request Sewer Cut-off Letter | 10 | 0 | 2020-10-19 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001g5 | [8 empty] | NYCHA Provide Sewer Cut-Off Letter | 90 | 0 | 2020-10-30 | 2021-03-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001h | [8 empty] | MLJ Request Water Cut-off Letter | 10 | 0 | 2020-10-19 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001h5 | [8 empty] | NYCHA Provide Water Cut-Off Letter | 90 | 0 | 2020-10-30 | 2021-03-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001i | [8 empty] | MLJ Request 5-Day Notice Letter to adjoining Owners | 10 | 0 | 2020-10-19 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001i5 | [8 empty] | NYCHA Provide 5-Day Notice Letter to adjoining Owners | 80 | 0 | 2020-10-30 | 2021-03-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001j | [8 empty] | MLJ Request Community Board Notification | 10 | 0 | 2020-10-19 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001j5 | [8 empty] | NYCHA Provide Community Board Notification | 80 | 0 | 2020-10-30 | 2021-03-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001k | [8 empty] | MLJ Request Asbestos Report (of all Sides/Facades) | 10 | 0 | 2020-10-19 | 2020-10-30 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div 1.Permits | PERMIT-05001k5 | [8 empty] | NYCHA Provide Asbestos Report (of all Sides/Facades) | 90 | 0 | 2020-10-30 | 2021-03-15 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01407 | [8 empty] | Install Remaining SOE after removal of Obstructions - OG-8 | 5 | 0 | 2021-06-17 | 2021-06-29 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01350 | MLJ | OGE | Excavation | Utilities | SITE | UTILITY EXC | 33-3100 | 33-3100-OGE | Excavate for Steam & HW OG3--> Street | 5 | 5 | 2023-07-11 08:00 | 2023-07-17 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01355 | WELKIN | OGW | UG PIPE | Utilities | SITE |  |  |  | Install Steam and HW piping OG3--> Street | 5 | 5 | 2023-07-18 08:00 | 2023-07-24 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01360 | WELKIN | OGW | UG PIPE | Utilities | SITE |  |  |  | Test Steam & HW Piping OG3--> Street | 5 | 5 | 2023-07-25 08:00 | 2023-07-31 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.6.6 | OGW-01365 | MLJ | OGE | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-OGE | Backfill Steam & HW Piping OG3--> Street | 5 | 5 | 2023-08-01 08:00 | 2023-08-07 17:00 | -71 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01280 | MLJ | S8 | Excavation | Utilities | SITE | UTILITY EXC | 33-3100 | 33-3100-S8 | Excavate for Steam Piping - Street -> S8.1 | 5 | 5 | 2023-07-11 08:00 | 2023-07-17 17:00 | -132 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01285 | WELKIN | S8 | UG PIPE | Utilities | SITE |  |  |  | Install Steam Piping - Street -> S8.1 | 5 | 5 | 2023-07-18 08:00 | 2023-07-24 17:00 | -132 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01290 | WELKIN | S8 | UG PIPE | Utilities | SITE |  |  |  | Test Steam Piping - Street -> S8.1 | 5 | 5 | 2023-07-25 08:00 | 2023-07-31 17:00 | -132 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.3.6 | S8-01295 | MLJ | S8 | BACKFILL | Utilities | SITE | BACKFILL UTILITY | 31-2200 | 31-2200-S8 | Backfill Steam Piping - Street -> S8.1 | 5 | 5 | 2023-08-01 08:00 | 2023-08-07 17:00 | -132 | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01110 | [8 empty] | Basement not in a suitable condition to commence work - Site 8 | 0 | 0 | 2020-07-13 08:00 | 2022-02-21 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01450 | [8 empty] | DELAY - Exisiting Interfering Gas Line at SG7 | 5 | 0 | 2021-05-19 | 2021-07-27 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01455 | [8 empty] | DELAY - Building Color Change for All New Buildings | 20 | 0 | 2021-04-27 | 2021-09-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01385 | [8 empty] | DELAY - SG-South (Bulletin #3) - Con-Edison Changes - SG1,2,3,7 (RFI 219 & 370) | 90 | 0 | 2021-02-08 | 2021-10-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01460 | [8 empty] | DELAY - Awaiting Access to First Floor Room - SG5 | 10 | 0 | 2020-07-13 08:00 | 2021-10-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01465 | [8 empty] | DELAY - Awaiting Access to First Floor Room - SG4 | 10 | 0 | 2020-07-13 08:00 | 2021-09-22 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01470 | [8 empty] | DELAY - Awaiting Access to First Floor Room - OG1 | 20 | 0 | 2020-07-13 08:00 | 2021-12-27 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01475 | [8 empty] | DELAY - Awaiting Access to First Floor Room - OG2 | 20 | 0 | 2020-07-13 08:00 | 2021-12-27 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01480 | [8 empty] | DELAY - Awaiting Access to First Floor Room - OG3 | 20 | 0 | 2020-07-13 08:00 | 2021-12-28 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01485 | [8 empty] | DELAY - Awaiting Access to First Floor Room - OG4 | 20 | 0 | 2020-07-13 08:00 | 2021-12-27 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01490 | [8 empty] | DELAY - Awaiting Access to First Floor Room - OG5 | 20 | 0 | 2020-07-13 08:00 | 2021-12-27 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01495 |  | OG6 | [6 empty] | DELAY - Awaiting Access to First Floor Room - OG6 | 20 | 0 | 2020-07-13 08:00 | 2022-11-07 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01500 | [8 empty] | DELAY - Awaiting Access to First Floor Room - SG3 | 20 | 0 | 2020-07-13 08:00 | 2022-06-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01505 |  | SG5 | [6 empty] | DELAY - Tenants vacate 2nd Floor Apartment - SG5 | 20 | 0 | 2020-07-13 | 2022-08-26 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01510 | [8 empty] | DELAY - OG8 Obstructions in Ground #2 - Underground Tank | 35 | 0 | 2021-07-28 | 2021-08-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01515 | [8 empty] | DELAY - Underground HW & CW Plumbing Permit | 25 | 0 | 2021-07-26 | 2021-09-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22911 | [8 empty] | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - OGE | 40 | 0 | 2021-08-13 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22912 | [8 empty] | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - OGW | 40 | 0 | 2021-06-21 | 2021-08-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22913 | [8 empty] | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - OGP1 | 40 | 0 | 2021-08-12 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 22 | 22914 | [8 empty] | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - SGS | 40 | 0 | 2021-10-05 | 2021-11-15 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24201 | [8 empty] | Fab/Del. Steam and Condensate Piping - OGP1 | 35 | 0 | 2021-08-16 08:00 | 2021-09-22 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24202 | [8 empty] | Fab/Del. Steam and Condensate Piping - OGE | 35 | 0 | 2021-08-02 08:00 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24203 | [8 empty] | Fab/Del. Steam and Condensate Piping - OGW | 35 | 0 | 2021-03-25 08:00 | 2021-09-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.Procurement.Div. 23 | 24204 | [8 empty] | Fab/Del. Steam and Condensate Piping - SGS | 35 | 0 | 2021-09-24 08:00 | 2021-09-26 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01605 | [8 empty] | DELAY - RFI #325 - Regarding Light Fixtures in all existing Cellars - Submit | 5 | 0 | 2021-07-29 08:00 | 2021-07-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01610 | [8 empty] | DELAY - RFI #325 - Regarding Light Fixtures in all existing Cellars - Response | 15 | 0 | 2021-07-30 | 2021-09-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01520 | [8 empty] | DELAY - UG plumbing pipe Inspection failure due to pipe type - Eng to Re-file Dwgs/OTCR | 10 | 0 | 2021-09-23 | 2022-06-24 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01525 | [8 empty] | DELAY - OG Fence Change required by residents | 20 | 0 | 2021-09-16 | 2021-12-02 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01530 | [8 empty] | DELAY - Existing Pipe under W33rd | 75 | 0 | 2021-06-22 | 2022-08-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01535 | [8 empty] | DELAY - Condition of existing basement walls preventing waterproofing (RFI 302 & RFI 311) | 75 | 0 | 2021-07-08 | 2022-07-10 |  | 0
In Progress |  | CI NYCHA Update #20.1 | CO008-01005 |  |  | CO008 | [5 empty] | Bulletin #1 - PCO #44 Civil Work | 120 | 30 | 2021-05-05 | 2023-04-07 17:00 | -68 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01060 | [8 empty] | Abate asbestos on Existing Steam Line --> SG7 | 3 | 0 | 2022-03-28 | 2022-04-15 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.7 | SG7-01062 | [8 empty] | Relocate Existing steam --> SG7 | 5 | 0 | 2022-04-18 | 2022-04-18 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01705 | [8 empty] | DELAY - RFI's 242,365 &381 - Fire Standpipe CO21 - Submit | 5 | 0 | 2021-05-05 08:00 | 2021-10-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01710 | [8 empty] | DELAY - RFI's 242,365 &381 - Fire Standpipe CO21 - Response | 5 | 0 | 2021-09-25 | 2021-10-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01715 | [8 empty] | CO #21 - MLJ Awaits Receipt of CO21 Fire Standpipe Relocation - Site 8 | 10 | 0 | 2021-10-23 | 2022-03-14 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01720 | [8 empty] | CO #21 - Fire Standpipe Relocation (Incl Shutdown and Testing) | 15 | 0 | 2022-03-14 | 2022-04-05 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01805 | [8 empty] | DELAY - AWP Approved by Saban | 1 | 0 | 2021-02-08 08:00 | 2021-02-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01810 | [8 empty] | DELAY - Additional review and change to formatting requried by CSQ | 188 | 0 | 2021-02-09 | 2022-02-11 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01905 | [8 empty] | CO- ACM Found on Exterior of Foundation Wall @ Existing Buildings | 1 | 0 | 2021-10-06 08:00 | 2021-10-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01910 | [8 empty] | CO - Expose, Test and confirm quantities | 25 | 0 | 2021-10-07 08:00 | 2021-11-18 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01915 | [8 empty] | CO #55 - Abate ACM for Underground utilities - SG-1 | 2 | 0 | 2021-12-20 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01920 |  | SG1 | [6 empty] | CO #54 - Abate ACM for masonry foundation - SG-1 | 5 | 0 | 2022-08-15 | 2022-08-19 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01015 | [8 empty] | Site closure due to shooting - June 11, 2021 | 1 | 0 | 2021-06-11 08:00 | 2021-06-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01020 | [8 empty] | Site closure due to shooting - June 29, 2021 | 1 | 0 | 2021-06-29 08:00 | 2021-06-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01025 | [8 empty] | Site closure due to shooting - June 30, 2021 | 1 | 0 | 2021-06-30 08:00 | 2021-06-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01030 | [8 empty] | Site closure due to shooting - August 19, 2021 | 1 | 0 | 2021-08-19 08:00 | 2021-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01035 | [8 empty] | Site closure due to shooting - October 25, 2021 | 1 | 0 | 2021-10-25 08:00 | 2021-10-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01925 | [8 empty] | CO #55 - Abate ACM for Underground utilities - SG-2 | 2 | 0 | 2021-12-13 08:00 | 2021-12-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01930 |  | SG2 | [6 empty] | CO #54 - Abate ACM for masonry foundation - SG-2 | 5 | 0 | 2022-08-15 | 2022-08-19 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01935 | [8 empty] | CO #55 - Abate ACM for Underground utilities - SG-3 | 2 | 0 | 2021-12-14 08:00 | 2021-12-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01940 |  | SG3 | [6 empty] | CO #54 - Abate ACM for masonry foundation - SG-3 | 5 | 0 | 2022-08-29 | 2022-08-31 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01950 | [8 empty] | CO #54 - Abate ACM for masonry foundation - SG-4 | 5 | 0 | 2022-03-10 | 2022-03-11 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01960 | [8 empty] | CO #54 - Abate ACM for masonry foundation - SG-5 | 5 | 0 | 2022-02-16 08:00 | 2022-02-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01965 | [8 empty] | CO #55 - Abate ACM for Underground utilities - OG-1 | 2 | 0 | 2021-11-16 08:00 | 2021-11-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01970 | [8 empty] | CO #54 - Abate ACM for masonry foundation - OG-1 | 5 | 0 | 2022-04-21 | 2022-05-05 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01975 | [8 empty] | CO #55 - Abate ACM for Underground utilities - OG-2 | 2 | 0 | 2021-12-02 | 2022-04-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01980 | [8 empty] | CO #54 - Abate ACM for masonry foundation - OG-2 | 5 | 0 | 2022-04-26 | 2022-04-29 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01985 | [8 empty] | CO #55 - Abate ACM for Underground utilities - OG-3 | 2 | 0 | 2021-11-26 | 2022-04-13 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01990 |  | OG3 | [6 empty] | CO #54 - Abate ACM for masonry foundation - OG-3 | 5 | 0 | 2022-05-19 | 2022-09-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01995 | [8 empty] | CO #55 - Abate ACM for Underground utilities - OG-4 | 2 | 0 | 2021-10-25 08:00 | 2021-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02000 |  | OG4 | [6 empty] | CO #54 - Abate ACM for masonry foundation - OG-4 | 5 | 0 | 2022-06-03 08:00 | 2022-10-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02005 | [8 empty] | CO #55 - Abate ACM for Underground utilities - OG-5 | 2 | 0 | 2022-01-06 | 2022-04-14 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02010 |  | OG5 | [6 empty] | CO #54 - Abate ACM for masonry foundation - OG-5 | 5 | 0 | 2022-05-20 | 2022-09-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02015 | [8 empty] | CO #55 - Abate ACM for Underground utilities - OG-6 | 2 | 0 | 2021-11-17 08:00 | 2021-11-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02020 |  | OG6 | [6 empty] | CO #54 - Abate ACM for masonry foundation - OG-6 | 5 | 0 | 2022-09-01 | 2022-09-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02025 |  | S8 | [6 empty] | CO #55 - Abate ACM for Underground utilities - Site 8 | 2 | 0 | 2022-02-18 | 2022-10-24 |  | 0
Not Started |  | CI NYCHA Update #20.19 | DELAY-02030 |  | S81 | [6 empty] | CO #54 - Abate ACM for masonry foundation - Site 8 | 5 | 3 | 2023-01-25 | 2023-03-01 17:00 | -106 | 0
Completed |  | CI NYCHA Update #20.1 | CO007-01035 |  |  | CO007 | [5 empty] | Install Boiler Accessories | 10 | 0 | 2022-09-14 | 2022-10-14 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-03005 | [8 empty] | DELAY - Manufacturing Supply/Chain Issues for ATS Equipment | 40 | 0 | 2021-10-11 | 2021-12-17 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01005 |  |  | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - OG1 | 10 | 0 | 2022-04-15 | 2022-04-20 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01010 |  |  | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - OG2 | 10 | 0 | 2022-04-25 | 2022-04-28 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01015 |  |  | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - OG3 | 10 | 0 | 2022-04-22 | 2022-04-28 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01020 |  |  | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - OG4 | 10 | 0 | 2022-04-18 | 2022-04-21 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01025 |  |  | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - OG5 | 10 | 0 | 2022-04-25 | 2022-04-28 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01030 |  | OG6 | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - OG6 | 10 | 0 | 2022-11-21 | 2022-11-28 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01035 |  | SG3 | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - SG3 | 10 | 0 | 2022-10-03 | 2022-10-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO016-01040 |  |  | CO016 | [5 empty] | Relocate Obstructions in 1st Floor - SG5 | 10 | 0 | 2022-04-07 | 2022-04-15 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01911 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - SG-1 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01912 | [8 empty] | CO #55 - Filing with DEP - SG-1 | 10 | 0 | 2021-11-18 08:00 | 2021-12-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01922 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - SG-2 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01923 | [8 empty] | CO #55 - Filing with DEP - SG-2 | 10 | 0 | 2021-11-18 08:00 | 2021-12-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01932 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - SG-3 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01933 | [8 empty] | CO #55 - Filing with DEP- SG-3 | 10 | 0 | 2021-11-18 08:00 | 2021-12-07 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01942 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - SG-4 | 20 | 0 | 2021-11-25 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01943 | [8 empty] | CO #55 - Filing with DEP- SG-4 | 10 | 0 | 2022-01-03 08:00 | 2022-01-14 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01952 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - SG-5 | 20 | 0 | 2021-11-25 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01953 | [8 empty] | CO #55 - Filing with DEP- SG-5 | 10 | 0 | 2022-01-03 08:00 | 2022-01-14 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01962 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - OG-1 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01963 | [8 empty] | CO #55 - Filing with DEP- OG-1 | 10 | 0 | 2021-10-27 08:00 | 2021-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01972 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - OG-2 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01973 | [8 empty] | CO #55 - Filing with DEP- OG-2 | 10 | 0 | 2021-11-18 08:00 | 2021-11-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01982 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - OG-3 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01983 | [8 empty] | CO #55 - Filing with DEP- OG-3 | 10 | 0 | 2021-11-02 08:00 | 2021-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01992 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - OG-4 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01993 | [8 empty] | CO #55 - Filing with DEP- OG-4 | 10 | 0 | 2021-10-11 08:00 | 2021-10-14 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02002 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - OG-5 | 20 | 0 | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02003 | [8 empty] | CO #55 - Filing with DEP- OG-5 | 10 | 0 | 2021-11-18 08:00 | 2021-12-03 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02012 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - OG-6 | 20 | 0 | 2021-11-25 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02013 | [8 empty] | CO #55 - Filing with DEP- OG-6 | 10 | 0 | 2021-10-27 08:00 | 2021-11-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02022 | [8 empty] | CO #55 - NYCHA Instruct PCO 55 - Site 8 | 20 | 0 | 2021-11-25 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02023 | [8 empty] | CO #55 - Filing with DEP- Site 8 | 10 | 0 | 2021-11-18 08:00 | 2021-12-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01005 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Instruction - SGS and OGW Electrical Feeder Changes (RFI #370) | 8 | 0 | 2021-12-21 | 2021-12-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01115 | [8 empty] | Basement not in a suitable condition to continue work (Steam) - SG5 | 20 | 0 | 2022-01-11 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01120 | [8 empty] | Basement not in a suitable condition to continue work (Flooding) - OG4 | 20 | 0 | 2022-01-11 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-01125 | [8 empty] | Basement not in a suitable condition to continue work (Sewage) - OG4 | 20 | 0 | 2022-01-11 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI462-01005 | [8 empty] | 2nd floor apartment DOB Plumbing Drawings - Submit | 1 | 0 | 2021-12-27 08:00 | 2021-12-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI462-01010 | [8 empty] | 2nd floor apartment DOB Plumbing Drawings - Response | 10 | 0 | 2021-12-28 | 2022-04-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI302-01005 | [8 empty] | RFI 302, 311 & 483 - Waterproofing to existing buildings - Submit | 1 | 0 | 2021-07-13 08:00 | 2022-01-24 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI302-01010 | [8 empty] | RFI 302, 311 & 483 - Waterproofing to existing buildings - Response | 10 | 0 | 2021-07-14 08:00 | 2022-07-10 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI408-01005 | [8 empty] | RFI 408 - Existing Building Masonry interferences - Submit (SG4,5) | 5 | 0 | 2021-10-15 | 2021-10-20 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI408-01010 | [8 empty] | RFI 408 - Existing Building Masonry interferences - Response (SG4,5) | 10 | 0 | 2021-10-21 | 2022-05-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI473-01005 | [8 empty] | RFI #473 - Fuel Oil Tank between OG5&OG6 - Submit | 1 | 0 | 2022-01-19 08:00 | 2022-01-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI473-01010 | [8 empty] | RFI #473 - Fuel Oil Tank between OG5&OG6 - Response | 10 | 0 | 2022-01-20 | 2022-02-14 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO046-01005 |  |  | CO046 | [5 empty] | CO #46 - Scope Development - OG5 & OG6 Sanitary Vent Connections | 1 | 0 | 2021-10-06 08:00 | 2021-10-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI294-01005 | [8 empty] | RFI #294 - OG5 Existing Vents - Submit | 5 | 0 | 2021-07-01 | 2021-07-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI294-01010 | [8 empty] | RFI #294 - OG5 Existing Vents - Response | 10 | 0 | 2021-07-02 | 2021-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO046-01010 |  |  | CO046 | [5 empty] | CO #46 - Scope Agreement - OG5 & OG6 Sanitary Vent Connections | 65 | 0 | 2021-10-07 | 2022-01-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO046-01015 |  |  | CO046 | [5 empty] | CO #46 - Submit Price - OG5 & OG6 Sanitary Vent Connections | 5 | 0 | 2022-01-14 | 2022-01-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO046-01020 |  | OG6 | CO046 | [5 empty] | CO #46 - Negotiate/Instruction - OG5 & OG6 Sanitary Vent Connections | 20 | 0 | 2022-01-19 | 2022-08-23 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO046-01025 |  | OG5 | CO046 | [5 empty] | CO #46 - Sanitary Vent Connections @ OG-5 | 10 | 0 | 2022-09-06 08:00 | 2022-09-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO046-01030 |  | OG6 | CO046 | [5 empty] | CO #46 - Sanitary Vent Connections @ OG-6 | 10 | 0 | 2022-09-06 08:00 | 2022-09-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO052-01005 |  |  | CO052 | [5 empty] | CO #52 - Scope Development - Playground removal (RFI 375) | 5 | 0 | 2021-10-26 08:00 | 2021-10-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO052-01010 |  |  | CO052 | [5 empty] | CO #52 - Scope Agreement - Playground removal (RFI 375) | 5 | 0 | 2021-10-27 | 2022-01-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO052-01015 |  |  | CO052 | [5 empty] | CO #52 - Submit Price - Playground removal (RFI 375) | 5 | 0 | 2022-01-06 | 2022-01-06 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO052-01020 |  |  | CO052 | [5 empty] | CO #52 - Negotiate/Instruction - Playground removal (RFI 375) | 20 | 0 | 2022-01-07 | 2022-08-23 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO052-01025 |  |  | CO052 | [5 empty] | CO #52 - Remove Playround - OG East | 5 | 0 | 2022-02-07 | 2022-02-09 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI375-01005 | [8 empty] | RFI #375 - OGE Playground Clash with ductbank - Submit | 5 | 0 | 2021-09-29 | 2021-09-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI375-01010 | [8 empty] | RFI #375 - OGE Playground Clash with ductbank - Response | 10 | 0 | 2021-09-30 | 2021-10-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO053-01005 |  |  | CO053 | [5 empty] | CO #53 - Scope Development - SG6 and OG8 boiler stack support (RFI #213) | 5 | 0 | 2021-04-13 08:00 | 2021-10-29 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO053-01010 |  |  | CO053 | [5 empty] | CO #53 - Scope Agreement - - SG6 and OG8 boiler stack support (RFI #213) | 20 | 0 | 2021-11-01 | 2022-02-10 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO053-01015 |  |  | CO053 | [5 empty] | CO #53 - Submit Price - SG6 and OG8 boiler stack support (RFI #213) | 5 | 0 | 2022-02-10 | 2022-02-11 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO053-01020 |  | SG6 | CO053 | [5 empty] | CO #53 - Negotiate/Instruction - SG6 and OG8 boiler stack support (RFI #213) | 20 | 0 | 2022-02-24 08:00 | 2022-08-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI213-01005 | [8 empty] | RFI #213 - Boiler Stack Support - Submit | 5 | 0 | 2021-03-31 | 2021-03-31 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI213-01010 | [8 empty] | RFI #213 - Boiler Stack Support - Response | 10 | 0 | 2021-04-01 | 2021-04-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO053-01025 |  |  | CO053 | [5 empty] | CO #53 - Install Additional Boiler Stack Supports - SG6 | 10 | 0 | 2022-04-26 | 2022-04-26 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO053-01030 |  |  | CO053 | [5 empty] | CO #53 - Install Additional Boiler Stack Supports - OG8 | 10 | 0 | 2022-04-27 | 2022-04-29 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI189-01005 | [8 empty] | RFI #189 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 2021-03-04 | 2021-03-04 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI189-01010 | [8 empty] | RFI #189 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 2021-03-05 | 2021-03-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI205-01005 | [8 empty] | RFI #205 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 2021-03-15 | 2021-03-15 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI205-01010 | [8 empty] | RFI #205 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 2021-03-16 | 2021-03-25 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI219-01005 | [8 empty] | RFI #219 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 2021-04-06 | 2021-04-06 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI219-01010 | [8 empty] | RFI #219 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 2021-04-07 | 2021-05-12 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI276-01005 | [8 empty] | RFI #276 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 2021-06-09 | 2021-06-09 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI276-01010 | [8 empty] | RFI #276 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 2021-06-10 | 2021-10-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI355-01005 | [8 empty] | RFI #355 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 2021-09-13 | 2021-09-13 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI355-01010 | [8 empty] | RFI #355 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 2021-09-14 | 2021-10-01 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI370-01005 | [8 empty] | RFI #370 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 2021-09-27 | 2021-09-27 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI370-01010 | [8 empty] | RFI #370 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 2021-09-28 | 2021-10-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01000 |  |  | CO059 | [5 empty] | CO #59 - Scope Development - SGS and OGW Electrical Feeder Changes (RFI #370) | 5 | 0 | 2021-10-21 08:00 | 2021-11-03 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01001 |  |  | CO059 | [5 empty] | CO #59 - Scope Agreement - SGS and OGW Electrical Feeder Changes (RFI #370) | 20 | 0 | 2021-11-01 | 2021-12-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01002 |  |  | CO059 | [5 empty] | CO #59 - Submit Price - SGS and OGW Electrical Feeder Changes (RFI #370) | 5 | 0 | 2021-12-20 08:00 | 2021-12-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01010 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Perform Engineering Coordination - SGS - (FSE CO: 18-0016) | 30 | 0 | 2021-12-22 08:00 | 2022-05-13 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01015 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Perform Engineering Coordination - OGW | 30 | 0 | 2022-02-07 08:00 | 2022-02-28 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01020 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Excavate for electric Existing Manhole to SG3 (PDLCO1) | 3 | 0 | 2022-03-07 08:00 | 2022-08-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01025 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Install Electrical conduit Existing Manhole to SG3 (PDLCO1) | 2 | 0 | 2022-08-23 | 2022-08-23 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01030 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Encase conduit in concrete Existing Manhole to SG3 (PDLCO1) | 1 | 0 | 2022-08-23 08:00 | 2022-08-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01035 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Backfill Electrical Existing Manhole to SG3 (PDLCO1) | 2 | 0 | 2022-08-25 08:00 | 2022-08-25 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.1 | CO059-01050 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Excavate for New MH to existing MH (PDLCO1) | 3 | 2 | 2022-03-07 08:00 | 2023-04-05 17:00 | -53 | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01055 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Install Electrical conduit for New MH to existing MH (PDLCO1) | 2 | 2 | 2023-04-07 08:00 | 2023-04-10 17:00 | -53 | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01060 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Backfill conduit New MH to Existing Manhole (PDLCO1) | 1 | 1 | 2023-04-11 08:00 | 2023-04-11 17:00 | -53 | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01065 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Pull Cable - New MH to Existing Manhole (PDLCO1) | 2 | 2 | 2023-04-12 08:00 | 2023-04-13 17:00 | -53 | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01018 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Install Temp Electrical conduit MH to SG3 (PDLCO1) | 10 | 0 | 2022-08-11 08:00 | 2022-08-24 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-02005 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Excavate for electric Existing Manhole to OG6 (PDLCO1) | 5 | 0 | 2022-03-01 08:00 | 2022-03-04 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-02010 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Install Electrical conduit Existing Manhole to OG6 (PDLCO1) | 5 | 0 | 2022-04-04 08:00 | 2022-05-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-02015 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Encase conduit in concrete Existing Manhole to OG6 (PDLCO1) | 2 | 0 | 2022-05-20 08:00 | 2022-05-23 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-02020 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Backfill Electrical Existing Manhole to OG6 (PDLCO1) | 5 | 0 | 2022-05-24 08:00 | 2022-05-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO039-01005 |  |  | CO039 | [5 empty] | CO #39 - Scope Development - Site 8 Electrical Repairs | 5 | 0 | 2021-08-30 | 2021-08-31 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO039-01010 |  |  | CO039 | [5 empty] | CO #39 - Scope Agreement - Site 8 Electrical Repairs | 20 | 0 | 2021-09-01 | 2021-12-13 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO039-01015 |  |  | CO039 | [5 empty] | CO #39 - Submit Price - Site 8 Electrical Repairs | 5 | 0 | 2021-12-14 08:00 | 2021-12-20 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO039-01020 |  |  | CO039 | [5 empty] | CO #39 - Negotiate/Instruction - Site 8 Electrical Repairs | 20 | 0 | 2021-12-21 08:00 | 2022-01-26 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO039-01025 |  |  | CO039 | [5 empty] | CO #39 - Perform Electrical Repairs - Site 8 Basement | 10 | 0 | 2022-02-14 08:00 | 2022-02-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO071-01005 |  |  | CO071 | [5 empty] | CO #71 (PDLCO3) - Scope Development - Site 8 Basement Cleaning | 5 | 0 | 2021-12-17 | 2021-12-17 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO071-01010 |  |  | CO071 | [5 empty] | CO #71 (PDLCO3) - Scope Agreement - Site 8 Basement Cleaning | 20 | 0 | 2021-12-20 | 2021-12-30 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO071-01015 |  |  | CO071 | [5 empty] | CO #71 (PDLCO3) - Submit Price - Site 8 Basement Cleaning | 5 | 0 | 2021-12-31 08:00 | 2022-01-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO071-01020 |  |  | CO071 | [5 empty] | CO #71 (PDLCO3) - Negotiate/Instruction - Site 8 Basement Cleaning | 20 | 0 | 2022-01-06 08:00 | 2022-01-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO071-01025 |  |  | CO071 | [5 empty] | CO #71 (PDLCO3) - Perform Site 8 Cleaning - Site 8 Basement | 10 | 0 | 2022-02-11 08:00 | 2022-02-14 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01006 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Negotiate - SGS and OGW Electrical Feeder Changes (RFI #370) | 8 | 0 | 2021-12-29 08:00 | 2022-02-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI469-01005 | [8 empty] | RFI #469 - SG1,2,3, & 7 Electrical Diagrams - Submit | 5 | 0 | 2021-12-22 | 2022-01-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI469-01010 | [8 empty] | RFI #469 - SG1,2,3, & 7 Electrical Diagrams - Response (Inadequate) | 10 | 0 | 2022-01-12 | 2022-01-20 |  | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01052 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Coring for New MH to existing MH (PDLCO1) | 1 | 1 | 2023-04-06 08:00 | 2023-04-06 17:00 | -53 | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01090 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Excavate for New MH to SG7 (PDLCO1) | 2 | 0 | 2022-02-21 08:00 | 2022-02-24 17:00 |  | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01100 |  | SG7 | CO059 | [5 empty] | CO #59 (PDLCO1) - Install Electrical conduit for New MH to SG7 (PDLCO1) | 2 | 2 | 2023-04-17 08:00 | 2023-04-18 17:00 | -53 | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01105 |  | SG7 | CO059 | [5 empty] | CO #59 (PDLCO1) - Backfill conduit New MH to SG7 (PDLCO1) | 1 | 1 | 2023-04-19 08:00 | 2023-04-19 17:00 | -53 | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01110 |  | SG7 | CO059 | [5 empty] | CO #59 (PDLCO1) - Pull Cable - New MH to SG7 (PDLCO1) | 2 | 2 | 2023-04-20 08:00 | 2023-04-21 17:00 | -53 | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01095 |  | SG7 | CO059 | [5 empty] | CO #59 (PDLCO1) - Coring for New MH to SG7 (PDLCO1) | 1 | 1 | 2023-04-14 08:00 | 2023-04-14 17:00 | -53 | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01022 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Coring for Existing MH to SG3 (PDLCO1) | 1 | 0 | 2022-08-19 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01023 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Formwork for Existing MH to SG3 (PDLCO1) | 1 | 0 | 2022-08-22 08:00 | 2022-08-22 17:00 |  | 0
In Progress |  | CI NYCHA Update #20.1 | CO059-01040 |  | SG3 | CO059 | [5 empty] | CO #59 (PDLCO1) - Pull/Terminate/Energize Cable - Existing Manhole to SG3 (PDLCO1) | 20 | 23 | 2022-08-26 | 2023-03-29 17:00 | -53 | 0
Completed |  | CI NYCHA Update #20.1 | CO059-02050 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Additional Time for Excavation (SGS-01205) | 2 | 0 | 2022-06-28 08:00 | 2022-06-29 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-02055 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Additional Time for Backfill (SGS-01220) | 1 | 0 | 2022-07-05 08:00 | 2022-07-05 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO021-01005 |  |  | CO021 | [5 empty] | CO #21 - Prep and Submit S8 Fire Standpipe Submittals | 47 | 0 | 2021-11-24 | 2022-01-27 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO021-01010 |  |  | CO021 | [5 empty] | CO #21 - Review/Approve S8 Fire Standpipe Submittals | 10 | 0 | 2022-01-28 | 2022-02-07 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO021-01015 |  |  | CO021 | [5 empty] | CO #21 - Asbestos Abatement including Preparation and Completion of work | 6 | 0 | 2022-02-08 | 2022-02-18 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO021-01020 |  |  | CO021 | [5 empty] | CO #21 - DOB ACP 20 | 3 | 0 | 2022-02-09 | 2022-02-24 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO021-01025 |  |  | CO021 | [5 empty] | CO #21 - S8 Fire Stand Pipe Relocation Filings | 5 | 0 | 2022-02-10 | 2022-02-24 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO021-01030 |  |  | CO021 | [5 empty] | CO #21 - Initial S8 Fire Stand Pipe Relocation Filing and DOB comments | 55 | 0 | 2021-11-23 | 2022-02-24 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI519-01005 | [8 empty] | RFI #519 - SG1,2,3, & 7 Crab Details - Submit | 1 | 0 | 2022-03-02 | 2022-03-02 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI519-01010 | [8 empty] | RFI #519 - SG1,2,3, & 7 Crab Details - Response (Inadequate) | 10 | 0 | 2022-03-03 | 2022-03-08 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI540-01005 | [8 empty] | RFI #540 - SG1,2,3, & 7 Request for Missing information regd. MH Termination in RFI #519 - Submit | 10 | 0 | 2022-03-21 | 2022-03-22 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI540-01010 | [8 empty] | RFI #540 - SG1,2,3, & 7 Request for Missing information regd. MH Termination in RFI #519 - Response | 10 | 0 | 2022-03-23 | 2022-04-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01031 | ATCO | SG5 | ABESTOS | [5 empty] | Test for Asbestos - 2nd Foor --> SG5 | 10 | 0 | 2022-08-24 | 2022-08-30 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01032 | ATCO | SG5 | ABESTOS | [5 empty] | File for Asbestos Abatement- 2nd Foor --> SG5 | 10 | 0 | 2022-08-30 | 2022-09-05 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.5.1 | SG5-01033 | ATCO | SG5 | [6 empty] | Asbestos Abatement - 2nd Foor --> SG5 | 5 | 0 | 2022-09-06 | 2022-09-09 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI519-01015 | [8 empty] | RFI #519 - MLJ Perform Survey & Excavation | 5 | 0 | 2022-03-21 | 2022-03-21 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI512-01005 | [8 empty] | RFI #512 - SG 1-3 Steam Tunnel Abatement - Submit | 1 | 0 | 2022-02-24 | 2022-02-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI512-01010 | [8 empty] | RFI #512 - SG 1-3 Steam Tunnel Abatement - Response | 10 | 0 | 2022-02-25 | 2022-03-02 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI446-01005 | [8 empty] | RFI #446 - SG 1-3 Steam Tunnel Abatement - Submit | 1 | 0 | 2021-10-11 | 2021-10-11 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI446-01010 | [8 empty] | RFI #446 - SG 1-3 Steam Tunnel Abatement - Response | 10 | 0 | 2021-10-12 | 2021-10-22 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI389-01005 | [8 empty] | RFI #389 - SG 1-3 Steam Tunnel Abatement - Submit | 1 | 0 | 2021-12-08 | 2021-12-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | RFI389-01010 | [8 empty] | RFI #389 - SG 1-3 Steam Tunnel Abatement - Response | 10 | 0 | 2021-10-11 | 2021-10-11 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO077-01005 |  |  | CO077 | [5 empty] | CO #77 - Scope Development - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 5 | 0 | 2022-03-03 08:00 | 2022-03-07 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO077-01010 |  |  | CO077 | [5 empty] | CO #77 - Scope Agreement - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 20 | 0 | 2022-03-08 | 2022-03-16 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO077-01015 |  |  | CO077 | [5 empty] | CO #77 - Submit Price - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 5 | 0 | 2022-03-17 08:00 | 2022-03-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO077-01020 |  | SG1 | CO077 | [5 empty] | CO #77 - Negotiate/Instruction - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 20 | 0 | 2022-03-18 08:00 | 2022-11-17 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO077-01025 |  |  | CO077 | [5 empty] | CO #77 - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 12 | 0 | 2022-03-28 | 2022-04-15 |  | 0
Not Started |  | CI NYCHA Update #20.1 | CO059-01045 |  | SG7 | CO059 | [5 empty] | CO #59 (PDLCO1) - Remove Existing Ductbank East of SG7 | 3 | 3 | 2023-03-30 08:00 | 2023-04-03 17:00 | -53 | 0
Completed |  | CI NYCHA Update #20.19 | RFI462-01015 | [8 empty] | RFI #462 - Second Floor Apt Gas Riser Relocation - OG1 - Submit | 1 | 0 | 2021-12-20 08:00 | 2021-12-27 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI462-01020 | [8 empty] | RFI #462 - Second Floor Apt Gas Riser Relocation - Response | 10 | 0 | 2021-12-28 | 2022-04-12 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01005 | [8 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation - Submit | 1 | 0 | 2022-04-04 08:00 | 2022-04-08 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01010 | [8 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation - Response | 10 | 0 | 2022-04-09 | 2022-04-13 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01015 | [8 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation - OG1 | 3 | 0 | 2022-04-14 08:00 | 2022-04-18 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01020 | [8 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation - OG1 DOB Inspection Failed | 3 | 0 | 2022-04-19 | 2022-04-21 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01025 |  | OG1 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG1 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01030 |  | SG4 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - SG4 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01035 |  | SG5 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - SG5 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01040 |  | SG3 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - SG3 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01045 |  | OG2 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG2 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01050 |  | OG3 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG3 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01055 |  | OG4 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG4 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01060 |  | OG5 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG5 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI548-01065 |  | OG6 | [6 empty] | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG6 | 25 | 0 | 2022-11-03 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01011 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - Provide Proposal inc pricing on alternatives - SGS - (FSE CO: 18-0016) | 5 | 0 | 2022-04-29 08:00 | 2022-05-13 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01012 |  |  | CO059 | [5 empty] | CO #59 (PDLCO1) - NYCHA Confirm Scope - SGS - (FSE CO: 18-0016) | 10 | 0 | 2022-05-06 08:00 | 2022-05-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.4.7.1 | SG6-02112 | MLJ | SG6 | CONCRETE | Structure | NEW BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - 1st Floor | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -87 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.2.2.6.1 | SG4-02232 | MLJ | SG4 | CONCRETE |  |  | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2022-11-30 | 2022-12-23 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.2.3.6.1 | SG5-02217 | MLJ | SG5 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 10 | 2023-03-17 10:00 | 2023-03-31 10:00 | -92 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.3.1.8.1 | OG8-02117 | MLJ | OG8 | CONCRETE | Structure | NEW BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - 1st Floor | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -61 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.6.8.1 | OG4-02022 | MLJ | OG4 | CONCRETE |  |  | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2022-12-13 | 2022-12-16 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.3.3.8.1 | OG5-02017 | MLJ | OG5 | CONCRETE |  |  | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2023-01-09 | 2023-01-13 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.5.4.5.1 | OG9-02117 | MLJ | OG9 | CONCRETE | Structure | NEW BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - 1st Floor | 10 | 10 | 2023-02-27 13:00 | 2023-03-13 12:00 | -74 | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.3.8.1 | OG3-02022 | MLJ | OG3 | CONCRETE |  |  | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2022-12-05 | 2022-12-19 |  | 0
Completed | CONSTRUCTION | CI NYCHA Update #20.Construction.5.2.8.1 | OG2-02022 | MLJ | OG2 | CONCRETE |  |  | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2022-11-24 | 2022-11-30 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.1.4.5.1 | OG10-02117 | MLJ | OG10 | CONCRETE | Structure | NEW BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - 1st Floor | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -26 | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.2.5.1 | OG6-02022 | MLJ | OG6 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2022-12-05 | 2023-01-11 17:00 |  | 0
In Progress | CONSTRUCTION | CI NYCHA Update #20.Construction.1.3.5.1 | OG1-02017 | MLJ | OG1 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 0 | 2022-12-21 | 2023-01-11 |  | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.4.5.1 | SG7-02117 | MLJ | SG7 | CONCRETE | Structure | NEW BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - 1st Floor | 10 | 10 | 2023-03-06 10:00 | 2023-03-20 10:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.3.8.1 | SG3-02017 | MLJ | SG3 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 10 | 2023-04-12 08:00 | 2023-04-25 17:00 | -51 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.7.8.1 | SG1-02037 | MLJ | SG1 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 10 | 2023-07-26 10:00 | 2023-08-09 10:00 | -110 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.4.2.4.1 | SG2-02022 | MLJ | SG2 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 10 | 2023-04-06 15:00 | 2023-04-20 15:00 | -34 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.2.5.1 | S8A-02142 | MLJ | S81 | CONCRETE | Exterior | EXISTING BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - 1st Floor | 10 | 10 | 2023-03-06 10:00 | 2023-03-20 10:00 | -19 | 0
Not Started | CONSTRUCTION | CI NYCHA Update #20.Construction.8.1.8.1 | S8E-02032 | MLJ | S82 | CONCRETE | Structure | NEW BUILDINGS | CONDUIT ENCASE |  |  | Encase Electrical Conduits - Cellar | 10 | 10 | 2023-04-07 08:00 | 2023-04-20 17:00 | -34 | 0
Completed |  | CI NYCHA Update #20.19 | RFI546-01005 | [8 empty] | RFI 546 - Tree Clash with Underground Steam OG East - Submit | 5 | 0 | 2022-04-01 | 2022-04-01 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI546-01010 | [8 empty] | RFI 546 - Tree Clash with Underground Steam OG East - Response | 10 | 0 | 2022-04-04 | 2022-05-17 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02105 | [8 empty] | Delay - Unable to Pull Permit due to NYCHA Violations - OG4 | 20 | 0 | 2022-05-27 | 2022-06-20 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-02110 | [8 empty] | Delay - Unable to Pull Permit due to NYCHA Violations - OG5 | 20 | 0 | 2022-05-27 | 2022-06-20 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01007 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Negotiate Revised Scope - SGS and OGW Electrical Feeder Changes (RFI #370) | 10 | 0 | 2022-02-22 08:00 | 2022-06-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.1 | CO059-01008 |  | SGS | CO059 | [5 empty] | CO #59 (PDLCO1) - Issue Instruction - SGS and OGW Electrical Feeder Changes (RFI #370) | 20 | 0 | 2022-06-24 08:00 | 2022-06-24 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI589-01015 | [8 empty] | RFI #589 - Site 8 Access Space - Response | 25 | 0 | 2022-06-20 | 2022-07-22 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | RFI589-01010 | [8 empty] | RFI #589 - Site 8 Access Space - Submit | 25 | 0 | 2022-06-01 | 2022-06-17 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-04005 |  | OG4 | [6 empty] | Remove AC units from First floor apartments OG4 | 20 | 0 | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-04010 |  | OG5 | [6 empty] | Remove AC units from First floor apartments OG5 | 20 | 0 | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-04015 |  | OG3 | [6 empty] | Remove AC units from First floor apartments OG3 | 20 | 0 | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-04020 |  | OG2 | [6 empty] | Remove AC units from First floor apartments OG2 | 20 | 0 | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-04025 |  | OG6 | [6 empty] | Remove AC units from First floor apartments OG6 | 20 | 0 | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-04030 |  | OG1 | [6 empty] | Remove AC units from First floor apartments OG1 | 20 | 0 | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #20.19 | DELAY-05005 |  | SG1 | [6 empty] | NYCHA Relocate Tenant Association Plants --> SG1 & SG2 | 20 | 0 | 2022-06-01 08:00 | 2022-06-24 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000a | [8 empty] | CO #PCO 59 Rev 1 Issued 12/20/21 | 31 | 0 | 2021-11-04 | 2021-12-20 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000b | [8 empty] | CO #PCO 59 Rev 2 Issued 1/10/22 | 13 | 0 | 2021-12-21 | 2022-01-10 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000c | [8 empty] | CO #PCO 59 Initial Negotiation agreed 3/4/22 | 37 | 0 | 2022-01-11 | 2022-03-04 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000d | [8 empty] | CO #PCO 59 Rev 3 Issued 3/25/22 | 15 | 0 | 2022-03-07 | 2022-03-25 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000e | [8 empty] | CO #PCO 59 Rev 4 Issued 5/20 | 40 | 0 | 2022-03-28 | 2022-05-20 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000f | [8 empty] | CO #PCO 59 Rev 5 issued 5/27 | 5 | 0 | 2022-05-23 | 2022-05-27 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000g | [8 empty] | CO #PCO 59 Rev 6 issued 7/13 | 31 | 0 | 2022-05-31 | 2022-07-13 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000h | [8 empty] | CO #PCO 59 - Meeting with EOR on 7/14 | 1 | 0 | 2022-07-14 08:00 | 2022-07-14 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000i | [8 empty] | CO #PCO 59 Rev 7 issued 7/19 (2 options for EOR comments) | 3 | 0 | 2022-07-15 08:00 | 2022-07-19 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000j | [8 empty] | CO #PCO 59 Rev 8 issued 7/26 | 5 | 0 | 2022-07-20 08:00 | 2022-07-26 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.1 | CO059-01000k | [8 empty] | CO #PCO 59 - PCO 59 Scope Agreed 7/26 | 1 | 0 | 2022-07-26 08:00 | 2022-07-26 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | DELAY-01111 | [8 empty] | Basement not in a suitable condition for Engineering - Site 8 | 90 | 0 | 2020-06-14 08:00 | 2022-03-25 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | COXXX-01005 | [8 empty] | CO #XX (TBD) - SWO Issued for waterproofing existing buildings | 20 | 0 | 2022-06-20 08:00 | 2022-07-22 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO102-01005 | [8 empty] | CO #102 - Scope Development - SGS Shutdown Temp Power | 5 | 0 | 2022-07-25 08:00 | 2022-07-28 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO102-01010 | [8 empty] | CO #102 - Scope Agreement - SGS Shutdown Temp Power | 10 | 0 | 2022-07-29 08:00 | 2022-08-25 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO102-01015 | [8 empty] | CO #102 - Submit Price - SGS Shutdown Temp Power | 10 | 0 | 2022-08-25 08:00 | 2022-09-01 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO102-01020 | [8 empty] | CO #102 - Negotiate/Instruction - SGS Shutdown Temp Power | 160 | 0 | 2022-09-02 | 2022-09-30 |  | 0
Not Started |  | CI NYCHA Update #27.1 | CO102-01025 | [8 empty] | CO #102 - Provide Temp Power for Shutdown | 1 | 1 | 2023-02-27 08:00 | 2023-02-27 17:00 | -31 | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01005 | [8 empty] | CO #100 - Scope Development - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 5 | 0 | 2022-06-25 08:00 | 2022-07-25 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01010 | [8 empty] | CO #100 - Scope Agreement - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 15 | 0 | 2022-07-26 | 2022-10-05 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01015 | [8 empty] | CO #100 - Submit Price - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 10 | 0 | 2022-10-05 | 2022-10-05 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01020 | [8 empty] | CO #100 - Negotiate/Instruction - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 30 | 0 | 2022-10-05 | 2022-10-05 |  | 0
Not Started |  | CI NYCHA Update #27.1 | CO100-01025 |  | SG7 | [6 empty] | CO #100 - Install Additional Metal Panel Support SG7 | 20 | 0 | 2023-01-25 | 2023-02-22 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01030 | [8 empty] | CO #100 - Install Additional Metal Panel Support OG8 | 20 | 0 | 2022-09-23 | 2022-12-23 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01035 | [8 empty] | CO #100 - Install Additional Metal Panel Support OG9 | 20 | 0 | 2022-07-05 | 2022-08-15 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO100-01040 | [8 empty] | CO #100 - Install Additional Metal Panel Support OG10 | 20 | 0 | 2022-08-10 | 2022-10-14 |  | 0
Not Started |  | CI NYCHA Update #27.1 | CO100-01045 |  | S81 | [6 empty] | CO #100 - Install Additional Metal Panel Support S8A | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -69 | 0
Completed |  | CI NYCHA Update #27.1 | CO098-01005 | [8 empty] | CO #98 - Scope Development - OG6 Structural Steel Interference | 5 | 0 | 2022-06-18 | 2022-07-18 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO098-01010 | [8 empty] | CO #98 - Scope Agreement - OG6 Structural Steel Interference (PDL 10) | 30 | 0 | 2022-07-19 | 2022-11-17 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO098-01015 | [8 empty] | CO #98 - Submit Price - OG6 Structural Steel Interference (PDL 10) | 10 | 0 | 2022-11-17 | 2022-11-17 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO098-01020 | [8 empty] | CO #98 - Negotiate/Instruction - OG6 Structural Steel Interference (PDL 10) | 30 | 0 | 2022-11-17 | 2022-11-17 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO098-01025 | [8 empty] | CO #98 - Make changes to structural steel supports (PDL 10) | 10 | 0 | 2022-11-28 08:00 | 2022-12-16 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO093-01005 | [8 empty] | CO #93 - Scope Development - Roof Access and ATS Room Door Issue | 5 | 0 | 2022-05-15 08:00 | 2022-06-15 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO093-01010 | [8 empty] | CO #93 - Scope Agreement - Roof Access and ATS Room Door Issue | 30 | 0 | 2022-06-16 | 2022-06-27 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO093-01015 | [8 empty] | CO #93 - Submit Price - Roof Access and ATS Room Door Issue | 10 | 0 | 2022-06-28 08:00 | 2022-07-13 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO093-01020 | [8 empty] | CO #93 - Negotiate/Instruction - Roof Access and ATS Room Door Issue | 160 | 0 | 2022-07-13 08:00 | 2022-10-04 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO093-01025 | [8 empty] | CO #93 - Manufacture Steel - SG6 | 20 | 0 | 2022-10-04 | 2022-10-07 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO093-01030 | [8 empty] | CO #93 - Remove Blockwork and protect equipment - SG6 | 5 | 0 | 2022-10-04 | 2022-10-07 |  | 0
In Progress |  | CI NYCHA Update #27.1 | CO093-01035 |  | SG6 | [6 empty] | CO #93 - Install Steel Supports - SG6 | 5 | 2 | 2022-10-09 | 2023-02-28 17:00 | 41 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01040 |  | SG6 | [6 empty] | CO #93 - Fireproof Steel Supports - SG6 | 5 | 5 | 2023-03-01 08:00 | 2023-03-07 17:00 | 41 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01105 |  | OG8 | [6 empty] | CO #93 - Manufacture Steel - OG8 | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -19 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01110 |  | OG8 | [6 empty] | CO #93 - Remove Blockwork and protect equipment - OG8 | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -19 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01115 |  | OG8 | [6 empty] | CO #93 - Install Steel Supports - OG8 | 5 | 5 | 2023-04-03 08:00 | 2023-04-07 17:00 | -19 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01120 |  | OG8 | [6 empty] | CO #93 - Fireproof Steel Supports - OG8 | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -19 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01205 |  | OG10 | [6 empty] | CO #93 - Manufacture Steel - OG10 | 20 | 20 | 2023-02-27 08:00 | 2023-03-24 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01210 |  | OG10 | [6 empty] | CO #93 - Remove Blockwork and protect equipment - OG10 | 5 | 5 | 2023-03-27 08:00 | 2023-03-31 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01215 |  | OG10 | [6 empty] | CO #93 - Install Steel Supports - OG10 | 5 | 5 | 2023-04-03 08:00 | 2023-04-07 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01220 |  | OG10 | [6 empty] | CO #93 - Fireproof Steel Supports - OG10 | 5 | 5 | 2023-04-10 08:00 | 2023-04-14 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01315 |  | OG9 | [6 empty] | CO #93 - Cut Steel and blockwork and protect equipment - OG9 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 11 | 0
Not Started |  | CI NYCHA Update #27.1 | CO093-01320 |  | OG9 | [6 empty] | CO #93 - Fireproof Steel Supports - OG9 | 5 | 5 | 2023-03-06 08:00 | 2023-03-10 17:00 | 11 | 0
Completed |  | CI NYCHA Update #27.19 | RFI589-01005 | [8 empty] | RFI #589 - Site 8 Access Space - Submit | 1 | 0 | 2022-06-17 08:00 | 2022-06-17 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI589-01020 | [8 empty] | RFI #589 - Site 8 Access Space - Response | 5 | 0 | 2022-06-20 08:00 | 2022-07-22 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI625-01005 | [8 empty] | RFI #625 - Site 8 Access Space - Submit | 10 | 0 | 2022-07-25 08:00 | 2022-08-08 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI625-01010 | [8 empty] | RFI #625 - Site 8 Access Space - Response | 15 | 0 | 2022-08-09 08:00 | 2022-09-06 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI557-01005 | [8 empty] | RFI #557 - 2nd FL Electrical Room Lockable Gas Valve - Submit | 5 | 0 | 2022-04-22 | 2022-04-27 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI557-01010 | [8 empty] | RFI #557 - 2nd FL Electrical Room Lockable Gas Valve - Response | 10 | 0 | 2022-04-28 | 2022-06-09 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI557-01015 | [8 empty] | RFI #557 - Weekly Progress Meeting Item 68.2 - 2nd Floor Apt DOB Approved Plumbing Dwgs - NYCHA Rev. Schedule B | 60 | 0 | 2022-06-10 08:00 | 2022-11-03 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO108-01005 | [8 empty] | CO #108 - Scope Development - Replace Steam & Water Pipe under W33rd | 5 | 0 | 2022-08-12 08:00 | 2022-09-11 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO108-01010 | [8 empty] | CO #108 - Scope Agreement - Replace Steam & Water Pipe under W33rd (PDL Letter 11) | 10 | 0 | 2022-09-12 08:00 | 2022-12-12 |  | 0
Not Started |  | CI NYCHA Update #27.1 | CO108-01015 | [8 empty] | CO #108 - Submit Price - Replace Steam & Water Pipe under W33rd | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | -200 | 0
Not Started |  | CI NYCHA Update #27.1 | CO108-01020 | [8 empty] | CO #108 - Negotiate/Instruction - Replace Steam & Water Pipe under W33rd | 30 | 30 | 2023-03-13 08:00 | 2023-04-21 17:00 | -200 | 0
Completed |  | CI NYCHA Update #27.1 | CO108-01025 | [8 empty] | CO #108 - Prepare Shop Drawings | 10 | 0 | 2022-10-21 | 2022-10-21 |  | 0
Completed |  | CI NYCHA Update #27.1 | CO108-01030 | [8 empty] | CO #108 - Review/Approve Shop Drawings | 10 | 0 | 2022-10-22 | 2022-11-07 |  | 0
In Progress |  | CI NYCHA Update #27.1 | CO108-01035 | [8 empty] | CO #108 - Procure Pipe | 60 | 12 | 2022-11-08 | 2023-03-14 17:00 | -172 | 0
Not Started |  | CI NYCHA Update #27.1 | CO108-01040 | [8 empty] | CO #108 - Perform Pipe Replacement | 90 | 90 | 2023-04-24 08:00 | 2023-08-29 17:00 | -200 | 0
Completed |  | CI NYCHA Update #27.19 | RFI628-01005 | [8 empty] | RFI #628 - Underground Steam Piping Route from OG8 to OG5 Street Crossing - Submit | 1 | 0 | 2022-08-12 08:00 | 2022-08-12 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI628-01010 | [8 empty] | RFI #628 - Underground Steam Piping Route from OG8 to OG5 Street Crossing - Response | 24 | 0 | 2022-08-15 | 2022-09-16 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI518-01005 | [8 empty] | RFI #518 PCOCO 68 Expose Existing Underground Pipe Under W33rd & W35th St - Submit | 1 | 0 | 2022-03-02 08:00 | 2022-03-02 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI518-01010 | [8 empty] | RFI #518 PCOCO 68 Expose Existing Underground Pipe Under W33rd & W35th St - Response | 11 | 0 | 2022-03-03 | 2022-03-17 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI501-01005 | [8 empty] | RFI #501 - Underground Pipe Street Crossing at OG-5 - Submit | 1 | 0 | 2022-02-09 08:00 | 2022-02-09 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI501-01010 | [8 empty] | RFI #501 - Underground Pipe Street Crossing at OG-5 - Response | 99 | 0 | 2022-02-10 | 2022-06-30 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI428-01005 | [8 empty] | RFI #428 - Underground Pipe Street Crossing at OG-5 - Submit | 1 | 0 | 2021-11-17 08:00 | 2021-11-17 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI428-01010 | [8 empty] | RFI #428 - Underground Pipe Street Crossing at OG-5 - Response | 267 | 0 | 2021-11-18 | 2021-12-13 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI426-01005 | [8 empty] | RFI #426 - Underground Pipe insulation Street Crossing at OG-5, OG-3 & S8 - Submit | 1 | 0 | 2021-11-15 08:00 | 2021-11-15 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI426-01010 | [8 empty] | RFI #426 - Underground Pipe insulation Street Crossing at OG-5, OG-3 & S8 - Response | 11 | 0 | 2021-11-16 | 2021-12-01 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI422-01005 | [8 empty] | RFI #422 - Underground Pipe Street Crossing at 33rd St - Submit | 1 | 0 | 2021-11-08 08:00 | 2021-11-08 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI422-01010 | [8 empty] | RFI #422 - Underground Pipe Street Crossing at 33rd St - Response | 2 | 0 | 2021-11-09 | 2021-11-11 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI398-01005 | [8 empty] | RFI #398 - OG-5 Underground Street Crossing Electrical - Submit | 1 | 0 | 2021-10-15 08:00 | 2021-10-15 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI398-01010 | [8 empty] | RFI #398 - OG-5 Underground Street Crossing Electrical - Response | 2 | 0 | 2021-10-18 | 2021-10-19 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI332-01005 | [8 empty] | RFI #332 - OG8 Underground Pre-Engineered Pipe Layout & POE - Submit | 1 | 0 | 2021-08-06 08:00 | 2021-08-06 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI332-01010 | [8 empty] | RFI #332 - OG8 Underground Pre-Engineered Pipe Layout & POE - Response | 9 | 0 | 2021-08-09 | 2021-08-19 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI304-01005 | [8 empty] | RFI #304 - Potential Deterioration to underground pipe installed under previous contract - Submit | 1 | 0 | 2021-07-15 08:00 | 2021-07-15 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI304-01010 | [8 empty] | RFI #304 - Potential Deterioration to underground pipe installed under previous contract - Response | 54 | 0 | 2021-07-16 | 2021-09-30 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI301-01005 | [8 empty] | RFI #301 - Underground Pre-installed utilities - Package 2 - Submit | 1 | 0 | 2021-07-02 08:00 | 2021-07-02 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI301-01010 | [8 empty] | RFI #301 - Underground Pre-installed utilities - Package 2 - Response | 6 | 0 | 2021-07-05 | 2021-07-13 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI283-01005 | [8 empty] | RFI #283 - Revised OG8 Foundation Drawings - Submit | 1 | 0 | 2021-06-21 08:00 | 2021-06-21 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI283-01010 | [8 empty] | RFI #283 - Revised OG8 Foundation Drawings - Response | 9 | 0 | 2021-06-22 | 2021-07-02 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI281-01005 | [8 empty] | RFI #281 - OG-8 into OG-5 UG LPS POE connecting to interior new LPS routing / design - Submit | 1 | 0 | 2021-06-21 08:00 | 2021-06-21 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI281-01010 | [8 empty] | RFI #281 - OG-8 into OG-5 UG LPS POE connecting to interior new LPS routing / design - Response | 4 | 0 | 2021-06-22 | 2021-06-25 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI200-01005 | [8 empty] | RFI #200 - Package 2 Discrepancies with Electrical - Submit | 1 | 0 | 2021-03-11 08:00 | 2021-03-11 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI200-01010 | [8 empty] | RFI #200 - Package 2 Discrepancies with Electrical - Response | 7 | 0 | 2021-03-12 | 2021-03-22 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI194-01005 | [8 empty] | RFI #194 - Package 2 As-built Drawings - Submit | 1 | 0 | 2021-03-05 08:00 | 2021-03-05 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI194-01010 | [8 empty] | RFI #194 - Package 2 As-built Drawings - Response | 1 | 0 | 2021-03-08 | 2021-03-08 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI111-01005 | [8 empty] | RFI #111 - OG-5 to OG-8 Underground Electrical Conduit Ductbank - Submit | 1 | 0 | 2020-09-22 08:00 | 2020-09-22 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI111-01010 | [8 empty] | RFI #111 - OG-5 to OG-8 Underground Electrical Conduit Ductbank - Response | 16 | 0 | 2020-09-23 | 2020-10-15 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI506-01005 | [8 empty] | RFI #506 - Site 8 Underground Steam POE to Street Connection - Submit (CO #60) | 5 | 0 | 2022-02-16 08:00 | 2022-02-16 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI506-01010 | [8 empty] | RFI #506 - Site 8 Underground Steam POE to Street Connection - Response (CO #60) | 5 | 0 | 2022-02-17 | 2022-03-22 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.2 | CO060-01005 | [8 empty] | CO #60 - Scope Development - Replace Steam & Water Pipe under W35th Street | 5 | 0 | 2021-10-06 08:00 | 2021-11-06 |  | 0
Completed |  | CI NYCHA Update #27.1.2 | CO060-01010 | [8 empty] | CO #60 - Scope Agreement - Replace Steam & Water Pipe under W35th Street | 20 | 0 | 2021-11-08 | 2022-01-13 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.2 | CO060-01015 | [8 empty] | CO #60 - Submit Price - Replace Steam & Water Pipe under W35th Street | 5 | 0 | 2022-01-14 08:00 | 2022-02-11 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.2 | CO060-01020 | [8 empty] | CO #60 - Negotiate - Replace Steam & Water Pipe under W35th Street | 8 | 0 | 2022-02-14 08:00 | 2022-11-03 17:00 |  | 0
In Progress |  | CI NYCHA Update #27.1.2 | CO060-01025 |  | OG3 | [6 empty] | CO #60 - Revise Scope - Additional Steam Pipe - OG3 to Site 8 | 30 | 0 | 2022-11-04 | 2023-02-15 |  | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01030 |  | OG3 | [6 empty] | CO #60 - Revised Scope Agreement - Additional Steam Pipe - OG3 to Site 8 | 20 | 10 | 2023-02-16 | 2023-03-10 17:00 | -118 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01035 |  | OG3 | [6 empty] | CO #60 - Submit Revised Price - Additional Steam Pipe - OG3 to Site 8 | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -118 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01040 |  | OG3 | [6 empty] | CO #60 - Negotiate Revised Scope - Additional Steam Pipe - OG3 to Site 8 | 30 | 30 | 2023-03-27 08:00 | 2023-05-05 17:00 | -118 | 0
In Progress |  | CI NYCHA Update #27.1.2 | CO060-01045 |  | OG3 | [6 empty] | CO #60 - Prepare Drawings - Additional Steam Pipe - OG3 to Site 8 | 15 | 0 | 2022-12-16 08:00 | 2023-02-15 |  | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01050 |  | OG3 | [6 empty] | CO #60 - Review/Approve Drawings - Additional Steam Pipe - OG3 to Site 8 | 10 | 4 | 2023-02-16 | 2023-03-02 17:00 | -132 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01055 |  | OG3 | [6 empty] | CO #60 - Procure Pipe - Additional Steam Pipe - OG3 to Site 8 | 60 | 60 | 2023-03-03 08:00 | 2023-05-25 17:00 | -132 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01060 |  | OG3 | [6 empty] | CO #60 - Install Additional Steam Pipe - OG3 to Site 8 | 30 | 30 | 2023-05-26 08:00 | 2023-07-10 17:00 | -132 | 0
Completed |  | CI NYCHA Update #27.19 | RFI421-01005 | [8 empty] | RFI #421 Underground Pipe Street Crossing at OG-3 - Submit (CO #60) | 5 | 0 | 2021-11-05 08:00 | 2021-11-05 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI421-01010 | [8 empty] | RFI #421 Underground Pipe Street Crossing at OG-3 - Response (CO #60) | 5 | 0 | 2021-11-08 | 2021-12-23 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.3 | CO122-01005 | [8 empty] | CO #122 - Scope Development - SG3 AC Units & Window Guards | 5 | 0 | 2022-11-07 08:00 | 2022-11-13 |  | 0
Completed |  | CI NYCHA Update #27.1.3 | CO122-01010 | [8 empty] | CO #122 - Scope Agreement - SG3 AC Units & Window Guards (PDL Letter 12) | 30 | 0 | 2022-11-14 | 2022-12-15 |  | 0
Not Started |  | CI NYCHA Update #27.1.3 | CO122-01015 |  | SG3 | [6 empty] | CO #122 - Submit Price - SG3 AC Units & Window Guards | 10 | 10 | 2023-02-27 08:00 | 2023-03-10 17:00 | 25 | 0
Not Started |  | CI NYCHA Update #27.1.3 | CO122-01020 |  | SG3 | [6 empty] | CO #122 - Negotiate - SG3 AC Units & Window Guards | 30 | 30 | 2023-03-13 08:00 | 2023-04-21 17:00 | 25 | 0
In Progress |  | CI NYCHA Update #27.1.3 | CO122-01025 |  | SG3 | [6 empty] | CO #122 - Perform Work - SG3 AC Units & Window Guards | 20 | 5 | 2023-01-06 08:00 | 2023-03-03 17:00 | -108 | 0
Not Started |  | CI NYCHA Update #27.1.3 | CO122-01030 | [8 empty] | CO #122 - Additional Time for Heating under Low Temperatures | 10 | 10 | 2023-03-06 08:00 | 2023-03-17 17:00 | -108 | 0
Completed |  | CI NYCHA Update #27.1.4 | CO123-01005 | [8 empty] | CO #123 - Scope Development - Substitute for Cladding Design OG9, OG10, SG7, S8 | 5 | 0 | 2022-11-18 08:00 | 2022-11-22 |  | 0
In Progress |  | CI NYCHA Update #27.1.4 | CO123-01010 |  | SG7 | [6 empty] | CO #123 - Scope Agreement - Substitute for Cladding Design OG9, OG10, SG7, S8 | 30 | 0 | 2022-11-23 | 2023-01-23 |  | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01015 |  | SG7 | [6 empty] | CO #123 - Submit Price - Substitute for Cladding Design OG9, OG10, SG7, S8 | 10 | 0 | 2023-01-23 08:00 | 2023-01-23 17:00 |  | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01020 |  | SG7 | [6 empty] | CO #123 - Negotiate - Substitute for Cladding Design OG9, OG10, SG7, S8 | 30 | 0 | 2023-01-23 08:00 | 2023-01-23 17:00 |  | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01025 |  | SG7 | [6 empty] | CO #123 - Procure Materials - Substitute for Cladding Design OG9, OG10, SG7, S8 | 10 | 10 | 2023-03-06 08:00 | 2023-03-17 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01030 |  | OG9 | [6 empty] | CO #123 - Perform Work @ OG9 | 10 | 10 | 2023-03-20 08:00 | 2023-03-31 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01040 |  | OG10 | [6 empty] | CO #123 - Perform Work @ OG10 | 10 | 10 | 2023-04-03 08:00 | 2023-04-14 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01050 |  | SG7 | [6 empty] | CO #123 - Perform Work @ SG7 | 10 | 10 | 2023-04-17 08:00 | 2023-04-28 17:00 | -22 | 0
Not Started |  | CI NYCHA Update #27.1.4 | CO123-01060 | [8 empty] | CO #123 - Perform Work @ Site 8 | 10 | 10 | 2023-05-01 08:00 | 2023-05-12 17:00 | -22 | 0
In Progress |  | CI NYCHA Update #27.1 | CO007-01037 |  | OG8 | [6 empty] | Install Boiler Accessories - OG8 | 15 | 15 | 2022-12-12 | 2023-03-17 17:00 | -106 | 0
Completed |  | CI NYCHA Update #27.19 | RFI127-01005 | [8 empty] | RFI #127 - OG9 Structural Steel missing dimensions - Submit | 1 | 0 | 2020-10-30 08:00 | 2020-10-30 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI127-01010 | [8 empty] | RFI #127 - OG9 Structural Steel missing dimensions - Response | 5 | 0 | 2020-11-02 | 2020-11-09 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI166-01005 | [8 empty] | RFI #166 - Follow up RFI for RFI #127 - OG9 Missing Dimensions - Submit | 1 | 0 | 2021-01-04 08:00 | 2021-01-04 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI166-01010 | [8 empty] | RFI #166 - Follow up RFI for RFI #127 - OG9 Missing Dimensions - Response | 16 | 0 | 2021-01-05 | 2021-01-27 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI619-01005 | [8 empty] | RFI #619 - OG9 Windscreen vs Metal Panel - Submit | 1 | 0 | 2022-08-05 08:00 | 2022-08-05 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI619-01010 | [8 empty] | RFI #619 - OG9 Windscreen vs Metal Panel - Response | 7 | 0 | 2022-08-08 | 2022-08-16 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI656-01005 | [8 empty] | RFI #656 - Metal panel vs wind screen issue - Submit | 1 | 0 | 2022-09-29 08:00 | 2022-09-29 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI656-01010 | [8 empty] | RFI #656 - Metal panel vs wind screen issue - Response | 11 | 0 | 2022-09-30 | 2022-10-17 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI672-01005 | [8 empty] | RFI #672 - Follow Up to RFI 656: Metal Panel vs Wind Screen Issue - Submit | 1 | 0 | 2022-10-24 08:00 | 2022-10-24 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI672-01010 | [8 empty] | RFI #672 - Follow Up to RFI 656: Metal Panel vs Wind Screen Issue - Response | 16 | 0 | 2022-10-25 | 2022-11-17 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI619-01015 | [8 empty] | RFI #619 - Designer Review Options and provide direction to cut panels | 38 | 0 | 2022-08-16 08:00 | 2022-10-07 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI663-01005 | [8 empty] | RFI #663 - SG3 AC Units & Window Guards - Submit | 1 | 0 | 2022-10-12 | 2022-10-12 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI663-01010 | [8 empty] | RFI #663 - SG3 AC Units & Window Guards - Response | 16 | 0 | 2022-10-13 | 2022-10-31 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI681-01005 | [8 empty] | RFI #681 - SG3 Window Guards (Follow up to RFI 663) - Submit | 1 | 0 | 2022-11-01 08:00 | 2022-11-01 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI681-01010 | [8 empty] | RFI #681 - SG3 Window Guards (Follow up to RFI 663) - Response | 6 | 0 | 2022-11-02 | 2022-11-09 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI690-01005 | [8 empty] | RFI #690 - SG3 Window Guards (Follow up to RFI 663 & 681) - Submit | 1 | 0 | 2022-11-17 08:00 | 2022-11-17 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI690-01010 | [8 empty] | RFI #690 - SG3 Window Guards (Follow up to RFI 663 & 681) - Response | 3 | 0 | 2022-11-18 | 2022-11-22 17:00 |  | 0
Completed |  | CI NYCHA Update #27.19 | RFI628-01015 | [8 empty] | RFI #628 - Weekly Meeting Topic 68.12 OG5 to Street Connection (33rd Street Crossing) | 5 | 0 | 2022-01-26 | 2022-09-14 17:00 |  | 0
Completed |  | CI NYCHA Update #27.1.2 | CO060-02030 | [8 empty] | CO #60 - Weekly Meeting Topic 68.11 OG3 & Site 8 Existing/New (35th Street Crossing) | 5 | 0 | 2022-01-26 08:00 | 2022-09-14 17:00 |  | 0
In Progress |  | CI NYCHA Update #27.1.1 | CO059-01037 | [8 empty] | CO #59 (PDLCO1) - Con Ed Price and Schedule Shutdown | 20 | 10 | 2022-08-26 08:00 | 2023-03-10 17:00 | -40 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01065 | [8 empty] | CO #60 - Excavate at Curtain Wall for flood protection | 3 | 3 | 2023-08-08 08:00 | 2023-08-10 17:00 | -132 | 0
Completed |  | CI NYCHA Update #27.19 | RFI421-01015 | [8 empty] | RFI #421 - Weekly Meeting Topic 68.11 OG3 & Site 8 Existing/New (35th Street Crossing) | 5 | 0 | 2022-01-26 | 2022-09-14 17:00 |  | 0
Not Started |  | CI NYCHA Update #27.1 | CO108-01045 | [8 empty] | CO #108 - Complete Remaining Curtain Wall affected by Change Order #108 | 10 | 10 | 2023-10-27 08:00 | 2023-11-13 17:00 | -187 | 0
In Progress |  | CI NYCHA Update #27.1 | CO108-01012 | [8 empty] | CO #108 - NYCHA formalize PDL | 50 | 20 | 2022-12-13 08:00 | 2023-03-24 17:00 | -180 | 0
Not Started |  | CI NYCHA Update #27.19 | DELAY-02035 |  | SG6 | [6 empty] | EOR file drawings for sewer connection SG6 (RFI 644 & 686) | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | 51 | 0
Not Started |  | CI NYCHA Update #27.19 | DELAY-02040 |  | OG8 | [6 empty] | EOR file drawings for sewer connection OG8 | 5 | 5 | 2023-02-27 08:00 | 2023-03-03 17:00 | -19 | 0
Not Started |  | CI NYCHA Update #27.Construction.2.2.5.EFPC.4 | SG4-01763 | MLJ | SG4 |  |  | SITE |  |  |  | NYCHA Remove Temp Boilers @ SG4 | 10 | 10 | 2023-03-15 08:00 | 2023-03-28 17:00 | 8 | 0
Completed |  | CI NYCHA Update #27.1.2 | CO060-01027 | [8 empty] | CO #60 - PDL Letter Issued for Materials Only | 5 | 0 | 2022-12-15 | 2022-12-15 17:00 |  | 0
Not Started |  | CI NYCHA Update #27.Construction.1.5.5 | OGE-01766 | ASPEN | OGE |  |  | SITE |  |  |  | Place topsoil --> OG Phase 4 (Building Perimeters) | 3 | 3 | 2023-09-01 08:00 | 2023-09-05 17:00 | -13 | 0
Not Started |  | CI NYCHA Update #27.Construction.1.5.5 | OGE-01767 | ASPEN | OGE |  |  | SITE |  |  |  | Place trees and plantings --> OG Phase 4 (Building Perimeters) | 5 | 5 | 2023-09-06 08:00 | 2023-09-12 17:00 | -13 | 0
Not Started |  | CI NYCHA Update #27.Construction.1.5.5 | OGE-01768 | ASPEN | OGE |  |  | SITE |  |  |  | Place lawn --> OG Phase 4 (Building Perimeters) | 5 | 5 | 2023-09-13 08:00 | 2023-09-19 17:00 | -13 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01170 | [8 empty] | CO #60 - Install remaining Concrete walkways affected by CO#60 | 10 | 10 | 2023-10-12 08:00 | 2023-10-26 17:00 | -133 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01070 | [8 empty] | CO #60 - Form concrete footings at Curtain Wall for flood protection | 4 | 4 | 2023-08-11 08:00 | 2023-08-16 17:00 | -132 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01075 | [8 empty] | CO #60 - Rebar concrete footings at Curtain Wall for flood protection | 3 | 3 | 2023-08-17 08:00 | 2023-08-21 17:00 | -132 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01080 | [8 empty] | CO #60 - Pour concrete footings at Curtain Wall for flood protection | 2 | 2 | 2023-08-22 08:00 | 2023-08-23 17:00 | -132 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01085 | [8 empty] | CO #60 - Cure concrete footings at Curtain Wall for flood protection | 7 | 7 | 2023-08-24 08:00 | 2023-08-30 17:00 | -189 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01090 | [8 empty] | CO #60 - Strip Forms concrete footings at Curtain Wall for flood protection | 2 | 2 | 2023-08-31 08:00 | 2023-09-01 17:00 | -133 | 0
Not Started |  | CI NYCHA Update #27.1.2 | CO060-01095 | [8 empty] | CO #60 - Backfill surrounding area at Curtain Wall for flood protection | 2 | 2 | 2023-09-05 08:00 | 2023-09-06 17:00 | -133 | 0
Not Started |  | CI NYCHA Update #27.Construction.2.2.6.2 | SG4-03111 | WELKIN | SG4 |  |  | EXISTING BUILDINGS |  |  |  | Install Remaining Ductwork after MEP demo - 1st Floor | 5 | 5 | 2023-07-26 08:00 | 2023-08-01 17:00 | -60 | 0
Not Started |  | CI NYCHA Update #27.Construction.2.2.6.2 | SG4-03111a | WELKIN | SG4 |  |  | EXISTING BUILDINGS |  |  |  | Handover Remaining Ductwork | 5 | 5 | 2023-08-02 08:00 | 2023-08-08 17:00 | -55 | 0
In Progress |  | CI NYCHA Update #27.1 | CO108-01011 | [8 empty] | CO #108 - NYCHA Issue Instruction - Replace Steam & Water Pipe under W33rd (PDL Letter 11) | 40 | 40 | 2022-12-13 08:00 | 2023-04-21 17:00 | -200 | 0
In Progress |  | CI NYCHA Update #28.19 | RFI730-01010 | [8 empty] | RFI #730 - Phone Line for Smoke Detection Panel - Response | 15 | 5 | 2023-02-10 | 2023-03-03 17:00 | 19 | 0
Completed |  | CI NYCHA Update #28.19 | RFI730-01005 | [8 empty] | RFI #730 - Phone Line for Smoke Detection Panel - Submit | 1 | 0 | 2023-02-09 08:00 | 2023-02-09 17:00 |  | 0
Completed |  | CI NYCHA Update #28.19 | RFI718-01015 | [8 empty] | RFI #718 - Phone Line for Smoke Detection Panel - Response | 15 | 0 | 2023-01-25 | 2023-02-09 17:00 |  | 0
Completed |  | CI NYCHA Update #28.19 | RFI718-01010 | [8 empty] | RFI #718 - Phone Line for Smoke Detection Panel - Submit | 1 | 0 | 2023-01-24 08:00 | 2023-01-24 17:00 |  | 0
Completed |  | CI NYCHA Update #28.19 | RFI718-01005 | [8 empty] | RFI #718 - Request by E-Mail - Phone Line for Smoke Detection Panel | 5 | 0 | 2022-08-30 | 2023-01-23 17:00 |  | 0
Not Started |  | CI NYCHA Update #28.19 | RFI692-01025 | [8 empty] | RFI #692 - Site 8-1 - Missing exterior foundation rebar detail - Fab/Del Rebar | 10 | 10 | 2023-03-02 08:00 | 2023-03-15 17:00 | -116 | 0
In Progress |  | CI NYCHA Update #28.19 | RFI692-01020 | [8 empty] | RFI #692 - Site 8-1 - Missing exterior foundation rebar detail - Review Shop Dwgs | 15 | 3 | 2023-02-20 | 2023-03-01 17:00 | -116 | 0
Completed |  | CI NYCHA Update #28.19 | RFI692-01015 | [8 empty] | RFI #692 - Site 8-1 - Missing exterior foundation rebar detail - Submit Shop Dwgs | 1 | 0 | 2023-01-16 08:00 | 2023-02-17 17:00 |  | 0
Completed |  | CI NYCHA Update #28.19 | RFI692-01010 | [8 empty] | RFI #692 - Site 8-1 - Missing exterior foundation rebar detail - Response | 15 | 0 | 2022-11-25 | 2023-01-13 17:00 |  | 0
Completed |  | CI NYCHA Update #28.19 | RFI692-01005 | [8 empty] | RFI #692 - Site 8-1 - Missing exterior foundation rebar detail - Submit | 1 | 0 | 2022-11-14 08:00 | 2022-11-23 |  | 0
In Progress |  | CI NYCHA Update #28.19 | DELAY-05010 | [8 empty] | Steam Leak - OG4 - 2nd Floor - Equipment Damage | 30 | 20 | 2023-02-07 | 2023-03-24 17:00 | -77 | 0
In Progress |  | CI NYCHA Update #28.19 | DELAY-01135 | [8 empty] | Basement not in a suitable condition to continue work (Steam) - SG1 | 20 | 20 | 2022-12-05 | 2023-03-24 17:00 | -58 | 0
In Progress |  | CI NYCHA Update #28.19 | DELAY-01130 | [8 empty] | Basement not in a suitable condition to continue work (Sewage) - SG3 | 20 | 20 | 2022-12-07 | 2023-03-24 17:00 | -112 | 0
Not Started |  | CI NYCHA Update #28.1 | CO154-01025 | [8 empty] | CO #154 - SG1 Steam Leak Repair | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -113 | 0
Not Started |  | CI NYCHA Update #28.1 | CO154-01020 | [8 empty] | CO #154 - Negotiate/Instruction - SG1 Steam Leak Repair | 30 | 30 | 2023-04-10 08:00 | 2023-05-19 17:00 | -108 | 0
Not Started |  | CI NYCHA Update #28.1 | CO154-01015 | [8 empty] | CO #154 - Submit Price - SG1 Steam Leak Repair | 10 | 10 | 2023-03-27 08:00 | 2023-04-07 17:00 | -108 | 0
In Progress |  | CI NYCHA Update #28.1 | CO154-01010 | [8 empty] | CO #154 - Scope Agreement - SG1 Steam Leak Repair | 30 | 20 | 2023-02-23 | 2023-03-24 17:00 | -108 | 0
Completed |  | CI NYCHA Update #28.1 | CO154-01005 | [8 empty] | CO #154 - Scope Development - SG1 Steam Leak Repair | 5 | 0 | 2023-01-22 | 2023-02-22 |  | 0
Not Started |  | CI NYCHA Update #28.1 | CO141-01025 | [8 empty] | CO #141 - Install Vita Link Cable - OG6 | 10 | 10 | 2023-05-30 08:00 | 2023-06-12 17:00 | -123 | 0
Not Started |  | CI NYCHA Update #28.1 | CO141-01020 | [8 empty] | CO #141 - Negotiate/Instruction - OG6 Vita Link | 30 | 30 | 2023-03-27 08:00 | 2023-05-05 17:00 | -123 | 0
Not Started |  | CI NYCHA Update #28.1 | CO141-01015 | [8 empty] | CO #141 - Submit Price - OG6 Vita Link | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -123 | 0
In Progress |  | CI NYCHA Update #28.1 | CO141-01010 | [8 empty] | CO #141 - Scope Agreement - OG6 Vita Link | 30 | 10 | 2023-02-15 | 2023-03-10 17:00 | -123 | 0
Completed |  | CI NYCHA Update #28.1 | CO141-01005 | [8 empty] | CO #141 - Scope Development - OG6 Vita Link | 5 | 0 | 2023-01-13 | 2023-02-14 |  | 0
Not Started |  | CI NYCHA Update #28.1 | CO136-01020 | [8 empty] | CO #136 - Negotiate/Instruction - Upsize ATS-HTP from 400A to 600A - SG3 | 30 | 30 | 2023-03-27 08:00 | 2023-05-05 17:00 | -128 | 0
Not Started |  | CI NYCHA Update #28.1 | CO136-01015 | [8 empty] | CO #136 - Submit Price - Upsize ATS-HTP from 400A to 600A - SG3 | 10 | 10 | 2023-03-13 08:00 | 2023-03-24 17:00 | -128 | 0
In Progress |  | CI NYCHA Update #28.1 | CO136-01010 | [8 empty] | CO #136 - Scope Agreement - Upsize ATS-HTP from 400A to 600A - SG3 | 30 | 10 | 2022-12-15 | 2023-03-10 17:00 | -128 | 0
Completed |  | CI NYCHA Update #28.1 | CO136-01005 | [8 empty] | CO #136 - Scope Development - Upsize ATS-HTP from 400A to 600A - SG3 | 5 | 0 | 2022-11-15 | 2022-12-14 |  | 0
In Progress |  | CI NYCHA Update #28.1.4 | CO123-01022 | [8 empty] | CO #123 - Review/Approve EIFS product data | 15 | 5 | 2023-02-17 | 2023-03-03 17:00 | -22 | 0
Completed |  | CI NYCHA Update #28.1.4 | CO123-01021 | [8 empty] | CO #123 - Submit EIFS product data | 15 | 0 | 2023-01-25 08:00 | 2023-02-16 17:00 |  | 0
Completed |  | CI NYCHA Update #28.1 | CO063-01020 | [8 empty] | CO #63 - Negotiate/Instruction - Support for Electrical Conduit Concrete Encasements | 30 | 0 | 2022-09-30 | 2022-10-19 |  | 0
Completed |  | CI NYCHA Update #28.1 | CO063-01015 | [8 empty] | CO #63 - Submit Price - Support for Electrical Conduit Concrete Encasements | 10 | 0 | 2022-09-28 | 2022-09-29 |  | 0
Completed |  | CI NYCHA Update #28.1 | CO063-01010 | [8 empty] | CO #63 - Scope Agreement - Support for Electrical Conduit Concrete Encasements | 15 | 0 | 2021-11-16 08:00 | 2022-09-27 |  | 0
Completed |  | CI NYCHA Update #28.1 | CO063-01005 | [8 empty] | CO #63 - Scope Development - Support for Electrical Conduit Concrete Encasements | 10 | 0 | 2021-11-01 08:00 | 2021-11-15 17:00 |  | 0